## Data
Queue Number | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Queue Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected In Service Date | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Queue | Sliding Queue
A01 | South Lebanon 230 KV | Ironwood | PA | Lebanon | In Service | ME | 720 | 720 | 673 | 673 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a01_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a01_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 4/1/2002 | 4/1/2002 | 4/1/2002 | N | No
A02 | Oak Hall 138 kV (Oil CT) | Chesapeake | VA | Unknown | In Service | DPL | 315 | 315 | 315 | 311.8 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/a02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 8/22/2001 |  | 8/22/2001 | N | No
A03 | Linden 230 kV or 138 kV | Linden 5 & 6 | NJ | Union | In Service | PSEG | 120 | 120 | 120 | 114 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/a03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2000 |  | 6/1/2000 | N | No
A04 | Linden 230 kV or 138 kV | Linden 1, 2 & 3 | NJ | Union | In Service | PSEG | 1186 | 750 | 750 | 750 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a04_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a04_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 4/1/1997 | N/A | N/A | 3/11/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
A05 | Bergen | Bergen | NJ | Bergen | In Service | PSEG | 500 | 500 | 500 | 500 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a05_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a05_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/1/1997 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
A06 | Kearny |  | NJ | Gloucester | Withdrawn | PSEG | 800 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/1997 | N/A | N/A |  | 8/28/2000 |  |  |  |  | N | No
A07 | Dickerson 120 MW |  | MD | Montgomery | Withdrawn | PEPCO | 120 | 25 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a07_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a07_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/1/1997 | N/A | N/A |  | 7/22/2002 | Customer Initiated Withdrawal |  |  |  | N | No
A08 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a08_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 7/1/2002 |  | 7/1/2002 | N | No
A09 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 1140 | 35 | 35 | 35 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a09_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a09_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/1/1997 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
A10 | Glory 115 kV | Colver Power | PA | Cambria | In Service | PENELEC | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a10_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 6/2/1997 | N/A | N/A |  |  |  | 1/8/2000 |  | 1/8/2000 | N | No
A11 | Harwood 230 kV | Hazelton | PA | Luzerne | In Service | PPL | 356 | 201 | 201 | 31.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a11_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1997 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
A12 | Martins Creek 230 kV | Lower Mt Bethel | PA | Northampton | In Service | PPL | 600 | 600 | 600 | 582 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a12_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/13/2003 | 8/20/1997 | N/A | N/A | 12/15/2003 |  |  | 5/14/2004 |  | 5/14/2004 | N | No
A13 | Mickleton 230 kV | Mantua Creek Generating Station | NJ | Gloucester | Withdrawn | AEC | 803 | 803 | 803 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a13_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a13_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/26/1997 | N/A | N/A |  |  |  | 6/1/2004 |  |  | N | No
A14 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a14_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1998 | N/A | N/A |  | 6/18/2002 |  |  |  |  | N | No
A15 | Sayreville 230 kV | Red Oak CC1, CT1 - CT4 | NJ | Middlesex | In Service | JCPL | 765 | 765 | 765 | 765 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/a15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/1998 | N/A | N/A |  |  |  | 2/1/2002 |  | 2/1/2002 | N | No
A16 | Eagle Point 230 kV |  | NJ | Gloucester | Withdrawn | PSEG | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a16_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/1998 | N/A | N/A |  | 4/19/2000 |  |  |  |  | N | No
A17 | Linden 230 kV |  | NJ | Union | Withdrawn | PSEG | 1100 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a17_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/8/1998 | N/A | N/A |  | 10/10/2003 |  | 5/1/2006 |  |  | N | No
A18 | North Temple 230 kV |  | PA | Berks | In Service | ME | 557 | 557 | 557 | 557 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a18_imp2.pdf | Interim Study | https://www.pjm.com/pub/planning/project-queues/facilities/a18_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/11/1998 | N/A | N/A |  |  |  | 12/1/2002 | 12/1/2002 | 12/1/2002 | N | No
A19 | Eddystone 230 kV | Liberty (Eddy) | PA | Delaware | In Service | PECO | 521 | 521 | 521 | 521 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a19_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a19_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/1998 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
A20 | Juniata 500 kV |  | PA | Dauphin | Withdrawn | PPL | 485 | 12 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a20_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/9/1998 | N/A | N/A |  | 7/18/1999 | Customer Milestone Not Met |  |  |  | N | No
A21 | Chichester 230 kV | Phillips Island | PA | Philadelphia | In Service | PECO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a21_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a21_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/a21_csa.pdf | Document Posted | N/A | N/A | 6/2/2003 | 8/17/1998 | N/A | N/A | 6/4/2004 |  |  | 12/31/2004 |  | 12/31/2004 | N | No
A22 | Hudson 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/1998 | N/A | N/A |  | 8/28/2000 |  |  |  |  | N | No
A23 | New Castle 138 kV |  | DE | New Castle | Withdrawn | DPL | 257 | 257 | 257 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/1998 | N/A | N/A |  | 7/23/1999 |  |  |  |  | N | No
A24 | South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 725 | 725 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/1998 | N/A | N/A |  | 6/26/1999 |  |  |  |  | N | No
A25 | Hosensack 500 kV |  | PA | Northampton | Withdrawn | PPL | 1000 | 1000 | 1000 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a25_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a25_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/30/1998 | N/A | N/A |  | 1/24/2002 |  |  |  |  | N | No
A26 | Linden | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 180 |  | 157.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a26_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a26_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/1998 | N/A | N/A |  |  |  | 1/25/2002 |  | 1/25/2002 | N | No
A27 | Passyunk 230 kV |  | PA | Philadelphia | Withdrawn | PECO | 615 | 615 | 515 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a27_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a27_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/4/1998 | N/A | N/A |  | 4/30/2002 |  |  |  |  | N | No
A28 | Dover | Kent | DE | Kent | In Service | DPL | 100 | 100 | 98 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a28_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a28_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/4/1998 | N/A | N/A |  |  |  | 6/14/2001 |  | 6/14/2001 | N | No
A29 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a29_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a29_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/18/1998 | N/A | N/A |  |  |  | 6/13/2003 |  | 6/13/2003 | N | No
A30 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | 465 | 465 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a30_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a30_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/2/2002 | 12/3/1998 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
A31 | Peckville/Varden 69 kV | Archbald | PA | Lackawanna | In Service | PPL | 46 | 44 | 44 | 43.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a31_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a31_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a31_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/22/1998 | N/A | N/A |  |  |  | 10/27/2001 |  | 10/27/2001 | N | No
A32 | Montour #1 | Montour #1 | PA | Montour | In Service | PPL | 759 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/a32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 6/19/2001 |  | 6/19/2001 | N | No
A33 | Montour #2 | Montour #2 | PA | Montour | In Service | PPL | 14 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/a33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 11/1/2000 |  | 11/1/2000 | N | No
A34 | Brunner 230 kV |  | PA | York | In Service | PPL | 749 | 14 | 14 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a34_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a34_imp2.pdf | Interim Study | https://www.pjm.com/pub/planning/project-queues/facilities/a34_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/1999 | N/A | N/A |  |  |  | 4/27/2002 |  | 4/27/2002 | N | No
A35 | North Bangor 34.5 kV | Grand Central Sanitary LF | PA | Northampton | In Service | ME | 10 | 10 | 10 | 8.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a35_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a35_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/13/1999 | N/A | N/A |  |  |  | 4/18/2001 |  | 4/18/2001 | N | No
A36 | Hunterstown 500 kV | Hunterstown | PA | Adams | In Service | ME | 830 | 830 | 830 | 810 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a36_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a36_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/1999 | N/A | N/A | 4/23/2003 |  |  | 7/31/2003 | 7/31/2003 | 7/31/2003 | N | No
A37 | Sayreville 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 749 | 749 | 749 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 9/8/1999 |  |  |  |  | N | No
A38 | Erie West 345 kV |  | PA | Crawford | Withdrawn | PENELEC | 765 | 765 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a38_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A39 | Pequest River 115 kV |  | NJ | Warren | Withdrawn | JCPL | 73 | 73 | 73 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a39_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A40 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 1271 | 1271 | 1271 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 10/12/1999 |  |  |  |  | N | No
A41 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 765 | 765 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a41_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A | [6 empty] | N | No
A42 | Atlantic 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 449 | 449 | 449 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/6/2001 |  |  |  |  | N | No
A43 | Portland 230 kV |  | PA | Northampton | Withdrawn | ME | 472 | 472 | 472 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a43_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a43_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 7/20/2003 |  |  |  |  | N | No
A44 | Shelocta 230 kV |  | PA | Indiana | Withdrawn | PENELEC | 402 | 402 | 402 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 10/22/1999 |  |  |  |  | N | No
A45 | Oyster Creek 230 kV |  | NJ | Ocean | Withdrawn | JCPL | 752 | 752 | 752 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 12/6/1999 |  |  |  |  | N | No
A46 | Gilbert 115 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a46_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/1999 | N/A | N/A |  | 8/30/1999 |  |  |  |  | N | No
A47 | Perryman 230kV or 115kV |  | MD | Harford | Withdrawn | BGE | 740 | 740 | 740 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/1999 | N/A | N/A |  | 8/30/1999 |  |  |  |  | N | No
A48 | East Towanda 230kV |  | NJ | Union | Withdrawn | PENELEC | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 10/3/2001 |  |  |  |  | N | No
A49 | West Hempfield 230kV |  | NJ | Bergen | Withdrawn | PPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a49_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 9/10/1999 |  |  |  |  | N | No
A50 | Bayonne |  | NJ | Hudson | Withdrawn | PSEG | 60 | 60 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a50_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  |  | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
A51 | Camden |  | NJ | Camden | Withdrawn | PSEG | 258 | 258 | 258 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 11/26/2001 |  |  |  |  | N | No
A52 | Linden |  | NJ | Union | Withdrawn | PSEG | 180 | 180 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a52_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 3/17/2004 |  | 6/1/2005 | 6/1/2005 |  | N | No
A53 | Titusville |  | PA | Crawford | Withdrawn | PENELEC | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a53_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a53_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/1999 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
A54 | TMI 230 kV |  | PA | Dauphin | Withdrawn | ME | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a54_imp2.pdf | Interim Study |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/9/1999 | N/A | N/A |  |  | Customer Milestone Not Met | 6/1/2002 |  |  | N | No
A55 | Lakewood 230kV | Lakewood NUG | NJ | Ocean | In Service | JCPL | 500 | 500 | 500 | 301 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a55_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a55_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 1/7/2003 | 2/22/1999 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | N | No
A56 | Pedricktown 230kV |  | NJ | Salem | Withdrawn | AEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a56_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/1999 | N/A | N/A |  | 8/17/1999 |  |  |  |  | N | No
A57 | Edgemoor | Unit 1 | PA | Dauphin | Withdrawn | AEC | 500 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a57_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a57_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/1999 | N/A | N/A |  | 7/27/2000 |  | 10/31/2001 |  |  | N | No
A58 | Hawkins Gate / Oak Grove 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a58_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/1999 | N/A | N/A |  | 8/28/1999 |  |  |  |  | N | No
A59 | Emilie | Ford Mill | PA | Bucks | In Service | PECO | 1145 | 540 | 540 | 540 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a59_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/a59_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/a59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/1/2003 | 4/1/1999 | N/A | N/A | 1/21/2004 |  |  | 5/27/2004 |  | 5/27/2004 | N | No
A59_W00 | Springdale 138 kV | Springdale 1 & 2 | PA | Allegheny | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a59_w00_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/a59_w00_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 12/1/2000 |  | 12/1/2000 | N | No
A60 | Hunterstown 500 kV |  | PA | Adams | Withdrawn | ME | 679 | 679 | 679 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a60_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/8/1999 | N/A | N/A | [6 empty] | N | No
A61 | Hawkins Gate / Oak Grove 230kV |  | DE | New Castle | Withdrawn | PEPCO | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/a61_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/1999 | N/A | N/A | [6 empty] | N | No
B01 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 398 | 398 | 398 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b01_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b01_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/29/1999 | N/A | N/A |  | 7/22/2002 |  |  |  |  | N | No
B02 | Morgantown | Morgantown Units 1 & 2 | MD | Charles | In Service | PEPCO | 80 | 80 | 80 | 80 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
B03 | Hosensack 500kV | Bethlehem | PA | Northampton | In Service | PPL | 750 | 750 | 750 | 788 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b03_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b03_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/28/2003 |  | 1/28/2003 | N | No
B04 | Oyster Creek |  | NJ | Ocean | Withdrawn | JCPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/1999 | N/A | N/A | [6 empty] | N | No
B05 | Wayne-Homer City 345kV |  | PA | Indiana | In Service | PENELEC | 265 | 265 | 250 | 265 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b05_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/1999 | N/A | N/A |  |  |  | 1/1/2002 |  | 1/1/2002 | N | No
B06 | Wayne-Homer City 345kV |  | PA | Indiana | Withdrawn | PENELEC | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/1999 | N/A | N/A | [6 empty] | N | No
B07 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/1999 | N/A | N/A | [6 empty] | N | No
B08 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b08_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/1999 | N/A | N/A | [6 empty] | N | No
B09A | Burlington 138kV | Burlington | NJ | Burlington | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b09a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b09a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b09a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b09a_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/10/1999 | N/A | N/A |  |  |  | 7/22/2000 |  | 7/22/2000 | N | No
B09b | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 336 | 336 | 336 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b09b_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b09b_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/1999 | N/A | N/A | [6 empty] | N | No
B10 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b10_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/1999 | N/A | N/A | [6 empty] | N | No
B12 | Limerick 230kV |  | PA | Montgomery | Withdrawn | PECO | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b12_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/14/1999 | N/A | N/A |  | 6/13/2002 |  |  |  |  | N | No
B12_W01 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b12_w01_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 3/1/2002 |  | 3/1/2002 | N | No
B12_W02 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 300 | 300 | 300 | 300 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b12_w01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b12_w02_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 10/1/2002 |  | 10/1/2002 | N | No
B13 | Lakewood 230kV |  | NJ | Ocean | Withdrawn | JCPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/1999 | N/A | N/A | [6 empty] | N | No
B14 | Arnold 115kV | Arnold (Green Mountain) WF | PA | Somerset | In Service | PENELEC | 10.4 | 10.4 | 2.08 | 10.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b14_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/6/1999 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
B15 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b15_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b15_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b15_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/12/1999 | N/A | N/A |  | 10/2/2002 |  | 6/1/2003 |  |  | N | No
B16 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b16_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b16_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b16_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/12/1999 | N/A | N/A |  | 10/2/2002 |  | 6/1/2004 |  |  | N | No
B17 | Jerseyville 34.5kV | Statoil | NJ | Monmouth | In Service | JCPL | 2.1 | 2.1 |  | 2.1 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/17/1999 | N/A | N/A |  |  |  | 1/1/1999 |  | 1/1/2001 | N | No
B18 | Limerick-Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/1999 | N/A | N/A | [6 empty] | N | No
B18_W03 | Springdale 138 kV | Springdale CT3, CT4, ST5 | PA | Allegheny | In Service | APS | 525 | 525 | 525 | 509 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/b18_w03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b18_w03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/1/1999 | N/A | N/A |  |  |  | 8/1/2003 |  | 8/1/2003 | N | No
B19 | Melrose 34.5kV | Middlesex Sewer | NJ | Middlesex | In Service | JCPL | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/1999 | N/A | N/A |  |  |  | 4/6/2001 |  | 4/6/2001 | N | No
B20 | Elm St. 115kV |  | PA | Warren | Withdrawn | PENELEC | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/1999 | N/A | N/A |  | 10/23/2000 |  |  |  |  | N | No
B21 | South Reading 500kV |  | PA | Berks | Withdrawn | ME | 925 | 925 | 925 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/1999 | N/A | N/A |  | 9/15/2000 |  |  |  |  | N | No
B22 | Gould St. 34.5 kV |  | MD | Baltimore City | Withdrawn | BGE | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/11/1999 | N/A | N/A | [6 empty] | N | No
B23 | Siegfried/Allentown 138kV | Northampton | PA | Northampton | In Service | PPL | 115 | 5 | 5 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/1999 | N/A | N/A |  |  |  | 6/10/2001 |  | 6/10/2001 | N | No
B23_W04 | Gans 138 kV | Gans 8 & 9 | PA | Fayette | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b23_w04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b23_w04_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/1999 | N/A | N/A |  |  |  | 12/1/2001 |  | 12/1/2001 | N | No
B24 | Oak Grove 13.8kV |  | MD | Prince George's | Withdrawn | PEPCO | 6.8 | 6.8 | 6.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/1999 | N/A | N/A | [6 empty] | N | No
B25 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b25_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b25_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/20/1999 | N/A | N/A |  | 5/3/2002 |  |  |  |  | N | No
B26 | Hunlock Creek 66kV | Hunlock Creek 66kV | PA | Luzerne | In Service | UGI | 50 | 50 | 50 | 44.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b26_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/1999 | N/A | N/A |  |  |  | 5/26/2002 |  | 5/26/2002 | N | No
B27 | Portland 230kV |  | PA | Northampton | Withdrawn | ME | 920.5 | 362 | 362 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/1999 | N/A | N/A |  | 11/6/2000 |  |  |  |  | N | No
B28 | Muddy Run 230kV | Muddy Run | PA | York | In Service | PECO | 160 | 160 | 160 | 160 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b28_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b28_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 8/27/2003 |  | 8/27/2003 | N | No
B28_W07 | Backbone Mountain 138 kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 90 | 18 | 66 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b28_w07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b28_w07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b28_w07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
B28_W08 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 | 15 |  | 15 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b28_w08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b28_w08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b28_w08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/12/1999 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
B29 | Perryman 230kV/115kV |  | MD | Harford | Withdrawn | BGE | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b29_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/1999 | N/A | N/A |  | 4/17/2001 |  |  |  |  | N | No
B30 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 605 | 605 | 605 | 528 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b30_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b30_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 8/26/2003 | 11/22/1999 | N/A | N/A | 4/1/2004 |  |  | 6/29/2004 |  | 6/29/2004 | N | No
B31 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/1999 | N/A | N/A |  | 10/9/2000 |  |  |  |  | N | No
B32 | TMI 230kV |  | PA | Dauphin | Withdrawn | ME | 650 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b32_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/1999 | N/A | N/A |  | 12/5/2000 |  |  |  |  | N | No
B33 | Steelton 230kV |  | PA | Dauphin | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b33_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/1999 | N/A | N/A |  | 12/3/2002 |  | 5/1/2005 |  |  | N | No
B34 | Seward 230kV | Seward 1 (Hay Road 5,6,7,8) | PA | Westmoreland | In Service | PENELEC | 525 | 525 | 304 | 325 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b34_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b34_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b34_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/1/2003 | 11/23/1999 | N/A | N/A | 3/10/2004 |  |  | 6/9/2006 |  | 6/9/2006 | N | No
B35 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 313 | 313 | 313 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b35_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b35_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b35_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 3/10/2003 |  |  |  |  | N | No
B36 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 78 | 78 | 78 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b36imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b35_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b36_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 3/10/2003 |  | 6/30/2004 |  |  | N | No
B37 | East Greenville 69kV |  | PA | Montgomery | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b37_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 4/9/2002 |  |  |  |  | N | No
B38 | Elroy 138kV |  | PA | Montgomery | Withdrawn | PPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b38_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b38_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B39 | Quarryville 69kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B40 | West Hempfield 69kV |  | PA | Lancaster | Withdrawn | PPL | 100 | 100 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b40_fea.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/facilities/b40_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B41 | West Hempfield 138kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b41_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b41_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/24/1999 | N/A | N/A |  | 1/7/2002 |  |  |  |  | N | No
B42 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b42_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 11/8/2000 |  |  |  |  | N | No
B43 | Homer City-Wayne 345kV |  | PA | Venango | Withdrawn | PENELEC | 284 | 284 | 284 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 11/8/2000 |  |  |  |  | N | No
B44 | Elko-Forrest 230kV |  | PA | Elk | Withdrawn | PENELEC | 240 | 240 | 240 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A | [6 empty] | N | No
B45 | Lackawanna 230kV |  | PA | Lackawanna | Withdrawn | PPL | 555 | 555 | 555 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/1999 | N/A | N/A |  | 7/23/2002 |  | 6/1/2004 |  |  | N | No
B46 | Conowingo 230kV | Conowingo | MD | Harford | In Service | PECO | 548 | 36 | 36 | 36 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/b46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 11/21/2003 |  | 11/21/2003 | N | No
B47 | Red Lion 500kV | Hay Road 5, 6, 7 | DE | New Castle | In Service | DPL | 351 | 351 | 351 | 351 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b47_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b47_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b47_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/b47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/1999 | N/A | N/A |  |  |  | 7/22/2002 |  | 7/22/2002 | N | No
B48 | Graceton 230kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b48_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/b48_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 10/17/2003 |  | 6/1/2005 |  |  | N | No
B49 | Erie South-Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/b49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 7/31/2001 |  |  |  |  | N | No
B50 | Morgantown 69kV |  | PA | Erie | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A | [6 empty] | N | No
B51 | Wayne 345 |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 11/19/2001 |  |  |  |  | N | No
B52 | Woodbridge 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/b52_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/1999 | N/A | N/A |  | 12/5/2000 |  |  |  |  | N | No
C01 | Linden 138kV | Linden 1, 2 & 3 | NJ | Union | In Service | PSEG | 1186 | 436 | 436 | 436 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c01_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c01_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/c01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/10/2004 | 12/17/1999 | N/A | N/A | 4/22/2005 |  |  | 5/1/2006 |  | 5/1/2006 | N | No
C02 | South Lebanon 230kV | Ironwood | PA | Lebanon | Withdrawn | ME | 720 | 47 | 47 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c02_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2000 | N/A | N/A |  |  |  | 1/1/2007 |  |  | N | No
C03 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c03_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c03_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/11/2000 | N/A | N/A |  | 9/16/2002 |  | 12/1/2003 |  |  | N | No
C04 | Burches Hill 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c04_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2000 | N/A | N/A |  | 1/25/2002 |  |  |  |  | N | No
C05 | Somerset 34.5kV |  | NJ | Somerset | Withdrawn | JCPL | 3.8 | 3.75 | 3.75 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c05_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2000 | N/A | N/A | [6 empty] | N | No
C06 | Susquehanna 230kV** |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2000 | N/A | N/A |  | 7/6/2001 |  |  |  |  | N | No
C07 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 1119 | 26 | 26 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c07_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c07_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/c07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 7/19/2001 |  | 7/19/2001 | N | No
C08 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1100 | 69 | 69 | 18 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c08_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/c08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2000 | N/A | N/A |  |  |  | 8/1/2001 |  | 8/1/2001 | N | No
C09 | Fairlawn 26.4kV |  | NJ | Bergen | Withdrawn | PSEG | 37 | 37 | 37 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2000 | N/A | N/A |  | 1/25/2001 |  |  |  |  | N | No
C10 | Erie East 230kV | Northeast Cogen | PA | Erie | Withdrawn | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c10_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c10_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/c10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/8/2000 | N/A | N/A |  | 6/23/2005 | Customer Milestone Not Met | 6/1/2006 |  |  | N | No
C11 | Mifflintown 69kV |  | PA | Juniata | Withdrawn | PPL | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2000 | N/A | N/A |  | 7/6/2001 |  |  |  |  | N | No
C11_W11 | Hunker 138 kV |  | PA | Westmoreland | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2000 | N/A | N/A | [6 empty] | N | No
C12 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c12_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/15/2000 | N/A | N/A |  | 6/22/2004 |  | 12/1/2004 |  |  | N | No
C13 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/c13_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/15/2000 | N/A | N/A |  | 6/22/2004 |  | 12/1/2004 |  |  | N | No
C14 | Keystone - Conemaugh 550 |  | PA | Indiana | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/c14_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2000 | N/A | N/A |  | 3/1/2002 |  |  |  |  | N | No
C15 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c15_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A |  |  |  | 12/1/2002 |  |  | N | No
C16 | Westover South 34.5kV |  | PA | Clearfield | Withdrawn | PENELEC | 13.5 | 13.15 | 13.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A | [6 empty] | N | No
C17 | Somerset 23kV |  | PA | Somerset | Withdrawn | PENELEC | 4.5 | 4.5 | 4.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/c17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2000 | N/A | N/A | [6 empty] | N | No
D01 | Engleside 69kV | Sight and Sound Theater | PA | Lancaster | In Service | PPL | 1.6 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2000 | N/A | N/A |  |  |  | 5/31/2000 |  | 5/31/2000 | N | No
D02 | Edgemoor | Hay Road 1-4 | DE | New Castle | In Service | DPL | 521 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2000 | N/A | N/A |  |  |  | 4/12/2000 |  | 4/12/2000 | N | No
D03 | Harwood 69kV | Haxelton Units 2-4 | PA | Luzerne | In Service | PPL | 99 | 99 | 99 | 60.8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d03_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/d03_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/d03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2000 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
D03_W15 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 10.6 | 12 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d03_w15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d03_w15_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2000 | N/A | N/A |  |  |  | 6/1/2003 |  |  | N | No
D04 | Peckville 69kV | Archbald | PA | Wayne | In Service | PPL | 20 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/26/2000 | N/A | N/A |  |  |  | 6/9/2000 |  | 6/9/2000 | N | No
D05 | East Carbondale 69kV | Waymart WF | PA | Wayne | In Service | PPL | 70 | 70 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d05_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/d05_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/d05_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/d05_csa.pdf | Document Posted | N/A | N/A |  | 6/15/2000 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
D05_W17 | Friendsville 500 kV |  | MD | Garrett | Withdrawn | APS | 432 | 432 | 432 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d05_w17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d05_w17_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2000 | N/A | N/A |  | 9/20/2002 |  | 6/1/2004 |  |  | N | No
D06 | Eclipse 115kV | Scrubgrass NUG | PA | Unknown | In Service | PENELEC | 85 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/19/2000 | N/A | N/A |  |  |  | 7/15/2000 |  | 7/15/2000 | N | No
D07 | Blueball 69kV | Sunoil Gen Unit | PA | Delaware | Deactivated | PECO | 53 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2000 | N/A | N/A |  |  |  | 7/25/2000 |  | 7/25/2000 | N | No
D08 | Kearny 230kV | Kearny #12 | NJ | Hudson | In Service | PSEG | 168 | 168 | 168 | 168 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/d08_fac2.pdf | Interim Study | https://www.pjm.com/pub/planning/project-queues/isa/d08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/3/2000 | N/A | N/A |  |  |  | 8/4/2001 |  | 8/4/2001 | N | No
D08_W18 | Terra Alta 138 kV |  | WV | Preston | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2000 | N/A | N/A | [6 empty] | N | No
D08_W19 | Bald Eagle 46 kV |  | PA | Centre | Withdrawn | APS | 88 | 88 | 88 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2000 | N/A | N/A | [6 empty] | N | No
D09 | 9th St (sub 117) 13kV | Central Heating & Refrigeriation Facility 1 & 2 | DC | N/A | In Service | PEPCO | 11 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/15/2003 | 7/24/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D10 | NIH 13kV | NIH Unit 1 | MD | Montgomery | In Service | PEPCO | 25 | 25 |  | 25 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d10_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/d10_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/d10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/30/2003 | 7/26/2000 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
D11 | Clayton 138kV | DEMEC/Smyrna 1 &2 | DE | Kent | In Service | DPL | 100 | 100 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/26/2000 | N/A | N/A |  |  |  | 5/1/2002 |  | 5/1/2002 | N | No
D13 | Deep Run 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 12 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2000 | N/A | N/A |  | 3/21/2002 |  |  |  |  | N | No
D14 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 711 | 190 | 190 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 3/1/2002 |  |  |  |  | N | No
D15 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A | [6 empty] | N | No
D16 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
D17 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 1/15/2002 |  |  |  |  | N | No
D18 | Hosensack 230kV | Conectiv Bethlem CT 6, ST2 | PA | Northampton | In Service | PPL | 350 | 350 | 350 | 304 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d18_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/d18_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/d18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/d18_csa.pdf | Document Posted | N/A | N/A | 5/31/2003 | 7/28/2000 | N/A | N/A |  |  |  | 5/1/2004 |  | 5/1/2004 | N | No
D19 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d19_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2004 |  |  | N | No
D20 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d20_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 5/1/2005 |  |  | N | No
D21 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d21_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2005 |  |  | N | No
D22 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2000 | N/A | N/A |  | 4/28/2003 |  | 12/1/2005 |  |  | N | No
D23 | Keystone 500kV |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 3/27/2002 |  |  |  |  | N | No
D24 | Mansfield 115kV |  | PA | Tioga | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 3/27/2002 |  |  |  |  | N | No
D25 | Hay Road 69kV & 138kV |  | DE | New Castle | Withdrawn | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d25_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d25_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 9/17/2003 |  |  |  |  | N | No
D26 | Mercer 230kV |  | NJ | Mercer | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A | [6 empty] | N | No
D27 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d27_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2000 | N/A | N/A |  | 12/3/2002 |  | 12/1/2004 |  |  | N | No
D28 | Passyunk 230kV |  | PA | Philadelphia | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d28_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2000 | N/A | N/A |  | 11/12/2002 |  |  |  |  | N | No
D29 | Derwood 13kV |  | MD | Montgomery | In Service | PEPCO | 3 | 3 | 3 | 2.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/d29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/d29_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/d29_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2000 | N/A | N/A |  |  |  | 6/29/2001 |  | 6/29/2001 | N | No
E01 | Kearny 230kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2000 | N/A | N/A |  | 11/1/2001 |  |  |  |  | N | No
E02 | N. Lebanon 69kV |  | PA | Lebanon | In Service | ME | 1.2 | 1.2 | 1.2 | 1.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e02_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2000 | N/A | N/A |  |  |  | 11/17/2000 |  | 11/17/2000 | N | No
E03 | Somerville 13.8kV |  | NJ | Middlesex | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e03_imp2.pdf | Interim Study |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/17/2000 | N/A | N/A |  | 10/25/2002 |  | 1/31/2001 |  |  | N | No
E04 | Atlantic 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 598 | 24 | 24 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2000 | N/A | N/A | [6 empty] | N | No
E04_W20 | Guilford 138 kV |  | PA | Franklin | In Service | APS | 88 | 88 | 88 | 88 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e04_w20_fea.pdf | Document Posted |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 9/6/2000 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
E05 | Bethlehem Steel 33kV | Sparrow Point | MD | Baltimore County | In Service | BGE | 152.5 | 2.5 | 2.5 | 2.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2000 | N/A | N/A |  |  |  | 1/1/2001 |  | 1/1/2001 | N | No
E05_W25 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 620 | 620 | 620 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e05_w25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e05_w25_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2000 | N/A | N/A |  | 11/26/2002 |  | 5/1/2004 |  |  | N | No
E06 | Bear Creek 69kV (Wind) | Bear Creek | PA | Luzerne | Withdrawn | PPL | 15.6 | 15.6 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e06_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/e06_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/e06_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/5/2000 | N/A | N/A |  | 10/25/2002 |  | 12/1/2002 |  |  | N | No
E07 | Montour 230kV | Montour #2 | PA | Montour | In Service | PPL | 766 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/6/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 5/6/2002 | N | No
E08 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2000 | N/A | N/A | [6 empty] | N | No
E09 | Kiamensi 34kV |  | DE | New Castle | Withdrawn | DPL | 8.4 | 8.4 | 8.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e09_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/19/2000 | N/A | N/A | [6 empty] | N | No
E10 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 500 | 162 | 162 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2000 | N/A | N/A | [6 empty] | N | No
E11 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2000 | N/A | N/A | [6 empty] | N | No
E12 | Larrabee 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 661 | 661 | 661 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2000 | N/A | N/A | [6 empty] | N | No
E13 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 10 | 10 |  | 10 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/e13_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/e13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/3/2000 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
E14 | Elm St. 115 kV |  | PA | Erie | Withdrawn | PENELEC | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2000 | N/A | N/A | [6 empty] | N | No
E15 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2000 | N/A | N/A | [6 empty] | N | No
E16 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 776 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2000 | N/A | N/A | [6 empty] | N | No
E17 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2000 | N/A | N/A |  | 6/25/2002 |  | 12/1/2003 |  |  | N | No
E17_W26 | Taylorstown 500 kV |  | PA | Unknown | Withdrawn | APS | 1595 | 1595 | 1595 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e17_w26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e17_w26_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/14/2000 | N/A | N/A |  |  |  | 7/1/2005 |  |  | N | No
E17_W27 | Ronco | Ronco CT1, CT2, STG | PA | Fayette | In Service | APS | 661 | 620 | 620 | 620 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e17_w27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e17_w27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e17_w27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2000 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
E17_W29 | Yukon 500 kV |  | PA | Westmoreland | Withdrawn | APS | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e17_w29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e17_w29_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/e17_w29_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/15/2000 | N/A | N/A |  | 6/2/2004 |  | 12/31/2005 |  |  | N | No
E18 | Essex / Foundry St 138kV |  | NJ | Essex | Withdrawn | PSEG | 275 | 275 | 275 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A | [6 empty] | N | No
E19 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 330 | 330 | 330 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A | [6 empty] | N | No
E20 | Croydon 230kV | Croydon #11,12,21,22,31,32,41,42 | PA | Bucks | In Service | PECO | 386.5 | 6.5 | 6.5 | 6.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/28/2000 | N/A | N/A |  |  |  | 12/20/2002 |  | 12/20/2002 | N | No
E21 | Camden-Richmond 230kV |  | NJ | Camden | Withdrawn | PSEG | 727 | 727 | 727 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e21_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/e21_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/28/2000 | N/A | N/A |  | 11/11/2004 | Customer Initiated Withdrawal | 12/1/2004 |  |  | N | No
E22 | Burches Hill 500kV |  | VA | Prince William | Withdrawn | Dominion | 960 | 960 | 960 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2000 | N/A | N/A |  | 8/8/2002 |  | 1/1/2005 |  |  | N | No
E23 | Lakehurst 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e23_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A |  | 9/17/2002 |  | 12/1/2003 |  |  | N | No
E24 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A |  | 5/22/2002 |  |  |  |  | N | No
E27 | Hosensack 500kV |  | PA | Northampton | Withdrawn | PPL | 1100 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2000 | N/A | N/A | [6 empty] | N | No
E28 | Motiva | Delaware City/Motiva Unit G6 | DE | New Castle | In Service | DPL | 75 | 60 | 60 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/e28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/e28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/e28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/30/2000 | N/A | N/A |  |  |  | 10/1/2003 |  | 10/1/2003 | N | No
F01 | TMI |  | PA | Dauphin | Withdrawn | ME | 650 | 551 | 551 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2000 | N/A | N/A |  | 4/2/2002 |  | 12/1/2004 |  |  | N | No
F02 | Hudson |  | NJ | Hudson | Withdrawn | PSEG | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/7/2000 | N/A | N/A |  | 12/1/2001 |  |  |  |  | N | No
F03 | Martins Creek 230kV | Martins Creek #3 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/f03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/f03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/13/2000 | N/A | N/A |  |  |  | 4/1/2001 |  | 4/1/2001 | N | No
F04 | Somerset 115kV | Keystone | PA | Somerset | Withdrawn | PENELEC | 30 | 30 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/f04_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/f04_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 1/18/2001 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
F05 | Keystone-Conemaugh 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 646 | 646 | 646 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2001 | N/A | N/A | [6 empty] | N | No
F05_W38 | White Oak 500 kV |  | PA | Unknown | Withdrawn | APS | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f05_w38_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2001 | N/A | N/A |  |  |  | 3/1/2004 |  |  | N | No
F06 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 6.5 | 6.5 | 6.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2001 | N/A | N/A | [6 empty] | N | No
F07 | Dickerson 230kV | Dickerson | MD | Montgomery | In Service | PEPCO | 20 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/f07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/f07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
F08 | Chalk Point 230kV | Chalk Point | MD | Prince George's | In Service | PEPCO | 20 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/f08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/f08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2001 | N/A | N/A |  |  |  | 3/17/2001 |  | 3/17/2001 | N | No
F09 | Central City West 23kV |  | PA | Somerset | Withdrawn | PENELEC | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/f09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/f09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2001 | N/A | N/A |  | 10/15/2002 |  | 12/1/2003 |  |  | N | No
G00_MTX2B | Keeney-Steele 230kV |  | DC | Unknown | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx2b_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX2C | Vienna-Piney Grove 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR/FTR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx2c_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2001 | N/A | N/A |  |  |  | 1/1/2005 |  |  | S | No
G00_MTX3 | Erie West 345kV |  | PA | Erie | Withdrawn | Unknown | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | C/TIR/1000 F/TW | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g00_mtx3_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g00_mtx3_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2001 | N/A | N/A |  | 7/10/2003 |  | 6/30/2004 |  |  | S | No
G00_W39 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 668 | 668 | 668 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g00_w39_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2001 | N/A | N/A |  | 10/25/2002 |  | 4/1/2004 |  |  | N | No
G00_W40 | Warren 138 kV |  | VA | Warren | Withdrawn | APS | 264 | 264 | 264 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g00_w40_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2001 | N/A | N/A |  | 11/4/2002 |  | 5/1/2005 |  |  | N | No
G02 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 234 | 234 | 234 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g02_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/14/2001 | N/A | N/A |  | 10/23/2003 |  | 5/1/2006 |  |  | N | No
G02_W43 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g02_w43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2001 | N/A | N/A |  | 1/31/2003 |  | 7/1/2005 |  |  | N | No
G03 | Todd 69kV |  | MD | Dorchester | Withdrawn | DPL | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g03_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/22/2001 | N/A | N/A |  | 4/22/2002 |  | 12/1/2002 | 12/1/2002 |  | N | No
G04 | Brunner Island #2 | Brunner Island #2 | PA | York | Withdrawn | PPL | 749 | 14 | 14 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g04_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 1/1/2002 |  |  | N | No
G05 | Brunner Island #1 | Brunner Island #1 | PA | York | Withdrawn | PPL | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g05_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 1/1/2002 |  |  | N | No
G06 | Martins Creek #4 | Martins Creek #4 | PA | Northampton | In Service | PPL | 850 | 30 | 30 | 30 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2001 | N/A | N/A |  |  |  | 3/1/2012 | 3/1/2012 | 3/1/2012 | N | No
G06_W44 | Fort Martin 500 kV |  | WV | Monongalia | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g06_w44_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G06_W45 | Harrison 500 kV |  | WV | Harrison | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g06_w45_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G06_W47 | Black Oak 500 kV |  | PA | Allegheny | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g06_w47_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G07 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g07_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2001 | N/A | N/A |  | 12/4/2001 |  |  |  |  | N | No
G07_MTX1 | Sayreville 230kV | Neptune | NJ | Middlesex | In Service | JCPL | 790 | 790 |  |  | Energy | Merchant Transmission |  | DC | F/TWR 685; NF/TWR 105 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g07_mtx1_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g07_mtx1_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/g07_mtx1_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/g07_mtx1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/g07_mtx1_csa.pdf | Document Posted | N/A | N/A |  | 3/8/2001 | N/A | N/A | 1/4/2007 |  |  | 6/30/2007 |  | 6/30/2007 | S | No
G08 | Kearny | Kearny #12 | NJ | Hudson | In Service | PSEG | 215 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g08_fac2.pdf | Interim Study | https://www.pjm.com/pub/planning/project-queues/isa/g08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/13/2001 | N/A | N/A |  |  |  | 6/30/2001 |  | 6/30/2001 | N | No
G09 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 547 | 547 | 547.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G10 | Bergen | Bergen #2 | NJ | Bergen | In Service | PSEG | 550 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/20/2001 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
G11 | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 622 | 622 | 622 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2001 | N/A | N/A |  | 1/8/2002 |  |  |  |  | N | No
G12 | Burlington 230kV |  | NJ | Burlington | Withdrawn | PSEG | 316 | 316 | 316 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2001 | N/A | N/A |  | 1/4/2002 |  |  |  |  | N | No
G13 | Woodbourne |  | PA | Bucks | Withdrawn | PECO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g13_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2001 | N/A | N/A |  | 6/3/2003 |  | 12/1/2005 |  |  | N | No
G14 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 610 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G15 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 800 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2001 | N/A | N/A |  |  |  | 6/1/2004 |  |  | N | No
G16 | Bayview 26kV (Wind) |  | VA | Northampton | Withdrawn | DPL | 8 | 8 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g16_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g16_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/2/2001 | N/A | N/A |  |  |  | 12/1/2002 | 12/1/2002 |  | N | No
G17 | Burlington | Burlington #10 | NJ | Burlington | In Service | PSEG | 261 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 7/19/2002 |  | 7/19/2002 | N | No
G18 | Linden | Linden 5 & 6 | NJ | Union | In Service | PSEG | 172 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G19 | Linden | Linden 7 & 8 | NJ | Union | In Service | PSEG | 168 | 12 | 12 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 5/4/2004 |  | 5/4/2004 | N | No
G20 | Essex | Essex 9 | NJ | Essex | In Service | PSEG | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/5/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G21 | Meyersdale North | Meyersdale WF | PA | Somerset | In Service | PENELEC | 48 | 48 |  | 48 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g21_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g21_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/g21_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/g21_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 12/3/2003 | 12/3/2003 | 12/3/2003 | N | No
G22 | North Wales 34.5 kV | Merck | PA | Montgomery | In Service | PECO | 38 | 38 | 38 | 38 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/6/2001 | N/A | N/A |  |  |  | 9/30/2002 |  | 9/30/2002 | N | No
G22_MTX5 | Linden 230kV | Linden VFT | NJ | Union | In Service | PSEG | 330 | 330 | 330 |  | Capacity | Merchant Transmission |  | AC | TWR 330 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g22_mtx5_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g22_mtx5_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/g22_mtx5_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/g22_mtx5_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/g22_mtx5_csa.pdf | Document Posted | N/A | N/A | 6/1/2009 | 6/2/2001 | N/A | N/A | 9/16/2009 |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | S | No
G24 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 1.9 | 1.9 | 1.9 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g24_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g24_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 6/8/2002 |  | 6/8/2002 | N | No
G25 | Marion 26.4kV | Baler LF | NJ | Bergen | In Service | PSEG | 3.8 | 3.8 | 3.8 | 3.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/1/2001 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
G26 | England 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G27 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G28 | Vienna 230kV |  | MD | Dorchester | Withdrawn | DPL | 750 | 390 | 390 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  |  |  | 12/1/2004 |  |  | N | No
G29 | Indian River 138kV |  | DE | Sussex | Withdrawn | DPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g29_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2001 | N/A | N/A |  | 1/10/2002 |  |  |  |  | N | No
G30 | Perryman 115kV | Perryman 51 | MD | Harford | In Service | BGE | 152 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g30_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g30_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2001 | N/A | N/A |  |  |  | 6/1/2001 |  | 6/1/2001 | N | No
G30_W51 | Fort Martin 500 kV | Longview ST1 | WV | Monongalia | In Service | APS | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g30_w51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g30_w51_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g30_w51_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/g30_w51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/g30_w51_csa.pdf | Document Posted | N/A | N/A | 4/5/2009 | 5/21/2001 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 6/1/2008 | N | No
G30_W52 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 354 | 54 | 54 | 15.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g30_w52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g30_w52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g30_w52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/g30_w52_csa.pdf | Document Posted | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G30_W53 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 704 | 104 | 104 | 25.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g30_w53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g30_w53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g30_w53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/23/2001 | N/A | N/A |  |  |  | 6/1/2003 |  | 6/1/2003 | N | No
G30_W55 | Kempton 500 kV |  | MD | Unknown | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g30_w55_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2001 | N/A | N/A |  | 11/19/2002 |  | 1/1/2006 |  |  | N | No
G31 | Johnstown 230kV |  | PA | Indiana | Withdrawn | PENELEC | 610 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2001 | N/A | N/A |  | 4/11/2003 |  | 12/1/2005 |  |  | N | No
G32 | TMI - Juniata 500kV |  | PA | York | Withdrawn | ME | 675 | 675 | 675 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g32_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
G32_MTX6 | Linden 230kV, 138kV |  | NJ | Union | Withdrawn | PSEG | 365 | 365 | 365 |  | Capacity | Merchant Transmission |  | DC | R/TIR/365 F/TWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/g32_mtx6_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/g32_mtx6_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/3/2001 | N/A | N/A |  | 8/12/2004 |  | 12/31/2005 |  |  | S | No
G33 | Brunner Island 230kV |  | PA | York | Withdrawn | PPL | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g33_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2001 | N/A | N/A | [6 empty] | N | No
G34 | Frackville 69kV |  | PA | Schuylkill | Withdrawn | PPL | 51.6 | 51.6 | 51.6 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g34_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/2001 | N/A | N/A | [6 empty] | N | No
G35 | Chalk Point |  | MD | St. Mary's | Withdrawn | PEPCO | 340 | 340 | 340 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g35_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2001 | N/A | N/A |  | 9/25/2003 |  | 12/1/2004 |  |  | N | No
G36 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 107 | 107 | 107 | 5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g36_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/16/2001 | N/A | N/A |  |  |  | 4/1/2002 |  | 4/1/2002 | N | No
G36_W58 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g36_w58_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A | [6 empty] | N | No
G37 | Atlantic |  | NJ | Monmouth | Withdrawn | JCPL | 471 | 471 | 471 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 4/10/2002 |  |  |  |  | N | No
G38 | Portland |  | PA | Northampton | Withdrawn | ME | 558 | 86 | 86 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 4/10/2002 |  | 12/1/2004 |  |  | N | No
G39 | Joppatowne 13kV |  | MD | Baltimore County | Withdrawn | BGE | 4.2 | 4.2 | 4.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g39_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/19/2001 | N/A | N/A |  | 6/13/2002 |  | 6/1/2002 |  |  | N | No
G40 | Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2001 | N/A | N/A |  | 3/15/2002 |  |  |  |  | N | No
G41 | Croydon |  | PA | Bucks | Withdrawn | PECO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g41_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  | 3/18/2002 |  |  |  |  | N | No
G42 | Keystone/Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g42_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  | 4/10/2002 |  | 12/1/2004 |  |  | N | No
G43 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g43_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2001 | N/A | N/A |  | 4/9/2002 |  |  |  |  | N | No
G44 | Dupont Seaford 69kV | DuPont Seaford | DE | Sussex | In Service | DPL | 30 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g44_fea2.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g44_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g44_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2001 | N/A | N/A |  |  |  | 6/1/2002 |  | 6/1/2002 | N | No
G45 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g45_fea2.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2001 | N/A | N/A |  | 6/18/2003 |  | 12/1/2005 |  |  | N | No
G46 | Peach Bottom 500kV | Peach Bottom 2 & 3 | PA | York | In Service | PECO | 2256 | 70 | 70 | 38 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/g46_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 12/31/2001 | 12/31/2001 | 12/31/2001 | N | No
G47 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 32 | 32 | 32 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g47_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 4/10/2002 |  |  |  |  | N | No
G48 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 6/11/2003 |  | 12/1/2003 |  |  | N | No
G49 | Clinton 69kV |  | PA | Lycoming | Withdrawn | PPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/13/2002 |  |  |  |  | N | No
G50 | Dickerson 230kV |  | MD | Frederick | Withdrawn | PEPCO | 910 | 910 | 910 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 5/25/2002 |  | 12/1/2005 |  |  | N | No
G51 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/25/2002 |  |  |  |  | N | No
G51_W60 | Hatfield Ferry 500 kV | Greene Energy Resource Recovery Project | PA | Greene | Withdrawn | APS | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g51_w60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g51_w60_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g51_w60_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/g51_w60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/g51_w60_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 3/19/2013 | Customer Initiated Withdrawal | 8/1/2015 | 8/1/2015 |  | N | No
G51_W61 | Gates Hill 138 kV |  | PA | Fayette | Withdrawn | APS | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g51_w61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 7/1/2002 |  | 1/1/2006 |  |  | N | No
G51_W62 | Eastalco 230 kV | Catoctin CC | MD | Frederick | Withdrawn | APS | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g51_w62_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g51_w62_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g51_w62_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/g51_w62_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/g51_w62_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2001 | N/A | N/A |  | 4/21/2010 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
G51_W63 | Upton 34.5 kV | Upton | PA | Franklin | In Service | APS | 9.9 | 9.9 | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/g51_w63_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/g51_w63_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/g51_w63_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/g51_w63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2001 | N/A | N/A |  |  |  | 4/1/2003 |  | 4/1/2003 | N | No
H01 | Susquehanna 500kV |  | PA | Columbia | Withdrawn | PPL | 52 | 2 | 2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2001 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 |  | N | No
H02 | Susquehanna 230kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 9 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h02_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/20/2001 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
H03 | Susquehanna 500kV | Susquehanna #2 | PA | Columbia | In Service | PPL | 1153 | 9 | 9 | 9 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/21/2001 | N/A | N/A |  |  |  | 12/1/2003 | 12/1/2003 | 12/1/2003 | N | No
H04 | Wright 69kV (Wind) |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h04_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2001 | N/A | N/A |  |  |  | 12/1/2002 |  |  | N | No
H04_W64 | Henry 138 kV |  | WV | Grant | Withdrawn | APS | 150 | 150 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h04_w64_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h04_w64_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h04_w64_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/17/2001 | N/A | N/A |  | 6/29/2004 |  | 12/31/2005 |  |  | N | No
H05 | Riverside 230/115kV |  | MD | Baltimore County | Withdrawn | BGE | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2001 | N/A | N/A |  | 8/6/2002 |  | 12/1/2007 |  |  | N | No
H05_MTX9 |  |  | MD | Calvert | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
H05_W65 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h05_w65_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2001 | N/A | N/A |  |  |  | 7/1/2005 |  |  | N | No
H06 | Chichester 230kV | Phillips Island | PA | Philadelphia | In Service | PECO | 750 | 25 | 25 | 25 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/h06_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2001 | N/A | N/A |  |  |  | 12/31/2004 |  | 12/31/2004 | N | No
H07 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | AEC | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2001 | N/A | N/A |  | 6/11/2002 |  | 6/1/2004 |  |  | N | No
H08 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2001 | N/A | N/A |  | 6/18/2002 |  | 12/1/2005 |  |  | N | No
H08_W66 | Windsor 138 kV |  | WV | Unknown | Withdrawn | APS | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h08_w66_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/14/2001 | N/A | N/A |  |  |  | 6/1/2005 |  |  | N | No
H09 | Hooversville & Johns-Alt 230kV |  | PA | Somerset | Withdrawn | PENELEC | 635 | 635 | 635 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2001 | N/A | N/A |  | 11/4/2002 |  | 12/1/2006 |  |  | N | No
H10 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2001 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
H11 | New Freedom - Cardiff 230kV |  | NJ | Gloucester | Withdrawn | AEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2001 | N/A | N/A |  | 7/22/2002 |  | 12/1/2005 |  |  | N | No
H12 | Edgemoor 230kV | Hay Road 4 | DE | New Castle | In Service | DPL | 189 | 10 | 10 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/20/2001 | N/A | N/A |  |  |  | 12/1/2005 |  | 12/1/2005 | N | No
H13 | Dolfield | Owings Mills | MD | Baltimore County | In Service | BGE | 9 | 9 | 0 | 9 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/27/2001 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
H14 | TMI-Peach Bottom 500kV |  | PA | York | Withdrawn | ME | 1060 | 1060 | 1060 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2001 | N/A | N/A |  | 10/29/2002 |  | 12/1/2005 |  |  | N | No
H14_W67 | Enon 138 kV |  | PA | Unknown | Withdrawn | APS | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h14_w67_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2001 | N/A | N/A |  | 7/8/2002 |  | 1/1/2007 |  |  | N | No
H15 | Chapman-Moshannon 230kV |  | PA | Clearfield | Withdrawn | PENELEC | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2001 | N/A | N/A |  | 11/4/2002 |  | 12/1/2006 |  |  | N | No
H16 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | 565 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2001 | N/A | N/A |  | 9/25/2002 |  | 12/1/2005 |  |  | N | No
H17 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 2336 | 115 | 115 | 83 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h17_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h17_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/h17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 6/18/2008 | 6/18/2008 | 6/1/2008 | N | No
H18 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 78 | 78 | 12 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h18_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h18_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/h18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H19 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 1221 | 43 | 43 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h19_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h19_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/h19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2002 | N/A | N/A |  |  |  | 8/26/2008 | 8/26/2008 | 12/1/2007 | N | No
H20 | Oak Grove 13.8kV |  | MD | Prince George's | In Service | PEPCO | 3.5 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/31/2003 | 1/21/2002 | N/A | N/A |  |  |  | 12/31/2003 | 12/31/2003 | 5/31/2003 | N | No
H20_CE12 |  |  | N/A | N/A | Withdrawn | ComEd | 700 |  |  |  | Energy | Generation Interconnection | Coal |  |  | N/A | [5 empty] | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2002 | N/A | N/A |  |  |  | 6/6/2001 |  |  | N | No
H21 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2002 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
H21_W68 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 | 300 | 0 | 264 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h21_w68_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h21_w68_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h21_w68_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/h21_w68_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/h21_w68_csa.pdf | Document Posted | N/A | N/A |  | 1/29/2002 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/30/2007 | N | No
H22 | Erie South |  | PA | Erie | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2002 | N/A | N/A |  | 3/17/2003 |  | 6/1/2006 |  |  | N | No
H23 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 10 | 10 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2002 | N/A | N/A |  | 10/25/2002 |  | 12/1/2002 |  |  | N | No
H23_W69 | Bluestone Dam 46 kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | 41 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h23_w69_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h23_w69_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2002 | N/A | N/A |  |  |  | 6/1/2006 |  |  | N | No
H23_W70 | Kelso Gap 138 kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 | 100 |  | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h23_w70_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h23_w70_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/h23_w70_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/h23_w70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/h23_w70_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2002 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
H24 | Forest 230kV |  | PA | Elk | Withdrawn | PENELEC | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 11/13/2002 |  | 6/1/2006 |  |  | N | No
H25 | Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h25_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 6/1/2007 |  |  | N | No
H26 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h26_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 7/3/2003 |  | 12/1/2003 |  |  | N | No
H27 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 2.9 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/h27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/h27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 12/1/2002 |  | 12/1/2002 | N | No
H27_W71 | McConnellsburg-Guilford 138 kV |  | PA | Fulton | Withdrawn | APS | 252 | 252 | 252 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h27_w71_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  | 4/10/2003 |  | 5/1/2004 |  |  | N | No
H27_W72 | McConnellsburg-Cherry Run 138 kV |  | PA | Fulton | Withdrawn | APS | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/h27_w72_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2002 | N/A | N/A |  |  |  | 5/1/2004 |  |  | N | No
I01 | Ontario 23kV | Jersey Atlantic WF | NJ | Atlantic | In Service | AEC | 7.5 | 7.5 |  | 7.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i01_csa.pdf | Document Posted | N/A | N/A | 7/1/2005 | 2/13/2002 | N/A | N/A | 12/20/2005 |  |  | 12/30/2005 |  | 12/30/2005 | N | No
I02 | Erie West-Ashtabula 345kV |  | OH | Ashtabula | Withdrawn | PENELEC | 1998 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2002 | N/A | N/A |  | 5/7/2003 |  | 12/1/2007 |  |  | N | No
I02_W73 | Harrison 500 kV | Harrison 1, 2, 3 | WV | Harrison | In Service | APS | 35 | 35 | 35 | 21 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i02_w73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i02_w73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i02_w73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/7/2002 | N/A | N/A |  |  |  | 9/22/2004 |  | 9/22/2004 | N | No
I03 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2002 | N/A | N/A |  | 4/28/2003 | Customer Milestone Not Met | 6/1/2005 |  |  | N | No
I03_W74 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS | 40 | 40 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i03_w74_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i03_w74_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/i03_w74_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/i03_w74_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i03_w74_csa.pdf | Document Posted | N/A | N/A |  | 3/27/2002 | N/A | N/A |  | 11/18/2009 | Customer Initiated Withdrawal | 9/30/2011 | 9/30/2011 |  | N | No
I04 | Somerset-Allegheny 115kV | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 45 | 45 | 9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i04_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/i04_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 3/29/2002 | N/A | N/A | 12/1/2005 | 4/14/2005 |  | 12/31/2005 |  |  | N | No
I05 | Whiteoak (sub153) 13kV |  | MD | Calvert | Withdrawn | PEPCO | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2002 | N/A | N/A |  | 5/21/2003 |  | 12/1/2003 |  |  | N | No
I06 | Greenwich Pumphousse 2.4kV | Repauno Unit 1 | NJ | Unknown | In Service | AEC | 1.7 | 1.7 |  | 1.7 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/8/2002 | N/A | N/A |  |  |  | 5/1/2003 |  | 5/1/2003 | N | No
I07 | W. H. Sammis 345kV |  | OH | Jefferson | Withdrawn | PENELEC | 1860 | 1860 | 1860 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i07_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 4/11/2002 | N/A | N/A |  | 12/10/2002 |  | 5/1/2005 |  |  | N | No
I07_MTX8 |  |  | NJ | Middlesex | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2001 | N/A | N/A | [6 empty] | S | No
I08 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2002 | N/A | N/A |  |  |  | 5/1/2005 |  |  | N | No
I09 | Bath County 500kV |  | VA | Bath | Withdrawn | APS | 252 | 252 | 252 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2002 | N/A | N/A |  | 1/15/2004 |  | 6/1/2009 |  |  | N | No
I10 | Bethesda (Sub 6) |  | MD | Montgomery | In Service | PEPCO | 2 | 2 |  | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i10_csa.pdf | Document Posted | N/A | N/A | 7/1/2004 | 6/11/2002 | N/A | N/A | 9/20/2004 |  |  | 10/1/2004 |  | 10/1/2004 | N | No
I11 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2002 | N/A | N/A |  | 2/23/2004 |  | 5/1/2006 |  |  | N | No
I12 | Grand Point 69kV | Orchard Park Generating Station | PA | Franklin | In Service | APS | 30.5 | 23.3 | 23.3 | 29.6 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i12_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2002 | N/A | N/A |  |  |  | 1/1/2004 |  | 1/1/2004 | N | No
I13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 29.4 | 0 | 29.4 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/i13_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/i13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i13_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2002 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 3/6/2008 | N | No
I14 | Upton 34.5kV | Upton | PA | Franklin | In Service | APS | 14 | 4.1 | 4.1 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/i14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/i14_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2002 | N/A | N/A |  |  |  | 6/1/2004 |  | 6/1/2004 | N | No
I15 | Scalp Level 115kV |  | PA | Somerset | Withdrawn | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 1/7/2003 |  | 5/1/2003 |  |  | N | No
I16 | Atwell 25kV |  | PA | Butler | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I17 | Pine Grove 69kV |  | PA | Berks | Withdrawn | PPL | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I18 | South Park 25kV |  | PA | Allegheny | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  |  |  | 5/1/2003 |  |  | N | No
I19 | Level Green 25kV |  | PA | Westmoreland | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I20 | Wycoff 25kV |  | PA | Allegheny | Withdrawn | APS | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 2/7/2003 |  | 5/1/2003 |  |  | N | No
I22 | Hinton 46kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | 41 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/i22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/i22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2002 | N/A | N/A |  | 11/4/2003 |  | 9/1/2004 |  |  | N | No
J01 | Monterey 69kV |  | VA | Highland | Withdrawn | APS | 41 | 41 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2002 | N/A | N/A |  | 1/20/2004 |  | 12/31/2004 |  |  | N | No
J01_MTX | Hope Creek 500kV Cedar Creek 230kV |  | DC | Unknown | Withdrawn | PSEG | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j01_mtx_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2002 | N/A | N/A |  | 12/5/2003 |  |  |  |  | S | No
J02 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2002 | N/A | N/A |  |  |  | 12/1/2005 |  |  | N | No
J02_MTX11 | Vienna 230kV - Chalk Point 230kV |  | MD | Dorchester | Withdrawn | Unknown | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2003 | N/A | N/A |  | 4/28/2005 |  | 1/1/2006 |  |  | S | No
J02_MTX13 | Keeney XFMR 230/138kV | Keeney Autotransformer AT20 | DE | New Castle | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j02_mtx13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/j02_mtx13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/j02_mtx13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/16/2002 | N/A | N/A |  | 12/8/2003 |  | 5/31/2003 |  | 5/31/2003 | S | No
J03 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | 565 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2002 | N/A | N/A |  | 2/12/2004 |  | 12/1/2005 |  |  | N | No
J03_CE14 | Sublette Wind Farm |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/j03_ce14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/15/2002 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
J04 | Bustleton 138kV |  | NJ | Burlington | Withdrawn | PSEG | 7 | 7 | 7 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j04_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/18/2002 | N/A | N/A |  | 8/4/2004 |  | 11/1/2004 |  |  | N | No
J04_CE15 | West Brooklyn Wind Farm |  | IL | Lasalle | Withdrawn | ComEd | 25 | 25 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/j04_ce15_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/20/2002 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
J05 | Huron 69kV | Borgata D1 / D2 | NJ | Atlantic | In Service | AEC | 8 | 8 | 8 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/j05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/25/2002 | N/A | N/A |  |  |  | 7/30/2003 |  | 7/30/2003 | N | No
J06 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 34 | 34 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j06_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/j06_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/j06_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 10/25/2002 | N/A | N/A |  | 5/14/2003 |  | 12/1/2003 |  |  | N | No
J06_CE16 |  |  | N/A | N/A | Withdrawn | ComEd | 100 |  |  |  | Energy | Generation Interconnection | Hydro |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2002 | N/A | N/A |  |  |  | 8/1/2005 |  |  | N | No
J07 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS | 155 | 155 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j07_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/j07_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/j07_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/j07_csa.pdf | Document Posted | N/A | N/A |  | 11/1/2002 | N/A | N/A |  | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
J07_MTX12 | Cheswold XFMR 138/69kV |  | DE | Kent | In Service | DPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/j07_mtx12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/j07_mtx12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/j07_mtx12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2002 | N/A | N/A |  |  |  | 12/31/2003 |  | 12/31/2003 | S | No
J08 | Whiteoak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 6 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/j08_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/j08_csa.pdf | Document Posted | N/A | N/A | 4/1/2004 | 12/12/2002 | N/A | N/A | 4/30/2004 |  |  | 8/15/2004 |  | 8/15/2004 | N | No
J08_MTX14 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 80 | 80 | 80 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 4/22/2003 |  | 6/30/2005 |  |  | S | No
J08_MTX15 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | Unknown | 790 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2003 | N/A | N/A |  | 9/26/2003 |  | 6/30/2006 |  |  | S | No
J09 | Harrisburg Authority | Harrisburg Municipal Solid Waste Authority | PA | Dauphin | In Service | PPL | 26 | 26 | 26 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/j09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/j09_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/j09_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/j09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/j09_csa.pdf | Document Posted | N/A | N/A | 6/30/2005 | 1/31/2003 | N/A | N/A | 2/1/2006 |  |  | 4/24/2006 |  | 4/24/2006 | N | No
K01 | Salem 69kV | Mannington Mills Units 1,2,3 | NJ | Salem | In Service | AEC | 8 | 8 | 8 | 8 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/10/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K02 | East Towanda-Moshannon 230kV | Laurel Hill | PA | Lycoming | In Service | PENELEC | 70 | 70 | 0 | 70 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k02_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k02_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k02_csa.pdf | Document Posted | N/A | N/A | 9/17/2012 | 2/25/2003 | N/A | N/A | 9/19/2012 |  |  | 10/29/2012 | 10/29/2012 | 9/25/2012 | N | No
K02_CE18 | Baileyville Wind Farm | Baileyville Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/k02_ce18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k02_ce18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k02_ce18_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2003 | N/A | N/A |  | 8/26/2013 | Customer Milestone Not Met | 12/31/2011 | 12/31/2011 |  | N | No
K03 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 39.6 | 39.6 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k03_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2003 | N/A | N/A |  | 6/5/2003 |  |  |  |  | N | No
K04 | Camden 26kV | Pennsauken Sanitary Landfill / Aluminum Shapes | NJ | Camden | In Service | PSEG | 5.1 | 5.1 | 0 | 5.1 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k04_csa.pdf | Document Posted | N/A | N/A | 9/15/2004 | 4/15/2003 | N/A | N/A | 10/15/2004 |  |  | 6/30/2005 |  | 6/30/2005 | N | No
K04_CE17 | Lena Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/k04_ce17_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/15/2003 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
K04_CE19 | Freeport Wind Farm | Freeport Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/k04_ce19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k04_ce19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k04_ce19_csa.pdf | Document Posted | N/A | N/A |  | 4/15/2003 | N/A | N/A |  | 9/26/2011 | Customer Milestone Not Met | 10/15/2011 | 10/15/2011 |  | N | No
K05 | Cedar 69kV |  | NJ | Ocean | Withdrawn | AEC | 0.1 | 0.12 |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/23/2003 | N/A | N/A |  |  |  | 6/1/2003 |  |  | N | No
K06 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k06_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/6/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K07 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 10 | 5 | 5 | 4.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2003 | N/A | N/A | 11/1/2004 |  |  | 11/1/2004 |  | 11/1/2004 | N | No
K07_CE20 | Benson Wind Farm | Benson Wind Farm | IL | Woodford | Withdrawn | ComEd | 158 | 158 | 31.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/k07_ce20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k07_ce20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k07_ce20_csa.pdf | Document Posted | N/A | N/A |  | 5/16/2003 | N/A | N/A |  | 9/18/2009 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
K08 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 |  | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/21/2003 | N/A | N/A |  | 8/13/2003 |  |  |  |  | N | No
K09 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 34 | 34 | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k09_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2003 | N/A | N/A |  | 1/9/2004 |  | 6/1/2004 |  |  | N | No
K10 | Somerset 115kV |  | PA | Somerset | Withdrawn | PENELEC | 6 |  | 6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k10_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k10_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/16/2003 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
K11 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 |  | 60 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k11_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k11_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2003 | N/A | N/A |  |  |  | 10/1/2007 | 10/1/2007 | 9/30/2007 | N | No
K12 | Somerset-Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 13 | 13.6 | 2.72 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k12_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k12_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A | 11/1/2005 | 7/28/2003 | N/A | N/A | 12/1/2005 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
K13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 0 | 5.88 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k13_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k13_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2003 | N/A | N/A |  |  |  | 3/6/2008 | 3/6/2008 | 9/1/2007 | N | No
K14 | Monterey 69kV |  | VA | Highland | Withdrawn | APS | 7 |  | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 1/20/2004 |  |  |  |  | N | No
K15 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 6.8 |  | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 1/9/2004 |  |  |  |  | N | No
K16 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9.9 |  | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 2/19/2004 |  | 8/1/2004 |  |  | N | No
K17 | Emerald 6 25kV |  | PA | Greene | Withdrawn | APS | 5 |  | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k17_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2003 | N/A | N/A |  | 2/12/2004 |  | 6/1/2004 |  |  | N | No
K18 | Arnold (Green Mountain) 115kV | Green Mountain | PA | Somerset | In Service | PENELEC | 10.4 |  | 2.08 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 8/13/2004 |  | 8/13/2004 | N | No
K19 | Backbone Mountain 138kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 0 | 18 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k19_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 6/1/2001 |  | 11/12/2006 | N | No
K20 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 |  | 3 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 4/1/2002 |  | 7/28/2005 | N | No
K21 | East Carbondale 69kV | Waymart | PA | Wayne | In Service | PPL | 69 |  | 13 | 64.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K22 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 9 |  | 1.8 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k22_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 1/1/1999 |  | 8/13/2004 | N | No
K23 | Meyersdale North | Meyersdale WF | PA | Somerset | In Service | PENELEC | 48 |  | 6 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2003 | N/A | N/A |  |  |  | 7/1/2004 |  | 7/1/2004 | N | No
K24 | Henry 138kV |  | WV | Grant | Withdrawn | APS | 150 |  | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k24_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 7/21/2004 |  | 12/1/2005 |  |  | N | No
K25 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS | 40 |  | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k25_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k25_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k25_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 11/12/2009 | Customer Initiated Withdrawal | 9/30/2011 | 9/30/2011 |  | N | No
K26 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS | 155 |  | 31 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k26_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/k26_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/k26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k26_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
K27 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE | 1740 |  | 35 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k27_imp2.pdf | Interim Study |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k27_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/30/2003 | N/A | N/A |  | 8/20/2005 |  | 6/1/2004 |  |  | N | No
K28 | Kelso Gap 138kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 |  | 20 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/k28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/k28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/k28_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2003 | N/A | N/A | 10/26/2010 |  |  | 10/26/2010 | 10/26/2010 | 11/6/2006 | N | No
K29 | Ontario |  | NJ | Atlantic | Withdrawn | AEC | 7.5 |  | 1.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/k29_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2003 | N/A | N/A |  | 9/28/2004 |  |  |  |  | N | No
L01 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2003 | N/A | N/A |  | 4/8/2004 |  | 1/6/2008 |  |  | N | No
L01_AEP137 | Bellefonte-N. Proctorville 138kV |  | OH | Lawrence | Withdrawn | AEP | 165 | 165 | 165 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Not Required |  | Not Required | https://www.pjm.com/pub/planning/project-queues/facilities/l01_aep137_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/l01_aep137_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l01_aep137_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2003 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
L01_CE21 | Pearl City Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 15 | 15 | 3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l01_ce21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l01_ce21_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/5/2003 | N/A | N/A |  | 11/1/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
L02 | Pleasantville 12 kV | Pleasantville / AC LF Unit 1 | NJ | Atlantic | In Service | AEC | 1.5 | 1.5 | 1.4 | 0.07 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l02_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2003 | N/A | N/A |  |  |  | 1/30/2005 |  | 1/30/2005 | N | No
L03 | Morgantown | Morgantown LF | PA | Berks | Withdrawn | PPL | 0.8 | 0.8 |  |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l03_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l03_csa.pdf | Document Posted | N/A | N/A | 2/6/2006 | 9/10/2003 | N/A | N/A | 5/1/2006 | 6/3/2008 | Customer Initiated Withdrawal | 5/31/2009 |  |  | N | No
L04 | Chestnut Ridge 138 kV |  | PA | Westmoreland | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2003 | N/A | N/A |  | 7/7/2004 |  | 12/31/2005 |  |  | N | No
L05 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2003 | N/A | N/A |  | 4/30/2004 |  | 6/30/2005 |  |  | N | No
L05_CE22 | Camp Grove | Camp Grove Wind Farm | IL | Stark | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l05_ce22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l05_ce22_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l05_ce22_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/l05_ce22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l05_ce22_csa.pdf | Document Posted | N/A | N/A |  | 10/15/2003 | N/A | N/A |  |  |  | 12/14/2007 | 12/14/2007 | 9/1/2006 | N | No
L06 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2003 | N/A | N/A |  | 6/22/2004 |  | 6/1/2006 |  |  | N | No
L07 | Jenkins-Harwood #2 69kV | Mountain Top | PA | Luzerne | Withdrawn | PPL | 42.9 | 42.9 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l07_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l07_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/23/2003 | N/A | N/A |  | 5/18/2005 |  | 12/31/2005 |  |  | N | No
L08 | Holtwood 69kV | Holtwood | PA | Lancaster | In Service | PPL | 109 | 2 | 2 | 2 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l08_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l08_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L09 | Montour #1 230kV | Montour #1 | PA | Montour | In Service | PPL | 761 | 2 | 2 | 2 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l09_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/7/2003 | N/A | N/A |  |  |  | 10/1/2003 |  | 8/16/2004 | N | No
L10 | Hatfield 500 kV |  | PA | Greene | Withdrawn | APS | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l10_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2003 | N/A | N/A |  | 7/12/2004 |  | 12/1/2006 |  |  | N | No
L11 | Rockwood 25 kV |  | PA | Somerset | Withdrawn | APS | 9.9 | 9.9 | 2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l11_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2003 | N/A | N/A |  | 4/15/2005 | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
L12 | Essex |  | NJ | Essex | Withdrawn | PSEG | 6 | 6.2 | 6.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l12_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/4/2003 | N/A | N/A |  | 8/31/2004 |  | 9/30/2004 |  |  | N | No
L12_CE23 | West Brooklyn II | West Brooklyn WF | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l12_ce23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l12_ce23_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/8/2003 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
L12_CE24 | Willow Creek Wind Farm |  | IL | Lee | Withdrawn | ComEd | 79 | 79 | 15.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l12_ce24_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2003 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 12/1/2005 |  |  | N | No
L13 | Rockwood | Casselman WF1 | PA | Somerset | In Service | PENELEC | 40 | 40 | 8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l13_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l13_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/l13_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l13_csa.pdf | Document Posted | N/A | N/A |  | 12/19/2003 | N/A | N/A |  |  |  | 1/11/2008 | 1/11/2008 | 12/31/2007 | N | No
L13_CE25 | Geneva | City of Geneva Units 1-5 | IL | Kane | In Service | ComEd | 29 | 29 | 29 | 29 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l13_ce25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l13_ce25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l13_ce25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2003 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
L13_CE26 | Heartland Grand Ridge |  | IL | Lasalle | Withdrawn | ComEd | 175 | 175 | 35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l13_ce26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l13_ce26_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l13_ce26_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2004 | N/A | N/A |  | 8/9/2006 | Customer Initiated Withdrawal | 10/30/2006 |  |  | N | No
L13_CE27 | Heartland Wind Livingston |  | IL | Livingston | Withdrawn | ComEd | 225 | 225 | 45 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l13_ce27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l13_ce27_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2004 | N/A | N/A |  | 10/3/2005 | Customer Initiated Withdrawal | 10/30/2006 |  |  | N | No
L14 | Berlin 69kV Tap 5 MW |  | MD | Worcester | Withdrawn | AEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2004 | N/A | N/A |  | 8/19/2004 | Customer Milestone Not Met | 7/1/2005 |  |  | N | No
L15 | Buffalo Road-Carry East to NY |  | NY | Chautauqua | Withdrawn | PENELEC | 34 | 34 | 34 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/l15_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2004 | N/A | N/A |  | 10/18/2004 | Customer Milestone Not Met | 11/1/2005 |  |  | S | No
L16 | Monterey 69KV |  | VA | Highland | Withdrawn | APS | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l16_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2004 | N/A | N/A |  | 9/20/2004 |  | 12/1/2005 |  |  | N | No
L17 | Rolling Hills | Rolling Hills | PA | Berks | Deactivated | ME | 6 | 6 |  | 6 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/l17_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l17_csa.pdf | Document Posted | N/A | N/A | 2/7/2005 | 1/22/2004 | N/A | N/A | 3/20/2005 |  |  | 4/1/2005 |  | 4/1/2005 | N | No
L18 | Bear Creek | Bear Creek WF | PA | Luzerne | In Service | PPL | 26 | 26 | 5.2 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l18_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l18_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/l18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l18_csa.pdf | Document Posted | N/A | N/A | 11/15/2005 | 1/28/2004 | N/A | N/A | 12/31/2005 |  |  | 2/26/2006 |  | 2/26/2006 | N | No
L19 | Karthaus 230kV | Karthaus | PA | Clearfield | Withdrawn | APS | 290 | 290 | 290 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/l19_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/l19_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/l19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/l19_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2004 | N/A | N/A |  | 3/24/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
L20 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 10 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l20_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2004 | N/A | N/A |  | 8/4/2004 |  | 3/31/2005 |  |  | N | No
L21 | Hudson #2 |  | NJ | Hudson | Withdrawn | PSEG | 0 |  | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/l21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2004 | N/A | N/A |  | 9/2/2004 |  | 1/1/2006 |  |  | N | No
M01 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | 1800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2004 | N/A | N/A |  | 3/18/2005 | Customer Milestone Not Met | 1/1/2008 |  |  | N | No
M02 | Jenkins-Harwood #2 | Mountain Top | PA | Luzerne | Withdrawn | PPL | 51 | 8.1 | 8.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m02_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m02_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2004 | N/A | N/A |  | 5/18/2005 |  | 12/31/2005 |  |  | N | No
M03 | Cardiff |  | NJ | Atlantic | Withdrawn | AEC | 450 | 150 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m03_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2004 | N/A | N/A |  | 4/5/2005 | Customer Milestone Not Met | 6/1/2005 |  |  | N | No
M04 | Calvert Cliffs | Clavert Cliffs 1 and 2 | MD | Calvert | In Service | BGE | 1740 | 63 |  | 63 | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m04_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/25/2004 | N/A | N/A |  |  |  | 6/30/2005 |  | 6/30/2005 | N | No
M05 | Black Oak - Bedington | Black Oak - Bedington Wave Traps 500kV | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/m05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/m05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/m05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/5/2004 | N/A | N/A |  |  |  | 12/31/2005 |  | 12/31/2005 | S | No
M06 | Grand Point |  | PA | Franklin | Withdrawn | APS | 30.5 | 30.5 | 30.5 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m06_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2004 | N/A | N/A |  | 10/20/2005 |  | 6/1/2006 |  |  | N | No
M07 | Peckville (Archbald) | Archbald | PA | Lackawanna | In Service | PPL | 50 | 6.3 | 6.3 | 6.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2004 | N/A | N/A |  |  |  | 3/15/2004 |  | 3/15/2004 | N | No
M08 | Somerset-Allegheny | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 65 | 65 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m08_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/29/2004 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
M09 | Island Road |  | PA | Philadelphia | Withdrawn | PECO | 50 | 50 |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/m09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/m09_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2004 | N/A | N/A |  |  | Customer Initiated Withdrawal | 8/31/2007 |  |  | S | No
M09_CE28 | Wempletown 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m09_ce28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2004 | N/A | N/A |  | 2/11/2005 | Customer Initiated Withdrawal | 11/30/2006 |  |  | N | No
M10 | Vienna/Chalk Point |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2004 | N/A | N/A |  | 10/28/2004 | Customer Initiated Withdrawal | 1/1/2008 |  |  | S | No
M11 | Susquehanna #1 | Susquehanna #1 | PA | Luzerne | In Service | PPL | 2520 | 111 | 111 | 111 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m11_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/m11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m11_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 7/24/2010 | 7/24/2010 | 7/24/2010 | N | No
M12 | Susquehanna #2 | Susquehanna #2 | PA | Luzerne | In Service | PPL | 2520 | 107 | 107 | 107 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m12_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/m12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m12_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2004 | N/A | N/A |  |  |  | 8/18/2011 | 8/18/2011 | 8/18/2011 | N | No
M13 | Amboy |  | IL | Lee | Withdrawn | ComEd | 3.3 | 3.3 | 3.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m13_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/27/2004 | N/A | N/A |  | 1/4/2005 | Customer Initiated Withdrawal | 6/1/2005 |  |  | N | No
M14 | Churchtown-Cumberland 230kV |  | NJ | Atlantic | Withdrawn | AEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m14_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2004 | N/A | N/A |  | 12/13/2004 | Customer Initiated Withdrawal | 6/15/2006 |  |  | N | No
M15 | Union City 230kV |  | PA | Erie | Withdrawn | PENELEC | 302 | 302 | 301.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m15_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2004 | N/A | N/A |  | 10/17/2005 | Customer Initiated Withdrawal | 6/1/2007 |  |  | N | No
M16 | Peach Bottom T1 |  | PA | York | Withdrawn | PECO | 0 |  |  |  | Energy | Merchant Transmission | Nuclear | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2004 | N/A | N/A |  | 12/7/2004 | Customer Initiated Withdrawal | 11/1/2005 |  |  | S | No
M17 | Mount Zion 13.8 kV |  | MD | Montgomery | Withdrawn | PEPCO | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2004 | N/A | N/A |  | 9/30/2004 |  | 5/1/2005 |  |  | N | No
M18 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 1.7 | 1.65 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m18_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/17/2004 | N/A | N/A |  | 1/3/2006 |  | 12/31/2005 |  |  | N | No
M19 | Otter Point | Otter Point LF-1 | MD | Baltimore County | In Service | BGE | 4.5 | 4.5 |  | 4.5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m19_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2004 | N/A | N/A |  |  |  | 9/1/2006 |  | 9/1/2006 | N | No
M20 | Chestnut Valley 25kV |  | PA | Fayette | Withdrawn | APS | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m20_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/13/2004 | N/A | N/A |  | 7/7/2006 | Customer Initiated Withdrawal | 5/30/2006 |  |  | N | No
M21 | Rochelle | City of Rochelle, IL | IL | Ogle | In Service | ComEd | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m21_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m21_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/23/2004 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 11/11/2005 | N | No
M22 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m22_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2004 | N/A | N/A |  | 10/23/2006 | Customer Milestone Not Met | 2/1/2008 |  |  | N | No
M23 | Henry 138kV | Mt Storm WF | WV | Grant | Withdrawn | APS | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m23_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m23_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/m23_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m23_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2004 | N/A | N/A |  | 2/4/2016 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
M24 | Grassy Falls | Beech Ridge / Field Mtn WF | WV | Greenbrier | In Service | APS | 186 | 186 | 37.2 | 132.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m24_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m24_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/m24_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m24_csa.pdf | Document Posted | N/A | N/A | 12/17/2009 | 7/27/2004 | N/A | N/A | 1/15/2010 |  |  | 12/1/2014 | 12/1/2014 | 11/1/2007 | N | No
M25 | South Reading (United Corrstack) 69kV | United Corrstack | PA | Berks | Withdrawn | ME | 12 | 11 | 2 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2004 | N/A | N/A |  | 11/18/2005 | Customer Milestone Not Met | 12/1/2006 |  |  | N | No
M26 | Champion | Beech Hollow | PA | Washington | Withdrawn | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m26_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/m26_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/m26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/m26_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2004 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
M27 | Eddystone 138kV | Eddystone | PA | Delaware | In Service | PECO | 1408 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2004 | N/A | N/A |  |  |  | 6/17/2004 |  | 12/1/2006 | N | No
M28 | Elwood-Dresden 345kV | Indeck-Elwood Energy Center | IL | Will | Withdrawn | ComEd | 700 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/m28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/m28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/m28_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 7/30/2004 | N/A | N/A |  | 11/30/2006 | Customer Milestone Not Met | 12/31/2011 | 12/31/2011 |  | N | No
1267313 | PJM-FE |  | N/A | N/A | Withdrawn | American Municipal Power, Inc. | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2010 | 6/1/2011 | [6 empty] | FF | No
1302456 | PJM-TVA |  | N/A | N/A | Confirmed | TVAM | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 5/1/2010 | 1/1/2015 | [6 empty] | FF | No
1363850 | CIN-PJM |  | N/A | N/A | Confirmed | Wabash Valley Power Association | 82 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2014 | 1/1/2019 | [6 empty] | FF | No
1363870 | CIN-PJM |  | N/A | N/A | Confirmed | Wabash Valley Power Association | 87 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2014 | 1/1/2014 | [6 empty] | FF | No
845542 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/20/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
845546 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/20/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
852544 | PJM-WEC |  | N/A | N/A | Confirmed | Wisconsin Public Power | 10 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/8/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
930679 | AMIL-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Company | 43 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2009 | 9/30/2035 | [6 empty] | FF | No
931128 | AMIL-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Company | 25 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2009 | 9/30/2035 | [6 empty] | FF | No
931224 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Company | 63 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/19/2008 | 6/1/2010 | 9/30/2035 | [6 empty] | FF | No
931229 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Company | 62 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/19/2008 | 6/1/2012 | 9/30/2035 | [6 empty] | FF | No
931258 | AMIL-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Company | 240 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/19/2008 | 1/1/2014 | 9/30/2035 | [6 empty] | FF | No
945095 | CIN-PJM |  | N/A | N/A | Confirmed | Dayton | 368 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/15/2008 | 8/1/2008 | 8/1/2020 | [6 empty] | FF | No
963385 | PJM-CPLE |  | N/A | N/A | Confirmed | SEPA | 89 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/11/2008 | 11/1/2008 | 11/1/2013 | [6 empty] | FF | No
999367 | FE-PJM |  | N/A | N/A | Withdrawn | First Energy Solutions | 108 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/26/2008 | 10/1/2008 | 6/1/2009 | [6 empty] | FF | No
N01 | Graceton-Nottingham 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n01_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2004 | N/A | N/A |  | 8/30/2005 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
N02 | Peach Bottom |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2004 | N/A | N/A |  | 8/30/2005 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
N02_AEP139 | McClung 138kV |  | WV | Greenbrier | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n02_aep139_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2004 | N/A | N/A |  | 6/23/2005 | Customer Milestone Not Met | 9/1/2006 |  |  | N | No
N03 | Edgemoor 69kV | Hay Road 2 | DE | New Castle | In Service | DPL | 121 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N04 | Edgemoor 230kV |  | DE | New Castle | Withdrawn | DPL | 189 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2004 | N/A | N/A |  | 10/12/2004 |  | 8/9/2004 |  |  | N | No
N05 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/25/2004 | N/A | N/A |  |  |  | 8/9/2004 |  | 6/1/2006 | N | No
N06 | Hamilton 12kV | Pine Hurst Acres | PA | Northumberland | In Service | PPL | 0 | 0.047 |  | 0.047 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n06_csa.pdf | Document Posted | N/A | N/A |  | 9/16/2004 | N/A | N/A |  |  |  | 3/1/2005 |  | 3/1/2005 | N | No
N07 | Monterey 69kV | Highland New Wind | VA | Highland | Withdrawn | APS | 39 | 39 | 7.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n07_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n07_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/n07_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/28/2004 | N/A | N/A | 4/29/2021 | 3/10/2020 |  | 4/29/2021 | 4/29/2021 |  | N | No
N08 | Dans Mountain |  | PA | Allegheny | Withdrawn | APS | 125 | 125 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2004 | N/A | N/A |  | 9/1/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N09 | Grassy Falls 138kV | West Greenbrier | WV | Greenbrier | Withdrawn | APS | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n09_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n09_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/4/2004 | N/A | N/A |  | 8/26/2008 |  | 3/31/2009 | 3/31/2009 |  | N | No
N10 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 300 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N11 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 275 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/11/2004 | N/A | N/A |  |  |  | 6/1/2005 | 6/1/2005 | 6/1/2005 | N | No
N12 | North Haverhill 69 kV | North Haverhill | OH | Scioto | In Service | AEP | 75 | 75 | 75 | 75 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n12_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n12_csa.pdf | Document Posted | N/A | N/A |  | 10/13/2004 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 6/1/2009 | N | No
N13 | Beaver Valley |  | PA | Beaver | In Service | DL | 1652 | 1630 | 1630 | 1630 | Capacity | Generation Interconnection | Nuclear |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2004 | N/A | N/A |  |  |  | 1/1/2005 |  | 1/1/2005 | N | No
N14 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 24 | 5.4 | 24 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n14_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n14_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n14_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2004 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
N15 | LaSalle 138 kV | Grand Ridge Energy LLC | IL | Lasalle | In Service | ComEd | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n15_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n15_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n15_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n15_csa.pdf | Document Posted | N/A | N/A |  | 12/2/2004 | N/A | N/A |  |  |  | 11/1/2009 | 11/1/2009 | 11/1/2009 | N | No
N16 | Kent-Harrington 69kV | Central Landfill Units 1-4 | DE | New Castle | In Service | DPL | 4 | 4 |  | 4 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n16_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 12/7/2006 | 12/7/2006 | 12/7/2006 | N | No
N17 | Laurel-Sussex 69kV | Southern Landfill Units 1-4 | DE | New Castle | In Service | DPL | 3 | 3 |  | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n17_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n17_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/9/2004 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
N18 | Clinton-Collier 345kV |  | PA | Allegheny | Withdrawn | DL | 19.2 | 19.2 | 19.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2004 | N/A | N/A |  | 2/16/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N19 | Paw Paw 12 kV |  | IL | Lee | Withdrawn | ComEd | 1.7 | 1.65 | 1.65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n19_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/28/2004 | N/A | N/A |  | 9/6/2005 | Customer Milestone Not Met | 3/31/2006 |  |  | N | No
N20 | Poplar Grove 34kV |  | IL | Boone | Withdrawn | ComEd | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2005 | N/A | N/A |  | 2/17/2005 | Customer Initiated Withdrawal | 12/29/2005 |  |  | N | No
N21 | Sublette Wind II | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 30 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n21_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N22 | Sublette Wind 3 | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 30 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n22_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N23 | West Brooklyn Wind 3 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 53 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n23_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N24 | West Brooklyn 4 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 53 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n24_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N25 | West Brooklyn 5 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 11 | 11 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/18/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
N26 | Daleville | SECCRA LF | PA | Chester | In Service | PECO | 1.7 | 1.74 | 1.7 | 1.7 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n26_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2005 | N/A | N/A |  |  |  | 12/31/2009 | 12/31/2009 | 12/31/2009 | N | No
N27 | Pequest River 34.5 kV | Warren County LF | NJ | Warren | In Service | JCPL | 3.6 | 3.6 | 3.6 | 3.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n27_csa.pdf | Document Posted | N/A | N/A |  | 1/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
N28 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 165 | 40 | 40 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2005 | N/A | N/A |  | 6/24/2005 | Customer Milestone Not Met | 2/1/2007 |  |  | N | No
N29 | Roth Rock 138kV |  | MD | Garrett | Withdrawn | APS | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n29_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n29_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 9/5/2007 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
N30 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 5 | 5 |  |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n30_fea.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 4/3/2007 | Customer Initiated Withdrawal | 12/31/2007 | 12/31/2007 |  | N | No
N31 | Freemansburg 69kV | Bethlehem LF | PA | Northampton | Deactivated | PPL | 5 | 5 |  | 5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n31_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/n31_wmpa.pdf |  | Not Required | N/A | N/A | 5/1/2007 | 1/28/2005 | N/A | N/A | 7/1/2007 |  |  | 5/1/2008 | 5/1/2008 | 5/1/2008 | N | No
N32 | Gans 138kV | South Chestnut WF | PA | Fayette | In Service | APS | 50.4 | 50.4 | 10.1 | 50.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n32_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n32_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n32_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/24/2011 | N | No
N33 | Afton 138kV | North Briery WF | WV | Preston | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n33_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n33_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n33_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n33_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
N34 | Motiva | Delaware City | DE | New Castle | In Service | DPL | 250 | 250 | 142 | 250 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n34_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/n34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 12/31/2005 | 12/31/2005 | 12/31/2005 | N | No
N35 | South Reading-Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 12/14/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N36 | Gold-Sabinsville 115kV | Gold Sabinsville | PA | Potter | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n36_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n36_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n36_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 1/15/2014 | Customer Initiated Withdrawal | 12/15/2014 | 12/15/2014 |  | N | No
N37 | Windsor 138kV |  | PA | Washington | Withdrawn | APS | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 11/1/2005 | Customer Initiated Withdrawal | 11/1/2006 |  |  | N | No
N38 | W. Newton-Lynn 138kV |  | OH | Hardin | Withdrawn | AEP | 120 | 120 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 8/2/2005 | Customer Initiated Withdrawal | 11/1/2006 |  |  | N | No
N39 | Johnstown-Altoona 230kV | Allegheny Ridge WF1 | PA | Cambria | In Service | PENELEC | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n39_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n39_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n39_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n39_csa.pdf | Document Posted | N/A | N/A |  | 1/28/2005 | N/A | N/A |  |  |  | 3/15/2007 | 3/15/2007 | 11/1/2006 | N | No
N40 | Champion 345kV |  | PA | Washington | Withdrawn | DL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n40_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2005 | N/A | N/A |  | 9/6/2005 | Customer Initiated Withdrawal | 5/31/2009 |  |  | N | No
N41 | Mountaineer 765kV |  | WV | Mason | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n41_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/21/2008 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N42 | Mountaineer-Belmont 765kV |  | OH | Meigs | Withdrawn | AEP | 1200 | 1200 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 12/1/2011 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N43 | Hanging Rock-Jefferson 765kV |  | KY | Lewis | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n43_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/28/2006 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
N44 | Dover |  | DE | Kent | Withdrawn | DPL | 103 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n44_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n44_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/11/2005 | Customer Milestone Not Met | 12/31/2005 |  |  | N | No
N45 | Ft. Martin 500kV |  | WV | Monongalia | Withdrawn | APS | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 12/14/2005 | Customer Initiated Withdrawal | 1/31/2010 |  |  | N | No
N46 | Cook 345kV |  | MI | Berrien | Withdrawn | AEP | 1120 | 1120 | 1120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 10/18/2005 | Customer Initiated Withdrawal | 6/1/2009 |  |  | N | No
N47 | Beryl 138kV | Pinnacle WF | WV | Mineral | In Service | APS | 85 | 85 | 17 | 55.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n47_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n47_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/n47_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/n47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/n47_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2005 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 11/16/2011 | N | No
N48 | Lancaster-Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 84 | 84 | 84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/11/2005 | Customer Initiated Withdrawal | 12/31/2005 |  |  | N | No
N49 | Salix-Claysburg 115kV |  | PA | Cambria | Withdrawn | PENELEC | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 4/14/2005 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
N50 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n50_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
N51 | Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 100.5 | 100.5 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/n51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/n51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
O01 | Letort 12kV | Frey Farms LF | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o01_csa.pdf | Document Posted | N/A | N/A | 12/1/2005 | 2/8/2005 | N/A | N/A | 1/3/2006 | 5/26/2011 | Customer Initiated Withdrawal | 1/12/2006 | 1/12/2006 | 1/12/2006 | N | No
O02 | Glendon 34.5kV |  | PA | Northampton | Withdrawn | PPL | 3 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o02_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/8/2005 | N/A | N/A |  | 8/16/2006 | Customer Milestone Not Met | 12/31/2006 | 12/31/2006 |  | N | No
O03 | Sublette | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 11 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o03_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 2/11/2005 | N/A | N/A |  | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007 | 4/15/2007 |  | N | No
O04 | Camden-Richmond |  | NJ | Camden | Withdrawn | PSEG | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2005 | N/A | N/A |  | 2/1/2006 | Customer Initiated Withdrawal | 6/1/2008 |  |  | N | No
O05 | Rochelle | City of Rochelle | IL | Ogle | In Service | ComEd | 22 | 22 | 2 | 22 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/22/2005 | N/A | N/A |  |  |  | 12/31/2006 | 12/31/2006 | 6/30/2005 | N | No
O06 | Ft. Martin Pruntytown |  | WV | Taylor | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o06_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2005 | N/A | N/A |  | 6/13/2006 |  | 6/1/2008 |  |  | S | No
O06_DP01 | Altavista 115kV | Pittsylvania | VA | Pittsylvania | In Service | Dominion | 83.6 | 4 | 4 | 3.4 | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o06_dp01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o06_dp01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o06_dp01_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/24/2005 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
O07 | Poplar Grove 34.5kV | Boone Heritage WF | IL | Boone | Withdrawn | ComEd | 25 | 25 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o07_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/1/2005 | N/A | N/A |  | 3/22/2007 | Customer Initiated Withdrawal | 6/30/2007 |  |  | N | No
O08 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2005 | N/A | N/A | [6 empty] | S | No
O09 | Normandy | Walnut Ridge Wind, LLC | IL | Lee | In Service | ComEd | 212 | 212 | 42.4 | 212 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o09_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o09_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o09_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o09_csa.pdf | Document Posted | N/A | N/A |  | 3/7/2005 | N/A | N/A |  |  |  | 10/15/2018 | 10/15/2018 | 10/31/2018 | N | No
O10 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 242 | 7 | 7 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/14/2005 | N/A | N/A |  |  |  | 6/1/2005 |  | 6/1/2005 | N | No
O11 | Bustelton 13kV | Burlington Co LF | NJ | Burlington | In Service | PSEG | 7.2 | 7 | 7 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o11_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2005 | N/A | N/A |  |  |  | 8/28/2007 | 8/28/2007 | 6/1/2007 | N | No
O12 | Chicago Heights 138kV | Geneva Energy LLC | IL | Adams | In Service | ComEd | 20 | 20 | 20 | 20 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2005 | N/A | N/A | 11/17/2005 |  |  | 12/31/2006 | 12/31/2006 | 12/1/2005 | N | No
O13 | Linden - Harbor Cable II |  | NJ | Union | Withdrawn | PSEG | 520 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR/520 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 2/1/2008 |  |  | S | No
O14 | Black Oak - Bedinton RTU |  | MD | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/5/2005 | N/A | N/A |  | 8/14/2006 | Customer Milestone Not Met |  |  |  | S | No
O15 | Black Oak - Hatfield Wave Trap |  | PA | Greene | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o15_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/6/2005 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal |  |  |  | S | No
O16 | Chichester-Linwood 230kV | FPL Energy Markus Hook | PA | Delaware | In Service | PECO | 230 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/o16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/o16_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2005 | N/A | N/A |  |  |  | 6/19/2005 |  | 6/19/2005 | S | No
O17 | Somerset-Allegheny 115kV | Stoney Creek WF | PA | Somerset | Withdrawn | PENELEC | 65 | 65 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o17_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/14/2005 | N/A | N/A |  | 1/6/2009 | Customer Milestone Not Met | 12/1/2009 | 12/1/2009 |  | N | No
O18 | Salix-Claysburg (Krayn) 115kV | Highland WF | PA | Somerset | In Service | PENELEC | 65 | 65 | 13 | 62.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o18_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o18_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2005 | N/A | N/A | 1/14/2009 |  |  | 12/18/2008 | 12/18/2008 | 12/18/2008 | N | No
O19 | Somerset 115kV | Somerset (Kimberly Run) WF | PA | Somerset | Withdrawn | PENELEC | 33 | 33 | 6.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o19_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o19_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o19_csa.pdf | Document Posted | N/A | N/A |  | 5/4/2005 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 5/31/2013 | 5/31/2013 |  | N | No
O20 | Lakehurst 34.5kV | Ocean Energy LF | NJ | Ocean | In Service | JCPL | 9.4 | 9.4 | 9.4 | 9.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o20_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/o20_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/4/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O21 | Liberty 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o21_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o21_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2005 | N/A | N/A |  | 10/6/2009 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
O22 | Powerton-Goodings Grove 345kV | Top Crop WF 1 & 2 | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o22_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o22_fac.pdf | Document Posted |  | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o22_csa.pdf | Document Posted | N/A | N/A | 10/17/2009 | 5/11/2005 | N/A | N/A | 10/23/2009 |  |  | 10/25/2010 | 10/25/2010 | 10/25/2010 | N | No
O23 | Powerton-Dresden 345kV | Top Crop Wind Farm | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o23_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o23_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o23_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 5/11/2005 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
O24 | Pontiac Midpoint-Dresden 345kV | Bright Stalk WF | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o24_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o24_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o24_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 5/11/2005 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
O25 | N. Salisbury 25kV | Newland Park LF | MD | Wicomico | In Service | DPL | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o25_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 6/1/2007 | N | No
O26 | Pine Grove 69kV | Guilford Mills LF | PA | Schuylkill | In Service | PPL | 8 | 8 | 8 | 6 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o26_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o26_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o26_csa.pdf | Document Posted | N/A | N/A |  | 5/12/2005 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
O27 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o27_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o27_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/13/2005 | N/A | N/A |  | 5/15/2012 | Customer Initiated Withdrawal | 5/31/2015 | 5/31/2015 |  | N | No
O28 | Jenkins-Harwood #2 69kV | Penobscot Mountain WF | PA | Luzerne | Withdrawn | PPL | 51 | 51 | 10.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o28_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o28_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o28_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 5/13/2005 | N/A | N/A |  | 4/15/2010 | Customer Initiated Withdrawal | 11/30/2011 | 11/30/2011 |  | N | No
O29 | Normandy 138kV | Green River Wind Farm Phase 2 | IL | Lee | In Service | ComEd | 225 | 225 | 45 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o29_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o29_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o29_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o29_csa.pdf | Document Posted | N/A | N/A |  | 5/16/2005 | N/A | N/A | 10/1/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/25/2019 | N | No
O30 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 9 | 9 |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/16/2005 | N/A | N/A |  | 7/25/2005 | Customer Initiated Withdrawal | 10/1/2006 |  |  | N | No
O31 | Fries 12kV | Fries Hydorelectric Plant | VA | Grayson | In Service | AEP | 5.2 | 5.21 | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o31_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o31_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o31_csa.pdf | Document Posted | N/A | N/A |  | 5/18/2005 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
O32 | Mountaineer 765kV | Mountaineer #1 | WV | Mason | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/31/2005 | N/A | N/A |  |  |  | 5/31/2005 | 5/31/2005 | 5/31/2005 | N | No
O33 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o33_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o33_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/o33_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
O34 | Frederick 12kV |  | MD | Frederick | Withdrawn | APS | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2005 | N/A | N/A |  | 10/6/2005 | Customer Initiated Withdrawal | 5/1/2006 |  |  | N | No
O35 | Providence Heights #1 138kV | Providence Heights WF | IL | Bureau | In Service | ComEd | 74 | 74 | 14.8 | 74 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o35_csa.pdf | Document Posted | N/A | N/A | 6/2/2008 | 6/6/2005 | N/A | N/A | 6/2/2008 |  |  | 6/26/2008 | 6/26/2008 | 6/30/2007 | N | No
O36 | Honey Brook 12kV | Honeybrook | PA | Chester | In Service | PPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o36_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/o36_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/6/2005 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
O37 | Belle 46kV |  | WV | Kanawha | Withdrawn | AEP | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o37_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2005 | N/A | N/A |  | 4/12/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | N | No
O38 | Johnstown-Altoona 230kV | North Alleghney WF | PA | Cambria | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o38_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o38_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 12/15/2007 | N | No
O39 | Sunbury - Dauphin 69kV | Mahantango WF | PA | Dauphin | Withdrawn | PPL | 56 | 56 | 11.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o39_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o39_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o39_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o39_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  | 5/18/2010 | Customer Initiated Withdrawal | 6/1/2010 | 6/1/2010 |  | N | No
O40 | Pine Grove - Frailey 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 28 | 28 | 5.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o40_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o40_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o40_csa.pdf | Document Posted | N/A | N/A |  | 6/27/2005 | N/A | N/A |  | 4/1/2011 | Customer Initiated Withdrawal | 7/1/2012 | 7/1/2012 |  | N | No
O42 | Cook 345 kV | Cook #1 | MI | Berrien | In Service | AEP | 1100 | 84 | 84 | 84 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o42_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/6/2005 | N/A | N/A |  |  |  | 1/19/2007 | 1/19/2007 | 12/31/2006 | N | No
O43 | University Park | University Park North Energy Center | IL | Will | In Service | ComEd | 504 | 54 | 54 | 54 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o43_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o43_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/7/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 12/19/2011 | N | No
O44 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 540 | 540 | 540 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2005 | N/A | N/A |  | 1/23/2006 |  | 6/1/2007 | 6/1/2007 |  | N | No
O45 | Grassy Falls | University Park | WV | Greenbrier | Withdrawn | APS | 143 | 143 | 143 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o45_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/o45_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2005 | N/A | N/A |  | 1/6/2009 | Customer Initiated Withdrawal | 11/1/2007 |  |  | S | No
O46 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 2 | 0.4 | 2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o46_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o46_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o46_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2005 | N/A | N/A |  |  |  | 12/1/2007 |  | 12/1/2007 | N | No
O47 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 10 | 10 | 2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o47_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o47_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/25/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
O48 | Hays Mill - Lookout 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 36 | 36 | 7.2 | 36 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o48_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o48_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2005 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
O49 | Wempletown-Byron 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o49_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o49_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/26/2005 | N/A | N/A |  | 8/2/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
O50 | Powerton-Dresden 345kV | Minonk Wind Farm | IL | Woodford | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o50_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o50_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o50_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o50_csa.pdf | Document Posted | N/A | N/A | 10/16/2012 | 7/26/2005 | N/A | N/A | 10/31/2012 |  |  | 12/31/2012 | 12/31/2012 | 10/31/2012 | N | No
O51 | Pontiac Midpoint-Wilton Center 345kV | Cayuga Ridge South WF | IL | Livingston | In Service | ComEd | 300 | 300 | 60 | 300 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o51_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o51_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o51_csa.pdf | Document Posted | N/A | N/A | 9/29/2009 | 7/27/2005 | N/A | N/A | 10/26/2009 |  |  | 5/6/2010 | 5/6/2010 | 12/31/2007 | N | No
O52 | Gold-Potter Co 115kV | Potter WF | PA | Potter | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o52_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o52_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o52_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2005 | N/A | N/A |  | 5/8/2013 | Customer Initiated Withdrawal | 12/25/2014 | 12/25/2014 |  | N | No
O53 | Beaver Valley #1 | Beaver Valley 1 | PA | Beaver | In Service | DL | 902 | 81 | 81 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 6/1/2007 | 6/1/2007 | 9/15/2006 | N | No
O54 | Beaver Valley #2 | Beaver Valley 2 | PA | Beaver | In Service | DL | 908 | 77 | 77 | 54 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/27/2005 | N/A | N/A |  |  |  | 7/1/2008 | 7/1/2008 | 10/23/2006 | N | No
O55 | Peckville 69kV |  | PA | Lackawanna | Withdrawn | PPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o55_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/27/2005 | N/A | N/A |  | 7/17/2006 | Customer Milestone Not Met | 1/1/2007 |  |  | N | No
O56 | Osterburg East 115kV | Dunning Mountain WF | PA | Bedford | Withdrawn | PENELEC | 76 | 76 | 15.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o56_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o56_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o56_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o56_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o56_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2013 | 3/1/2013 |  | N | No
O57 | Kanawha 138kV |  | WV | Fayette | Withdrawn | AEP | 142 | 142 |  |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 4/18/2006 | Customer Milestone Not Met | 6/1/2006 |  |  | N | No
O58 | Tenn Eastman 138kV |  | TN | Sullivan | Withdrawn | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o58_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o58_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/28/2005 | N/A | N/A |  | 8/14/2008 | Customer Milestone Not Met | 6/1/2007 |  |  | N | No
O59 | Gold 115kV | Gold | PA | Potter | Withdrawn | PENELEC | 99 | 99 | 19.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o59_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 12/21/2009 | Customer Initiated Withdrawal | 12/1/2009 | 12/1/2009 |  | N | No
O60 | Berlin 23 kV | AMP Berlin WF | PA | Somerset | Withdrawn | PENELEC | 5.4 | 5.4 | 1.08 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o60_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o60_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o60_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 4/9/2014 | Customer Initiated Withdrawal | 1/31/2012 | 1/31/2012 |  | N | No
O61 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 3/9/2007 | Customer Initiated Withdrawal | 1/31/2007 |  |  | N | No
O62 | Shackleford 34.5kV |  | VA | King and Queen | Withdrawn | Dominion | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o62_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 4/27/2006 | Customer Milestone Not Met | 10/31/2006 |  |  | N | No
O63 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o63_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 3/7/2006 | Customer Milestone Not Met | 6/1/2009 |  |  | N | No
O64 | Grays Ferry - Island Road |  | PA | Philadelphia | Withdrawn | PECO | 201 | 201 | 201 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o64_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 2/11/2006 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
O65 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A |  | 10/17/2005 | Customer Initiated Withdrawal | 7/1/2010 |  |  | N | No
O66 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | PSEG | 670 | 670 | 320 |  | Capacity | Merchant Transmission |  | DC | NF/TWR 320/NFTWR 673 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/o66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/o66_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/o66_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/o66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/o66_csa.pdf | Document Posted | N/A | N/A |  | 7/29/2005 | N/A | N/A | 4/4/2013 |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
O67 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2005 | N/A | N/A | [6 empty] | S | No
O68 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o68_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o68_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
O69 | Beaver Creek-Hazard 138kV |  | KY | Perry | Withdrawn | AEP | 535 | 535 | 535 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o69_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 6/30/2006 | Customer Milestone Not Met | 7/1/2009 |  |  | N | No
O70 | Susquehanna - Harwood 230kV | Nescopeck WF | PA | Luzerne | Withdrawn | PPL | 124 | 124 | 24.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o70_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o70_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/o70_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/o70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o70_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 5/9/2011 | Customer Initiated Withdrawal | 12/1/2011 | 12/1/2011 |  | N | No
O71 | Hooversville 115kV |  | PA | Somerset | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o71_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 4/12/2006 | Customer Initiated Withdrawal | 11/30/2007 |  |  | N | No
O72 | Hooversville-Central City | Shaffer Mountain WF | PA | Somerset | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o72_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o72_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/o72_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/o72_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 6/12/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
O73 | Benson 345kV |  | IL | Woodford | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/o73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/o73_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2005 | N/A | N/A |  | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
P01 | Westover-Madera 115kV | Rock Run Wind Park | PA | Cambria | Withdrawn | PENELEC | 65 | 65 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p01_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p01_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p01_csa.pdf | Document Posted | N/A | N/A |  | 8/23/2005 | N/A | N/A |  | 1/4/2013 | Customer Initiated Withdrawal | 12/31/2011 | 12/31/2011 |  | N | No
P02 | Ohio Central 138kV |  | OH | Muskingum | Withdrawn | AEP | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p02_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2005 | N/A | N/A |  | 8/14/2006 | Customer Initiated Withdrawal | 6/1/2007 |  |  | N | No
P03 | Frackville-Hauto #3 | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 27.3 | 1.3 | 1.3 | 1.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p03_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p03_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p03_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p03_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P04 | Peach Bottom 500kV | Delta | PA | York | In Service | PECO | 557 | 550 | 550 | 550 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p04_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p04_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p04_csa.pdf | Document Posted | N/A | N/A |  | 9/8/2005 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
P05 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p05_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2005 | N/A | N/A |  | 6/12/2006 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
P06 | Cumberland 230 kV | Cumberland 2 | NJ | Cumberland | In Service | AEC | 225 | 225 | 225 | 100 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p06_csa.pdf | Document Posted | N/A | N/A | 2/6/2009 | 9/9/2005 | N/A | N/A | 5/4/2009 |  |  | 6/1/2016 | 6/1/2016 | 12/31/2008 | N | No
P07 | Middle 138kV |  | NJ | Cape May | Withdrawn | AEC | 122 | 122 | 122 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p07_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2005 | N/A | N/A |  | 6/16/2006 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
P08 | Possum Point |  | VA | Prince William | Withdrawn | Dominion | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p08_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2005 | N/A | N/A |  | 4/24/2009 | Customer Milestone Not Met | 6/1/2014 | 6/1/2014 |  | N | No
P09 | Kerr Dam 115kV | John H. Kerr Dam Hydro Units 1(15MW), 2-7(42MW) | VA | Mecklenburg | In Service | Dominion | 267 | 27 | 27 | 27 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p09_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p09_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p09_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/14/2005 | N/A | N/A |  |  |  | 1/19/2011 | 1/19/2011 | 1/19/2011 | N | No
P10 | LaSalle 138kV | Grand Ridge WF | IL | Lasalle | In Service | ComEd | 190.5 | 190.5 | 37.2 | 135 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p10_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p10_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p10_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p10_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2005 | N/A | N/A |  |  |  | 12/1/2013 | 12/1/2013 | 6/1/2010 | N | No
P11 | Kewanee 138kV | Bishop Hill WF | IL | Mercer | In Service | ComEd | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p11_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p11_csa.pdf | Document Posted | N/A | N/A | 2/1/2012 | 9/26/2005 | N/A | N/A | 2/16/2012 |  |  | 10/1/2011 | 10/1/2011 | 2/24/2012 | N | No
P12 | Cheswick - Springdale 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2005 | N/A | N/A |  | 4/28/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P13 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2005 | N/A | N/A |  | 6/27/2006 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
P14 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 80 | 80 | 16 | 80 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p14_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p14_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/p14_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/12/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P15 | McGirr - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 12/1/2006 |  |  | N | No
P16 | Bath County | Bath County | VA | Bath | In Service | Dominion | 3030 | 340 | 340 | 340 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p16_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p16_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p16_csa.pdf | Document Posted | N/A | N/A |  | 10/19/2005 | N/A | N/A |  |  |  | 12/1/2009 | 12/1/2009 | 12/1/2009 | N | No
P17 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 9/30/2006 |  |  | N | No
P18 | Dixon-Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 2.5 | 2.5 | 0.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p18_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
P19 | McGirr Road - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2005 | N/A | N/A |  | 2/2/2006 | Customer Initiated Withdrawal | 12/31/2006 |  |  | N | No
P20 | Nelson-Electric Junction 345kV | Walnut Ridge Wind Farm | IL | Bureau | Withdrawn | ComEd | 210 | 210 | 42 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p20_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p20_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p20_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2005 | N/A | N/A |  | 12/14/2016 |  | 12/31/2017 | 12/31/2017 |  | N | No
P21 | McGirr Road - Dixon 138kV |  | IL | Bureau | Withdrawn | ComEd | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2005 | N/A | N/A |  | 10/24/2006 | Customer Milestone Not Met | 9/15/2007 |  |  | N | No
P22 | Johnstown Altoona 230kV | North Allegheny WF | PA | Cambria | In Service | PENELEC | 20 | 20 | 4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p22_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p22_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p22_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2005 | N/A | N/A |  |  |  | 9/1/2009 | 9/1/2009 | 9/1/2009 | N | No
P23 | Bayonne 138kV |  | NJ | Hudson | Withdrawn | PSEG | 46 | 46 | 45.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p23_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p23_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/28/2005 | N/A | N/A |  | 2/18/2009 | Customer Milestone Not Met | 1/1/2009 | 1/1/2009 |  | N | No
P24 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p24_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P25 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p25_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A |  | 6/6/2014 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P26 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 9.5 | 9.5 | 1.9 | 9.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p26_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p26_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p26_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/p26_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/7/2005 | N/A | N/A | 4/30/2012 |  |  | 12/31/2012 | 12/31/2012 | 5/1/2012 | N | No
P27 | Winchester 34.5 kV | Bethel LF | VA | Unknown | In Service | Dominion | 13 | 13 | 13 | 13 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p27_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/p27_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/18/2005 | N/A | N/A |  |  |  | 1/25/2008 | 1/25/2008 | 1/25/2008 | N | No
P28 | Mehoopany 115kV | Mehoopany WF | PA | Wyoming | In Service | PENELEC | 150 | 150 | 30 | 148 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p28_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p28_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p28_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2005 | N/A | N/A |  |  |  | 1/21/2013 | 1/21/2013 | 1/9/2013 | N | No
P29 | Hunterstown 500/230kV |  | PA | Adams | Withdrawn | ME | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p29_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/2005 | N/A | N/A |  | 5/17/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P30 | Bellefonte - N. Proctorville 138kV | South Point | OH | Lawrence | Withdrawn | AEP | 185 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p30_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p30_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/30/2005 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 12/31/2012 | 12/31/2012 |  | N | No
P31 | Bath County |  | VA | Highland | In Service | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/p31_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/p31_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/p31_csa.pdf | Document Posted | N/A | N/A |  | 12/5/2005 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | S | No
P32 | White Oak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 19.5 | 19.5 |  | 19.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p32_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2005 | N/A | N/A |  |  |  | 12/31/2007 |  | 12/31/2007 | N | No
P33 | Laurel - Sussex 69kV | Southern Landfill Units 1-4 | DE | Sussex | In Service | DPL | 4.3 | 1 |  | 1 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p33_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p33_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2005 | N/A | N/A |  |  |  | 10/24/2006 |  | 10/24/2006 | N | No
P34 | Washington Landfill |  | PA | Washington | In Service | APS | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p34_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/p34_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 3/17/2009 | 3/17/2009 | 12/31/2006 | N | No
P35 | Pleasantville | Pleasantville /AC LF Unit 2 | NJ | Atlantic | In Service | AEC | 4 | 2 | 2 | 1.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p35_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p35_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2005 | N/A | N/A |  |  |  | 7/31/2006 |  | 7/31/2006 | N | No
P36 | Nelson - Lee Co. EC 345kV | Big Sky | IL | Bureau | In Service | ComEd | 240 | 240 | 48 | 240 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p36_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p36_csa.pdf | Document Posted | N/A | N/A |  | 12/22/2005 | N/A | N/A |  |  |  | 8/31/2010 | 8/31/2010 | 8/31/2010 | N | No
P37 | Normandy 138kV |  | IL | Bureau | Withdrawn | ComEd | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p37_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p37_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/22/2005 | N/A | N/A |  | 7/17/2013 | Customer Initiated Withdrawal | 5/31/2013 | 5/31/2013 |  | N | No
P38 | Bremo 230kV | Bremo | VA | Buckingham | In Service | Dominion | 675 | 675 | 625 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p38_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p38_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p38_csa.pdf | Document Posted | N/A | N/A | 7/21/2010 | 12/22/2005 | N/A | N/A |  |  |  | 3/30/2011 | 3/30/2011 | 3/30/2011 | N | No
P39 | Kewanee-Powerton 138kV |  | IL | Stark | Withdrawn | ComEd | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2005 | N/A | N/A |  | 3/2/2011 | Customer Milestone Not Met | 12/1/2008 | 12/1/2008 |  | N | No
P40 | Crescent Ridge 138kV | Providence Heights WF | IL | Bureau | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p40_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2005 | N/A | N/A |  | 2/21/2013 | Customer Initiated Withdrawal | 11/12/2010 | 11/12/2010 |  | N | No
P41 | South Reading - Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p41_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/3/2006 | N/A | N/A |  | 6/28/2006 | Customer Milestone Not Met | 9/30/2006 |  |  | N | No
P42 | West Kingsport 138kV | West Kingsport | TN | Sullivan | In Service | AEP | 50 | 50 | 45 | 45 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p42_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/2006 | N/A | N/A |  |  |  | 1/8/2007 | 1/8/2007 | 1/8/2007 | N | No
P43 | Weyerhaeuser 115kV | Domtar Paper Company Generating Units 7-10 | NC | Martin | Under Construction | Dominion | 62.5 | 62.5 | 50 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p43_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p43_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p43_csa.pdf | Document Posted | N/A | N/A |  | 1/13/2006 | N/A | N/A |  |  |  | 10/1/2021 | 10/1/2021 |  | N | No
P44 | City of Columbus | Columbus Floodwall | OH | Franklin | In Service | AEP | 7.5 | 7.47 | 7 | 7 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p44_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p44_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p44_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/16/2006 | N/A | N/A |  |  |  | 12/31/2006 |  | 12/31/2006 | N | No
P45A | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 120 | 120 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p45a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p45a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p45a_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/17/2006 | N/A | N/A |  | 9/1/2009 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
P45B | Mt. Storm 500kV |  | WV | Unknown | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2006 | N/A | N/A |  | 10/3/2006 | Customer Initiated Withdrawal | 6/1/2006 |  |  | S | No
P46 | Lena 138kV | EcoGrove WF (67 WT) | IL | JoDaviess | In Service | ComEd | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p46_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p46_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p46_csa.pdf | Document Posted | N/A | N/A | 2/11/2009 | 1/23/2006 | N/A | N/A | 2/11/2009 |  |  | 3/11/2009 | 3/11/2009 | 10/1/2007 | N | No
P47 | Mansfield-S. Troy 115kV | Armenia Mountain WF | PA | Bradford | In Service | PENELEC | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p47_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p47_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p47_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p47_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p47_csa.pdf | Document Posted | N/A | N/A | 10/23/2009 | 1/25/2006 | N/A | N/A | 11/4/2009 |  |  | 12/16/2009 | 12/16/2009 | 12/16/2009 | N | No
P48 | Bedford North - Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 120 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p48_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2006 | N/A | N/A |  | 2/12/2007 | Customer Initiated Withdrawal | 12/15/2007 |  |  | N | No
P49 | Adkins 345kV | Darby Generating Station | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P50 | Greenville 69kV | Greenville Electric Generating Station | OH | Darke | In Service | Dayton | 236 | 14 | 14 | 14 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P51 | Stuart 345kV | Stuart Electric Generating Station | OH | Adams | In Service | Dayton | 2362 | 7 | 7 | 7 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/27/2006 | N/A | N/A |  |  |  | 6/1/2006 |  | 6/1/2006 | N | No
P52 | Albright 138kV |  | WV | Preston | Withdrawn | APS | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p52_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 12/30/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
P53 | Bent Mtn. 138kV |  | VA | Roanoke | Withdrawn | AEP | 81 | 81 | 16.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p53_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 8/21/2006 | Customer Initiated Withdrawal | 12/31/2008 |  |  | N | No
P54 | Sporn - Waterford 345kV | Racine | OH | Meigs | Withdrawn | AEP | 1035 | 1035 | 1035 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p54_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p54_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p54_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p54_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2006 | N/A | N/A |  | 1/26/2010 | Customer Milestone Not Met | 8/30/2014 | 8/30/2014 |  | N | No
P55 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p55_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 3/20/2009 | Customer Milestone Not Met | 10/1/2010 | 10/1/2010 |  | N | No
P56 | Elrama-Mitchell 138kV |  | PA | Allegheny | Withdrawn | DL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p56_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/p56_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/21/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
P57 | Charleroi - Mitchell 138kV |  | PA | Allegheny | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/p57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 8/28/2006 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
P58 | Canaan - Seneca 138kV |  | WV | Randolph | Withdrawn | APS | 150 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p58_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2006 | N/A | N/A |  | 2/17/2010 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
P59 | Belington 138kV | Laurel Mountain WF | WV | Barbour | In Service | APS | 97.6 | 97.6 | 19.52 | 97.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p59_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A | 5/23/2011 |  |  | 6/15/2011 | 6/15/2011 | 12/31/2008 | N | No
P60 | New Baltimore 115kV (Stony Creek) | Stony Creek WF | PA | Somerset | In Service | PENELEC | 52.5 | 52.5 | 10.5 | 52.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p60_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/p60_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/p60_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p60_csa.pdf | Document Posted | N/A | N/A | 10/22/2009 | 1/31/2006 | N/A | N/A | 10/23/2009 |  |  | 3/1/2010 | 3/1/2010 | 3/1/2010 | N | No
P61 | Gavin #1 765kV | Gavin 1 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p61_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p61_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p61_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 1/1/2010 | 1/1/2010 | 5/1/2007 | N | No
P62 | Gavin #2 765kV | Gavin 2 | OH | Adams | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/p62_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/p62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/p62_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/p62_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2006 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 5/1/2009 | N | No
Q01 | Olive-Dequine 345kv | Fowler Ridge WF | IN | Benton | In Service | AEP | 500 | 500 | 100 | 500 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q01_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2006 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 12/1/2008 | N | No
Q02 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2006 | N/A | N/A |  | 7/17/2006 | Customer Initiated Withdrawal | 12/31/2008 |  |  | N | No
Q03 | Olive-Dequine 345kV | Fowler Ridge 4 WF | IN | Benton | In Service | AEP | 250 | 250 | 50 | 250 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q03_imp.pdf | Document Posted |  | Not Required |  | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2006 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/3/2015 | N | No
Q04 | Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q05 | Emmaville Mountain |  | PA | Fulton | Withdrawn | APS | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q05_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q06 | Breezewood |  | PA | Fulton | Withdrawn | APS | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q06_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q07 | DuVall South |  | PA | Fulton | Withdrawn | PENELEC | 18 | 18 | 5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2006 | N/A | N/A |  | 6/14/2006 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
Q08 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q08_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q08_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q08_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/21/2006 | N/A | N/A |  | 8/18/2009 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
Q09 | Emporia | Emporia Hydro | VA | Greensville | In Service | Dominion | 2.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q09_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q09_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/21/2006 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
Q10 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/23/2006 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
Q11 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q11_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2006 | N/A | N/A |  | 3/31/2010 | Customer Milestone Not Met | 12/1/2011 | 12/1/2011 |  | N | No
Q12 | Fox River Heights 12kV |  | IL | Kane | Withdrawn | ComEd | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q12_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q13 | Kankakee 12kV |  | IL | Kankakee | Withdrawn | ComEd | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q13_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q14 | Hegewisch 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q14_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q15 | Woodridge 12kV |  | IL | Du Page | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q15_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/10/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q16 | Western Ave 12kV |  | IL | Kane | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q16_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/23/2010 | Customer Milestone Not Met | 9/1/2007 | 9/1/2007 |  | N | No
Q17 | Northbrook 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q17_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/8/2006 | N/A | N/A |  | 8/23/2010 | Customer Milestone Not Met | 6/1/2007 | 6/1/2007 |  | N | No
Q18 | Moser 34.5kV | Pottstown LF Units 1 & 2 | PA | Montgomery | In Service | PECO | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q18_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q18_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/8/2006 | N/A | N/A |  |  |  | 11/6/2007 | 11/6/2007 | 11/6/2007 | N | No
Q19 | Atlantic 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | 1 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q19_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/13/2006 | N/A | N/A |  | 12/6/2006 | Customer Milestone Not Met | 11/1/2006 |  |  | N | No
Q20 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 249 | 140 | 140 | 140 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q20_csa.pdf | Document Posted | N/A | N/A |  | 3/17/2006 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 10/30/2010 | N | No
Q21 | Lewistown-Juniata 230kV |  | PA | Cambria | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2006 | N/A | N/A |  | 5/4/2006 | Customer Initiated Withdrawal | 12/15/2006 |  |  | S | No
Q22 | Columbia 34.5kV | Great Bear Hydro | NJ | Warren | In Service | JCPL | 0.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q22_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q22_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q22_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/20/2006 | N/A | N/A |  |  |  | 5/5/2009 | 5/5/2009 | 12/26/2006 | N | No
Q23 | Bayard |  | WV | Grant | Withdrawn | APS | 19 | 19 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q23_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2006 | N/A | N/A |  | 11/27/2006 | Customer Milestone Not Met | 3/31/2007 |  |  | N | No
Q24 | Gold-Sabinsville 115kV |  | PA | Potter | Withdrawn | PENELEC | 101 | 101 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q24_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2006 | N/A | N/A |  | 2/2/2009 | Customer Milestone Not Met | 12/30/2010 | 12/30/2010 |  | N | No
Q25 | Donegal-Iron City 138kV | Harmony WF | PA | Fayette | Withdrawn | APS | 80 | 80 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q25_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q25_csa.pdf | Document Posted | N/A | N/A |  | 3/24/2006 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2014 | 3/1/2014 |  | N | No
Q26 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2006 | N/A | N/A |  | 10/12/2006 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
Q27 | Frackville-Shennandoah 69kV | Locust Ridge II WF | PA | Schuylkill | In Service | PPL | 100 | 100 | 20 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q27_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q27_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2006 | N/A | N/A | 10/23/2008 |  |  | 4/29/2009 | 4/29/2009 | 4/29/2009 | N | No
Q28 | Eldred-Frackville 230kV | Rausch Creek WF (68 WT) | PA | Schuylkill | Withdrawn | PPL | 170 | 170 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q28_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q28_csa.pdf | Document Posted | N/A | N/A |  | 4/7/2006 | N/A | N/A |  | 8/2/2013 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
Q29 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 6 | 5.4 | 5.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q29_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 4/11/2006 | N/A | N/A |  | 10/29/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q30 | City of Columbus |  | OH | Franklin | Withdrawn | AEP | 3 | 3 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/11/2006 | N/A | N/A |  | 9/20/2006 | Customer Initiated Withdrawal | 12/31/2006 |  |  | N | No
Q31 | Wagner 34kV | Hawkins Point | MD | Baltimore City | In Service | BGE | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q31_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q31_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/11/2006 | N/A | N/A |  |  |  | 4/24/2007 | 4/24/2007 | 6/1/2006 | N | No
Q32 | Gosport 115kV | Gosport | VA | City of Portsmouth | Withdrawn | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q32_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2006 | N/A | N/A |  | 8/22/2007 | Customer Initiated Withdrawal | 7/1/2007 | 7/1/2007 |  | N | No
Q33 | Homer-Watercure 345kV |  | PA | Tioga | Withdrawn | PENELEC | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2006 | N/A | N/A |  | 6/6/2006 | Customer Initiated Withdrawal | 12/15/2008 |  |  | N | No
Q34 | Garrett 115kV |  | PA | Somerset | Withdrawn | PENELEC | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q34_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q34_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q34_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q34_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q34_csa.pdf | Document Posted | N/A | N/A |  | 4/24/2006 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 4/1/2011 | 4/1/2011 |  | N | No
Q35 | N. Coshocton 69kV |  | OH | Coshocton | Withdrawn | AEP | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/26/2006 | N/A | N/A |  | 11/28/2006 | Customer Milestone Not Met | 6/1/2007 |  |  | N | No
Q36 | Philipsburg - Tyrone North 115kV | Sandy Ridge WF | PA | Centre | In Service | PENELEC | 50 | 50 | 10 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q36_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q36_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q36_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2006 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 4/17/2012 | N | No
Q37 | Loganton 12kV | Schrack Farms | PA | Clinton | Withdrawn | PPL | 0 | 0.02 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q37_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q37_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/2/2006 | N/A | N/A |  | 1/12/2007 | Customer Initiated Withdrawal | 6/16/2006 |  |  | N | No
Q38 | C2 Tap - Mt. Union 46kV |  | PA | Cambria | Withdrawn | PENELEC | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/q38_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/4/2006 | N/A | N/A |  | 12/5/2007 | Customer Milestone Not Met | 12/15/2007 | 12/15/2007 |  | S | No
Q39 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 105 | 105 | 21 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q39_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q39_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/8/2006 | N/A | N/A |  | 10/22/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
Q40 | Renovo Lock Haven |  | PA | Clinton | Withdrawn | PPL | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q40_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/15/2006 | N/A | N/A |  | 8/29/2008 | Customer Initiated Withdrawal | 6/1/2009 | 6/1/2009 |  | N | No
Q41 | Mt. Hope Mine 34.5kV | Mt Hope Waterpower Project | NJ | Morris | Withdrawn | JCPL | 30 | 30 |  |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q41_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q41_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/5/2006 | N/A | N/A |  | 11/11/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
Q42 | Indian River |  | DE | Sussex | Withdrawn | DPL | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q42_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2006 | N/A | N/A |  | 7/30/2008 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
Q43 | Clinch River 138kV | Virginia City Hybrid Energy Center - 1 Unit | VA | Wise | In Service | AEP | 534 | 534 | 534 | 534 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q43_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q43_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q43_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 6/7/2006 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
Q44 | Elizabethtown | Elizabethtown | PA | Lancaster | In Service | PPL | 0.3 | 0.3 | 0 | 0.3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q44_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q44_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q44_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/9/2006 | N/A | N/A |  |  |  | 7/1/2006 |  | 7/1/2006 | N | No
Q45 | North Lebanon 13.2kV | GLRA LF | PA | Lebanon | In Service | ME | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q45_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q45_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q45_csa.pdf | Document Posted | N/A | N/A |  | 6/14/2006 | N/A | N/A |  |  |  | 9/25/2007 | 9/25/2007 | 9/25/2007 | N | No
Q46 | Curwensville 34.5 kV | Sunnyside Ethonol | PA | Clearfield | Withdrawn | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q46_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q46_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/16/2006 | N/A | N/A |  | 3/14/2013 | Customer Milestone Not Met | 3/1/2009 |  |  | N | No
Q47 | Peach Bottom | Peach Bottom - Units 2 & 3 | PA | York | In Service | PECO | 2532 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q47_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q47_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q47_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 4/1/2013 | 4/1/2013 | 11/12/2012 | N | No
Q48 | Calvert Cliffs | Calvert Cliffs Nuclear Power Plant Unit 3 | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q48_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q48_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q48_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2006 | N/A | N/A |  | 11/16/2009 | Customer Initiated Withdrawal | 1/1/2016 | 1/1/2016 |  | N | No
Q49 | Dresden 345kV | Dresden Nuclear Generating Station U2 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 11/14/2011 | N | No
Q50 | Dresden 345kV | Dresden Nuclear Station Unit 3 | IL | Grundy | In Service | ComEd | 957 | 70 | 70 | 70 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 12/12/2012 | N | No
Q51 | Quad City 345kV | Quad Cities - Units 1 & 2 | IL | Rock Island | In Service | ComEd | 1914 | 140 | 140 | 140 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q51_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q51_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2006 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 9/25/2011 | N | No
Q52 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q52_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/21/2006 | N/A | N/A |  | 12/11/2007 | Customer Initiated Withdrawal | 6/15/2011 |  |  | N | No
Q53 | Summit-West Fall 115kV | Chestnut Flats WF | PA | Blair | In Service | PENELEC | 38 | 38 | 7.6 | 38 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q53_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q53_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q53_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q53_csa.pdf | Document Posted | N/A | N/A |  | 6/23/2006 | N/A | N/A |  |  |  | 5/20/2011 | 5/20/2011 | 5/20/2011 | N | No
Q54 | Haviland-Tillman 138kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q54_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2006 | N/A | N/A |  | 10/27/2006 | Customer Milestone Not Met | 12/15/2009 |  |  | N | No
Q55 | Snowy Creek |  | WV | Preston | Withdrawn | APS | 62.5 | 62.5 | 12.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q55_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q55_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/28/2006 | N/A | N/A |  | 7/31/2012 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
Q56 | Claysburg 115kV |  | PA | Blair | Withdrawn | PENELEC | 180 | 180 | 36 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q56_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/5/2006 | N/A | N/A |  | 11/17/2006 | Customer Milestone Not Met | 6/30/2008 |  |  | N | No
Q57 | Steward-Waterman 138kV | Lee - DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 240 | 48 | 237.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q57_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q57_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q57_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q57_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q57_csa.pdf | Document Posted | N/A | N/A |  | 7/6/2006 | N/A | N/A |  |  |  | 6/1/2010 | 6/1/2010 | 11/14/2014 | N | No
Q58 | Sunbury-Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q58_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/6/2006 | N/A | N/A |  | 8/18/2008 | Customer Initiated Withdrawal | 12/31/2009 | 12/31/2009 |  | N | No
Q59 | S. Reading-Birdsboro 64kV | Pioneer Crossing LF | PA | Berks | In Service | ME | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q59_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q59_csa.pdf | Document Posted | N/A | N/A |  | 7/7/2006 | N/A | N/A |  |  |  | 5/30/2008 | 5/30/2008 | 5/30/2008 | N | No
Q60 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 201 | 201 | 40.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q60_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2006 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 3/1/2009 | 3/1/2009 |  | N | No
Q61 | Grassy Falls 138kV |  | WV | Greenbrier | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2006 | N/A | N/A |  | 8/26/2008 |  | 1/1/2010 |  |  | N | No
Q62 | Sayton -Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q62_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q62_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2006 | N/A | N/A |  | 3/27/2009 | Customer Initiated Withdrawal | 12/1/2009 | 12/1/2009 |  | N | No
Q63 | Seneca 230kV | Seneca Pumped Storage Generating Station Unit 1 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q63_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/11/2006 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
Q64 | Gosport 115kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q64_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2006 | N/A | N/A |  | 5/31/2007 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
Q65 | North Anna 500kV | North Anna Power Station Unit 3 | VA | Louisa | Withdrawn | Dominion | 1594 | 1594 | 1570 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q65_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q65_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q65_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q65_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q65_csa.pdf | Document Posted | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 4/28/2016 | Customer Initiated Withdrawal | 1/1/2024 | 1/1/2024 |  | N | No
Q66 | Beecher Energy - Distribution Cener #36 |  | IL | Will | Withdrawn | ComEd | 2 | 2.1 | 2.1 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q66_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q67 | LaGrange Park - West Chester Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 4 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q67_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q67_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q67B | Mt. Prospect - Des Plaines Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 4 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q67b_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q67b_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2006 | N/A | N/A |  | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007 | 6/1/2007 |  | N | No
Q68 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 726 | 726 | 641 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q68_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q68_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2006 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
Q69 | Shackleford 34.5kV | King - Queen | VA | Brunswick | In Service | Dominion | 10 | 10 | 10 | 10 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q69_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q69_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q69_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q69_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 2/7/2008 | 2/7/2008 | 2/7/2008 | N | No
Q70 | Lawrenceville 34.5kV | Brunswick | VA | King and Queen | In Service | Dominion | 11 | 11 | 11 | 11 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q70_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q70_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2006 | N/A | N/A |  |  |  | 11/1/2007 | 11/1/2007 | 11/1/2007 | N | No
Q71 | Cranes Corner 13.2kV | Strafford Regional LF | VA | Stafford | In Service | Dominion | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q71_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q71_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q71_csa.pdf | Document Posted | N/A | N/A | 2/3/2009 | 7/26/2006 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
Q72 | Mansfield - S. Troy 115kV |  | PA | Bradford | Withdrawn | PENELEC | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q72_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q72_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2006 | N/A | N/A |  | 12/23/2009 | Customer Initiated Withdrawal | 12/1/2010 | 12/1/2010 |  | N | No
Q73 | South Reading 69kV | Evergreen Community Power | PA | Berks | Deactivated | ME | 30 | 30 | 16 | 19 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q73_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q73_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2006 | N/A | N/A | 8/17/2009 |  |  | 4/6/2010 | 4/6/2010 | 4/6/2010 | N | No
Q74 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q74_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q74_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/22/2008 | Customer Initiated Withdrawal | 6/1/2013 | 6/1/2013 |  | N | No
Q75 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 1000 | 1000 | 685 |  | Capacity | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/q75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 12/2/2008 |  | 6/1/2010 |  |  | S | No
Q76 | Quinton 12kV | Salem County LF Generating Unit I | NJ | Salem | In Service | AEC | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q76_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q76_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/q76_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/31/2006 | N/A | N/A |  |  |  | 12/19/2008 | 12/19/2008 | 12/19/2008 | N | No
Q77 | Calvert Cliffs |  | MD | Calvert | Withdrawn | PEPCO | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q77_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 3/21/2007 | Customer Initiated Withdrawal | 12/30/2016 |  |  | N | No
Q78 | Trail Fork 34.5kV |  | WV | McDowell | Withdrawn | AEP | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 1/24/2007 | Customer Milestone Not Met | 4/1/2007 |  |  | N | No
Q79 | Ft. Martin - Kammer 500kV | Longview ST1 | WV | Monongalia | In Service | APS | 700 | 100 | 100 | 100 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q79_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/q79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/5/2009 | 7/31/2006 | N/A | N/A | 5/6/2011 |  |  | 4/22/2011 | 4/22/2011 | 9/1/2010 | N | No
Q80 | Ft. Martin - Kammer 500kV |  | WV | Monongalia | Withdrawn | APS | 750 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q80_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q80_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
Q81 | AMOS 765kV |  | WV | Putnam | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q81_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/24/2006 | Customer Milestone Not Met | 12/30/2007 |  |  | N | No
Q85 | Minonk 34.5kV |  | IL | Marshall | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 12/15/2008 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
Q86 | Hudson - Essex 230kV |  | NJ | Hudson | Withdrawn | PSEG | 455.1 | 455.1 | 455.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q86_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q86_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 4/2/2009 | Customer Milestone Not Met | 5/31/2010 | 5/31/2010 |  | N | No
Q87 | Quad Cities 345kV |  | IL | Whiteside | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 1/22/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
Q88 | Black Oak SVC |  | WV | Berkeley | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/q88_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 10/31/2006 | Customer Initiated Withdrawal | 6/1/2008 |  |  | S | No
Q89 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q89_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2006 | N/A | N/A |  | 3/30/2007 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
Q90 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 650 | 650 | 650 | 650 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/q90_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/q90_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/q90_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/q90_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/q90_csa.pdf | Document Posted | N/A | N/A | 7/1/2014 | 7/31/2006 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/11/2014 | N | No
R01 | Susquehanna |  | PA | Montour | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r01_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r01_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
R02 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r02_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r02_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
R03 | Adams - Allen 138kV |  | IN | Adams | Withdrawn | AEP | 130 | 130 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r03_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2006 | N/A | N/A |  | 2/5/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
R04 | Sunbury 500kV |  | PA | Snyder | Withdrawn | PPL | 817 | 817 | 817 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r04_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r04_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2006 | N/A | N/A |  | 10/13/2008 | Customer Initiated Withdrawal | 12/15/2011 |  |  | N | No
R05 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r05_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2006 | N/A | N/A |  | 8/5/2009 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
R06 | Weissport 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r06_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2006 | N/A | N/A |  | 4/3/2007 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
R07 | Pleasantville | AC Landfill Energy Units 1-3 | NJ | Atlantic | In Service | AEC | 6 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r07_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r07_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r07_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/12/2006 | N/A | N/A |  |  |  | 10/1/2007 | 10/1/2007 | 10/1/2007 | N | No
R08 | Central City 115kV, Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r08_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2006 | N/A | N/A |  | 2/18/2009 | Customer Initiated Withdrawal | 12/10/2012 |  |  | N | No
R09 | Johnstown-Altoona 230 kV |  | PA | Cambria | Withdrawn | PENELEC | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r09_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r09_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2006 | N/A | N/A |  | 9/3/2009 | Customer Milestone Not Met | 12/15/2009 | 12/15/2009 |  | N | No
R11 | South River 230 kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r11_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r11_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r11_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r11_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2006 | N/A | N/A |  | 11/27/2019 |  | 5/16/2020 | 5/16/2020 |  | N | No
R12 | Bedington - Nipetown |  | WV | Berkeley | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r12_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/r12_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2006 | N/A | N/A |  |  |  | 4/4/2008 | 4/4/2008 | 6/1/2008 | S | No
R13 | Tidd - Canton Central 345kV |  | OH | Columbiana | Withdrawn | AEP | 350 | 350 | 350 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r13_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2006 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
R14 | Tait 69kV | Tait Generating Units 4-7 | OH | Montgomery | In Service | Dayton | 376 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r14_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r14_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R15 | Adkins 345kV | Darby Generation Station Units 1-6 | OH | Pickaway | In Service | Dayton | 564 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r15_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r15_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/29/2006 | N/A | N/A |  |  |  | 5/1/2007 | 5/1/2007 | 5/1/2007 | N | No
R16 | Lena 138kV |  | IL | Stephenson | Withdrawn | ComEd | 126 | 126 | 25.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r16_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2006 | N/A | N/A |  | 11/24/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
R17 | Morgantown - Oak Grove 230kV | CPV St. Charles | MD | Charles | Withdrawn | PEPCO | 645 | 645 | 645 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r17_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r17_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/2/2006 | N/A | N/A |  | 4/1/2010 | Customer Milestone Not Met | 6/1/2013 | 6/1/2013 |  | N | No
R18 | Blackhawk | Winnebago Energy Center | IL | Boone | In Service | ComEd | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r18_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r18_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/r18_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/2/2006 | N/A | N/A |  |  |  | 1/3/2008 | 1/3/2008 | 1/3/2008 | N | No
R19 | Ladysmith 230kV | Ladysmith CT Units 3 & 4 | VA | Carolina | In Service | Dominion | 720 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r19_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r19_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r19_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r19_csa.pdf | Document Posted | N/A | N/A |  | 10/3/2006 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
R20 | Rock Springs | Rock Springs Units 3 & 4 | MD | Cecil | In Service | ODEC | 330 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r20_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/4/2006 | N/A | N/A |  |  |  | 7/1/2010 | 7/1/2010 | 1/1/2007 | N | No
R21 | Short Mountain |  | WV | Hardy | Withdrawn | APS | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r21_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2006 | N/A | N/A |  | 5/18/2007 | Customer Initiated Withdrawal | 11/30/2010 |  |  | N | No
R22 | Elk Garden - Junction 138kV |  | WV | Mineral | Withdrawn | APS | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2006 | N/A | N/A |  | 1/9/2009 | Customer Initiated Withdrawal | 11/30/2009 |  |  | N | No
R23 | Lakewood 230kV | Ocean Peaking Power (Lakewood CT1, CT2) | NJ | Ocean | In Service | JCPL | 375.6 | 20 | 20 | 19.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r23_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r23_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/16/2006 | N/A | N/A |  |  |  | 1/1/2007 |  | 1/1/2007 | N | No
R24 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r24_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r24_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2006 | N/A | N/A |  | 7/16/2008 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
R25 | Dickerson - Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2006 | N/A | N/A |  | 1/30/2007 | Customer Initiated Withdrawal | 6/1/2007 |  |  | S | No
R26 | Sunbury - Susquehanna 500kV |  | PA | Northumberland | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2006 | N/A | N/A |  | 6/13/2007 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
R27 | Frackville |  | PA | Schuylkill | Withdrawn | PPL | 52 | 52 | 52 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r27_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 1/20/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
R28 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r28_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 7/19/2007 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
R29 | Kawanee 138kV |  | IL | Knox | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r29_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r29_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 1/20/2010 | Customer Milestone Not Met | 12/1/2008 |  |  | N | No
R30 | Pontiac Mid-Point 345kV | Pleasant Ridge Wind Farm | IL | Livingston | Withdrawn | ComEd | 500 | 500 | 100 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r30_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r30_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r30_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r30_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2006 | N/A | N/A |  | 8/19/2019 |  | 12/31/2020 | 12/31/2020 |  | N | No
R31 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 18 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r31_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r31_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2006 | N/A | N/A |  | 4/27/2010 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | N | No
R32 | Salix - Claysburg 115kV | Highland North | PA | Cambria | In Service | PENELEC | 75 | 75 | 15 | 75 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r32_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r32_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r32_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2006 | N/A | N/A | 10/23/2010 |  |  | 3/31/2012 | 3/31/2012 | 3/23/2012 | N | No
R33 | Nelson 345 kV | Nelson Energy Center | IL | Unknown | In Service | ComEd | 600 | 600 | 600 | 600 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r33_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r33_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r33_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r33_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2006 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 5/8/2015 | N | No
R34 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2006 | N/A | N/A | [6 empty] | S | No
R35 | Robbins 138kV | Robbins Community Power | IL | Cook | Withdrawn | ComEd | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r35_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/3/2006 | N/A | N/A |  | 1/25/2013 | Customer Milestone Not Met | 9/30/2011 | 9/30/2011 |  | N | No
R36 | Bethany 138kV | Bluewater Wind - Bethany | DE | Unknown | Withdrawn | DPL | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r36_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r36_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r36_csa.pdf | Document Posted | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 8/6/2012 | Customer Initiated Withdrawal | 6/1/2018 | 6/1/2018 |  | N | No
R37 | Rehoboth 138kV |  | DE | Sussex | Withdrawn | DPL | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r37_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 1/12/2009 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
R38 | Milford 230kV |  | DE | Sussex | Withdrawn | DPL | 547 | 547 | 110 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2006 | N/A | N/A |  | 9/7/2007 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
R39 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2006 | N/A | N/A |  | 12/2/2008 |  | 8/1/2009 |  |  | N | No
R40 | Rockwood - Meyersdale 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 1.8 | 1.8 | 0.36 | 1.8 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r40_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r40_csa.pdf | Document Posted | N/A | N/A |  | 11/15/2006 | N/A | N/A |  |  |  | 6/30/2008 | 6/30/2008 | 6/30/2008 | N | No
R41 | Roxbury - Blain 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 6 | 6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2006 | N/A | N/A |  | 11/27/2007 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R42 | Moselem 69kV | Evansville Biomass | PA | Berks | Withdrawn | ME | 9 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r42_csa.pdf | Document Posted | N/A | N/A |  | 11/21/2006 | N/A | N/A |  | 8/6/2009 | Customer Initiated Withdrawal | 3/1/2009 | 3/1/2009 |  | N | No
R43 | Frackville - Hauto #3 | GCC Realty | PA | Schuylkill | Withdrawn | PPL | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r43_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r43_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r43_csa.pdf | Document Posted | N/A | N/A |  | 11/27/2006 | N/A | N/A |  | 6/15/2015 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
R44 | Rockport 765kV |  | KY | Henderson | Withdrawn | AEP | 485 | 485 | 485 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r44_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2006 | N/A | N/A |  | 5/21/2010 | Customer Initiated Withdrawal | 3/31/2011 |  |  | N | No
R45 | Mansfield - Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r45_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2006 | N/A | N/A |  | 2/2/2009 |  | 4/30/2009 | 4/30/2009 |  | N | No
R46 | Providence Heights #1A 138kV |  | IL | Bureau | Withdrawn | ComEd | 9 | 9 | 1.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2006 | N/A | N/A |  | 10/1/2007 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R47 |  |  | PA | Lancaster | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2006 | N/A | N/A | [6 empty] | S | No
R48 | Antwerp - Payne 69kV | Paulding aka Project R48 | OH | Paulding | Withdrawn | AEP | 48.3 | 48.3 | 9.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r48_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r48_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r48_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 1/4/2018 |  | 11/30/2020 | 11/30/2020 |  | N | No
R49 | Haviland - Milan 138kV | Timber Road II WF | OH | Paulding | In Service | AEP | 150 | 150 | 30 | 99 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r49_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r49_csa.pdf | Document Posted | N/A | N/A | 6/9/2011 | 12/6/2006 | N/A | N/A | 6/13/2011 |  |  | 12/31/2012 | 12/31/2012 | 7/15/2011 | N | No
R50 | Liberty - Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r50_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/6/2007 | Customer Milestone Not Met | 2/15/2009 |  |  | N | No
R51 | Kings Creek - Woodstock 69kV |  | OH | Champaign | Withdrawn | Dayton | 48 | 48 | 9.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r51_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/6/2007 | Customer Milestone Not Met | 12/15/2010 |  |  | N | No
R52 | Mechanicsburg - Darby | Buckeye Wind Farm - Phase 1 | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r52_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r52_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r52_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r52_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 2/21/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
R52A | Kings Creek 69kV | Buckeye Wind Farm - Phase 2 | OH | Champaign | Withdrawn | Dayton | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r52a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r52a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r52a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r52a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r52a_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2006 | N/A | N/A |  | 9/12/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
R53 | Stanton-Brookside 69kV |  | PA | Lackawanna | Withdrawn | PPL | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r53_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/8/2006 | N/A | N/A |  | 2/19/2009 | Customer Milestone Not Met | 11/11/2009 | 11/11/2009 |  | N | No
R54 | Dixon - Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r54_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2013 | 12/1/2013 |  | N | No
R55 | Dixon - Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r55_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2014 | 12/1/2014 |  | N | No
R56 | Quemahoning - Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 124 | 124 | 24.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r56_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r56_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2006 | N/A | N/A |  | 12/31/2009 | Customer Milestone Not Met | 11/30/2009 |  |  | N | No
R57 | South Reading 69kV | Evergreen Community Power | PA | Berks | In Service | ME | 30 | 30 | 9 | 11 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r57_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r57_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r57_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r57_csa.pdf | Document Posted | N/A | N/A |  | 12/20/2006 | N/A | N/A | 8/17/2009 |  |  | 4/6/2010 | 4/6/2010 | 4/6/2010 | N | No
R58 | Gloucester 230kV | Camden Cogen Tech | NJ | Camden | Withdrawn | PSEG | 204 | 55 | 55 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r58_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r58_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r58_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2006 | N/A | N/A |  | 12/3/2009 | Customer Initiated Withdrawal | 6/1/2013 | 6/1/2013 |  | N | No
R59 | Nelson-Lee County Energy Ctr 345kV |  | IL | Bureau | Withdrawn | ComEd | 160 | 160 | 32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r59_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/3/2007 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R60 | Convoy-East Lima 345kV | Blue Creek WF | OH | Van Wert | In Service | AEP | 350 | 350 | 70 | 304 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r60_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r60_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/15/2011 | 1/8/2007 | N/A | N/A | 10/7/2011 |  |  | 4/1/2012 | 4/1/2012 | 4/1/2012 | N | No
R61 | Collingwood-Hiple 345kV |  | IN | LeGrange | Withdrawn | AEP | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r61_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r61_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/8/2007 | N/A | N/A |  | 4/13/2009 | Customer Initiated Withdrawal | 6/30/2010 | 6/30/2010 |  | N | No
R62 | Big Sandy 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r62_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r62_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r62_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2007 | N/A | N/A |  |  |  | 6/1/2009 | 6/1/2009 | 5/31/2016 | N | No
R63 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 19 | 19 | 19 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r63_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/11/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
R64 | Lancaster 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r64_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r64_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/12/2007 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 7/1/2009 |  |  | N | No
R65 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r65_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r65_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/12/2007 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 2/25/2010 | 2/25/2010 |  | N | No
R66 | Fairlawn 138kV | Marcal Paper | NJ | Bergen | In Service | PSEG | 67 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r66_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r66_csa.pdf | Document Posted | N/A | N/A |  | 1/12/2007 | N/A | N/A |  |  |  | 5/1/2009 | 5/1/2009 | 3/1/2007 | N | No
R67 | Beaver Valley 345kV |  | PA | Beaver | Withdrawn | DL | 2510 | 2510 | 2510 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R68 | Sammis 345kV |  | OH | Jefferson | Withdrawn | AEP | 1940 | 1940 | 1940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R69 | Clifty Creek 345kV |  | IN | Jefferson | Withdrawn | AEP | 251 | 251 | 251 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R70 | Kygov Creek |  | OH | Gallia | Withdrawn | AEP | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2007 | N/A | N/A |  | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980 |  |  | N | No
R72 | Indian River 230kV | Indian River Units 3-4 | DE | Sussex | In Service | DPL | 438 | 18 | 18 | 18 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r72_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r72_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r72_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/18/2007 | N/A | N/A |  |  |  | 12/10/2008 | 12/10/2008 | 12/10/2008 | N | No
R73 | Indian River 138kV | Indian River Units #3 & #4 | DE | Sussex | In Service | DPL | 170 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/18/2007 | N/A | N/A |  |  |  | 12/10/2008 | 12/10/2008 | 12/10/2008 | N | No
R74 | Carlls Corner | Shoreham Energy Units 1-3 | NJ | Atlantic | In Service | AEC | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r74_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r74_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/r74_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/19/2007 | N/A | N/A |  |  |  | 11/14/2008 | 11/14/2008 | 11/14/2008 | N | No
R75 | Mitchell - Shepler Hill 138kV |  | PA | Allegheny | Withdrawn | APS | 242 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r75_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2007 | N/A | N/A |  | 5/3/2007 | Customer Milestone Not Met | 1/1/2008 |  |  | S | No
R76 | Kanawha 138kV | Hawks Nest Hydro | WV | Fayette | In Service | AEP | 54.2 | 6.16 | 5.5 | 6.159 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r76_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r76_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r76_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r76_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r76_csa.pdf | Document Posted | N/A | N/A |  | 1/23/2007 | N/A | N/A |  |  |  | 1/23/2017 | 1/23/2017 | 3/1/2009 | N | No
R77 | Morrisville 500kV |  | VA | Warren | Withdrawn | APS | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r77_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r77_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2007 | N/A | N/A |  | 7/20/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
R78 | Dresden-Pontiac 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 300.3 | 60.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r78_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r78_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2007 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
R79 | Tazewell-Kendall 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 300.3 | 60.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r79_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r79_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2007 | N/A | N/A |  | 5/5/2014 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
R80 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 640 | 0 | 60 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r80_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 1/26/2017 | 1/26/2017 | 4/30/2015 | N | No
R81 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1268 | 101 | 101 | 101 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r81_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r81_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r81_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/r81_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r81_csa.pdf | Document Posted | N/A | N/A |  | 1/26/2007 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 2/8/2010 | N | No
R82 | Kanawha #1 | Kanawna River #1 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r82_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r82_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R83 | Kanawha #2 | Kanawna River #2 | WV | Kanawha | In Service | AEP | 200 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r83_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r83_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R84 | Picway #5 | Pickway #5 | OH | Pickaway | In Service | AEP | 95 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r84_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r84_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R85 | Tanners Creek #1 | Tanners Creek #1 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r85_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r85_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R86 | Tanners Creek #2 | Tanners Creek #2 | IN | Dearborn | In Service | AEP | 145 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r86_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R87 | Muskingum River #5 | Muskingum River #5 | OH | Washington | In Service | AEP | 585 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r87_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/29/2007 | N/A | N/A |  |  |  | 4/1/2007 | 4/1/2007 | 4/1/2007 | N | No
R88 | Providence Heights #2 138kV |  | IL | Bureau | Withdrawn | ComEd | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r88_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2007 | N/A | N/A |  | 7/8/2008 | Customer Initiated Withdrawal | 12/31/2008 | 12/31/2008 |  | N | No
R89 | Conowingo | Conowingo Hydro Station | MD | Harford | In Service | PECO | 572 | 24 | 24 | 12 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r89_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
R90 | Dickerson-Pleasant View 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 14 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/r90_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/r90_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 1/30/2007 | N/A | N/A |  | 7/3/2007 | Customer Milestone Not Met | 6/1/2007 |  |  | S | No
R91 | Columbus-NJ |  | NJ | Burlington | In Service | PSEG | 0.4 | 0.37 | 0 | 0.25 | Energy | Generation Interconnection | Methane |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r91_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/r91_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2007 | N/A | N/A |  |  |  | 10/15/2008 | 10/15/2008 | 6/1/2007 | N | No
R92 | DuBois 115kV |  | PA | Clearfield | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r92_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r92_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/r92_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 12/19/2013 | Customer Initiated Withdrawal | 6/30/2009 |  |  | N | No
R93 | Kelford 115kV |  | NC | Bertie | Withdrawn | Dominion | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r93_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 5/31/2007 | Customer Milestone Not Met | 3/1/2008 | 3/1/2008 |  | N | No
R94 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 7/23/2007 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
R95 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | 940 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 7/23/2007 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
R96 | Lancaster-Maryland 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r96_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r96_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 8/29/2012 | Customer Initiated Withdrawal | 5/31/2010 | 5/31/2010 |  | N | No
R97 | Rockport 765kV | Rockport Unit 1 | IN | Spencer | In Service | AEP | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r97_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r97_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/r97_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2007 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 11/1/2011 | N | No
R98 | Northeast 34.5kV |  | VA | Henrico | Withdrawn | Dominion | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/r98_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/r98_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2007 | N/A | N/A |  | 2/27/2008 | Customer Milestone Not Met | 6/30/2008 |  |  | N | No
S01 | Derwood 13kV | Gude LF | MD | Montgomery | Deactivated | PEPCO | 1 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s01_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s01_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s01_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s01_csa.pdf | Document Posted | N/A | N/A |  | 2/5/2007 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 7/1/2008 | N | No
S02 | Mt. Zion 13kV | Oaks LF | MD | Montgomery | In Service | PEPCO | 4 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s02_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s02_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s02_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s02_csa.pdf | Document Posted | N/A | N/A |  | 2/5/2007 | N/A | N/A |  |  |  | 7/1/2009 | 7/1/2009 | 7/1/2008 | N | No
S03 | Edgemoor 230kV | Edgemoor #5 | DE | New Castle | In Service | DPL | 450 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s03_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s03_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s03_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/13/2007 | N/A | N/A |  |  |  | 12/31/2007 | 12/31/2007 | 12/31/2007 | N | No
S04 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 633 | 633 | 633 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s04_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2007 | N/A | N/A |  | 11/1/2007 | Customer Milestone Not Met | 7/1/2010 |  |  | N | No
S05 | Seneca #2 230kV | Seneca Pumped Generating Station Unit 2 | PA | Warren | In Service | PENELEC | 468 | 16 | 16 | 16 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s05_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s05_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s05_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 8/11/2010 | 8/11/2010 | 8/11/2010 | N | No
S06 | Olive-DeQuine 345kV | Meadow Lake | IN | White | In Service | AEP | 202 | 202 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s06_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s06_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2007 | N/A | N/A |  |  |  | 10/6/2009 | 10/6/2009 | 12/1/2009 | N | No
S07 | Keystone-Branchburg | AC Landfill Energy Units 1, 2, 3 | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s07_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s07_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s07_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S08 | Kammer-Doubs |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s08_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s08_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s08_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S09 | Conemaugh-Conastone |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s09_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s09_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s09_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S10 | Jacksons Ferry-Burches Hill |  | N/A | N/A | Withdrawn | APS | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/s10_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/s10_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/s10_arr-csa.pdf | Document Posted | N/A | N/A |  | 3/1/2007 | N/A | N/A |  | 2/20/2013 |  |  |  |  | EE | No
S100 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 614 | 80 | 80 | 80 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s100_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s100_csa.pdf | Document Posted | N/A | N/A | 11/12/2010 | 7/31/2007 | N/A | N/A |  |  |  | 3/1/2012 |  | 3/22/2012 | N | No
S101 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 580 | 580 | 580 | 580 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s101_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s101_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 10/22/2011 | 10/22/2011 | 10/22/2011 | N | No
S102 | Ladysmith 230kV | Ladysmith Combustion Turbine Unit 5 | VA | Carolina | In Service | Dominion | 950 | 170 | 170 | 170 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s102_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
S103 | Warren 115kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 57 | 57 | 57 | 57 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s103_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s103_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s103_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A | 4/5/2011 |  |  | 4/5/2011 | 4/5/2011 | 4/5/2011 | N | No
S104 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 5/14/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | S | No
S105 | Croydon-Emilie |  | PA | Bucks | Withdrawn | PECO | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s105_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 3/3/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
S107 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s107_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
S108 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S109 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S11 | Seward-Tower 51 115kV |  | PA | Cambria | Withdrawn | PENELEC | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s11_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2007 | N/A | N/A |  | 6/26/2009 | Customer Initiated Withdrawal | 2/1/2009 |  |  | N | No
S110 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 1023 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/2/2010 | 5/2/2010 | 5/2/2010 | N | No
S111 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S112 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 1030 | 65 | 65 | 65 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/18/2010 | 5/18/2010 | 5/18/2010 | N | No
S113 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 15 | 15 | 15 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S114 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 6/13/2012 | N | No
S115 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 932 | 75 | 75 | 75 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s115_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 7/1/2011 | 7/1/2011 | 7/1/2011 | N | No
S116 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 912 | 912 | 912 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 2/24/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
S117 | Haviland 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008 |  |  | N | No
S118 | North Delphos 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008 |  |  | N | No
S119 | Lexington-Dooms 500kV |  | VA | Augusta | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s119_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S12 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 1300 | 1300 | 1300 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s12_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2007 | N/A | N/A |  | 3/12/2008 |  | 1/1/2014 |  |  | N | No
S120 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s120_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 1/16/2008 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
S121 | Vineland 69kV | Howard M. Down Power Plant Unit 11 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s121_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s121_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 4/18/2012 | N | No
S122 | Churchtown-Cumberland 230kV |  | NJ | Cumberland | Withdrawn | AEC | 478 | 478 | 478 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s122_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/28/2008 |  | 6/1/2010 | 6/1/2010 |  | N | No
S123 | Tiltonsville 138kV | Pike Island | OH | Jefferson | Withdrawn | AEP | 50 | 50 | 39 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s123_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
S124 | Aroyo-Wilie Ridge 138kV |  | WV | Hancock | Withdrawn | APS | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s124_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 3/27/2009 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
S13 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 238 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s13_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s13_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/19/2007 | N/A | N/A |  |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
S14 | Dans Mountain | Dans Mountain | PA | Allegheny | Engineering and Procurement | APS | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s14_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s14_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s14_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A | 12/31/2021 |  |  | 11/6/2019 | 11/6/2019 |  | N | No
S15 | Burches Hill 500-230kV |  | MD | Prince George's | Withdrawn | PEPCO | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s15_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s15_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 8/7/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S16 | Gilbert-Glen Gardner 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s16_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 12/4/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
S17 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s17_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s17_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s17_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s17_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s17_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 12/18/2013 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
S18 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 1250 | 1250 | 1250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s18_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 2/21/2008 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
S19 | Pine Grove-Frailey 69kV |  | PA | Schuylkill | Withdrawn | PPL | 28 | 28 | 5.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s19_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 11/1/2007 | Customer Initiated Withdrawal | 10/1/2009 |  |  | N | No
S20 | Pine Grove-Fishbach 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s20_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A |  | 5/12/2011 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
S21B |  |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 0 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
S22 | Peach Bottom 500kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s22_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2007 | N/A | N/A |  | 11/13/2007 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
S23 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s23_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s23_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2007 | N/A | N/A |  | 9/9/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
S25 | Parlin 230kV | Calpine Parlin Energy Center | NJ | Middlesex | In Service | JCPL | 124 | 114 | 114 | 114 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s25_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s25_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s25_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2007 | N/A | N/A |  |  |  | 5/13/2008 |  | 5/13/2008 | N | No
S26 | Bluff Point-Jay 138kV |  | IN | Jay | Withdrawn | AEP | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s26_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2007 | N/A | N/A |  | 5/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
S27 | Blue Mound I | Twin Groves I WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s27_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s27_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s27_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S28 | Blue Mound II | Twin Groves II WF | IL | McLean | In Service | ComEd | 198 | 0 | 39.6 | 198 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s28_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s28_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s28_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/17/2007 | N/A | N/A |  |  |  | 6/24/2010 | 6/24/2010 | 6/24/2010 | N | No
S28B |  |  | N/A | N/A | Withdrawn | DTE Energy Trading | 0 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
S29 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 900 | 900 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s29_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2007 | N/A | N/A |  | 2/23/2008 | Customer Milestone Not Met | 12/31/2007 | 12/31/2007 |  | N | No
S29B | Somerset 23kV | SCI Laurel Highlands | PA | Somerset | In Service | PENELEC | 6.8 | 6.75 | 5.7 | 6.75 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s29b_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s29b_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s29b_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s29b_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s29b_csa.pdf | Document Posted | N/A | N/A | 6/20/2011 | 4/27/2007 | N/A | N/A | 9/27/2011 |  |  | 9/1/2011 | 9/1/2011 | 9/29/2011 | N | No
S30 | Gould | Sun Paper | MD | Baltimore City | In Service | BGE | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s30_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s30_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/s30_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2007 | N/A | N/A |  |  |  | 8/8/2008 | 8/8/2008 | 12/31/2007 | N | No
S30B 564954 | LGEE-PJM |  | N/A | N/A | Withdrawn | Cash Creek Generation LLC | 640 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/564954_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 5/1/2007 | 3/1/2012 | 3/1/2041 |  | 8/31/2007 |  |  |  |  | FF | No
S31 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 450 | 450 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s31_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2007 | N/A | N/A |  | 4/9/2008 | Customer Milestone Not Met | 12/9/2009 |  |  | N | No
S32 | Perryman | Perryman 6 Units 1-4 | MD | Harford | In Service | BGE | 130 | 130 | 130 | 130 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s32_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s32_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s32_csa.pdf | Document Posted | N/A | N/A | 5/6/2015 | 5/3/2007 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/9/2015 | N | No
S33 | Riverside |  | MD | Baltimore County | Withdrawn | BGE | 120 | 120 | 85 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s33_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s33_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/3/2007 | N/A | N/A |  | 7/2/2009 | Customer Initiated Withdrawal | 5/1/2010 |  |  | N | No
S34 | Handsome Lake Energy 345kV | Handsome Lake | PA | Venango | In Service | PENELEC | 270 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s34_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s34_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s34_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/1/2007 |  | 6/1/2007 | N | No
S35 | Beverly 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 620 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s35_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s35_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s35_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/27/2007 | 6/27/2007 | 6/1/2008 | N | No
S36 | Kankakee 138 kV | Kankakee Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s36_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s36_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s36_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s36_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s36_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 6/30/2015 | 6/30/2015 | 7/28/2015 | N | No
S37 | Kankakee 138kV | Kelly Creek Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 175 | 35 | 175 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s37_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s37_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s37_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s37_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s37_csa.pdf | Document Posted | N/A | N/A |  | 5/7/2007 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 11/9/2016 | N | No
S38 | Westvaco 138kV | Luke Paper | PA | Allegheny | In Service | APS | 8 | 8 | 0 | 8 | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s38_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s38_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s38_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s38_csa.pdf | Document Posted | N/A | N/A | 1/26/2009 | 5/7/2007 | N/A | N/A | 1/26/2009 |  |  | 1/26/2009 | 1/26/2009 | 4/1/2009 | N | No
S39 |  |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 0 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
S40 | Hegins | Commonwealth LF | PA | Schuylkill | In Service | PPL | 10.5 | 10.5 | 10.5 | 10.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s40_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s40_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s40_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s40_csa.pdf | Document Posted | N/A | N/A | 12/23/2008 | 5/10/2007 | N/A | N/A | 1/22/2009 |  |  | 1/21/2009 | 1/21/2009 | 1/21/2009 | N | No
S41 | Eldred-Reed 69kV | IntelliWatt | PA | Northumberland | Withdrawn | PPL | 12.5 | 12.5 | 12.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s41_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s41_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s41_csa.pdf | Document Posted | N/A | N/A |  | 5/10/2007 | N/A | N/A |  | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
S42 | Eldred-Fairview | Penn Wind | PA | Northumberland | Withdrawn | PPL | 18 | 18 | 3.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s42_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s42_csa.pdf | Document Posted | N/A | N/A |  | 5/15/2007 | N/A | N/A |  | 1/8/2014 | Customer Initiated Withdrawal | 5/1/2013 | 5/1/2013 |  | N | No
S43 | Vineland | Vineland Unit #9 | NJ | Cumberland | In Service | AEC | 17 | 17 | 17 | 17 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s43_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s43_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/15/2007 | N/A | N/A |  |  |  | 11/12/2007 | 11/12/2007 | 11/12/2007 | N | No
S44 | Mifflin County |  | PA | Mifflin | Withdrawn | PENELEC | 110 | 110 | 22 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 10/28/2008 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
S45 | Mechanicsburg North |  | OH | Champaign | Withdrawn | Dayton | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 3/12/2012 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
S46 | Mechanicsburg South |  | OH | Champaign | Withdrawn | Dayton | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s46_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s46_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2007 | N/A | N/A |  | 5/15/2009 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
S47 |  |  | N/A | N/A | Withdrawn | MidAmerican Energy Company |  |  |  |  | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  |  | N/A | N/A | [9 empty] | 12/14/2007 |  |  |  |  | FF | No
S48 |  |  | N/A | N/A | Withdrawn | MidAmerican Energy Company |  |  |  |  | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  |  | N/A | N/A | [9 empty] | 12/14/2007 |  |  |  |  | FF | No
S49 | Bedford 115kV |  | PA | Bedford | Withdrawn | PENELEC | 202.5 | 90 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s49_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2007 | N/A | N/A |  | 9/22/2010 | Customer Initiated Withdrawal | 10/31/2013 | 10/31/2013 |  | N | No
S50 | Occoquan 230kV | Ogden Martin | VA | Fairfax | In Service | Dominion | 98 | 18 | 18 | 18 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s50_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s50_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s50_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/24/2007 | N/A | N/A |  |  |  | 6/30/2007 |  | 6/30/2007 | N | No
S51 | E. Liberty-Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 99 | 99 | 19.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s51_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 4/7/2010 | Customer Initiated Withdrawal | 6/1/2009 |  |  | N | No
S52 | Morrisville 500kV |  | VA | Warren | Withdrawn | Dominion | 600 | 50 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s52_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s52_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 7/2/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
S53 | Lee County E.C. 345kV |  | IL | Bureau | Withdrawn | ComEd | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s53_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2007 | N/A | N/A |  | 8/15/2008 | Customer Milestone Not Met | 9/1/2008 |  |  | N | No
S53B 568550 | PJM.AP-PJM.DPL |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/568550_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
S53C 565854 | PJM-CIN |  | N/A | N/A | Withdrawn | Duke Energy Ohio, Inc. | 310 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/565855_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/565855_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/1/2007 | 6/1/2010 | 6/1/2011 |  | 9/12/2008 |  |  |  |  | FF | No
S54 | Tazewell 138kV |  | VA | Tazewell | Withdrawn | AEP | 130 | 130 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s54_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/5/2007 | N/A | N/A |  | 6/25/2009 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
S55 | Zion 345kV | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 585 | 495 | 585 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/6/2007 | N/A | N/A |  |  |  | 2/25/2011 | 2/25/2011 | 12/19/2011 | N | No
S56 | Beaver Creek-Hazard 138kV |  | KY | Knott | Withdrawn | AEP | 535 | 535 | 535 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s56_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2007 | N/A | N/A |  | 4/28/2008 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
S57 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1500 |  |  |  | Energy | Merchant Transmission | Wind | DC | F/TIR 300/NF/TIR 1200 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s57_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s57_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
S58 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1600 | 0 | 0 |  | Energy | Merchant Transmission | Wind | DC | F/TIR 400/NF/TIR 1200 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s58_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/s58_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/11/2007 | N/A | N/A |  | 1/19/2018 |  | 12/31/2020 | 12/31/2020 |  | S | No
S58B 573929 | AMIL-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Agency | 240 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/573929_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/19/2007 | 1/1/2012 | 1/1/2014 |  | 6/4/2008 |  |  |  |  | FF | No
S58C 574221 | PJM-CIN |  | N/A | N/A | Confirmed | Cargill Power Markets LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/574222_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/574222_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/20/2007 | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
S58D 574906 | PJM.AP-PJM.DOM |  | N/A | N/A | Confirmed | Gen Power Coal III | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/574906_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 6/21/2007 | 4/1/2011 | 3/31/2041 | [6 empty] | FF | No
S59 | Sharpsburg 12kV | Wenning Poultry | OH | Mercer | In Service | Dayton | 1.9 | 1.89 | 0 | 1.5 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s59_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/s59_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/25/2007 | N/A | N/A |  |  |  | 11/1/2007 |  | 10/30/2008 | N | No
S59B 577135 | PJM-CIN |  | N/A | N/A | Confirmed | Duke Energy Ohio, Inc. | 20 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/577135_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/577135_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/26/2007 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
S60 | Essex 26kV | Newark Boxboard | NJ | Essex | Withdrawn | PSEG | 63 | 63 | 63 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s60_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s60_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/27/2007 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 6/1/2008 |  |  | N | No
S61 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s61_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s61_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s61_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/27/2007 | N/A | N/A |  |  |  | 10/11/2011 | 10/11/2011 | 10/11/2011 | N | No
S62 | LaSalle-Braidwood 345kV |  | IL | Lasalle | Withdrawn | ComEd | 500 | 500 | 100 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s62_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s62_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2007 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
S63 | Tait 69kV | Tait Generating Station | OH | Montgomery | In Service | Dayton | 376 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s63_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s63_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s63_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/5/2007 | N/A | N/A |  |  |  | 6/29/2007 |  | 10/5/2007 | N | No
S64 | York Inc. 115kV |  | PA | York | Withdrawn | ME | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s64_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s64_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s64_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/6/2007 | N/A | N/A |  | 5/31/2013 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
S65 | Cambria |  | PA | Cambria | Withdrawn | PENELEC | 85 | 85 | 17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s65_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2007 | N/A | N/A |  | 12/30/2008 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
S66 | Downing Avenue 115kV |  | PA | Erie | Withdrawn | PENELEC | 96 | 96 | 96 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s66_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2007 | N/A | N/A |  | 8/28/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
S67 | Gould St. | Gould Street | MD | Baltimore City | Deactivated | BGE | 106 | 101 | 101 | 99.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s67_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s67_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s67_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s67_csa.pdf | Document Posted | N/A | N/A |  | 7/26/2007 | N/A | N/A |  |  |  | 5/30/2008 | 5/30/2008 | 6/1/2008 | N | No
S68 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 660 | 660 | 0 |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/s68_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2007 | N/A | N/A |  | 4/23/2008 | Customer Initiated Withdrawal | 12/31/2007 |  |  | S | No
S70 | Eureka 138kV | Willow Island Hydro Generation Project | WV | Wetzel | In Service | APS | 36.4 | 36.4 | 36.4 | 36.4 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s70_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s70_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s70_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s70_csa.pdf | Document Posted | N/A | N/A |  | 7/27/2007 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
S71 | Bluff Point 138kV | Bluff Point | IN | Jay | In Service | AEP | 120 | 120 | 24 | 120 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s71_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s71_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s71_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s71_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s71_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2007 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 9/15/2017 | N | No
S72 | Convoy-East Lima 345kV | Dog Creek Wind Farm | IN | Allen | Withdrawn | AEP | 240 | 240 | 48 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s72_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s72_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s72_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s72_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s72_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2007 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
S73 | Lincoln-North Delphos |  | IN | Allen | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s73_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s73_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2007 | N/A | N/A |  | 1/7/2014 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
S74 | Mount Storm 500kV | Mount Storm Unit 2 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s74_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S75 | Mount Storm 500kV | Mount Storm Unit 3 | WV | Grant | Withdrawn | Dominion | 574 | 29 | 29 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s75_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s75_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2012 | 6/1/2012 |  | N | No
S76 | Mount Storm 500kV | Mount Storm Unit 1 | WV | Grant | In Service | Dominion | 585 | 38 | 25 | 38 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s76_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s76_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/6/2013 | N | No
S77 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 450 | 16 | 16 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s77_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 12/4/2008 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
S78 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 450 | 19 | 19 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s78_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 12/4/2008 | Customer Initiated Withdrawal | 4/1/2012 |  |  | N | No
S79 | Chesterfield 230kV | Chesterfield Unit #6 | VA | Chesterfield | In Service | Dominion | 691 | 27 | 27 | 27 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s79_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s79_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 12/1/2010 | 12/1/2010 | 12/1/2010 | N | No
S80 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 356 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s80_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s80_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s80_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
S81 | Basin 230kV | Bellemeade | VA | City of Richmond | Deactivated | Dominion | 306 | 22 | 22 | 22 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s81_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s81_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s81_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 4/27/2010 | 4/27/2010 | 4/27/2010 | N | No
S82 | Surry 230kV | Gravel Neck Gas Turbine #3 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s82_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s82_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s82_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s82_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S83 | Surry 230kV | Gravel Neck Gas Turbine #4 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s83_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s83_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s83_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s83_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S84 | Surry 230kV | Gravel Neck Gas Turbine #5 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s84_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s84_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s84_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s84_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S85 | Surry 230kV | Gravel Neck Gas Turbine #6 | VA | Surry | In Service | Dominion | 92 | 19 | 19 | 19 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s85_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s85_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 5/6/2010 | 5/6/2010 | 5/6/2010 | N | No
S86 | Darbytown 230kV | Darbytown GT1 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s86_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s86_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S87 | Darbytown 230kV | Darbytown GT2 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s87_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s87_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s87_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S88 | Darbytown 230kV | Darbytown GT3 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s88_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s88_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s88_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S89 | Darbytown 230kV | Darbytown GT4 | VA | Henrico | In Service | Dominion | 92 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s89_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s89_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s89_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S90 | Elizabeth River 230kV | Elizabeth River GT1 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s90_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s90_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s90_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S91 | Elizabeth River 230kV | Elizabeth River GT2 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s91_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s91_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s91_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S92 | Elizabeth River 230kV | Elizabeth River GT3 | VA | City of Chesapeake | In Service | Dominion | 125 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s92_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s92_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s92_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S93 | Remington 230kV | Remington GT1 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s93_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s93_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s93_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S94 | Remington 230kV | Remington GT2 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s94_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s94_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s94_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S95 | Remington 230kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s95_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s95_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s95_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S96 | Remington 230kV | Remington GT4 | VA | Fauquier | In Service | Dominion | 190 | 15 | 15 | 15 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s96_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s96_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s96_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
S97 | South Anna 230kV | South Anna Unit 1 | VA | Orange | Withdrawn | Dominion | 144 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s97_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s97_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s97_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2013 | 6/1/2013 |  | N | No
S98 | South Anna 230kV | South Anna Unit 2 | VA | Orange | Withdrawn | Dominion | 144 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s98_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s98_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/s98_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 6/1/2013 | 6/1/2013 |  | N | No
S99 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 806 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s99_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s99_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2007 | N/A | N/A |  | 4/3/2009 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
T01 639662 | ALTE-PJM |  | N/A | N/A | Withdrawn | Madison Gas &amp; Electric | 75 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 8/30/2007 |  |  |  |  | FF | No
T02 639671 | CPLE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 172 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/639671_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 10/30/2007 |  |  |  |  | FF | No
T03 639678 | CPLE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 172 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/639678_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T04 639742 | DUK-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/639742_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T05 639743 | DUK-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/639743_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/1/2007 | 6/1/2008 | 6/1/2009 |  | 10/30/2007 |  |  |  |  | FF | No
T06 | Yorktown 230kV | Yorktown 3 | VA | York | Withdrawn | Dominion | 838 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t06_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t06_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t06_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 8/3/2007 | N/A | N/A |  | 7/12/2012 | Queue Not Required | 5/1/2014 |  |  | N | No
T07 664042 | PJM-CIN |  | N/A | N/A | Withdrawn | Conectiv Energy Supply | 1000 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/664042_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 8/6/2007 | 1/1/2008 | 1/1/2010 |  | 8/30/2007 |  |  |  |  | FF | No
T08 692322 | PJM-NIPS |  | N/A | N/A | Withdrawn | PP&amp;L Energy Plus Company | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/692322_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/10/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T09 692342 | PJM-CIN |  | N/A | N/A | Withdrawn | PP&amp;L Energy Plus Company | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/692342_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/10/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T10 | Cranes Corner 34.5KV | Stafford Regional LF | VA | Stafford | In Service | Dominion | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t10_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t10_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 2/3/2009 | 8/15/2007 | N/A | N/A | 2/6/2009 |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T100 | Grover-East Towanda 230 kV |  | PA | Bradford | Withdrawn | PENELEC | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2007 | N/A | N/A |  | 10/15/2008 | Customer Initiated Withdrawal | 9/30/2009 |  |  | N | No
T101 | Glassrock 69kV |  | OH | Perry | Withdrawn | AEP | 6.4 | 6.4 | 6.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2007 | N/A | N/A |  | 5/21/2008 |  | 11/1/2008 |  |  | N | No
T102 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t102_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T103 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 160 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/13/2007 | N/A | N/A |  |  |  | 10/30/2007 |  | 9/2/2008 | N | No
T104 | Gosport 115kV | SPSA Navy Power Plant | VA | City of Portsmouth | In Service | Dominion | 50 | 20 |  | 20 | Energy | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t104_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t104_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2007 | N/A | N/A |  |  |  | 4/1/2008 |  | 4/1/2008 | N | No
T105 | Pontiac Midpoint-Wilton Center 350 MW |  | IL | Livingston | Withdrawn | ComEd | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t105_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2007 | N/A | N/A |  | 12/20/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T106 | Lee County |  | IL | Bureau | Withdrawn | ComEd | 140 | 140 | 28 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t106_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/21/2007 | N/A | N/A |  | 4/27/2010 | Customer Milestone Not Met | 12/31/2008 |  |  | N | No
T107 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 675 | 625 | 625 | 625 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t107_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t107_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 11/21/2007 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
T108 | Archbald 69kV | Archbald Generating Station | PA | Lackawanna | In Service | PPL | 9.2 | 9.2 | 9.2 | 9.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t108_csa.pdf | Document Posted | N/A | N/A |  | 11/29/2007 | N/A | N/A | 11/13/2009 |  |  | 1/25/2010 | 1/25/2010 | 1/25/2010 | N | No
T109 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 918 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T11 | Laurel-Sussex 69kV | Southern LF Units 1-5 | DE | Sussex | In Service | DPL | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 5/21/2010 | 5/21/2010 | 5/21/2010 | N | No
T110 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 916 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/3/2007 | N/A | N/A |  |  |  | 8/23/2010 | 8/23/2010 | 8/23/2010 | N | No
T111 | Buchanan Hydro-Niles 69kV | Southeast Berrien LF | MI | Berrien | In Service | AEP | 6.4 | 6.4 | 6.4 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t111_csa.pdf | Document Posted | N/A | N/A |  | 12/12/2007 | N/A | N/A |  |  |  | 5/29/2009 | 5/29/2009 | 5/29/2009 | N | No
T112 | Morrisville-Loudoun 500kV |  | VA | Fauquier | Withdrawn | Dominion | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/t112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/t112_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/12/2007 | N/A | N/A |  | 7/28/2009 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | S | No
T113 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 132 | 16 | 16 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t113_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 11/10/2008 | Customer Initiated Withdrawal | 5/31/2010 |  |  | N | No
T114 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 600 | 32.5 | 32.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t114_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 2/20/2008 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
T115 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 600 | 32.5 | 32.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2007 | N/A | N/A |  | 2/20/2008 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
T116 | LaSalle 1 |  | IL | Lasalle | Withdrawn | ComEd | 1151 | 18 | 18 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/17/2007 | N/A | N/A |  | 3/19/2010 | Customer Milestone Not Met | 3/1/2008 |  |  | N | No
T117 | Hunlock Creek 69kV | Hunlock Creek | PA | Luzerne | In Service | UGI | 126 | 126 | 126 | 126 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t117_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t117_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t117_csa.pdf | Document Posted | N/A | N/A |  | 12/17/2007 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 1/31/2011 | N | No
T118 | Linwood 230kV | Phillips Island CT1, CT2, CT3, CT4 | PA | Delaware | In Service | PECO | 840 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t118_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t118_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/19/2007 | N/A | N/A |  |  |  | 9/30/2009 | 9/30/2009 | 9/30/2009 | N | No
T119 | Metuchen 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t119_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2007 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
T12 | Kent-Harrington 69kV | Central LF Units 1-4 | DE | Kent | In Service | DPL | 4.3 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t12_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t12_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2007 | N/A | N/A |  |  |  | 8/14/2007 |  | 10/1/2007 | N | No
T120 | Kankakee #3 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 6/30/2010 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T121 | Potter-Gold 115kV | Potter Wind Farm | PA | Potter | Withdrawn | PENELEC | 75 | 75 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t121_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t121_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t121_csa.pdf | Document Posted | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
T122 | Ocean Bay 138kV |  | MD | Worcester | Withdrawn | DPL | 600 | 600 | 120 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2007 | N/A | N/A |  | 7/30/2009 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
T123 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 5/29/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T124 | Latham-Pontiac I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t124_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
T125 | Latham-Pontiac II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t125_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/2/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
T126 | Olive-Dequine 345kV | Meadow Lake WF II, Meadow Lake WF III | IN | Benton | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t126_csa.pdf | Document Posted | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 10/28/2010 | 10/28/2010 | 10/28/2010 | N | No
T127 | Olive-Dequine 345kV | Meadow Lake WF 4 - 5 | IN | White | In Service | AEP | 200 | 200 | 40 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/30/2010 | N | No
T128 | Masontown 500kV |  | PA | Fayette | Withdrawn | APS | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t128_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2008 | N/A | N/A |  | 6/2/2008 | Customer Milestone Not Met | 1/1/2012 |  |  | N | No
T129 | Printz 230kV | Liberty | PA | Delaware | In Service | PECO | 541 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t129_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/8/2008 | N/A | N/A |  |  |  | 12/1/2008 | 12/1/2008 | 12/1/2008 | N | No
T13 707849 | PJM-MECS |  | N/A | N/A | Withdrawn | PP&amp;L Energy Plus Company | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/707849_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/15/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T130 | Maddox Creek-RP Mone 345 kV |  | OH | Paulding | Withdrawn | AEP | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t130_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/9/2008 | N/A | N/A |  | 1/26/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T131 | Lincoln-Sterling 138kV | Paulding Wind Farm III LLC | OH | Paulding | In Service | AEP | 150 | 150 | 30 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t131_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t131_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t131_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/23/2016 | N | No
T132 | Cloverdale-Lexington 500kV |  | VA | Botetourt | Withdrawn | AEP | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2008 | N/A | N/A |  | 12/9/2009 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
T133 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t133_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t133_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t133_csa.pdf | Document Posted | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018 | 7/31/2018 |  | N | No
T134 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 325 | 325 | 325 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t134_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t134_csa.pdf | Document Posted | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018 | 7/31/2018 |  | N | No
T135 | Chambers 230kV |  | NJ | Salem | Withdrawn | AEC | 240 | 15 | 15 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t135_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 1/10/2008 | N/A | N/A |  | 4/28/2009 | Queue Not Required | 1/7/2008 |  |  | N | No
T136 852816 | MECS-PJM |  | N/A | N/A | Withdrawn | Fortis Energy M&amp;T GP | 350 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T137 852819 | MECS-PJM |  | N/A | N/A | Withdrawn | Fortis Energy M&amp;T GP | 350 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T138 852821 | MECS-PJM |  | N/A | N/A | Withdrawn | Fortis Energy M&amp;T GP | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/9/2008 | 6/1/2008 | 6/1/2009 |  | 1/29/2008 |  |  |  |  | FF | No
T139 853465 | FE-PJM |  | N/A | N/A | Withdrawn | FirstEnergy Solutions Corp. | 707 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/853465_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/853465_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 1/10/2008 | 6/1/2008 | 6/1/2009 |  | 9/18/2009 |  |  |  |  | FF | No
T14 707852 | PJM-WEC |  | N/A | N/A | Withdrawn | PP&amp;L Energy Plus Company | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/707852_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/15/2007 | 11/1/2007 | 11/1/2008 |  | 11/13/2007 |  |  |  |  | FF | No
T140 853531 | FE-PJM |  | N/A | N/A | Withdrawn | FirstEnergy Solutions Corp. | 2510 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/853531_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/853531_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 1/10/2008 | 6/1/2008 | 6/1/2009 |  | 11/4/2008 |  |  |  |  | FF | No
T141 853853 | PJM-MEC |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/853853_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 1/11/2008 | 6/1/2008 | 6/1/2013 |  | 4/14/2008 |  |  |  |  | FF | No
T142 | Southwest Lima-Marysville 345kV | Van Wert II | OH | Hardin | Withdrawn | AEP | 300 | 300 | 60 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t142_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t142_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t142_csa.pdf | Document Posted | N/A | N/A |  | 1/15/2008 | N/A | N/A |  | 9/18/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
T143 | Hennepin |  | IL | Putnam | Withdrawn | ComEd | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2008 | N/A | N/A |  | 11/16/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T144 | Pocomoke |  | MD | Somerset | Withdrawn | DPL | 19.8 | 19.8 | 10 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t144_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t144_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/17/2008 | N/A | N/A |  | 7/30/2014 | Customer Initiated Withdrawal | 1/1/2010 |  |  | N | No
T145 | AP South 500kV |  | N/A | N/A | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2008 | N/A | N/A |  | 12/29/2009 | Customer Milestone Not Met | 12/31/2008 |  |  | S | No
T146 | England |  | NJ | Cape May | Withdrawn | AEC | 346 | 346 | 69.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t146_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2008 | N/A | N/A |  | 1/28/2014 | Customer Initiated Withdrawal | 12/31/2020 | 12/31/2020 |  | N | No
T147 | Perryman | Perryman Generating Unit 51 | MD | Harford | In Service | BGE | 183 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t147_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t147_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/24/2008 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T148 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t148_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2008 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
T149 | Birchwood 230kV |  | VA | King George | Withdrawn | Dominion | 580 | 580 | 580 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t149_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 5/29/2008 | Customer Milestone Not Met | 1/1/2012 |  |  | N | No
T15 709682 | CPLE-PJM |  | N/A | N/A | Confirmed | DTE Energy Trading | 47 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/709682_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/709682_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/16/2007 | 1/1/2009 | 1/1/2014 | [6 empty] | FF | No
T152 | North Haverhill 69kV |  | OH | Scioto | Withdrawn | AEP | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 9/28/2009 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
T153 | Milford 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.1 | 1.12 | 1.12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t153_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2008 | N/A | N/A |  | 12/11/2008 | Customer Initiated Withdrawal | 6/1/2008 |  |  | N | No
T154 | Bellefontaine 69kV | Cherokee Run LF | OH | Logan | Deactivated | Dayton | 10 | 10 | 10 | 10 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/t154_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/28/2008 | N/A | N/A |  |  |  | 2/27/2009 | 2/27/2009 | 2/27/2009 | N | No
T155 | Belknap 25kV | Mahoning Creek Dam Hydro Project | PA | Armstrong | In Service | APS | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t155_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/t155_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2008 | N/A | N/A |  |  |  | 3/1/2014 | 3/1/2014 | 12/26/2013 | N | No
T156 | Champion |  | PA | Washington | Withdrawn | APS | 292 | 20 | 20 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t156_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/28/2013 | Customer Initiated Withdrawal | 2/28/2011 |  |  | N | No
T157 | New Creek Mountain 500kV | New Creek Mountain Wind Farm | WV | Mineral | In Service | Dominion | 102.5 | 102.5 | 20.5 | 102.5 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t157_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t157_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t157_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2008 | N/A | N/A |  |  |  | 12/18/2016 | 12/18/2016 | 12/26/2016 | N | No
T158 | Elk Garden-Junction 138kV |  | WV | Mineral | Withdrawn | APS | 70 | 70 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t158_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 7/24/2008 |  | 11/30/2010 |  |  | N | No
T159 | Bergen 230kV |  | NJ | Hudson | Withdrawn | PSEG | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t159_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/7/2008 |  | 6/1/2011 |  |  | N | No
T16 | Kelso Gap 138kV | Fair Wind Project | MD | Garrett | In Service | APS | 30 | 30 | 6 | 30 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t16_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t16_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t16_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t16_csa.pdf | Document Posted | N/A | N/A |  | 8/20/2007 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 11/15/2015 | N | No
T162 | Lock Haven |  | PA | Clinton | Withdrawn | PPL | 90 | 90 | 63 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t162_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 7/16/2009 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
T163 | Carter Fabrics 115kV |  | VA | Halifax | Withdrawn | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t163_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2008 | N/A | N/A |  | 5/29/2008 | Customer Milestone Not Met | 4/1/2012 |  |  | N | No
T164 | Muskingum River | Muskingum River #5 | OH | Washington | In Service | AEP | 600 | 15 | 15 | 15 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t164_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t164_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T165 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 395 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t165_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t165_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T166 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 395 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t166_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t166_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 2/1/2008 | N | No
T167 | Four Rivers 230kV | Four Rivers NUG CC | VA | Hanover | Withdrawn | Dominion | 287.3 | 190 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t167_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t167_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t167_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t167_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
T168 | Four Rivers 500kV |  | VA | Hanover | Withdrawn | Dominion | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t168_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 7/21/2009 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
T169 | Corson |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t169_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/3/2008 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
T17 774202 | PJM-DUK |  | N/A | N/A | Withdrawn | Constellation Power Source | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/774202_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/774202_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T170 | Graceton |  | MD | Harford | Withdrawn | BGE | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T171 | Morgantown 69kV | Newburg High Efficiency Flywheel | MD | Charles | Withdrawn | PEPCO | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/t171_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 7/23/2010 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T172 | Northwest |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009 |  |  | N | No
T174 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 930 | 930 | 900 | 930 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t174_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t174_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t174_csa.pdf | Document Posted | N/A | N/A | 3/22/2018 | 1/31/2008 | N/A | N/A | 9/25/2018 |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
T175 | Tiltonsville 69kV |  | OH | Jefferson | Withdrawn | AEP | 50 | 11 | 11 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t175_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
T176 | Juniata-Branchburg |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T177 | Belmont-Brighton |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T178 | Keystone-Juniata |  | N/A | N/A | Withdrawn | Unknown | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/25/2009 |  |  |  |  | EE | No
T179 | Steel City |  | PA | Northampton | Withdrawn | PPL | 873 | 873 | 873 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t179_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 9/19/2008 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
T18 774383 | PJM-DUK |  | N/A | N/A | Withdrawn | Constellation Power Source | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/774383_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/774383_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T180 | Gainesville 230kV |  | VA | Prince William | Withdrawn | Dominion | 690 | 690 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t180_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t180_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
T182 | TMI 230kV | Three Mile Island 1 | PA | Dauphin | Deactivated | ME | 824 | 14 | 16.8 | 14 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t182_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2008 | N/A | N/A |  |  |  | 4/10/2015 | 4/10/2015 | 10/22/2015 | N | No
T183 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t183_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010 |  |  | N | No
T184 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 200 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t184_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010 |  |  | N | No
T185 | Lewis |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t185_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/19/2008 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
T186 | England |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t186_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 6/19/2008 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
T187 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t187_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 8/24/2009 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
T188 863799 |  |  | N/A | N/A | Withdrawn |  | 545 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
T189 863796 |  |  | N/A | N/A | Withdrawn |  | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
T19 774404 | PJM-DUK |  | N/A | N/A | Withdrawn | Constellation Power Source | 106 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/774404_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/774404_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/28/2007 | 1/1/2009 | 1/1/2014 |  | 10/7/2008 |  |  |  |  | FF | No
T190 863792 | AMIL-PJM |  | N/A | N/A | Withdrawn |  | 1045 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/863792_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/863792_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 |  | 11/4/2008 |  |  |  |  | FF | No
T192 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.8 | 1.8 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2008 | N/A | N/A |  | 4/30/2008 | Customer Initiated Withdrawal | 9/30/2008 |  |  | N | No
T20 | Falls | Exelon Epuron Solar Energy Center | PA | Bucks | In Service | PECO | 3.3 | 3.3 | 1.1 | 3.3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t20_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t20_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t20_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t20_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2007 | N/A | N/A |  |  |  | 12/23/2008 | 12/23/2008 | 4/28/2008 | N | No
T21 805563 | LGEE-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805563_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2008 | 6/1/2010 |  | 12/14/2007 |  |  |  |  | FF | No
T22 805594 | AMIL-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805594_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T23 805597 | AMIL-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805597_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T24 805598 | AMIL-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805598_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T25 805599 | AMIL-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805599_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2012 | 6/1/2014 |  | 12/14/2007 |  |  |  |  | FF | No
T26 805601 | LGEE-PJM |  | N/A | N/A | Withdrawn | Illinois Municipal Electric Agency | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/805601_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/6/2007 | 6/1/2008 | 6/1/2010 |  | 12/14/2007 |  |  |  |  | FF | No
T27 | Hyndman 34kV |  | PA | Somerset | Withdrawn | APS | 60 | 60 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t27_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2007 | N/A | N/A |  | 1/9/2009 | Customer Initiated Withdrawal | 1/1/2010 |  |  | N | No
T28 807067 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/807067_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/10/2007 | 6/1/2008 | 6/1/2009 |  | 10/29/2007 |  |  |  |  | FF | No
T29 807071 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/807071_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/10/2007 | 6/1/2009 | 6/1/2010 |  | 10/29/2007 |  |  |  |  | FF | No
T31 807646 | WEC-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 195 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/807646_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/12/2007 | 6/1/2009 | 6/1/2010 |  | 10/30/2007 |  |  |  |  | FF | No
T32 | Collins |  | SD | McPherson | Withdrawn | ComEd | 2500 | 2500 | 925 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t32_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t32_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 12/6/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T33 | Collins II |  | SD | McPherson | Withdrawn | ComEd | 1000 | 1000 | 370 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t33_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T34 | Collins III |  | SD | McPherson | Withdrawn | ComEd | 1500 | 1500 | 555 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t34_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T35 | Byron Wind IV |  | ND | LaMoure | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t35_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2007 | N/A | N/A |  | 4/22/2010 | Customer Initiated Withdrawal | 9/12/2014 |  |  | N | No
T36 808148 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Agency | 62 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/808148_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/13/2007 | 6/1/2010 | 6/1/2012 |  | 6/4/2008 |  |  |  |  | FF | No
T37 | Hegins |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 30 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t37_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 12/17/2008 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
T38 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 900 | 900 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t38_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 9/8/2008 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T39 | Coudersport 46kV |  | PA | Potter | Withdrawn | APS | 18 | 18 | 3.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t39_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t39_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 12/6/2010 | Customer Initiated Withdrawal | 3/31/2011 | 3/31/2011 |  | N | No
T40 | South Harrington |  | DE | Kent | Withdrawn | DPL | 225 | 225 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t40_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t40_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2007 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
T41 | Kearny 138kV | Kearny #13 | NJ | Hudson | In Service | PSEG | 178 | 178 | 178 | 178 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t41_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t41_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t41_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t41_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t41_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T42 | Kearny 138kV | Kearny #14 | NJ | Hudson | In Service | PSEG | 89 | 89 | 89 | 89 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t42_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t42_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t42_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t42_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t42_csa.pdf | Document Posted | N/A | N/A |  | 9/19/2007 | N/A | N/A |  |  |  | 8/31/2012 | 8/31/2012 | 5/7/2012 | N | No
T43 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 178 | 178 | 178 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t43_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t43_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t43_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012 | 6/1/2012 |  | N | No
T44 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 205 | 205 | 205 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t44_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t44_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 7/28/2009 | Customer Milestone Not Met | 9/19/2014 | 9/19/2014 |  | N | No
T45 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 205 | 205 | 205 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t45_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t45_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2007 | N/A | N/A |  | 4/10/2012 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
T46 810954 | PJM-CIN |  | N/A | N/A | Withdrawn | Duke Energy Ohio, Inc. | 80 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/811015_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/811015_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 9/20/2007 | 6/1/2010 | 6/1/2015 |  | 10/3/2008 |  |  |  |  | FF | No
T47 | Mt. Storm-Doubs 500kV |  | VA | Unknown | Withdrawn | Dominion | 0 | 0 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/t47_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2007 | N/A | N/A |  | 12/17/2007 | Customer Milestone Not Met | 6/1/2009 |  |  | S | No
T48 | Coldwater-Rossburg 69kV |  | OH | Mercer | Withdrawn | Dayton | 40 | 40 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t48_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t48_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 5/9/2012 | Customer Initiated Withdrawal | 11/30/2013 |  |  | N | No
T49 | Steel City | Bethlehem Gen Facility Units 1 - 8 | PA | Northampton | In Service | PPL | 1134 | 42 | 42 | 42 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t49_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t49_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t49_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/6/2009 | 5/6/2009 | 5/6/2009 | N | No
T51 | Hay Road | Hay Road Units 1, 2, 3, 4 | DE | New Castle | In Service | DPL | 565 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t51_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t51_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t51_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/26/2010 | 5/26/2010 | 5/26/2010 | N | No
T52 | Red Lion 500kV | Hay Road Units 5, 6, 7, 8 | DE | New Castle | In Service | DPL | 565 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t52_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t52_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t52_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/1/2008 | 5/1/2008 | 5/1/2008 | N | No
T53 | Delaware City | Delaware City Unit #10 | DE | New Castle | In Service | DPL | 23.3 | 7.3 | 7.3 | 7.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t53_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t53_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t53_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 6/1/2008 |  | 6/1/2008 | N | No
T54 | Cumberland 138kV | Cumberland Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 9.4 | 9.4 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t54_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t54_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t54_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 8/12/2010 | 8/12/2010 | 8/12/2010 | N | No
T55 | Sherman Ave | Sherman Avenue Unit 1 | NJ | Cumberland | In Service | AEC | 93.4 | 12.4 | 12.4 | 12.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t55_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t55_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t55_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 5/3/2010 | N | No
T56 | Christiana | Christiana Units #11 & 14 | DE | New Castle | In Service | DPL | 53.4 | 8.4 | 8.4 | 8.4 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t56_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t56_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t56_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 5/31/2009 | 5/31/2009 | 5/31/2009 | N | No
T57 | Middle |  | NJ | Cape May | Withdrawn | AEC | 109.2 | 22.2 | 22.2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t57_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T59 | Mickleton |  | NJ | Gloucester | In Service | AEC | 73.4 | 14.4 | 14.4 | 7.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t59_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t59_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t59_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 7/7/2011 | 7/7/2011 | 7/7/2011 | N | No
T60 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 798 | 10.5 | 10.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t60_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T61 | Cedar |  | NJ | Ocean | Withdrawn | AEC | 68.3 | 8.3 | 8.3 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t61_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T63 | Carlls Corner |  | NJ | Cumberland | Withdrawn | AEC | 102.2 | 27.2 | 27.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t63_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2007 | N/A | N/A |  | 2/7/2008 | Customer Milestone Not Met | 4/1/2009 |  |  | N | No
T66 | Tasley | Tasley | VA | Accomack | In Service | DPL | 33 | 6.7 | 6.7 | 6.7 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t66_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t66_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t66_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 3/26/2009 | 3/26/2009 | 3/26/2009 | N | No
T67 | West | West #1 | DE | New Castle | In Service | DPL | 20.3 | 5.3 | 5.3 | 5.3 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t67_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t67_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t67_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T68 | Edgemoor | Edgemoor #10 | DE | New Castle | In Service | DPL | 18.2 | 5.2 | 5.2 | 5.2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t68_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t68_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t68_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2007 | N/A | N/A |  |  |  | 4/1/2009 | 4/1/2009 | 4/1/2009 | N | No
T69 811670 | DUK-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 171 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/811670_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T70 811671 | CPLE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 172 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/811671_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 9/24/2007 |  |  |  |  | FF | No
T71 811672 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 218 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/811672_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/21/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T72 812613 | NYISJK-PJM-NYISABC |  | N/A | N/A | Confirmed | Consolidated Edison of NY | 1000 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/24/2007 | 5/1/2012 | 5/1/2017 | [6 empty] | FF | No
T73 | Hanging Rock 765kV | Hanging Rock CC2 | OH | Lawrence | In Service | AEP | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t73_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t73_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t73_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2007 | N/A | N/A |  |  |  | 6/1/2008 | 6/1/2008 | 6/1/2008 | N | No
T74 | Elgin | Elgin Energy Center | IL | Kane | In Service | ComEd | 484 | 16 | 16 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t74_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t74_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t74_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2007 | N/A | N/A |  |  |  | 9/1/2007 |  | 1/8/2013 | N | No
T75 | South River 230kV | South River | NJ | Middlesex | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t75_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t75_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t75_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t75_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 4/16/2009 | 4/16/2009 | 11/15/2012 | N | No
T76 | South River 230 kV | South River | NJ | Middlesex | In Service | JCPL | 307 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t76_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t76_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t76_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t76_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2007 | N/A | N/A |  |  |  | 6/15/2009 |  | 11/15/2012 | N | No
T77 | Linden 230kV | Linden 1 & 2 | NJ | Union | In Service | PSEG | 1570 | 44 | 44 | 44 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/t77_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t77_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/1/2008 | N | No
T78 | Arnolds Corner 34.5kV | King George Renewable Energy Facility | VA | King George | In Service | Dominion | 9.8 | 9.8 | 8.5 | 9.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t78_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t78_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t78_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t78_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 5/4/2010 | 5/4/2010 | 5/4/2010 | N | No
T79 | Shacklefords 34.5kv | Middle Pennisula Gas to Energy Power Plant | VA | Gloucester | In Service | Dominion | 6.2 | 6.2 | 6.2 | 6.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t79_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t79_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t79_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t79_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2007 | N/A | N/A |  |  |  | 10/1/2009 | 10/1/2009 | 10/1/2009 | N | No
T80 818375 | TVA-PJM |  | N/A | N/A | Withdrawn | Duke Energy Ohio, Inc. | 436 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/818375_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/8/2007 | 6/1/2010 | 6/1/2011 |  | 1/4/2008 |  |  |  |  | FF | No
T81 | Cedar 230kV |  | NJ | Ocean | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t81_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
T82 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t82_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t82_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/20/2009 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
T83 | Merion 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t83_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 7/9/2008 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
T84 | Corson 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 350 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t84_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t84_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2007 | N/A | N/A |  | 10/15/2012 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
T85 | Roxbury-Blain 23kV | Cumberland County LF | PA | Cumberland | In Service | PENELEC | 6.4 | 6.4 | 6 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t85_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t85_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t85_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t85_csa.pdf | Document Posted | N/A | N/A | 1/26/2009 | 10/16/2007 | N/A | N/A | 1/27/2009 |  |  | 12/31/2008 | 12/31/2008 | 12/31/2008 | N | No
T86 | Bradford 34.5kV | North Tier LF | PA | Bradford | In Service | PENELEC | 1.6 | 1.6 | 1.5 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t86_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t86_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/t86_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t86_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2007 | N/A | N/A | 1/9/2009 |  |  | 7/1/2008 | 7/1/2008 | 7/1/2008 | N | No
T87 822067 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 103 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/822067_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 10/18/2007 | 1/1/2008 | 1/1/2009 |  | 10/19/2007 |  |  |  |  | FF | No
T88 822068 | PJM-TVA |  | N/A | N/A | Withdrawn |  | 103 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/822068_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 10/18/2007 | 1/1/2008 | 1/1/2009 |  | 10/19/2007 |  |  |  |  | FF | No
T90 823424 | PJM-DUK |  | N/A | N/A | Withdrawn | Coral Power LLC | 885 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/823424_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/22/2007 | 6/1/2010 | 6/1/2012 |  | 2/5/2008 |  |  |  |  | FF | No
T92 | Paddtown I Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2007 | N/A | N/A |  | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010 |  |  | N | No
T93 | Paddtown II Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 1500 | 300 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2007 | N/A | N/A |  | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010 |  |  | N | No
T94 | Cook-Palesades 345kV |  | MI | Van Buren | In Service | ITCI | 1035 | 1035 | 1035 | 1035 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t94_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t94_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/t94_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/t94_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/t94_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2007 | N/A | N/A |  |  |  | 6/30/2016 | 6/30/2016 | 6/1/2016 | N | No
T95 824309 | PJM-MEC |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/824309_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T96 824313 | PJM-MEC |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/824313_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T97 824314 | PJM-MEC |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/824314_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/25/2007 | 6/1/2008 | 6/1/2013 |  | 2/5/2008 |  |  |  |  | FF | No
T98 | South Mahwah 69kV |  | NJ | Bergen | Withdrawn | RECO | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2007 | N/A | N/A |  | 6/2/2009 | Customer Initiated Withdrawal | 10/29/2007 |  |  | N | No
T99 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 100 | 20 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/t99_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/t99_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2007 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
U1-001 864402 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 486 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/864402_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 5/2/2008 |  |  |  |  | FF | No
U1-002 864412 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 162 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 2/6/2008 |  |  |  |  | FF | No
U1-003 864415 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 162 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/4/2008 | 6/1/2011 | 6/1/2012 |  | 2/6/2008 |  |  |  |  | FF | No
U1-004 865838 | FE-PJM |  | N/A | N/A | Retracted | Constellation Energy Commodities Group | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/865838_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-005 865843 | FE-PJM |  | N/A | N/A | Retracted | Constellation Energy Commodities Group | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/865843_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-006 866341 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2012 |  | 2/7/2008 |  |  |  |  | FF | No
U1-007 866343 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2012 |  | 2/7/2008 |  |  |  |  | FF | No
U1-008 866347 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 |  | 2/7/2008 |  |  |  |  | FF | No
U1-009 866348 | TVA-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 |  | 2/7/2008 |  |  |  |  | FF | No
U1-010 | Peach Bottom | Delta | PA | York | In Service | PECO | 575 | 18 | 18 | 18 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/7/2008 | N/A | N/A | 12/21/2010 |  |  | 3/1/2011 | 3/1/2011 | 3/1/2011 | N | No
U1-011 | Minonk II 34.5kV |  | IL | Woodford | Withdrawn | ComEd | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 12/15/2008 | Customer Initiated Withdrawal | 12/1/2009 |  |  | N | No
U1-012 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1012_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 9/3/2009 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-013 | Eddystone |  | PA | Delaware | Withdrawn | PECO | 630 | 630 | 630 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 10/14/2009 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-014 | Cromby |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 8/15/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-015 | Barbados |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-016 | Muddy Run |  | PA | Lancaster | Withdrawn | PECO | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2008 | N/A | N/A |  | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
U1-017 866822 | PJM-CIN |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-018 866823 | PJM-AMIL |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-019 866827 | PJM-CIN |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-020 866830 | PJM-AMIL |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2008 | 6/1/2009 |  | 2/14/2008 |  |  |  |  | FF | No
U1-021 866856 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/866856_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2011 | 6/1/2013 |  | 5/2/2008 |  |  |  |  | FF | No
U1-022 866859 |  |  | N/A | N/A | Withdrawn |  | 468 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 3/18/2008 |  |  |  |  | FF | No
U1-023 867311 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 486 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/867311_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/8/2008 | 6/1/2012 | 6/1/2013 |  | 5/2/2008 |  |  |  |  | FF | No
U1-024 | Dequine-Eugene 345kV |  | IN | Warren | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2008 | N/A | N/A |  | 9/8/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U1-025 869760 | PJM-AMIL |  | N/A | N/A | Withdrawn | AEP | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 6/1/2008 | 6/1/2009 |  | 3/5/2008 |  |  |  |  | FF | No
U1-026 869774 | PJM-CIN |  | N/A | N/A | Withdrawn | AEP | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 6/1/2008 | 6/1/2009 |  | 3/5/2008 |  |  |  |  | FF | No
U1-027 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
U1-028 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
U1-029 | Sherman Ave 138kV |  | NJ | Cumberland | Withdrawn | AEC | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1029_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U1-030 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
U1-031 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u1031_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/19/2008 | N/A | N/A |  | 12/3/2010 | Customer Initiated Withdrawal | 6/30/2012 | 6/30/2012 |  | N | No
U1-032 | Hopewell 230kV |  | VA | City of Hopewell | Deactivated | Dominion | 112.5 | 20 | 0 | 20 | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_032_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/20/2008 | N/A | N/A |  |  |  | 9/28/2009 | 9/28/2009 | 9/28/2009 | N | No
U1-033 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 180 | 4 | 4 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2008 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008 |  |  | N | No
U1-034 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 180 | 4 | 4 |  | Capacity | Generation Interconnection | Coal |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2008 | N/A | N/A |  | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008 |  |  | N | No
U1-034A 874121 | PJM-CIN |  | N/A | N/A | Retracted | American Electric Power | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/874121_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/21/2008 | 6/1/2008 | 6/1/2009 |  | 5/21/2008 |  |  |  |  | FF | No
U1-034B 874123 | PJM-AMIL |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/21/2008 | 6/1/2008 | 6/1/2009 |  | 4/15/2008 |  |  |  |  | FF | No
U1-035 875042 | FE-PJM |  | N/A | N/A | Retracted | PP&amp;L Energy Plus Company | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/875042_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/22/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-036 | Steel Side 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 220 | 220 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1036_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2008 | N/A | N/A |  | 10/29/2009 | Customer Milestone Not Met | 6/1/2011 | 6/1/2011 |  | N | No
U1-037 | LaSalle-Plano 345kV |  | IL | Lasalle | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2008 | N/A | N/A |  | 7/12/2010 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U1-038 | Millheim |  | PA | Centre | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1038_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2008 | N/A | N/A |  | 1/27/2010 |  | 12/1/2010 |  |  | N | No
U1-039 877998 | NYIS-PJM |  | N/A | N/A | Retracted | Brookfield Energy Marketing, Inc. | 774 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/877998_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/28/2008 | 6/1/2011 | 6/1/2016 |  | 5/29/2008 |  |  |  |  | FF | No
U1-040 878534 | NYIS-PJM-FE |  | N/A | N/A | Withdrawn | Coral Power LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/29/2008 | 4/1/2009 | 4/1/2010 |  | 3/21/2008 |  |  |  |  | FF | No
U1-041 882124 | NYIS-PJM |  | N/A | N/A | Withdrawn | Coral Power, LLC | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/7/2008 | 6/1/2011 | 6/1/2012 |  | 3/17/2008 |  |  |  |  | FF | No
U1-042 885633 | PJM-NIPS |  | N/A | N/A | Withdrawn | American Electric Power | 25 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/885633_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/14/2008 | 6/1/2008 | 6/1/2009 |  | 6/12/2008 |  |  |  |  | FF | No
U1-043 885634 | PJM-NIPS |  | N/A | N/A | Withdrawn | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/14/2008 | 6/1/2008 | 6/1/2009 |  | 3/19/2008 |  |  |  |  | FF | No
U1-044 | Frederick County VA Regional Landfill | Fredrick County Regional LF | VA | Frederick | In Service | APS | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u1044_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/18/2008 | N/A | N/A |  |  |  | 11/4/2010 | 11/4/2010 | 1/1/2009 | N | No
U1-045 886741 | NYIS-PJM |  | N/A | N/A | Withdrawn | Coral Power, LLC | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/886741_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/17/2008 | 6/1/2012 | 6/1/2014 |  | 5/7/2008 |  |  |  |  | FF | No
U1-046 886748 | NYIS-PJM |  | N/A | N/A | Withdrawn | Coral Power, LLC | 150 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/886748_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/17/2008 | 6/1/2012 | 6/1/2015 |  | 5/7/2008 |  |  |  |  | FF | No
U1-047 887539 | PJM-NIPS |  | N/A | N/A | Withdrawn | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/19/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
U1-048 | Reichs Ford Landfill | Reichs LF | MD | Frederick | Deactivated | APS | 2 | 2 | 2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u1048_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/24/2008 | N/A | N/A | 4/22/2010 |  |  | 5/3/2010 | 5/3/2010 | 2/1/2009 | N | No
U1-049 | Kankakee #4 138kV |  | IL | Kankakee | Withdrawn | ComEd | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2008 | N/A | N/A |  | 12/6/2013 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U1-050 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1050_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2008 | N/A | N/A |  | 5/12/2009 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U1-051 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2008 | N/A | N/A |  | 1/9/2012 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U1-052 889837 | Duquesne-PJM |  | N/A | N/A | Confirmed | Orion Power Midwest, LP&#x0D; | 1188 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/26/2008 | 9/9/2008 | 9/9/2009 | [6 empty] | FF | No
U1-053 889882 | FE-PJM |  | N/A | N/A | Withdrawn | Orion Power Midwest, LP&#x0D; | 1188 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/26/2008 | 9/9/2008 | 9/9/2013 | [6 empty] | FF | No
U1-054 | Calumet | River Energy Center | IL | Cook | In Service | ComEd | 327 | 27 | 27 | 27 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/26/2008 | N/A | N/A |  |  |  | 3/28/2008 |  | 1/25/2013 | N | No
U1-055 890480 | PJM-NIPS |  | N/A | N/A | Withdrawn | American Electric Power | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/890480_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/27/2008 | 6/1/2008 | 6/1/2009 |  | 6/12/2008 |  |  |  |  | FF | No
U1-056 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 45.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u1056_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2008 | N/A | N/A |  | 7/14/2014 | Customer Initiated Withdrawal | 4/1/2014 |  |  | N | No
U1-057 | North Lebanon |  | PA | Lebanon | Withdrawn | ME | 950 | 950 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1057_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2008 | N/A | N/A |  | 1/28/2010 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U1-058 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 586 | 586 | 586 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2008 | N/A | N/A |  | 1/8/2009 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
U1-059 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 48.3 | 48.3 | 9.6 | 48.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u1059_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u1_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u1_059_csa.pdf | Document Posted | N/A | N/A |  | 4/2/2008 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
U1-060 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 151.8 | 151.8 | 19.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2008 | N/A | N/A |  | 1/23/2013 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
U1-061 893756 | Duquesne-PJM |  | N/A | N/A | Confirmed | Reliant | 141 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/2/2008 | 9/9/2008 | 9/9/2009 | [6 empty] | FF | No
U1-062 893757 | FE-PJM |  | N/A | N/A | Withdrawn | Orion Power Midwest, LP&#x0D; | 141 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/2/2008 | 9/9/2008 | 9/9/2013 | [6 empty] | FF | No
U1-063 894818 | LGEE-PJM |  | N/A | N/A | Withdrawn | Orion Power Midwest, LP&#x0D; | 29 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 6/1/2010 | 6/1/2011 |  | 4/15/2008 |  |  |  |  | FF | No
U1-064 894826 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Agency | 29 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/894826_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/894826_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/3/2008 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
U1-065 | Middle 69kV |  | NJ | Cape May | Withdrawn | AEC | 97 | 20 | 20 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1065_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/7/2008 | N/A | N/A |  | 7/28/2009 | Customer Initiated Withdrawal | 5/1/2009 |  |  | N | No
U1-066 | Carlls Corner 69kV | Carll's Corner Units 1 & 2 | NJ | Cumberland | In Service | AEC | 91 | 18 | 18 | 6 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_066_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2008 | N/A | N/A |  |  |  | 6/24/2011 | 6/24/2011 | 6/24/2011 | N | No
U1-067 | Honey Brook | Granger of Honeybrook | PA | Lancaster | In Service | PPL | 3.2 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u1_067_csa.pdf | Document Posted | N/A | N/A |  | 4/9/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 6/1/2011 | N | No
U1-068 | York 115kV | York | PA | Lancaster | In Service | ME | 51 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_068_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  |  |  | 2/28/2011 | 2/28/2011 | 2/28/2011 | N | No
U1-069 | Emsworth Locks & Dam |  | PA | Allegheny | Withdrawn | DL | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1069_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-070 | Dashields Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1070_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 9/11/2008 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-071 | CW Bill Young Lock & Dam |  | PA | Allegheny | Withdrawn | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1071_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 10/23/2009 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-072 | Braddock Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1072_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 8/6/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-073 | Allegheny Lock & Dam #7 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1073_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-074 | Point Marion Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1074_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-075 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u1075_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/10/2013 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-076 | Allegheny Lock & Dam #2 |  | PA | Allegheny | Withdrawn | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1076_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-077 | Allegheny Lock & Dam #4 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/24/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-078 | Tionesta Dam |  | PA | Forest | Withdrawn | PENELEC | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 11/10/2008 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-079 | Opekiska Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1079_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-080 | Montgomery Lock & Dam |  | PA | Beaver | Withdrawn | DL | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-081 | Monongahela Lock & Dam #4 |  | PA | Westmoreland | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1081_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-082 | Maxwell Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1082_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
U1-083 | Hildebrand Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2008 | N/A | N/A |  | 7/24/2009 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
U1-086 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/17/2008 | N/A | N/A |  | 12/19/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
U1-087 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2008 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
U1-088 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2008 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
U1-089 | Paper Tap 69kV | Kimberly Clark | PA | Delaware | Deactivated | PECO | 20 | 0 | 20 | 0 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1089_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/18/2008 | N/A | N/A |  |  |  | 10/15/2008 |  | 10/15/2008 | N | No
U1-090 | Killen 345kV | Killen Electric Generating Station | OH | Adams | Deactivated | Dayton | 612 | 12 | 12 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1090_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_090_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/22/2008 | N/A | N/A |  |  |  | 5/31/2008 |  |  | N | No
U1-091 902731 | FE-PJM |  | N/A | N/A | Withdrawn | Reliant | 1329 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/22/2008 | 6/1/2011 | 6/1/2012 |  | 5/8/2008 |  |  |  |  | FF | No
U1-093 | Ladysmith 230kV | Ladysmith Unit 3 | VA | Carolina | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1093_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u1_093_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-094 | Ladysmith 230kV | Ladysmith Unit 4 | VA | Carolina | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1094_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u1_094_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 4/8/2008 | 4/8/2008 | 10/1/2009 | N | No
U1-095 | Ladysmith 230kV | Ladysmith Unit 5 | VA | Carolina | In Service | Dominion | 190 | 20 | 0 | 20 | Energy | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u1_095_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2008 | N/A | N/A |  |  |  | 3/31/2009 | 3/31/2009 | 3/31/2009 | N | No
U1-096 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2008 | N/A | N/A |  | 8/26/2008 | Customer Milestone Not Met | 1/1/2009 |  |  | N | No
U1-097 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u1097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2008 | N/A | N/A |  | 12/9/2008 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
U1-098 906034 | Duquesne-PJM |  | N/A | N/A | Confirmed | First Energy Solutions | 1788 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/30/2008 | 6/1/2011 | 6/1/2012 | [6 empty] | FF | No
U1-099 | Joliet 4 MW |  | IL | Will | Withdrawn | ComEd | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2008 | N/A | N/A |  | 4/21/2010 | Customer Initiated Withdrawal | 3/31/2011 | 3/31/2011 |  | N | No
U2-002 908694 | PJM-FE |  | N/A | N/A | Retracted | Cargill Power Markets, LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/908694_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/6/2008 | 1/1/2009 | 1/1/2010 |  | 7/31/2008 |  |  |  |  | FF | No
U2-003 | Wempletown |  | IL | Stephenson | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2008 | N/A | N/A |  | 4/29/2009 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
U2-004 911979 | MEC-PJM |  | N/A | N/A | Retracted | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/911979_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/13/2008 | 4/1/2009 | 4/1/2010 |  | 7/31/2008 |  |  |  |  | FF | No
U2-005 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
U2-006 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | 1010 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
U2-007 912864 | PJM-AMIL |  | N/A | N/A | Withdrawn | GE Energy Financial Services | 700 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-008 912865 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 500 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-009 912866 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-010 912867 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2011 |  | 5/20/2008 |  |  |  |  | FF | No
U2-011 912869 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 700 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/15/2008 | 6/1/2011 | 6/1/2016 |  | 6/12/2008 |  |  |  |  | FF | No
U2-012 913162 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/16/2008 | 6/1/2011 | 6/1/2016 |  | 6/12/2008 |  |  |  |  | FF | No
U2-013 | Northeast 34.5kV | Richmond Energy Facility | VA | Henrico | In Service | Dominion | 8 | 8 | 8 | 6.5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_013_csa.pdf | Document Posted | N/A | N/A | 9/15/2011 | 5/16/2008 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 12/29/2011 | N | No
U2-014 915083 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 1600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/20/2008 | 6/1/2011 | 6/1/2012 |  | 6/12/2008 |  |  |  |  | FF | No
U2-015 | Harwood-E. Palmerton 230kV | Buck Mountain Wind Farm | PA | Columbia | Withdrawn | PPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2015_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_015_csa.pdf | Document Posted | N/A | N/A |  | 5/22/2008 | N/A | N/A |  | 11/15/2019 |  | 10/1/2019 | 10/1/2019 |  | N | No
U2-016 | East Towanda-Grover 230kV |  | PA | Bradford | Withdrawn | PENELEC | 85 | 85 | 11.05 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 1/13/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
U2-017 | Tazewell-Baileysville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 10/30/2008 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-024 | Tazewell-Baileyville 138kV |  | WV | McDowell | Withdrawn | AEP | 900 | 900 | 825 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2008 | N/A | N/A |  | 1/6/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
U2-025 | Brooke County Landfill |  | WV | Brooke | Withdrawn | APS | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2025_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 2/23/2009 | Customer Milestone Not Met | 7/31/2009 |  |  | N | No
U2-026 | Antwerp 69kV |  | OH | Paulding | Withdrawn | AEP | 30 | 30 | 3.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 12/9/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-027 | Mehoopany 115kV |  | PA | Bradford | Withdrawn | PENELEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 12/8/2008 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-028 | Meadow Brook Capacitor |  | VA | Frederick | In Service | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IARR 64.5 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/u2028_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/u2_028_csa.pdf | Document Posted | N/A | N/A |  | 5/30/2008 | N/A | N/A |  |  |  | 10/26/2009 | 10/26/2009 | 6/1/2009 | S | No
U2-028A_AT1 | Ironville | FDS Coke Plant | OH | Lucas | Withdrawn | ATSI | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2028a_at1_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2028a_at1_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2028a_at1_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_028a_at1_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_028A_at1_csa.pdf | Document Posted | N/A | N/A |  | 5/29/2008 | N/A | N/A |  | 2/5/2015 | Customer Milestone Not Met | 7/1/2017 | 7/1/2017 |  | N | No
U2-029 | Passyunk |  | PA | Philadelphia | Withdrawn | PECO | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2029_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/5/2008 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
U2-030 | Four Mile Ridge Wind 138kV | Four Mile Ridge WF - 24 WT | MD | Garrett | In Service | APS | 60 | 60 | 7.8 | 40 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2030_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_030_csa.pdf | Document Posted | N/A | N/A | 11/20/2014 | 6/5/2008 | N/A | N/A | 11/20/2014 |  |  | 12/23/2017 | 12/23/2017 | 11/21/2014 | N | No
U2-031 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 30 | 30 | 24.75 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_031_csa.pdf | Document Posted | N/A | N/A |  | 6/9/2008 | N/A | N/A |  | 8/24/2010 | Customer Milestone Not Met | 6/1/2011 | 6/1/2011 |  | N | No
U2-032 | Elbow Mountain |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2008 | N/A | N/A |  | 12/4/2008 | Customer Milestone Not Met | 10/1/2010 |  |  | N | No
U2-033 925392 | PJM-DUK |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/925392_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/925392_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-034 925394 | PJM-DUK |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/925394_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/925394_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-035 925395 | PJM-TVA |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 104 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/925395_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/925395_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 6/9/2008 | 1/1/2009 | 1/1/2010 |  | 4/28/2009 |  |  |  |  | FF | No
U2-036 925941 | PJM-NIPS |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/925941_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/10/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-037 925947 | PJM_NIPS |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/925947_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/10/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-038 926231 | PJM-CWLP |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/926231_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/11/2008 | 1/1/2009 | 1/1/2010 |  | 8/25/2008 |  |  |  |  | FF | No
U2-039 926237 | PJM-IPL |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/926237_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/11/2008 | 1/1/2009 | 1/1/2010 |  | 9/3/2008 |  |  |  |  | FF | No
U2-040 | Bridgewater-Middlesex 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/12/2008 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U2-040A 926830 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 900 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/926830_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/926830_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 6/12/2008 | 6/1/2011 | 6/1/2016 |  | 4/7/2009 |  |  |  |  | FF | No
U2-040B 926832 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 1600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/926832_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/12/2008 | 6/1/2011 | 6/1/2012 |  | 8/25/2008 |  |  |  |  | FF | No
U2-041 | East Lima-Marysville 345kV | Hardin Wind Farm | OH | Hardin | Withdrawn | AEP | 166.4 | 166.4 | 21.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2041_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_041_csa.pdf | Document Posted | N/A | N/A |  | 6/13/2008 | N/A | N/A |  | 12/5/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
U2-042 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 201 | 201 | 26.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/13/2008 | N/A | N/A |  | 7/27/2010 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
U2-044 | Lewis 138kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/20/2008 | N/A | N/A |  | 11/21/2008 |  | 3/1/2011 |  |  | N | No
U2-045 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_045_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2008 | N/A | N/A |  | 3/12/2019 |  | 1/27/2019 | 1/27/2019 |  | N | No
U2-046 | Roseland 500kV |  | NJ | Essex | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 670 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2046_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-047 | Deans 500kV |  | NJ | Unknown | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 660/TWR 672 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2008 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 12/1/2013 |  |  | S | No
U2-048 | Cox's Corner-Croydon 230kV |  | NJ | Burlington | Withdrawn | PSEG | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 5/15/2012 |  |  | N | No
U2-049 | Monmouth |  | NJ | Monmouth | Withdrawn | JCPL | 640 | 640 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 2/9/2011 | Customer Initiated Withdrawal | 5/15/2012 |  |  | N | No
U2-050 | Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2050_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-051 | Glen Lyn-Wythe 138kV |  | VA | Giles | Withdrawn | AEP | 60 | 60 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2051_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2051_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-052 | S. Bluefield-Wythe 69kV |  | VA | Bland | Withdrawn | AEP | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 3/18/2009 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U2-053 | Martins Creek |  | PA | Northampton | Withdrawn | PPL | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2008 | N/A | N/A |  | 6/2/2009 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
U2-054 | Weissport | Beltzville Hydro Dam | PA | Carbon | Withdrawn | PPL | 2.6 | 2.6 | 2.6 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u2054_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/25/2008 | N/A | N/A |  | 2/26/2014 |  | 6/1/2014 | 6/1/2014 |  | N | No
U2-055 | Karthaus-Milesburg 230kV |  | PA | Centre | Withdrawn | APS | 89.1 | 89.1 | 11.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2055_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2055_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/27/2008 | N/A | N/A |  | 8/7/2013 | Customer Milestone Not Met | 7/1/2012 |  |  | N | No
U2-056 | West Point |  | VA | Unknown | Withdrawn | Dominion | 88.7 | 88.7 | 88.7 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2056_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 10/12/2010 | Customer Milestone Not Met | 12/1/2010 | 12/1/2010 |  | N | No
U2-057 | Hopewell 34.5kV |  | VA | City of Hopewell | Withdrawn | Dominion | 47.6 | 47.6 | 47.6 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2057_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 10/12/2010 | Customer Milestone Not Met | 12/1/2010 | 12/1/2010 |  | N | No
U2-058 | Kincaid Wind |  | IL | Christian | Withdrawn | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2008 | N/A | N/A |  | 7/20/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
U2-059 | Foul Rift 13kV | Belvidere SP | NJ | Warren | In Service | JCPL | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/7/2008 | N/A | N/A |  |  |  | 6/1/2011 | 6/1/2011 | 12/12/2011 | N | No
U2-060 | Camden | Pennsauk LF | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2060_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/7/2008 | N/A | N/A |  | 4/15/2009 | Customer Initiated Withdrawal | 12/15/2004 |  |  | N | No
U2-061 | Garrett County | Roth Rock WF | MD | Garrett | In Service | APS | 50 | 50 | 6.5 | 50 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_061_csa.pdf | Document Posted | N/A | N/A | 11/23/2010 | 7/7/2008 | N/A | N/A | 12/5/2010 |  |  | 1/5/2011 | 1/5/2011 | 12/1/2009 | N | No
U2-062 | Randolph 138kV |  | OH | Darke | Withdrawn | AEP | 187.5 | 187.5 | 24.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2062_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2062_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/9/2008 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
U2-063 | Croydon 230kV | Croydon Generating Station | PA | Bucks | In Service | PECO | 391 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/10/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 1/2/2014 | N | No
U2-064 | Branchburg-Ramapo 500kV |  | NJ | Sussex | Withdrawn | PSEG | 1000 | 1000 | 1000 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2008 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
U2-065 | Kankakee 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2008 | N/A | N/A |  | 7/28/2010 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
U2-066 | Marysville-SW Lima 345kV |  | OH | Hardin | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2008 | N/A | N/A |  | 12/19/2011 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
U2-067 | Eldred-Pine Grove 69kV | Westwood Generation | PA | Bucks | In Service | PPL | 32.5 | 2.5 | 2.5 | 2.5 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/15/2008 | N/A | N/A |  |  |  | 7/1/2008 |  | 12/29/2008 | N | No
U2-068 | Mount Storm-Valley 500kV | Lost River WF | VA | Rockingham | Withdrawn | Dominion | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_068_csa.pdf | Document Posted | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 1/10/2014 |  | 6/1/2018 | 6/1/2018 |  | N | No
U2-069 | Frackville | Broad Mountain WF | PA | Schuylkill | Withdrawn | PPL | 56 | 56 | 7.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2069_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_069_csa.pdf | Document Posted | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
U2-070 | Somerset |  | PA | Somerset | Withdrawn | PENELEC | 7.5 | 7.5 | 0.98 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2070_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/21/2008 | N/A | N/A |  | 7/2/2009 | Customer Milestone Not Met | 12/1/2010 |  |  | N | No
U2-071 | Tazewell-Saltville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2071_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2008 | N/A | N/A |  | 2/27/2009 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-072 | East Lima-Marysville 345kV | Scioto Ridge Wind Farm | OH | Hardin | Under Construction | AEP | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2072_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_072_csa.pdf | Document Posted | N/A | N/A | 4/1/2020 | 7/23/2008 | N/A | N/A | 7/1/2020 |  |  | 10/31/2020 | 10/31/2020 |  | N | No
U2-073 | Frostburg 138kV II | Twin Ridges Wind Farm | PA | Somerset | Partially in Service - Under Construction | APS | 200 | 200 | 26 | 139 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2073_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_073_csa.pdf | Document Posted | N/A | N/A |  | 7/23/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/21/2012 | N | No
U2-074 | Peach Bottom-Rock Springs 500kV |  | PA | Lancaster | Withdrawn | PECO | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2008 | N/A | N/A |  | 8/3/2012 | Customer Initiated Withdrawal | 10/1/2012 |  |  | N | No
U2-075 | Susquehanna-Roseland 500kV |  | PA | Lackawanna | Withdrawn | PPL | 636 | 636 | 636 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2008 | N/A | N/A |  | 4/13/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U2-076 | Falls | Grows North LF | PA | Bucks | Withdrawn | PECO | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_076_csa.pdf | Document Posted | N/A | N/A |  | 7/25/2008 | N/A | N/A |  | 1/7/2014 | Customer Milestone Not Met | 3/1/2011 | 3/1/2011 |  | N | No
U2-077 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 300 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 300; NF/TWR 330 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/u2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/25/2008 | N/A | N/A |  |  |  | 10/1/2009 |  | 6/1/2011 | S | No
U2-080 | South Portsmouth 138kV |  | KY | Greenup | Withdrawn | AEP | 134 | 134 | 134 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2080_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u2080_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 7/13/2012 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
U2-081 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-082 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2082_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-083 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-084 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U2-085 | Sakron-Prince #3 138kV |  | PA | Lancaster | Withdrawn | PPL | 11.4 | 11.4 | 11.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 4/15/2009 | Customer Milestone Not Met | 12/1/2009 |  |  | N | No
U2-086 | Airydale 500kV |  | PA | Huntingdon | Withdrawn | PENELEC | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/17/2010 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-087 | Juniata 500 MVAR SVC |  | PA | Dauphin | Withdrawn | PPL | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/u2087_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 7/6/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-088 | Meadow Brook 500kV |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u2088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 1/5/2012 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-089 | Kemptown 500kV |  | PA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2008 | N/A | N/A |  | 9/16/2008 | Customer Initiated Withdrawal | 1/1/2011 |  |  | S | No
U2-090 | Desoto-Tanners Creek 345kV | HeadwatersWF | IN | Randolph | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2090_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u2_090_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2008 | N/A | N/A |  |  |  | 10/31/2014 | 10/31/2014 | 10/27/2014 | N | No
U2-091 | Delaware-Richmond 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2091_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U2-092 | Delaware-Centerville 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2092_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U2-093 954414 | PJM-LGEE |  | N/A | N/A | Withdrawn | Louisville Gas &amp; Electric | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/954414_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/30/2008 | 1/1/2010 | 8/1/2015 |  | 3/12/2009 |  |  |  |  | FF | No
U2-094 | Foul Rift 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 19 | 19 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u2094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 9/2/2009 | Customer Initiated Withdrawal | 12/31/2010 | 12/31/2010 |  | N | No
U2-095 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U2-096 | Lock Haven-Lycoming #1 69kV |  | PA | Lycoming | Withdrawn | PPL | 1.5 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 11/10/2008 | Customer Initiated Withdrawal | 3/31/2009 |  |  | N | No
U2-098 | South Amboy |  | NJ | Middlesex | Withdrawn | JCPL | 1320 | 1320 | 1320 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 8/27/2009 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
U2-099 | Martins Creek 230kV |  | PA | Northampton | Withdrawn | PPL | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2099_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 11/30/2009 | Customer Initiated Withdrawal | 5/1/2014 | 5/1/2014 |  | N | No
U2-100 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 800 |  |  |  | Energy | Merchant Transmission |  | AC | NF/TWR 800 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u2100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 4/26/2011 | Customer Initiated Withdrawal | 12/1/2011 |  |  | S | No
U2-101 | Nelson Bio |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2008 | N/A | N/A |  | 9/5/2012 | Customer Initiated Withdrawal | 12/31/2011 | 12/31/2011 |  | N | No
U2-102 955153 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/955153_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/955153_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
U2-103 955155 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/955155_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/955155_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
U2-104 955156 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/955156_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/955156_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/31/2008 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
U3-001 | Barbadoes 34kV | AES Energy Storage Unit | PA | Montgomery | Withdrawn | PECO | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/11/2008 | N/A | N/A |  | 9/26/2018 |  | 8/31/2008 |  | 8/31/2008 | N | No
U3-002 | Deer Creek-Fisher Body-Mullin 138kV | Wildcat Wind Farm I | IN | Madison | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u3_002_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u3_002_csa.pdf | Document Posted | N/A | N/A | 6/1/2012 | 8/13/2008 | N/A | N/A | 10/8/2012 |  |  | 12/31/2012 | 12/31/2012 | 12/26/2012 | N | No
U3-003 | Mt. Olive 69kV | Worcester County Renewable Energy | MD | Worcester | Deactivated | DPL | 2 | 2 | 0 | 0.5 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u3_003_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/14/2008 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 3/1/2012 | N | No
U3-004 | Cecil | Cecil County Landfill | MD | Cecil | Withdrawn | DPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3004_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u3004_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2008 | N/A | N/A |  | 10/4/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
U3-005 | Meadow Brook |  | VA | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u3005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u3005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2008 | N/A | N/A |  | 2/1/2012 | Customer Initiated Withdrawal | 12/31/2008 |  |  | S | No
U3-006 967853 | PJM-CPLW |  | N/A | N/A | Withdrawn | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/967853_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/18/2008 | 6/1/2010 | 6/1/2015 |  | 10/23/2008 |  |  |  |  | FF | No
U3-007 967858 | PJM-DUK |  | N/A | N/A | Withdrawn | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/967858_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/18/2008 | 6/1/2010 | 6/1/2015 |  | 10/23/2008 |  |  |  |  | FF | No
U3-008 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2008 | N/A | N/A |  | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
U3-009 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 595 | 595 | 595 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2008 | N/A | N/A |  | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2014 |  |  | N | No
U3-010 | Towanda |  | PA | Bradford | Withdrawn | PENELEC | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-011 975675 | CPLE-PJM |  | N/A | N/A | Retracted | North Carolina Electric Membership | 60 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/975675_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/975675_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/26/2008 | 6/1/2012 | 6/1/2013 |  | 7/8/2009 |  |  |  |  | FF | No
U3-012 | Bradford 115kV |  | PA | McKean | Withdrawn | PENELEC | 85 | 85 | 11 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-013 | Clermont 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 125 | 16.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2008 | N/A | N/A |  | 3/9/2009 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
U3-016 | Midlothian 230kV |  | VA | Goochland | Withdrawn | Dominion | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2008 | N/A | N/A |  | 2/23/2009 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
U3-017 | Westvaco 138kV |  | PA | Allegheny | Withdrawn | APS | 12 | 4 | 0 |  | Energy | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3017_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2008 | N/A | N/A |  | 10/22/2010 | Customer Initiated Withdrawal | 8/22/2008 |  |  | N | No
U3-018 | Knieriem |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2008 | N/A | N/A |  | 3/3/2009 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
U3-019 989861 | NYIS-PJM |  | N/A | N/A | Withdrawn | Shell Energy North America (US), LP | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/989861_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/18/2008 | 6/1/2012 | 6/1/2017 |  | 10/28/2008 |  |  |  |  | FF | No
U3-020 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
U3-021 | Silver Lake-Cherry Valley |  | IL | Boone | Active | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2008 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 |  | N | No
U3-022 | Sherman-Cumberland 138kV |  | NJ | Cumberland | Withdrawn | AEC | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2008 | N/A | N/A |  | 2/20/2009 | Customer Initiated Withdrawal | 9/15/2009 |  |  | N | No
U3-023 | Printz 230kV |  | PA | Delaware | Withdrawn | PECO | 720 | 720 | 720 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2008 | N/A | N/A |  | 2/23/2009 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U3-025 | Elk Garden-Parr Run 138kV |  | WV | Mineral | Withdrawn | APS | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2008 | N/A | N/A |  | 2/28/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
U3-026 | Collins |  | IL | Grundy | Withdrawn | ComEd | 0 |  |  |  | Energy | Merchant Transmission | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/u3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2008 | N/A | N/A |  | 4/10/2017 |  | 12/31/2020 | 12/31/2020 |  | S | No
U3-027 1010165 | PJM-NYIS |  | N/A | N/A | Withdrawn | Cavallo Power LP | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1010165_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/19/2008 | 1/1/2012 | 1/1/2022 |  | 12/2/2008 |  |  |  |  | FF | No
U3-029 | Beaver Valley #1 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 950 | 48 | 37 | 48 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u3_029_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 11/15/2013 | N | No
U3-030 | Beaver Valley #2 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 951 | 43 | 38 | 43 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u3_030_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2008 | N/A | N/A |  |  |  | 11/1/2012 | 11/1/2012 | 11/7/2012 | N | No
U3-031 | Lincoln Generating Facility | Lincoln Generating Facility | IL | Will | In Service | ComEd | 616 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3031_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u3_031_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2008 | N/A | N/A |  |  |  | 10/31/2009 |  | 1/24/2013 | N | No
U3-032 | Traynor 34.5kV | Britton Road Solar Facility | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u3032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u3032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u3032_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2008 | N/A | N/A |  | 8/20/2018 |  | 6/1/2012 | 6/1/2012 |  | N | No
U3-033 1030332 | PJM-CIN |  | N/A | N/A | Withdrawn | Cargill Power Markets LLC | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1030332_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/3/2008 | 1/1/2010 | 1/1/2011 |  | 12/19/2008 |  |  |  |  | FF | No
U3-034 1033525 | TVA-PJM |  | N/A | N/A | Withdrawn | Magnolia Energy, LP | 905 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1033525_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1033525_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/31/2008 | 6/1/2012 | 6/1/2017 |  | 3/9/2010 |  |  |  |  | FF | No
U4-001 | Howard 138kV | Black Fork Wind | OH | Richland | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_001_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2008 | N/A | N/A |  | 1/23/2019 |  | 11/3/2019 | 11/3/2019 |  | N | No
U4-002 | Pickens-Monterville 138kV |  | WV | Randolph | Withdrawn | APS | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4002_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2008 | N/A | N/A |  | 12/17/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
U4-003 | Olive-Dequine 345kV |  | IN | Jasper | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4003_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2008 | N/A | N/A |  | 1/3/2013 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
U4-004 | York 115kV |  | PA | York | Withdrawn | ME | 162 | 120 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 10/16/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U4-005 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 700 | 700 | 640 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 11/25/2009 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
U4-006 | Mendota 138kV |  | IL | Lasalle | Withdrawn | ComEd | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2008 | N/A | N/A |  | 9/5/2012 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
U4-007 | Jennings Randolph Dam |  | MD | Garrett | Withdrawn | APS | 14 | 14 | 13.4 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/11/2008 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 7/2/2013 | 7/2/2013 |  | N | No
U4-008 | South Central Power | Suburban LF | OH | Perry | In Service | AEP | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4008_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4008_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2008 | N/A | N/A |  |  |  | 1/7/2011 | 1/7/2011 | 1/7/2011 | N | No
U4-009 | Louisa 230kV | Louisa Gas Turbines Units 1 through 5 | VA | Orange | In Service | Dominion | 144 | 3 | 3 | 3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4009_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_009_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/17/2008 | N/A | N/A |  |  |  | 5/26/2009 | 5/26/2009 | 5/26/2009 | N | No
U4-009A 1041029 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Agency | 29 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1041029_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1041029_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 11/19/2008 | 6/1/2010 | 6/1/2012 | [6 empty] | FF | No
U4-010 | Pontiac-Latham 345kV |  | IL | Ford | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
U4-011 | Pontiac Midpoint I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4011_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-012 | Pontiac Midpoint II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4012_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2008 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-013 | North Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 950 | 950 | 900 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/21/2008 | N/A | N/A |  | 6/8/2009 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
U4-014 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | In Service | PPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4014_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4014_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_014_csa.pdf | Document Posted | N/A | N/A |  | 11/24/2008 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/6/2012 | N | No
U4-015 | Rock Springs 500kV | Rocks Springs 1 & 2 | MD | Cecil | In Service | ODEC | 475 | 8.7 | 8.7 | 8.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2008 | N/A | N/A |  |  |  | 5/7/2009 | 5/7/2009 | 5/31/2009 | N | No
U4-016 | Harwood |  | PA | Luzerne | Withdrawn | PPL | 213 | 48 | 48 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2008 | N/A | N/A |  | 6/1/2009 | Customer Milestone Not Met | 6/1/2010 |  |  | N | No
U4-017 | Corder Crossing 138kV |  | WV | Barbour | Withdrawn | APS | 165 | 165 | 21.45 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2008 | N/A | N/A |  | 6/16/2009 | Customer Milestone Not Met | 12/1/2012 |  |  | N | No
U4-018 | Bedington-Harmony Jct 138kV |  | WV | Unknown | Withdrawn | APS | 0 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/u4018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2008 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/1/2009 |  |  | S | No
U4-019 1049345 | PJM-TVA |  | N/A | N/A | Withdrawn | Invenergy, LLC | 60 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2009 | 6/1/2014 |  | 12/11/2008 |  |  |  |  | FF | No
U4-020 1049348 | PJM-TVA |  | N/A | N/A | Retracted | Invenergy LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1049348_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1049348_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-021 1049350 | PJM-TVA |  | N/A | N/A | Retracted | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1049350_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 |  | 2/18/2009 |  |  |  |  | FF | No
U4-022 1049352 | PJM-TVA |  | N/A | N/A | Confirmed | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1049352_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1049352_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-023 1049355 | PJM-TVA |  | N/A | N/A | Confirmed | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1049355_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1049355_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/3/2008 | 6/1/2010 | 6/1/2015 | [6 empty] | FF | No
U4-024 1052862 | PJM-TVA |  | N/A | N/A | Retracted | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1052862_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/9/2008 | 6/1/2009 | 6/1/2010 |  | 2/18/2009 |  |  |  |  | FF | No
U4-025 1058858 | PJM-CWLP |  | N/A | N/A | Retracted | Cargill Power Markets LLC | 400 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1058858_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/18/2008 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
U4-026 | Lowmoor-Lexington 230kV | Rocky Ford WF | VA | Botetourt | Withdrawn | Dominion | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4026_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4026_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_026_csa.pdf | Document Posted | N/A | N/A |  | 12/19/2008 | N/A | N/A |  | 8/23/2013 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
U4-027 | Normandy-Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4027_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/22/2008 | N/A | N/A |  | 5/29/2019 |  | 12/31/2018 | 12/31/2018 |  | N | No
U4-028 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Suspended | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_028_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
U4-029 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Suspended | AEP | 200 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_029_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
U4-030 | Sabrooke 138kV | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 153 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_030_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 6/23/2010 | 6/23/2010 | 6/23/2010 | N | No
U4-031 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2008 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
U4-032 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 1063 | 400 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2008 | N/A | N/A |  | 5/28/2009 | Customer Milestone Not Met | 4/1/2013 |  |  | N | No
U4-033 | University Park North |  | IL | Will | In Service | ComEd | 540 | 36 | 36 | 36 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4033_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_033_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/31/2008 | N/A | N/A |  |  |  | 6/1/2009 |  | 1/21/2014 | N | No
U4-034 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 400 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/2009 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 1/1/2010 | N | No
U4-035 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 400 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_035_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/20/2009 | N/A | N/A |  |  |  | 2/1/2008 | 2/1/2008 | 1/1/2010 | N | No
U4-036 | Gloucester 26.4kV | Paradise SP | NJ | Gloucester | In Service | PSEG | 5.1 | 5.1 | 1.9 | 5.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/u4_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_036_csa.pdf | Document Posted | N/A | N/A | 12/22/2010 | 1/28/2009 | N/A | N/A | 12/22/2010 |  |  | 1/4/2011 | 1/4/2011 | 12/31/2009 | N | No
U4-037 | Brokaw-Lanesville 345kV |  | IL | DeWitt | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2009 | N/A | N/A |  | 12/12/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
U4-038 | Mullin-Greentown Tap 138kV |  | IN | Madison | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4038_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 5/7/2013 | Customer Initiated Withdrawal | 9/1/2013 |  |  | N | No
U4-039 | Greentown 138kV |  | IN | Madison | Withdrawn | AEP | 710 | 710 | 92.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 7/20/2015 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
U4-040 | Lincoln 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4040_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4040_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-041 | Valley 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4041_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-042 | Hanover 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-043 | Tolna 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4043_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-044 | Stoverstown 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4044_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-045 | Oil Creek 34.kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4045_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-046 | Teepleville 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4046_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-047 | Mill Village 34.5kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4047_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4047_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-048 | Saegertown 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/u4048_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/30/2009 | N/A | N/A |  | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011 | 6/1/2011 |  | N | No
U4-049 1092401 | PJM-LGEE |  | N/A | N/A | Withdrawn | Louisville Gas &amp; Electric Company | 99 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1092401_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1092401_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 1/30/2009 | 1/1/2010 | 1/1/2015 |  | 10/14/2009 |  |  |  |  | FF | No
V1-001 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
V1-002 1094626 | TVA-PJM |  | N/A | N/A | Annulled | Magnolia Energy, LP | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1094626_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1094626_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/2/2009 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
V1-003 1096809 | CIN-PJM |  | N/A | N/A | Withdrawn | Cinergy Services, CGE | 480 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/4/2009 | 6/1/2012 | 6/1/2017 |  | 2/11/2009 |  |  |  |  | FF | No
V1-004 1102137 | NYIS-PJM |  | N/A | N/A | Retracted | Brookfield Energy Marketing, Inc. | 705 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1102137_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/12/2009 | 6/1/2012 | 6/1/2017 |  | 4/21/2009 |  |  |  |  | FF | No
V1-005 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v1005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v1005_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 3/16/2010 | Customer Initiated Withdrawal | 1/1/2010 |  |  | S | No
V1-006 | Elrama-Mitchell 138kV |  | PA | Unknown | Withdrawn | DL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2009 | N/A | N/A |  | 4/30/2009 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
V1-007 1104452 | PJM-IPL |  | N/A | N/A | Retracted | Cargill Power Markets LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1104452_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/16/2009 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
V1-008 1104456 | PJM-AMIL |  | N/A | N/A | Retracted | Cargill Power Markets LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1104456_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/16/2009 | 1/1/2010 | 1/1/2011 |  | 4/21/2009 |  |  |  |  | FF | No
V1-009 | Gilbert 46kV |  | WV | Unknown | Withdrawn | AEP | 12 | 12 | 11 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2009 | N/A | N/A |  | 8/18/2009 | Customer Milestone Not Met | 4/1/2012 |  |  | N | No
V1-010 | Howard-Fostoria Central 138kV |  | OH | Crawford | Withdrawn | AEP | 260 | 260 | 33.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2009 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
V1-011 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | In Service | AEP | 100 | 100 | 13 | 100 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1011_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1011_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v1_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v1_011_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2009 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 9/10/2018 | N | No
V1-012 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1012_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1012_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v1_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v1_012_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2009 | N/A | N/A |  | 5/8/2018 |  | 12/31/2015 | 12/31/2015 |  | N | No
V1-013 | Springdale 138kV |  | PA | Allegheny | Withdrawn | APS | 580 | 580 | 580 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2009 | N/A | N/A |  | 9/11/2009 | Customer Initiated Withdrawal | 1/1/2012 |  |  | N | No
V1-014 1120188 | AMIL-PJM |  | N/A | N/A | Confirmed | Northern Illinois Municipal Power Agency | 130 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1120188_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1120188_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/10/2009 | 9/1/2011 | 9/1/2041 | [6 empty] | FF | No
V1-015 | New Liberty 138kV |  | OH | Hancock | Withdrawn | AEP | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2009 | N/A | N/A |  | 9/3/2009 | Customer Milestone Not Met | 2/1/2010 |  |  | N | No
V1-016 1125859 | PJM-IPL |  | N/A | N/A | Confirmed |  | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1125859_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1125859_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/19/2009 | 4/1/2010 | 4/1/2015 | [6 empty] | FF | No
V1-017 1125369 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1125369_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/19/2009 | 6/1/2012 | 6/1/2013 |  | 6/8/2009 |  |  |  |  | FF | No
V1-018 1125370 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1125370_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/19/2009 | 6/1/2012 | 6/1/2013 |  | 6/8/2009 |  |  |  |  | FF | No
V1-019 1126560 | MEC-PJM |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1126560_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1126560_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/20/2009 | 1/1/2010 | 1/1/2015 |  | 1/18/2010 |  |  |  |  | FF | No
V1-020 1126569 | MEC-PJM |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1126569_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1126569_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/20/2009 | 1/1/2010 | 1/1/2015 |  | 1/18/2010 |  |  |  |  | FF | No
V1-021 | Cape May County 12kV | Cape May County Municipal Utiltities Authority (CM | NJ | Cape May | In Service | AEC | 1.9 | 1.9 | 1.7 | 1.9 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/23/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 10/22/2013 | N | No
V1-022 | Plano 345kV |  | IL | Kendall | Withdrawn | ComEd | 380 | 380 | 380 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2009 | N/A | N/A |  | 12/17/2013 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
V1-023 | Bridge 12kV | Charlston LF | WV | Kanawha | In Service | AEP | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v1023_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/6/2009 | N/A | N/A |  |  |  | 12/7/2010 | 12/7/2010 | 12/7/2010 | N | No
V1-024 | LaSalle 1 | LaSalle Nuclear Station Unit 1 | IL | Lasalle | In Service | ComEd | 1188 | 20 | 11.9 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1024_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1024_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v1_024_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 11/1/2010 |  | 5/21/2015 | N | No
V1-025 | LaSalle 2 | LaSalle Nuclear Station Unit 2 | IL | Lasalle | In Service | ComEd | 1191 | 20 | 10.9 | 2.5 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1025_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v1_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 3/1/2011 |  | 5/21/2015 | N | No
V1-026 | Limerick |  | PA | Montgomery | Partially in Service - Active | PECO | 1213 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v1_026_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 4/4/2011 | 4/4/2011 | 4/4/2011 | N | No
V1-027 | Limerick |  | PA | Montgomery | Partially in Service - Active | PECO | 1213 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v1_027_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/9/2009 | N/A | N/A |  |  |  | 4/1/2011 |  | 6/12/2013 | N | No
V1-028 | North Wales | Morris Road | PA | Montgomery | In Service | PECO | 10 | 2 | 2 | 2 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v1_028_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2009 | N/A | N/A | 4/30/2012 |  |  | 5/31/2009 |  | 5/2/2012 | N | No
V1-029 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 56 | 6 | 0.78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1029_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/23/2009 | N/A | N/A |  | 9/14/2009 | Customer Milestone Not Met | 7/1/2013 |  |  | N | No
V1-030 | PSE&G Area |  | NJ | Various | In Service | PSEG | 52 | 52 | 19.8 | 46.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v1030_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2009 | N/A | N/A |  |  |  | 6/22/2010 | 6/22/2010 | 12/27/2011 | N | No
V1-031 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 950 | 950 | 875 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1031_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2009 | N/A | N/A |  | 1/30/2012 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | No
V1-032 | Highland 69kV |  | OH | Highland | Withdrawn | AEP | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2009 | N/A | N/A |  | 4/14/2011 | Customer Milestone Not Met | 8/1/2010 | 8/1/2010 |  | N | No
V1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 132 | 132 | 132 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v1033_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v1_033_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2009 | N/A | N/A |  | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V1-034 | Bergen 230kV | Hudson Transmission Project | NJ | Bergen | In Service | PSEG | 673 | 3 | 0 |  | Energy | Merchant Transmission |  | DC | NF/TWR 673 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v1034_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/v1034_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/v1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/v1_034_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2009 | N/A | N/A |  |  |  | 5/1/2013 | 5/1/2013 | 4/19/2013 | S | No
V1-035 | Kanawha 138kV | ST | WV | Fayette | Withdrawn | AEP | 53 | 53 | 53 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v1035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2009 | N/A | N/A |  | 1/14/2013 | Customer Milestone Not Met | 5/1/2011 |  |  | N | No
V2-001 | Bucyrus Center 138kV | 54 1.8 WT | OH | Crawford | Withdrawn | AEP | 91.8 | 91.8 | 11.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2001_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2009 | N/A | N/A |  | 3/18/2013 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V2-002 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 2.7 | 2.65 | 2.65 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2002_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/6/2009 | N/A | N/A |  | 2/8/2010 | Customer Milestone Not Met | 6/30/2010 |  |  | N | No
V2-003 | Beasley 23kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2003_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v2003_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/7/2009 | N/A | N/A |  | 1/6/2014 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V2-004 | Harwood-E. Hazleton #1 |  | PA | Schuylkill | Withdrawn | PPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 5/11/2009 | N/A | N/A |  | 12/4/2009 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V2-005 | Pleasantville 12kV |  | NJ | Atlantic | Withdrawn | AEC | 7.3 | 1.91 | 1.91 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2005_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/15/2009 | N/A | N/A |  | 2/17/2010 | Customer Milestone Not Met | 12/31/2010 | 12/31/2010 |  | N | No
V2-006 | East Leipsic 138kV | Leipsic Wind Project | OH | Putnam | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v2006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v2_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v2_006_csa.pdf | Document Posted | N/A | N/A |  | 5/28/2009 | N/A | N/A |  | 2/21/2020 |  | 12/31/2021 | 12/31/2021 |  | N | No
V2-007 | Bedington-Harmony Jct 138kV |  | MD | Allegany | Withdrawn | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2009 | N/A | N/A |  | 2/10/2012 | Customer Initiated Withdrawal | 6/1/2010 |  |  | S | No
V2-008 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2009 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 10/1/2014 |  |  | N | No
V2-009 | Plainsboro & Devils Brook 13kV | Cranbury SP | NJ | Middlesex | Under Construction | PSEG | 16.1 | 16.11 | 6.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2009_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/29/2009 | N/A | N/A | 6/1/2024 |  |  | 6/1/2012 | 6/1/2012 |  | N | No
V2-010 | Stewartsville 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2010_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2010_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/5/2009 | N/A | N/A |  | 3/15/2013 | Customer Milestone Not Met | 6/30/2011 | 6/30/2011 |  | N | No
V2-011 | Sunbury-Milton 69kV |  | PA | Northumberland | Withdrawn | PPL | 5.6 | 5.63 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2009 | N/A | N/A |  | 8/18/2009 | Customer Initiated Withdrawal | 2/1/2010 |  |  | N | No
V2-012 | Essex 26.4kV | Essex SP | NJ | Essex | Withdrawn | PSEG | 6 | 2.8 | 2.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2012_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 6/9/2009 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 3/5/2010 | 3/5/2010 |  | N | No
V2-013 | Farmingdale 12.47kV | Farmingdale Solar | NJ | Monmouth | Withdrawn | JCPL | 0.5 | 0.5 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2013_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/11/2009 | N/A | N/A |  | 1/11/2013 | Customer Milestone Not Met | 4/1/2011 | 4/1/2011 |  | N | No
V2-014 | Waretown 12.47kV |  | NJ | Ocean | Withdrawn | AEC | 5.1 | 5.065 | 1.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2009 | N/A | N/A |  | 2/17/2010 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
V2-015 | Lumberton 13.2kV |  | NJ | Burlington | Withdrawn | PSEG | 3.3 | 3.3 | 1.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2009 | N/A | N/A |  | 12/21/2009 | Customer Milestone Not Met | 12/31/2009 |  |  | N | No
V2-016 1179105 | DUK-PJM |  | N/A | N/A | Retracted | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/15/2009 | 6/1/2010 | 6/6/2011 |  | 7/13/2009 |  |  |  |  | FF | No
V2-017 1179108 | DUK-PJM |  | N/A | N/A | Retracted | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/15/2009 | 6/1/2010 | 6/1/2011 |  | 7/13/2009 |  |  |  |  | FF | No
V2-018 | Tuckahoe |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/17/2009 | N/A | N/A |  | 12/20/2010 | Customer Initiated Withdrawal | 11/1/2010 |  |  | N | No
V2-019 | Mansfield-S. Troy 115kV | AES Armenia Mountain Wind, LLC | PA | Bradford | In Service | PENELEC | 100.5 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v2_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 10/22/2010 | 6/18/2009 | N/A | N/A |  |  |  | 8/19/2010 |  | 8/19/2010 | N | No
V2-019A | Dumont 765kV |  | IN | Unknown | Withdrawn | AEP | 7900 |  |  |  | Energy | Merchant Transmission |  | DC | F/NF TIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v2019a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2009 | N/A | N/A |  | 5/25/2010 | Customer Milestone Not Met | 5/1/2015 |  |  | S | No
V2-020 | Howard-West End Fostoria 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2009 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 7/31/2012 | 7/31/2012 |  | N | No
V2-021 | Clayville |  | NJ | Cumberland | Withdrawn | AEC | 64 | 64 | 64 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/26/2009 | N/A | N/A |  | 5/4/2010 | Customer Milestone Not Met | 6/1/2014 |  |  | N | No
V2-022 | Galion-Leesburg 138kV |  | OH | Morrow | Withdrawn | AEP | 201 | 201 | 26.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 8/17/2009 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-023 | Galion-Muskingham River 345kV |  | OH | Morrow | Withdrawn | AEP | 250.5 | 250.5 | 37.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 4/7/2010 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
V2-025 | Turnpike 13.8kV | Kearny SP | NJ | Hudson | In Service | PSEG | 5 | 5 | 1.9 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2025_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2009 | N/A | N/A |  |  |  | 1/31/2012 | 1/31/2012 | 3/1/2012 | N | No
V2-026 | Denver 138kV |  | WV | Barbour | Withdrawn | APS | 164 | 164 | 21.32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2009 | N/A | N/A |  | 12/11/2009 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-027 | South Milton |  | PA | Northumberland | Withdrawn | PPL | 1.6 | 1.62 | 1.62 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2027_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/8/2009 | N/A | N/A |  | 2/21/2013 | Customer Initiated Withdrawal | 9/1/2013 | 9/1/2013 |  | N | No
V2-028 | Vienna | Vienna Solar Facility | MD | Dorchester | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v2_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v2_028_csa.pdf | Document Posted | N/A | N/A |  | 7/8/2009 | N/A | N/A |  | 2/9/2018 |  | 11/30/2018 | 11/30/2018 |  | N | No
V2-029 1194261 | DUK-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 418 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/14/2009 | 1/1/2010 | 1/1/2020 |  | 7/29/2009 |  |  |  |  | FF | No
V2-030 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 950 | 950 | 875 | 950 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v2030_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v2_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v2_030_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 7/14/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V2-031 1197326 | AMIL-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 66 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1197326_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1197326_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-032 1197340 | AMIL-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 65 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1197340_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1197340_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-033 1197345 | AMIL-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 1 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1197345_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1197345_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-034 1197351 | AMIL-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1197351_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1197351_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/20/2009 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
V2-035 | Pittsgrove | Pittsgrove Solar, LLC | NJ | Salem | In Service | AEC | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2035_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v2035_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v2_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v2_035_csa.pdf | Document Posted | N/A | N/A |  | 7/20/2009 | N/A | N/A |  |  |  | 4/14/2014 | 4/14/2014 | 4/19/2014 | N | No
V2-036 1199525 | PJM-TVA |  | N/A | N/A | Retracted | EDP Renewables North America LLC | 202 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1199525_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1199525_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/21/2009 | 1/1/2011 | 1/1/2016 | [6 empty] | FF | No
V2-037 | White Oak | White Oak | MD | Montgomery | In Service | PEPCO | 24 | 4.5 | 0 | 4.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v2_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/24/2009 | N/A | N/A |  |  |  | 5/3/2010 | 5/3/2010 | 3/31/2010 | N | No
V2-040 | Mountain Road 34.5kV | Henrico County Landfill | VA | Henrico | In Service | Dominion | 4 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v2_040_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2009 | N/A | N/A |  |  |  | 9/23/2010 | 9/23/2010 | 9/23/2010 | N | No
V2-041 | Clayville 12kV | Vineland-Mays Landing | NJ | Cumberland | In Service | AEC | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2041_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2009 | N/A | N/A |  |  |  | 9/30/2011 | 9/30/2011 | 9/30/2011 | N | No
V2-042 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | 1640 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2009 | N/A | N/A |  | 9/6/2012 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
V2-042A_AT2 | Galion 138kV |  | OH | Morrow | Withdrawn | ATSI | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2042a_at2_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2042a_at2_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2009 | N/A | N/A |  | 4/14/2014 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V2-043 | Upper Deerfield Township I |  | NJ | Cumberland | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2043_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010 |  |  | N | No
V2-044 | Upper Deerfield Township II |  | NJ | Cumberland | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010 |  |  | N | No
V2-045 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 12.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2045_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 9/12/2011 | Customer Initiated Withdrawal | 10/1/2011 | 10/1/2011 |  | N | No
V2-046 | Pilesgrove Township 12kV | Pilesgrove SP | NJ | Salem | In Service | AEC | 19.9 | 19.9 | 7 | 18.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v2046_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/31/2009 | N/A | N/A |  |  |  | 7/31/2011 | 7/31/2011 | 7/31/2011 | N | No
V2-047 | Maurice River Township |  | NJ | Cumberland | Withdrawn | AEC | 1.4 | 1.35 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v2047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v2047_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/31/2009 | N/A | N/A |  | 1/31/2013 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V2-048 1205761 | PJM-LGEE |  | N/A | N/A | Withdrawn | Louisville Gas &amp; Electric | 11 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1205761_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1205761_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/5/2009 | 10/1/2010 | 10/1/2015 |  | 4/6/2010 |  |  |  |  | FF | No
V3-001 | Burches Hill 500kV |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/3/2009 | N/A | N/A |  | 3/2/2010 | Customer Milestone Not Met | 5/1/2015 |  |  | N | No
V3-002 | Ellicott City |  | MD | Howard | Withdrawn | BGE | 1.2 | 1.2 | 0.456 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2009 | N/A | N/A |  | 3/10/2010 | Customer Milestone Not Met | 6/30/2010 |  |  | N | No
V3-003 | Greentown-Jefferson 765kV |  | IN | Clinton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/5/2009 | N/A | N/A |  | 2/10/2011 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V3-004 | Siegfried |  | PA | Carbon | Withdrawn | PPL | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2009 | N/A | N/A |  | 4/7/2010 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
V3-005 | Morris 34.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3005_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 11/7/2013 | Customer Initiated Withdrawal | 12/31/2013 | 12/31/2013 |  | N | No
V3-006 | Linglestown |  | PA | Dauphin | Withdrawn | PPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3006_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 4/14/2011 | Customer Initiated Withdrawal | 12/31/2009 |  |  | N | No
V3-007 | Desoto-Tanners Creek #1 345kV | Headwaters II | IN | Randolph | Under Construction | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3007_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3007_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v3_007_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_007_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 8/10/2009 | N/A | N/A | 7/1/2020 |  |  | 11/30/2020 | 11/30/2020 |  | N | No
V3-008 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3008_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3008_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/3/2016 | Customer Milestone Not Met | 5/18/2018 | 5/18/2018 |  | N | No
V3-009 | Desoto-Tanners Creek #2 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3009_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/3/2016 | Customer Milestone Not Met | 5/19/2019 | 5/19/2019 |  | N | No
V3-010 | Delaware-Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2009 | N/A | N/A |  | 6/4/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
V3-011 | Sussex 12.47kV | Sussex County Land Fill | NJ | Sussex | In Service | JCPL | 3.4 | 3.4 | 3.4 | 3.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3011_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/11/2009 | N/A | N/A | 6/2/2011 |  |  | 6/3/2011 | 6/3/2011 | 6/3/2011 | N | No
V3-012 1212383 | TVA-PJM |  | N/A | N/A | Annulled | Magnolia Energy, LP | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1212383_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1212383_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/11/2009 | 5/26/2014 | 6/1/2019 | [6 empty] | FF | No
V3-013 | Wilmington 69kV |  | OH | Clinton | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3013_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/18/2009 | N/A | N/A |  | 10/27/2011 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
V3-014 | Lee County |  | IL | Lee | Withdrawn | ComEd | 160.2 | 160.2 | 20.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/2009 | N/A | N/A |  | 2/23/2012 | Customer Milestone Not Met | 11/20/2011 |  |  | N | No
V3-015 | Keystone 345kV | Wells County Wind Farm | IN | Wells | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_015_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 4/19/2018 |  | 12/31/2014 | 12/31/2014 |  | N | No
V3-016 | Greenville-West Milton 138kV |  | OH | Darke | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 4/9/2012 | Customer Initiated Withdrawal | 8/1/2012 |  |  | N | No
V3-017 | Morgantown-Oak Grove | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3017_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3017_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v3_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_017_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2009 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 11/25/2016 | N | No
V3-018 | Towanda 115kV |  | PA | Bradford | Withdrawn | PENELEC | 75 | 75 | 9.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2009 | N/A | N/A |  | 9/1/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
V3-019 | Edinboro 13.8kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3019_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/27/2009 | N/A | N/A |  | 3/24/2010 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
V3-020 | Mt. Storm-Valley 115kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-021 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-022 | 502 Junction-Meadowbrook 500kV |  | WV | Hardy | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-023 | Alburtis-Hosensack 500kV |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2009 | N/A | N/A |  | 2/24/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | S | No
V3-024 | Devils Brook 13.2kV | RE Cranbury Solar I, LLC | NJ | Middlesex | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 9/27/2011 | 9/27/2011 | 9/27/2011 | N | No
V3-025 | Cranbury 13.8kV | English SP | NJ | Middlesex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3025_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 6/9/2010 | Customer Milestone Not Met | 5/31/2010 |  |  | N | No
V3-026 | Larrabee 230kV |  | NJ | Ocean | Withdrawn | JCPL | 550 |  |  |  | Energy | Merchant Transmission |  | DC | F/550 TIR/550 TWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v3026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 1/1/2013 |  |  | S | No
V3-027 | Pickens 138kV |  | WV | Webster | Withdrawn | APS | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
V3-028 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | Engineering and Procurement | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_028_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
V3-029 | Chatfield 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 7/27/2010 | Customer Milestone Not Met | 12/1/2013 |  |  | N | No
V3-030 | St. Benedict-Patton 46kV | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 30.6 | 3.98 | 30.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3030_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_030_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_030_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2009 | N/A | N/A |  |  |  | 6/30/2013 | 6/30/2013 | 12/24/2012 | N | No
V3-031 | Germantown |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2009 | N/A | N/A |  | 4/9/2010 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
V3-032 | Darwin-Eugene 345kV |  | IL | Vermilion | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2009 | N/A | N/A |  | 7/26/2012 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
V3-034 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 921.5 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2009 | N/A | N/A |  | 7/21/2010 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
V3-036 | Ontario 23kV | Midtown Thermal Control Center | NJ | Atlantic | In Service | AEC | 5.5 | 5.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v3_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_036_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 12/1/2011 | 12/1/2011 | 12/1/2011 | N | No
V3-037 | Naval Academy Junction 13kV | Millersville Landfill & Resource Recovery Facility | MD | Anne Arundel | In Service | BGE | 4 | 4 | 4 | 3.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_037_csa.pdf | Document Posted | N/A | N/A |  | 9/14/2009 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 6/13/2012 | N | No
V3-038 | Turnpike 13kV | Turnpike SP | NJ | Hudson | Withdrawn | PSEG | 0.6 | 0.6 | 0.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3038_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2009 | N/A | N/A |  | 1/10/2013 |  | 12/31/2010 | 12/31/2010 |  | N | No
V3-039 | Harrison 4kV | Harrison SP | NJ | Hudson | Withdrawn | PSEG | 1.2 | 1.2 | 0.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3039_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2009 | N/A | N/A |  | 1/10/2013 |  | 12/31/2010 | 12/31/2010 |  | N | No
V3-040 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | Withdrawn | PPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_040_csa.pdf | Document Posted | N/A | N/A |  | 9/17/2009 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 6/30/2016 | 6/30/2016 |  | N | No
V3-041 | Daleville | SECCRA Units 1, 2 & 3 | PA | Chester | In Service | PECO | 4 | 2 | 3.2 | 2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_041_csa.pdf | Document Posted | N/A | N/A |  | 9/21/2009 | N/A | N/A |  |  |  | 11/1/2011 | 11/1/2011 | 12/15/2010 | N | No
V3-042 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 84 | 84 | 10.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3042_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/2/2009 | N/A | N/A |  | 8/8/2014 | Customer Initiated Withdrawal | 9/30/2016 | 9/30/2016 |  | N | No
V3-044 | Glendon 34.5kV | Chrin LF | PA | Northampton | In Service | ME | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3044_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/28/2009 | N/A | N/A |  |  |  | 6/14/2011 | 6/14/2011 | 6/14/2011 | N | No
V3-045 | Zimmer-Spurlock 345kV | Meldahl Hydroelectric Plant | OH | Butler | In Service | DEOK | 112 | 112 | 112 | 112 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v3_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_045_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2009 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 11/1/2015 | N | No
V3-046 | Conemaugh-Juniata 500kV |  | PA | Cambria | Withdrawn | PENELEC | 741 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v3046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/v3046_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/v3_046_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2009 | N/A | N/A |  | 12/16/2014 | Customer Milestone Not Met | 7/1/2012 |  |  | S | No
V3-047 | Sutton Dam 69kV |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2009 | N/A | N/A |  | 3/1/2010 | Customer Milestone Not Met | 12/21/2010 |  |  | N | No
V3-050 | Penns Neck 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 4.6 | 4.6 | 4.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3050_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/12/2009 | N/A | N/A |  | 8/5/2011 | Customer Milestone Not Met | 9/1/2011 | 9/1/2011 |  | N | No
V3-051 | Letort | Turkey Hill Dairy WF | PA | Lancaster | In Service | PPL | 3.2 | 3.2 | 0.4 | 3.2 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_051_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_051_csa.pdf | Document Posted | N/A | N/A |  | 10/16/2009 | N/A | N/A |  |  |  | 1/17/2011 | 1/17/2011 | 1/17/2011 | N | No
V3-052 | NI HUB-DC Cook |  | N/A | N/A | In Service | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v3052_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v3052_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v3052_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/21/2009 | N/A | N/A |  |  |  | 2/1/2013 | 2/1/2013 |  | EE | No
V3-053 | Desoto 138kV |  | IN | Delaware | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v3053_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/22/2009 | N/A | N/A |  | 10/14/2013 | Customer Milestone Not Met | 12/31/2013 | 12/31/2013 |  | N | No
V3-054 1246457 | PJM-LGEE |  | N/A | N/A | Withdrawn | Louisville Gas &amp; Electric Company | 99 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1246457_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/22/2009 | 4/1/2010 | 4/1/2015 |  | 4/6/2010 |  |  |  |  | FF | No
V3-055 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3055_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/23/2009 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 1/1/2013 |  |  | N | No
V3-056 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3056_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 8/3/2010 | Customer Milestone Not Met | 10/1/2013 | 10/1/2013 |  | N | No
V3-057 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 5/20/2011 | Customer Milestone Not Met | 3/31/2011 | 3/31/2011 |  | N | No
V3-058 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_058_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-059 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v3_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v3_059_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/24/2011 | N | No
V3-060 | Antioch |  | IL | Lake | Withdrawn | ComEd | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3060_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 7/26/2010 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
V3-061 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3061_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
V3-062 | McConnellsburg-Guilford 138kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3062_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
V3-063 | Dupont 69kV |  | VA | City of Martinsville | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3063_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 2/25/2010 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
V3-064 | Rivesville-Pruntytown 138kV |  | WV | Marion | Withdrawn | APS | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3064_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 12/17/2011 | Customer Initiated Withdrawal | 12/1/2012 |  |  | N | No
V3-065 | Clay St. 4kV (Barringer) | Clay ST SP | NJ | Essex | In Service | PSEG | 0.5 | 0.549 | 0.21 | 0.549 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3065_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/1/2010 | 10/1/2010 | 10/1/2010 | N | No
V3-066 | Cook Road 13.8kV (Park) | Cook Rd SP | NJ | Essex | In Service | PSEG | 0.4 | 0.432 | 0.16 | 0.432 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/31/2010 | 12/31/2010 | 11/17/2010 | N | No
V3-067 | Norfolk St. 4kV (Central) | Newark I SP | NJ | Essex | In Service | PSEG | 0.8 | 0.773 | 0.29 | 0.773 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3067_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3067_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 3/16/2011 | 3/16/2011 | 2/16/2011 | N | No
V3-068 | Norfolk St. 4kV (New Central HS) | Newark II SP | NJ | Essex | In Service | PSEG | 0.4 | 0.425 | 0.16 | 0.425 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3068_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 12/20/2010 | 12/20/2010 | 12/31/2010 | N | No
V3-069 | Woodbridge 13kV (Matrix Bldg) | Woodbridge SP | NJ | Middlesex | In Service | PSEG | 2.3 | 2.308 | 0.877 | 2.308 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3069_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 10/31/2010 | 10/31/2010 | 1/26/2011 | N | No
V3-070 | J. Rinco 34.5kV | Lilac Site | NJ | Hunterdon | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v3070_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 1/2/2012 | N | No
V3-071 | Frenchtown 12.47kV | Frenchtown SP | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v3071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v3071_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2009 | N/A | N/A |  | 6/21/2012 | Customer Initiated Withdrawal | 10/1/2010 | 10/1/2010 |  | N | No
V4-001 | Lebanon 34.5kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4001_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/2/2009 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-002 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 575 | 575 | 575 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2009 | N/A | N/A |  | 5/21/2010 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
V4-003 | Churchmans |  | DE | New Castle | Withdrawn | DPL | 14 | 14 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2009 | N/A | N/A |  | 5/17/2010 | Customer Milestone Not Met | 3/31/2010 |  |  | N | No
V4-004 | Roxbury 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4004_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2009 | N/A | N/A |  | 5/7/2010 | Customer Initiated Withdrawal | 7/1/2010 | 7/1/2010 |  | N | No
V4-005 | Southampton 13.8kV | Lumberton SP | NJ | Burlington | In Service | PSEG | 2.9 | 2.9 | 1.1 | 2.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4005_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/11/2009 | N/A | N/A |  |  |  | 11/10/2011 | 11/10/2011 | 8/1/2010 | N | No
V4-006 | Byron 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4006_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4006_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4006_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 2/18/2012 |  |  | EE | No
V4-007 | Quad City 1-NI Hub |  | N/A | N/A | In Service | ComEd | 150 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4007_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4007_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4007_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-008 | Braidwood 1-AD Hub | Suburban Landfill | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4008_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 2/15/2012 |  |  |  |  | EE | No
V4-009 | Upper Deerfield | Deerfield Project | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4009_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4009_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/12/2009 | N/A | N/A |  | 11/25/2013 | Customer Milestone Not Met | 6/1/2014 | 6/1/2014 |  | N | No
V4-010 | Tiffin Center 138kV | Republic Wind LLC | OH | Seneca | Engineering and Procurement | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4010_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4010_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v4_010_csa.pdf | Document Posted | N/A | N/A |  | 11/12/2009 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
V4-011 | Granger Electric | Granger Electric of Hancock County | OH | Hancock | In Service | AEP | 3.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4011_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2009 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 3/31/2015 | N | No
V4-012 | Morgantown |  | PA | Berks | Withdrawn | PPL | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4012_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/13/2009 | N/A | N/A |  | 11/8/2011 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
V4-013 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 5.2 | 5.2 | 1.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/18/2009 | N/A | N/A |  | 6/9/2010 | Customer Milestone Not Met | 9/30/2010 |  |  | N | No
V4-014 | Greenridge Landfill |  | PA | Westmoreland | Withdrawn | APS | 6.5 | 6.5 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2009 | N/A | N/A |  | 11/12/2010 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
V4-015 | Fostoria Central 138kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 66.6 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/23/2009 | N/A | N/A |  | 9/15/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
V4-016 | Valley 138kV |  | MI | Cass | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 3/27/2015 | Customer Initiated Withdrawal | 11/30/2014 | 11/30/2014 |  | N | No
V4-017 | Woodruffs Gap 345kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 3.5 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4017_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 2/15/2012 | Customer Milestone Not Met | 9/30/2010 |  |  | N | No
V4-018 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1425 | 475 | 415 | 475 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4018_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4018_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v4_018_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 11/25/2009 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
V4-019 | Bergen 230kV | Bergen Generating Station | NJ | Bergen | In Service | PSEG | 1209 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v4_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/25/2009 | N/A | N/A |  |  |  | 6/1/2013 |  | 5/31/2013 | N | No
V4-020 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 650 | 650 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/25/2009 | N/A | N/A |  | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
V4-021 | Keystone 345kV |  | IN | Wells | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4021_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 2/23/2012 | Customer Milestone Not Met | 12/15/2014 | 12/15/2014 |  | N | No
V4-022 | Tasley | Tasley Solar | VA | Accomack | Withdrawn | ODEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4022_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 3/13/2019 |  | 11/30/2019 | 11/30/2019 |  | N | No
V4-023 | Upper Pittsgrove 1 | Upper Pittsgrove Project | NJ | Salem | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4023_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4023_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 9/30/2014 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
V4-024 | Upper Pittsgrove 2 | Quinton Project | NJ | Salem | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4024_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4024_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4024_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 2/12/2015 | Customer Initiated Withdrawal | 11/30/2016 | 11/30/2016 |  | N | No
V4-025 | Upper Pittsgrove 3 | Beckett ProjectWoodstown Project | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4025_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4025_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/30/2009 | N/A | N/A |  | 8/12/2015 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
V4-026 | Pontiac-Dumont 345kV |  | IL | Unknown | Withdrawn | AEP | 3000 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v4026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2009 | N/A | N/A |  | 1/3/2013 | Customer Milestone Not Met | 6/30/2014 |  |  | S | No
V4-027 | Quarryville | Keystone Solar | PA | Lancaster | In Service | PPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/7/2009 | N/A | N/A |  |  |  | 12/30/2012 | 12/30/2012 | 9/17/2012 | N | No
V4-028 | Kuller Road 13.2kV | Kuller Road SP | NJ | Passaic | Withdrawn | PSEG | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4028_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/7/2009 | N/A | N/A |  | 1/10/2010 | Customer Milestone Not Met | 7/1/2010 |  |  | N | No
V4-029 | Mannington Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4029_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/7/2009 | N/A | N/A |  | 9/17/2013 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-030 | Byron 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4030_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4030_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4030_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-031 | Quad 2-NI Hub |  | N/A | N/A | In Service | ComEd | 350 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/v4031_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/v4031_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/v4031_arr-csa.pdf | Document Posted | N/A | N/A |  | 12/8/2009 | N/A | N/A |  |  |  | 5/28/2012 |  |  | EE | No
V4-033 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Withdrawn | AEP | 299.2 | 299.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4033_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/11/2009 | N/A | N/A |  | 9/8/2016 | Customer Milestone Not Met | 12/31/2018 | 12/31/2018 |  | N | No
V4-035 | Yankee 12.5kV |  | OH | Montgomery | Withdrawn | Dayton | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 1/22/2010 | Customer Initiated Withdrawal | 4/30/2010 |  |  | N | No
V4-036 | Newport-South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4036_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 3/20/2012 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
V4-037 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2009 | N/A | N/A |  | 1/18/2013 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-037A 1274879 | DUK-PJM |  | N/A | N/A | Retracted | Southern Power Company | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1274879_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1274879_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/15/2009 | 1/1/2012 | 1/1/2020 |  | 10/19/2010 |  |  |  |  | FF | No
V4-038 | Friendship Manor 34.5kV | Alpha Ridge Landfill | MD | Carroll | In Service | BGE | 1 | 1 | 1 | 1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v4_038_csa.pdf | Document Posted | N/A | N/A |  | 12/16/2009 | N/A | N/A |  |  |  | 2/28/2013 | 2/28/2013 | 7/31/2012 | N | No
V4-039 | Church |  | MD | Queen Anne's | Withdrawn | DPL | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/18/2009 | N/A | N/A |  | 5/20/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
V4-039A_AT3 | MOABs A16, A17, A18 |  | OH | Sandusky | Withdrawn | ATSI | 22 | 22 | 22 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4039a_at3_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4039a_at3_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2009 | N/A | N/A |  | 7/27/2012 | Queue Not Required | 5/1/2010 |  |  | N | No
V4-040 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2009 | N/A | N/A |  | 5/28/2010 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
V4-041 | Upper Pittsgrove 4 | Upper Pittsgrove Township - Site 4 | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4041_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4041_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V4-042 | Upper Pittsgrove 5 | Upper Pittsgrove Township - Site 5 | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4042_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
V4-043 | Shirley 12kV | Stewartstown Generating Facility | NJ | Salem | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 10/27/2010 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-044 | Mannington Township 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2009 | N/A | N/A |  | 6/1/2010 | Customer Milestone Not Met | 12/31/2010 |  |  | N | No
V4-045 | Peach Bottom | Peach Bottom Units 2 & 3 | PA | York | In Service | PECO | 2665.8 | 133.8 | 206 | 133.8 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 10/3/2015 |  | 1/6/2016 | N | No
V4-046 | Byron 1 | Byron Nuclear Generating Station, Unit 1 | IL | Ogle | In Service | ComEd | 1232 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_046_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-047 | Byron 2 | Byron Nuclear Generating Station, Unit 2 | IL | Ogle | In Service | ComEd | 1210 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_047_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-048 | Braidwood 1 | Braidwood Nuclear Generating Station, Unit 1 | IL | Will | In Service | ComEd | 1240 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-049 | Braidwood 2 | Braidwood Nuclear Generating Station, Unit 2 | IL | Will | In Service | ComEd | 1214 | 20 | 20 | 20 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4049_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4049_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_049_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/24/2009 | N/A | N/A |  |  |  | 1/1/2012 |  | 2/6/2014 | N | No
V4-050 1276187 | PJM-AMIL |  | N/A | N/A | Annulled | Christian County Generation | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1276187_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1276187_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/17/2009 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
V4-051 1276193 | PJM-AMIL |  | N/A | N/A | Withdrawn | Christian County Generation | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1276193_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/17/2009 | 6/1/2015 | 6/1/2045 |  | 3/4/2010 |  |  |  |  | FF | No
V4-052 | West Reading | The Reading Hospital and Medical Center | PA | Berks | In Service | ME | 10 | 10 | 6 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4052_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2009 | N/A | N/A |  |  |  | 7/12/2011 |  | 7/12/2011 | N | No
V4-053 | Double Toll Gate 138kV |  | VA | Clarke | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2009 | N/A | N/A |  | 11/28/2012 | Customer Initiated Withdrawal | 11/1/2011 | 11/1/2011 |  | N | No
V4-054 | Fairfield Township 12kV | NJ Oak Solar | NJ | Cumberland | In Service | AEC | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4054_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4054_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/v4_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v4_054_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2009 | N/A | N/A |  |  |  | 12/20/2011 | 12/20/2011 | 12/20/2011 | N | No
V4-055 | Meigs-Ravenswood 69kV |  | OH | Meigs | Withdrawn | AEP | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2010 | N/A | N/A |  | 11/16/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
V4-055A 926517 | LGEE-PJM |  | N/A | N/A | Confirmed | Illinois Municipal Electric Agency | 5 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/926517_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/926517_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 1/6/2010 | 6/1/2010 | 6/1/2017 | [6 empty] | FF | No
V4-056 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
V4-057 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
V4-058 | Collins HVDC |  | SD | Hand | Withdrawn | ComEd | 3500 |  |  |  | Energy | Merchant Transmission |  |  | F/1650/NF/1850 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/v4058_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2010 | N/A | N/A |  | 9/14/2012 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
V4-059 | Pine Creek 46kV |  | WV | Mingo | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4059_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2010 | N/A | N/A |  | 11/18/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
V4-060 1297962 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1297962_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1297962_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 1/15/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
V4-061 1297967 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1297967_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1297967_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 1/15/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
V4-062 | Upper Pittsgrove 6 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-063 | Upper Pittsgrove 7 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4063_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2010 | N/A | N/A |  | 11/3/2010 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
V4-064 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/26/2010 | N/A | N/A |  | 12/11/2013 | Customer Initiated Withdrawal | 9/30/2012 | 9/30/2012 |  | N | No
V4-065 | Meadow Road 13kV | Edison Project | NJ | Middlesex | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4065_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/27/2010 | N/A | N/A |  | 2/8/2011 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
V4-066 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.6 | 3.6 | 1.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2010 | N/A | N/A |  | 2/12/2010 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
V4-067 | Cates Road Egg Harbor Township 12kV | McKee City Solar | NJ | Atlantic | In Service | AEC | 2.6 | 2.6 | 0.98 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/v4067_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4067_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/28/2010 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 12/22/2011 | N | No
V4-068 | Murphy's 34.5kV |  | NC | Hertford | In Service | Dominion | 5 | 5 | 3.23 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/v4_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/v4_068_csa.pdf | Document Posted | N/A | N/A | 8/1/2011 | 1/29/2010 | N/A | N/A | 8/1/2011 |  |  | 12/31/2011 | 12/31/2011 | 12/29/2011 | N | No
V4-069 | Frenchtown 34.5kV | Frenchtown 1 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4069_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4069_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 3/1/2011 | 3/1/2011 | 12/31/2011 | N | No
V4-070 | Frenchtown 12.5kV | Frenchtown 2 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4070_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 1/2/2012 | N | No
V4-071 | Bixby 13.8kV |  | OH | Franklin | Withdrawn | AEP | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4071_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 7/30/2010 | Customer Milestone Not Met | 6/1/2010 | 6/1/2010 |  | N | No
V4-072 | Blue Ridge Landfill |  | PA | Franklin | Withdrawn | APS | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4072_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 5/7/2012 | Customer Initiated Withdrawal | 5/1/2012 | 5/1/2012 |  | N | No
V4-073 | Yankee 12.5kV |  | OH | Montgomery | In Service | Dayton | 2.5 | 2.5 | 0.95 | 0.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  |  |  | 5/28/2010 | 5/28/2010 | 5/28/2010 | N | No
V4-074 | Quad Cities Wind |  | IL | Hancock | Withdrawn | ComEd | 1000 | 1000 | 130 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
V4-075 | Warwick 12kV |  | PA | Lancaster | Withdrawn | PPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4075_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 3/1/2015 | 3/1/2015 |  | N | No
V4-076 | Carlisle Pike 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 5.3 | 5.3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4076_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
V4-077 | Montgomery Avenue 12.47kV |  | PA | Mifflin | Withdrawn | PENELEC | 13 | 13 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/v4077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/v4077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/v4077_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
V4-078 | Hawks Bridge Road |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2010 | N/A | N/A |  | 3/15/2010 | Customer Initiated Withdrawal | 2/15/2011 |  |  | N | No
V4-081 1307470 | PJM-LGEE |  | N/A | N/A | Retracted | Invenergy LLC | 110 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1307470_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 1/29/2010 | 1/1/2011 | 1/1/2016 |  | 4/9/2010 |  |  |  |  | FF | No
W1-001 | Linden VFT 230kV | Linden VFT | NJ | Union | In Service | PSEG | 15 |  |  |  | Energy | Merchant Transmission |  | AC | TIR 15 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/w1_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/2/2010 | N/A | N/A |  |  |  | 3/31/2010 |  | 6/1/2011 | S | No
W1-002 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP | 98 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1002_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2010 | N/A | N/A |  | 7/20/2012 | Customer Initiated Withdrawal | 7/1/2010 |  |  | S | No
W1-003 | Oak Hall | Oak Hall Project A | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1003_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1003_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_003_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
W1-004 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1004_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1004_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_004_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
W1-005 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1005_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1005_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_005_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-006 | Oak Hall | Oak Hall Project D | VA | Unknown | In Service | DPL | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_006_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2010 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
W1-007 | Oak Hall |  | VA | Accomack | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1008_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 9/30/2016 | 9/30/2016 |  | N | No
W1-009 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W1-010 | Cooper |  | PA | York | Withdrawn | PECO | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
W1-011 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2010 | N/A | N/A |  | 5/19/2011 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
W1-011A 1318109 | DUK2-PJM |  | N/A | N/A | Retracted | North Carolina Municipal Power Agency | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1318109_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 2/11/2010 | 6/1/2013 | 6/1/2014 |  | 5/3/2010 |  |  |  |  | FF | No
W1-012 | Millheim-Brush Jct 46kV |  | PA | Centre | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1012_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/12/2010 | N/A | N/A |  | 5/8/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W1-013 | Saint Thomas 34kV I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/15/2011 | 12/15/2011 |  | N | No
W1-014 | Saint Thomas 34kV II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1014_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/18/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/15/2011 | 12/15/2011 |  | N | No
W1-015 | Shade Gap 115kV |  | PA | Unknown | Withdrawn | PENELEC | 60.8 | 60.8 | 7.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1015_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2010 | N/A | N/A |  | 5/14/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
W1-016 1325338 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1325338_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1325338_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
W1-017 1325402 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1325402_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1325402_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2010 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
W1-018 1325455 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1325455_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1325455_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-019 1325477 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1325477_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1325477_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-020 1325503 | MEC-PJM |  | N/A | N/A | Confirmed | Avangrid Renewables, LLC | 46 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1325503_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1325503_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2010 | 5/1/2010 | 5/1/2015 | [6 empty] | FF | No
W1-021 | Fairton 69kV I |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2010 | N/A | N/A |  | 10/16/2013 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-022 | Fairton 69kV II |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2010 | N/A | N/A |  | 7/30/2013 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-023 | Fairton 69kV III |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1023_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/24/2010 | N/A | N/A |  | 2/18/2014 | Customer Initiated Withdrawal | 7/1/2011 |  |  | N | No
W1-024 | Manalapan 12.5kV | Village at Manalapan Solar Farm | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.5 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1024_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_024_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_024_csa.pdf | Document Posted | N/A | N/A |  | 2/24/2010 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 12/14/2011 | N | No
W1-025 | Mt. Storm-Valley 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-026 | Mt. Storm-Doubs 500kV |  | WV | Unknown | Withdrawn | Dominion | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-027 | 502 Junction-Meadowbrook 500kV |  | WV | Unknown | Withdrawn | APS | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2013 |  |  | S | No
W1-028 | Alburtis-Hosensack |  | PA | Unknown | Withdrawn | PPL | 500 |  |  |  | Energy | Merchant Transmission |  | AC | IDR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 11/18/2010 | Customer Milestone Not Met | 12/31/2013 |  |  | S | No
W1-029 | Winfall 230kV | Desert Wind Farm | NC | Pasquotank | In Service | Dominion | 208 | 208 | 27 | 208 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_029_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 3/2/2017 | N | No
W1-030 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W1-031 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W1-032 | Millhurst 12.5kV | Millhurst Solar Farm | NJ | Monmouth | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_032_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/2/2016 | N | No
W1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 157 | 25 | 25 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1033_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_033_csa.pdf | Document Posted | N/A | N/A |  | 2/25/2010 | N/A | N/A |  | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W1-034 | Burches Hill |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 8/24/2010 | Customer Initiated Withdrawal | 5/1/2015 |  |  | N | No
W1-035 | Baker 345kV |  | KY | Lawrence | Withdrawn | AEP | 750 | 750 | 750 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 11/22/2010 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W1-036 | Matt Funk-Tech Drive 138kV | Central Solar Park | VA | Roanoke | Withdrawn | AEP | 45 | 45 | 5.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1036_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 3/21/2012 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
W1-037 | East Lima-South Kenton 138kV |  | VA | Unknown | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 1/3/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W1-038 | Fairlawn 138kV |  | NJ | Bergen | Withdrawn | PSEG | 77 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 8/31/2010 | Customer Milestone Not Met | 1/1/2011 |  |  | N | No
W1-039 | Pedricktown 230kV | PCLP Facility | NJ | Salem | In Service | AEC | 120.3 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/26/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 3/7/2012 | N | No
W1-040 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 2752 | 350 | 350 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 2/13/2012 | Customer Milestone Not Met | 4/10/2016 |  |  | N | No
W1-041 | W. Milton-Greenville |  | OH | Darke | Withdrawn | Dayton | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1041_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2010 | N/A | N/A |  | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W1-042 | Hubar Road 1 |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-043 | Hubar Road 2 |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1043_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-044 | Mont Alto |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011 | 12/15/2011 |  | N | No
W1-045 | Roxbury 23 kV | Roxbury Solar Project | PA | Franklin | In Service | PENELEC | 13.5 | 13.5 | 5.13 | 13.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_045_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2010 | N/A | N/A | 12/13/2019 |  |  | 12/31/2019 | 12/31/2019 | 12/31/2019 | N | No
W1-046 | Face Rock 69kV |  | PA | Lancaster | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1046_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_046_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2010 | N/A | N/A |  | 11/30/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
W1-048 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1048_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 3/15/2011 |  |  | N | No
W1-049 1342417 | TVA-PJM |  | N/A | N/A | Withdrawn | Magnolia Energy, LP | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1342417_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/9/2010 | 6/1/2014 | 6/1/2019 |  | 6/24/2010 |  |  |  |  | FF | No
W1-050 | Keller & Valley Camp Roads I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 10/17/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W1-051 | St. Thomas 34kV III |  | PA | Franklin | Withdrawn | APS | 130 | 130 | 49.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 10/14/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W1-052 | Keller & Valley Camp Roads II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W1-053 | Pleasant View 500kV |  | VA | Arlington | Withdrawn | Dominion | 229 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2010 | N/A | N/A |  | 9/14/2010 | Customer Milestone Not Met | 6/1/2013 |  |  | S | No
W1-054 | South Akron-Prince | Dart Container | PA | Lancaster | In Service | PPL | 11.4 | 11.4 | 11.4 | 11.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_054_csa.pdf | Document Posted | N/A | N/A |  | 3/16/2010 | N/A | N/A |  |  |  | 12/31/2011 |  | 10/6/2012 | N | No
W1-055 | Broadway 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2010 | N/A | N/A |  | 9/28/2011 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W1-056 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 66.7 | 18.4 | 2.4 | 18.4 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_056_csa.pdf | Document Posted | N/A | N/A |  | 3/18/2010 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/15/2017 | N | No
W1-057 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1057_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1057_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/23/2010 | N/A | N/A |  | 12/14/2011 | Customer Milestone Not Met | 5/31/2011 |  |  | N | No
W1-058 1352721 | PJM-CPLE |  | N/A | N/A | Retracted |  | 7 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1352721_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/22/2010 | 1/1/2011 | 1/1/2016 |  | 6/15/2010 |  |  |  |  | FF | No
W1-058A_DK1 | AK Steel Middletown-AK Steel 1C 138kV |  | OH | Butler | Withdrawn | Duke | 134.5 | 134.5 | 134.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1058a_dk1_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1058A_dk1_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2010 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
W1-059 | Denville |  | NJ | Morris | Withdrawn | JCPL | 2 | 2 | 0.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1059_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/24/2010 | N/A | N/A |  | 4/19/2012 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W1-060 | Carneys Point Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1060_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2010 | N/A | N/A |  | 1/11/2011 | Customer Milestone Not Met | 5/31/2011 |  |  | N | No
W1-061 | Brambleton |  | VA | Loudoun | Withdrawn | Dominion | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2010 | N/A | N/A |  | 5/25/2010 |  | 6/1/2013 |  |  | S | No
W1-061A 1365383 | PJM-TVA |  | N/A | N/A | Retracted | Roanoke Wind LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1365383_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/26/2010 | 12/1/2011 | 1/1/2032 |  | 6/15/2010 |  |  |  |  | FF | No
W1-061B 1365390 | PJM-TVA |  | N/A | N/A | Retracted | Roanoke Wind LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1365390_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/26/2010 | 12/1/2011 | 1/1/2032 |  | 6/15/2010 |  |  |  |  | FF | No
W1-062 | Clayton 138kV | Smyrna Units 1 & 2 | DE | Kent | In Service | DPL | 101 | 53 | 53 | 53 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_062_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2010 | N/A | N/A |  |  |  | 5/31/2012 | 5/31/2012 | 6/15/2012 | N | No
W1-063 | Branchburg-Elroy 500kV |  | NJ | Somerset | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1063_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2010 | N/A | N/A |  | 6/10/2010 |  | 6/1/2011 |  |  | S | No
W1-064 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.6 | 1.6 | 1.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 7/1/2014 | Customer Initiated Withdrawal | 1/31/2011 |  |  | N | No
W1-065 | Millstone |  | NJ | Monmouth | Withdrawn | JCPL | 2 | 1.99 | 0.756 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1065_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 11/17/2011 | Customer Milestone Not Met | 3/31/2011 |  |  | N | No
W1-066 | New Brooklyn Road 12kV |  | NJ | Camden | Withdrawn | AEC | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2010 | N/A | N/A |  | 2/27/2012 | Customer Initiated Withdrawal | 9/1/2010 |  |  | N | No
W1-067 1373369 | PJM-EKPC |  | N/A | N/A | Retracted | East Kentucky Power Cooperative, Inc. | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1373369_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1373369_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A |  | Withdrawn |  | Withdrawn |  | 4/9/2010 | 6/1/2011 | 6/1/2016 |  | 2/25/2011 |  |  |  |  | FF | No
W1-068 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1068_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/16/2010 | N/A | N/A |  | 2/20/2014 | Customer Initiated Withdrawal | 4/1/2011 |  |  | N | No
W1-070 | Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1070_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1070_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/20/2010 | N/A | N/A |  | 1/6/2014 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W1-070A_AT4 | Ashtabula 138kV |  | OH | Ashtabula | Withdrawn | ATSI | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1070a_at4_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1070a_at4_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1070a_at4_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/20/2010 | N/A | N/A |  | 4/16/2014 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W1-071 | Elk Road 12kV |  | NJ | Salem | Withdrawn | AEC | 1 | 1.04 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1071_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 10/31/2010 |  |  | N | No
W1-072A_AT5 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 640 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1072a_at5_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1072a_at5_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1072a_at5_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_072a_at5_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 4/11/2014 | N | No
W1-073 | Ladysmith CT 230kV |  | VA | Carolina | Withdrawn | Dominion | 1562 | 612 | 498 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W1-074 | Remington CT 230kV |  | VA | Fauquier | Withdrawn | Dominion | 1370 | 610 | 498 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W1-075 | Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1075_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
W1-076 | Kingwood | Keller Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_076_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  | 5/16/2014 |  | 6/30/2012 | 6/30/2012 |  | N | No
W1-077 | Shacklefords 34.5kV | King and Queen | VA | King and Queen | In Service | Dominion | 14 | 4 | 4 | 4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_077_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 9/1/2011 | N | No
W1-078 | Sammis-Wylie Ridge 345kV |  | OH | Jefferson | In Service | APS |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w1078_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2010 | N/A | N/A |  |  |  | 6/1/2012 | 6/1/2012 | 5/30/2012 | S | No
W1-079 1394028 | EKPC-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 70 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1394028_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1394028_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/28/2010 | 1/1/2011 | 6/1/2013 | [6 empty] | FF | No
W1-080 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 4/12/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W1-081 | Mickleton 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1081_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 10/5/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W1-082 | Milford | Milford Solar | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 3/7/2018 |  | 2/17/2018 | 2/17/2018 |  | N | No
W1-083 | Deptford 13kV | West Deptford Solar | NJ | Gloucester | Withdrawn | PSEG | 4.6 | 4.6 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1083_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/10/2013 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W1-084 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W1-085 | Millville 1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-086 | Millville 2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-087 | Millville 3 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-088 | Millville 4 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011 |  |  | N | No
W1-089 | Newport 69kV |  | NJ | Cumberland | Withdrawn | AEC | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 1/7/2011 |  |  | N | No
W1-090 | Berlin 69kV |  | NJ | Camden | Withdrawn | AEC | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1090_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/24/2014 | Customer Initiated Withdrawal | 4/25/2011 |  |  | N | No
W1-091 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 8/25/2010 | Customer Initiated Withdrawal | 4/25/2011 |  |  | N | No
W1-092 | Mays Landing 12kV |  | NJ | Cumberland | Withdrawn | AEC | 8.7 | 8.7 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1092_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-093 | Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1093_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-094 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1094_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-095 | Buena 12kV |  | NJ | Atlantic | Withdrawn | AEC | 18 | 18 | 7.02 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-096 | Woodbine 12kV |  | NJ | Cape May | Withdrawn | AEC | 7 | 7 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 7/21/2011 |  |  | N | No
W1-097 | Fairfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1097_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/13/2011 | Customer Milestone Not Met | 12/30/2010 |  |  | N | No
W1-098 | Levittown 13kV | Levittown SP | NJ | Burlington | Withdrawn | PSEG | 1 | 0.965 | 0.367 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1098_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1098_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-099 | Levittown 13kV | Levittown 2 SP | NJ | Burlington | Withdrawn | PSEG | 1.3 | 1.282 | 0.487 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-100 | Minue Street 12kV | Rathway SP | NJ | Middlesex | Withdrawn | PSEG | 1.7 | 1.741 | 0.662 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1100_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011 |  |  | N | No
W1-101 | Bayonne 13kV | Bayonne SP | NJ | Hudson | In Service | PSEG | 1.4 | 1.4 | 0.532 | 1.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1101_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W1-102 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1.9 | 1.9 | 0.722 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 6/1/2010 | Customer Milestone Not Met | 2/1/2011 |  |  | N | No
W1-103 | Millville 12kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1103_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/27/2010 | Customer Initiated Withdrawal | 6/15/2011 |  |  | N | No
W1-104 | Bellefonte 12kV |  | PA | Centre | Withdrawn | APS | 0.7 | 0.65 | 0.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1104_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 9/4/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W1-105 | Reamstown | Heatherwoods Solar Farm | PA | Lancaster | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1105_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017 | 6/30/2017 |  | N | No
W1-106 | West Carlisle | Shover Solar Farm | PA | Cumberland | Withdrawn | PPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1106_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017 | 6/30/2017 |  | N | No
W1-107 | Grove City Road 12kV | Grove City Road 12kV | PA | Butler | Withdrawn | APS | 2 | 2 | 0.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1107_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1107_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 10/12/2015 | Customer Milestone Not Met | 8/31/2015 | 8/31/2015 |  | N | No
W1-108 | Grays Ferry 230kV | Grays Ferry Cogeneration Partnership | PA | Philadelphia | In Service | PECO | 163 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2011 |  | 7/29/2013 | N | No
W1-109 | Bloom 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1109_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 1/20/2014 | 1/20/2014 |  | N | No
W1-110 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.2 | 3.21 | 1.19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/31/2010 | Customer Initiated Withdrawal | 9/3/2012 |  |  | N | No
W1-111 | Harwood-Berwick 69kV | Beacon Power Flywheel Station | PA | Luzerne | In Service | PPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1111_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1111_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w1_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_111_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 7/24/2014 | N | No
W1-112 | Holmdel | Holmdel SP | NJ | Monmouth | In Service | JCPL | 4 | 4 | 1.52 | 4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1112_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 3/1/2013 | 3/1/2013 | 3/1/2013 | N | No
W1-113 | Millstone 2 | Northpark Solar Farm #1 | NJ | Monmouth | In Service | JCPL | 8 | 8 | 3 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_113_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W1-114 | Port Carbon | East Norwegian Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1114_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 12/19/2016 |  | 12/31/2013 | 12/31/2013 |  | N | No
W1-115 | Tamanend | Ryan Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1115_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 12/19/2017 |  | 6/30/2014 | 6/30/2014 |  | N | No
W1-116 | Emmitsburg 34kV | Mount St. Mary's PV Park | MD | Frederick | In Service | APS | 14 | 14 | 5.32 | 14 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1116_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_116_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 4/30/2012 | 4/30/2012 | 7/5/2012 | N | No
W1-117 | Silica Spur 1 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/29/2014 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
W1-118 | Silica Spur 2 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1118_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 1/29/2014 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W1-119 | Pemberton Township 1 34.5 kV | Greenburg Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1119_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/16/2017 | N | No
W1-120 | Pemberton Township 2 34.5 kV | Perez Solar | NJ | Burlington | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1120_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1120_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 6/15/2017 | N | No
W1-121 | Crosswicks 13kV | Property #6 | NJ | Mercer | In Service | PSEG | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1121_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1121_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 1/1/2012 | 1/1/2012 | 12/14/2011 | N | No
W1-122 | Wantage 12.47kV | Lower Unionville Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 5.1 | 5.13 | 1.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1122_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1122_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 3/7/2014 |  | 12/31/2014 | 12/31/2014 |  | N | No
W1-123 | Mannington Township 1 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 9/1/2010 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W1-124 | Tinton Falls 34.5kV | Tinton Falls Solar | NJ | Monmouth | In Service | JCPL | 16.9 | 16.9 | 6.4 | 16.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1124_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_124_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_124_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 12/6/2012 | N | No
W1-125 | Mannington Township 2 12kV |  | NJ | Salem | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 8/26/2010 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
W1-126 | White | White Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_126_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_126_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 11/21/2012 | Customer Initiated Withdrawal | 12/30/2013 | 12/30/2013 |  | N | No
W1-127 | Phillipsburg 12.47kV | Harmony Solar Farm | NJ | Warren | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_127_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/30/2015 | N | No
W1-128 | Red School Lane 69kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 2/9/2011 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
W1-129 | Cookstown 34.5kV | Jacobstown Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1129_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w1_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w1_129_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 9/20/2014 | N | No
W1-130 | Vine Road 12kV | Cedar Branch Solar Farm | NJ | Cumberland | In Service | AEC | 9.2 | 9.2 | 3.5 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w1130_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1130_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 10/27/2016 | N | No
W1-131 | Kenney |  | MD | Worcester | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1131_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2010 | N/A | N/A |  | 2/3/2011 | Customer Milestone Not Met | 4/30/2011 |  |  | N | No
W1-132 | Pittstown | Paunch Solar | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w1132_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w1132_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/6/2013 | N | No
W2-001 | Fostoria Central 138/kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 66.6 | 8.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2001_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/6/2010 | N/A | N/A |  | 9/15/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
W2-002 | Kennedyville 1 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2010 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W2-003 | Kennedyville 2 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2010 | N/A | N/A |  | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W2-004 | Foundry St. 138kV |  | NJ | Essex | Withdrawn | PSEG | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2004_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 5/23/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
W2-005 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 12/16/2010 | Customer Milestone Not Met | 10/30/2013 |  |  | N | No
W2-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2010 | N/A | N/A |  | 11/19/2010 | Customer Milestone Not Met | 11/30/2010 |  |  | N | No
W2-007 | East Leipsic 138kV |  | OH | Putnam | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2007_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2010 | N/A | N/A |  | 1/29/2013 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W2-008 | Tiltonsville-Windsor 138kV |  | OH | Jefferson | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/18/2010 | N/A | N/A |  | 4/12/2012 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W2-009 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 18 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/19/2010 | N/A | N/A |  | 12/22/2010 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W2-010 | Conemaugh Unit 1 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-011 | Conemaugh Unit 2 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 870 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2011_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_011_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2010 | N/A | N/A |  |  |  | 6/30/2013 |  | 7/9/2012 | N | No
W2-013 | Branchburg-Elroy 500kV |  | NJ | Unknown | Withdrawn | PSEG | 33 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w2013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/24/2010 | N/A | N/A |  | 7/21/2014 | Customer Milestone Not Met | 6/1/2012 |  |  | S | No
W2-014 | Richmond |  | PA | Philadelphia | In Service | PECO | 98 | 2 | 2 | 2 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 11/25/2010 |  | 6/24/2014 | N | No
W2-015 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W2-016 | Frenchtown 34.5kV | Barbertown-Point Breeze Solar Farm | NJ | Hunterdon | In Service | JCPL | 15 | 15 | 5.7 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2016_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/25/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 12/31/2013 | N | No
W2-017 | Pennsville Township |  | NJ | Salem | Withdrawn | AEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 6/16/2010 |  | 6/1/2012 |  |  | N | No
W2-018 | Cumberland County Landfill | Cumberland County Landfill | PA | Cumberland | In Service | PENELEC | 11.2 | 4.8 | 4.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 4/22/2012 | N | No
W2-019 | Wrightstown 34.5kV | Shemesh Solar Farm | NJ | Burlington | In Service | JCPL | 6 | 6 | 2.3 | 4.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_019_csa.pdf | Document Posted | N/A | N/A | 9/22/2016 | 5/28/2010 | N/A | N/A | 10/1/2016 |  |  | 9/30/2016 | 9/30/2016 | 10/24/2016 | N | No
W2-020 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2020_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2020_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
W2-021 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2021_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/30/2011 | 8/30/2011 |  | N | No
W2-022 | Pantego 115kV | Pantego Wind Farm | NC | Hyde | Withdrawn | Dominion | 73.6 | 73.6 | 9.57 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_022_csa.pdf | Document Posted | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/22/2016 | Customer Initiated Withdrawal | 10/15/2018 | 10/15/2018 |  | N | No
W2-023 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | 625 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2023_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 2/24/2015 | Customer Initiated Withdrawal | 5/31/2017 | 5/31/2017 |  | N | No
W2-024 | Kearny 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | 625 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 5/31/2014 |  |  | N | No
W2-025 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 11/23/2010 | Customer Initiated Withdrawal | 9/30/2011 |  |  | N | No
W2-026 | Glassboro Road | Suncatcher Clean Energy | NJ | Gloucester | Withdrawn | AEC | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2026_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2026_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2026_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 5/14/2013 | Customer Milestone Not Met | 4/30/2013 | 4/30/2013 |  | N | No
W2-027 | Terrace 12kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2027_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/28/2010 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 9/30/2011 | 9/30/2011 |  | N | No
W2-028 | Limerick #1 |  | PA | Montgomery | Active | PECO | 1218 | 5 | 5 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2028_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 6/1/2010 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 |  | N | No
W2-029 | Limerick #2 |  | PA | Montgomery | Active | PECO | 1218 | 5 | 5 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2029_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 6/1/2010 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 |  | N | No
W2-030 | Egg Harbor Township | 1307 Doughty Road | NJ | Atlantic | In Service | AEC | 9.6 | 9.6 | 3.65 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2030_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/3/2010 | N/A | N/A |  |  |  | 9/30/2016 | 9/30/2016 | 10/4/2016 | N | No
W2-031 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 8.5 | 8.5 | 3.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2031_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_031_csa.pdf | Document Posted | N/A | N/A |  | 6/10/2010 | N/A | N/A |  | 9/13/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W2-032 | Stow Creek Township |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2010 | N/A | N/A |  | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-033 1457548 | OVEC-PJM-MECS |  | N/A | N/A | Confirmed | FirstEnergy Solutions Corp. | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1457548_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1457548_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 6/14/2010 | 9/1/2010 | 9/1/2015 | [6 empty] | FF | No
W2-034 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2010 | N/A | N/A |  | 2/2/2011 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-035 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 16 | 16 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2010 | N/A | N/A |  | 2/3/2014 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-036 | Polhemus Lane 13kV | Central SP | NJ | Somerset | In Service | PSEG | 0.7 | 0.749 | 0.284 | 0.749 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2036_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2036_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/18/2010 | N/A | N/A |  |  |  | 3/21/2010 | 3/21/2010 | 3/21/2011 | N | No
W2-037 | Cookstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 7 | 7 | 2.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
W2-038 | East Frankfort-Crete | Powerton – Joliet SPS | IL | Will | In Service | ComEd | 800 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2038_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w2_038_csa.pdf | Document Posted | N/A | N/A |  | 6/22/2010 | N/A | N/A |  |  |  | 10/1/2011 | 10/1/2011 | 10/5/2011 | S | No
W2-039 | Clayville 69kV | Clayville Unit #1 | NJ | Cumberland | In Service | AEC | 63 | 63 | 63 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2039_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2039_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_039_csa.pdf | Document Posted | N/A | N/A |  | 6/28/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 11/1/2015 | N | No
W2-040 | Camden 69kV | Preble Solar Energy | OH | Preble | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_040_csa.pdf | Document Posted | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 1/23/2020 |  | 6/1/2018 | 6/1/2018 |  | N | No
W2-041 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2.6 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 8/2/2010 | Customer Initiated Withdrawal | 3/1/2011 |  |  | N | No
W2-042 | Dennis Township |  | NJ | Cape May | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 6/30/2011 |  |  | N | No
W2-043 | Albright-Snowy Creek 138kV |  | WV | Preston | Withdrawn | APS | 101 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w2043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 1/17/2012 | Customer Milestone Not Met | 4/1/2011 |  |  | S | No
W2-044 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 100.5 | 100.5 | 13.06 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 1/5/2011 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
W2-046 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 450 | 450 | 58.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 12/7/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W2-047 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 7.5 | 7.5 | 2.85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2047_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/30/2010 | N/A | N/A |  | 5/15/2014 | Customer Initiated Withdrawal | 8/31/2011 |  |  | N | No
W2-048 | Brokaw-Lanesville | Hilltopper Wind, LLC | IL | Logan | In Service | ComEd | 62.5 | 62.5 | 0 | 62.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_048_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
W2-049 | Reedy Creek 115kV | South Boston Energy Facility | VA | Halifax | In Service | Dominion | 47.4 | 47.4 | 47.4 | 47.4 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2049_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2049_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w2_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_049_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2010 | N/A | N/A |  |  |  | 5/30/2013 |  | 9/24/2013 | N | No
W2-050 | Flemington | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_050_csa.pdf | Document Posted | N/A | N/A | 4/1/2016 | 7/13/2010 | N/A | N/A |  |  |  | 4/1/2016 | 4/1/2016 | 3/22/2016 | N | No
W2-051 | Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 2 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2051_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/13/2010 | N/A | N/A |  | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-052 | Pierson Avenue 13kV |  | NJ | Middlesex | In Service | PSEG | 0.6 | 0.592 | 0.225 | 0.592 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2052_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2052_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/19/2010 | N/A | N/A |  |  |  | 3/14/2011 | 3/14/2011 | 3/14/2011 | N | No
W2-053 | West Waynesboro 34.5kV I |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W2-054 | West Waynesboro II 34.5kV II |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W2-056 | Lumberton 13kV | Reeves Station Road Solar | NJ | Burlington | In Service | PSEG | 11 | 11 | 4.18 | 11 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2056_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2056_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2010 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 10/16/2012 | N | No
W2-057 | Laurel Mountain | Laurel Mountain BT | WV | Barbour | In Service | APS | 125 | 27.4 | 0 | 27.4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2010 | N/A | N/A |  |  |  | 7/30/2011 | 7/30/2011 | 9/21/2011 | N | No
W2-058 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2058_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 1/5/2011 | Customer Milestone Not Met | 2/28/2012 | 2/28/2012 |  | N | No
W2-059 | Strasburg 12kV | Sight & Sound Theaters | PA | Lancaster | Withdrawn | PPL | 2.4 | 2.4 | 1 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 8/27/2012 | CIW | 12/31/2012 | 12/31/2012 |  | N | No
W2-060 | Burlington 26kV | Florence solar | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2060_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2060_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 5/30/2013 | Customer Initiated Withdrawal | 2/28/2014 | 2/28/2014 |  | N | No
W2-061 | Ringoes 12kV | Everitt Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2061_wmpa.pdf |  | Not Required | N/A | N/A | 5/23/2016 | 7/29/2010 | N/A | N/A | 5/23/2016 |  |  | 1/18/2017 | 1/18/2017 | 6/1/2016 | N | No
W2-062 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.1 | 12.1 | 12.1 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2010 | N/A | N/A |  | 8/30/2010 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W2-063 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 70 | 70 | 70 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/11/2013 | Customer Initiated Withdrawal | 3/31/2014 | 3/31/2014 |  | N | No
W2-064 | Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2064_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/24/2012 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-065 | Woodstown Road 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/1/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W2-067 | Amsterdam 138kV |  | OH | Darke | Withdrawn | Dayton | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-068 | Bluff Point 138kV |  | OH | Mercer | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2068_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-069 | Fishburn/Tanney 46kV |  | PA | Centre | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2069_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/4/2011 | Customer Initiated Withdrawal | 12/1/2012 | 12/1/2012 |  | N | No
W2-070 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2070_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/2/2010 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W2-071 | Mt. Laurel 13kV |  | NJ | Burlington | In Service | PSEG | 2.8 | 2.8 | 1.06 | 2.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2071_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 10/31/2011 | 10/31/2011 | 12/15/2011 | N | No
W2-072 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2072_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W2-073 | New Canton 12kV | Ward's Nursery Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2073_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/17/2017 | Customer Initiated Withdrawal | 9/30/2017 | 9/30/2017 |  | N | No
W2-074 | Bennett 12kV | Hurley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2074_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2014 |  | 6/30/2014 | 6/30/2014 |  | N | No
W2-075 | Tolna Unit 2 | Tolna Unit 2 | PA | York | In Service | ME | 20 | 0.9 | 0.9 | 0 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2075_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 8/31/2010 |  | 7/28/2011 | N | No
W2-076 | Rocktown 4.8kV | West Amwell Mason Supply Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2076_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/15/2016 |  | 5/30/2017 | 5/30/2017 |  | N | No
W2-077 | Wrightstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 2.1 | 2.06 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/8/2010 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W2-078 | Applegarth 12.5kV | Northpark Solar Farm #2 | NJ | Monmouth | In Service | JCPL | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 3/22/2016 | N | No
W2-079 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 19.4 | 7.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/30/2013 | Customer Milestone Not Met | 3/31/2011 |  |  | N | No
W2-080 | Stanton 12kV | Fisher Solar Farm | NJ | Hunterdon | In Service | JCPL | 2 | 2 | 0.8 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2080_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/25/2017 | 6/25/2017 | 5/30/2017 | N | No
W2-081 | Port Carbon 12kV |  | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2081_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 2/22/2011 |  |  | N | No
W2-082 | Fort Dix-McGuire 34.5kV | North Hanover Solar Farm | NJ | Burlington | In Service | JCPL | 8 | 17 | 3 | 8.25 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2082_wmpa.pdf |  | Not Required | N/A | N/A | 3/17/2017 | 7/30/2010 | N/A | N/A | 3/17/2017 |  |  | 1/17/2017 | 1/17/2017 | 3/17/2017 | N | No
W2-083 | Frenchtown-Rosemont 34.5kV | Perotti Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2083_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-084 | Branchville-Holiday Lakes 34.5kV | Roberts Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2084_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/19/2013 | Customer Milestone Not Met | 6/30/2014 | 6/30/2014 |  | N | No
W2-085 | Baptistown-Frenchtown 34.5kV | Gombasi Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2085_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 2/19/2013 | Customer Milestone Not Met | 6/30/2014 | 6/30/2014 |  | N | No
W2-086 | Baptistown-East Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2086_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 1/10/2011 |  |  | N | No
W2-087 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2087_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/16/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W2-088 | Gravel Hill-Smithburg 34.5kV | Freehold Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
W2-089 | Cookstown-Fort Dix 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 20 | 17 | 6.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2089_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 6/8/2011 | Customer Milestone Not Met | 1/6/2012 |  |  | N | No
W2-090 | Lumberton 230kV | Stacy Haines Road | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2090_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 1/19/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W2-091 | Broadway-Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 0 | 8 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2091_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2091_wmpa.pdf |  | Not Required | N/A | N/A | 5/20/2016 | 7/30/2010 | N/A | N/A | 5/20/2016 |  |  | 6/13/2016 | 6/13/2016 | 5/31/2016 | N | No
W2-092 | Hunterstown 115kV II |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2092_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-093 | Hunterstown 115kV III |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2093_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-094 | Lincoln 13.2kV | Lincoln Solar Farm | PA | Adams | Withdrawn | ME | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2094_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w2094_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 |  | N | No
W2-095 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/23/2011 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W2-096 | West Carlisle-Newville 1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2096_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2096_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-097 | West Carlisle-Newville 2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2097_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2097_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-098 | Hunterstown 115kV IV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2098_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2098_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 9/13/2012 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W2-099 | Kenney 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2099_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 5/4/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W2-100 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 11/19/2010 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W2-101 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2101_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w2101_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/30/2010 | N/A | N/A |  | 10/16/2014 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
W2-102 | Mt. Holly 26.4kV | West Pemberton Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w2102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w2102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w2_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w2_102_csa.pdf | Document Posted | N/A | N/A |  | 7/30/2010 | N/A | N/A |  |  |  | 6/30/2014 | 6/30/2014 | 7/3/2014 | N | No
W3-001 | Gilbert-Morris Park 34.5kV | Alpha Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/28/2010 | N/A | N/A |  | 9/28/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-002 | Occoquan 34.5kV |  | VA | Fairfax | Deactivated | Dominion | 6.4 | 6.4 | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3002_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w3_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2010 | N/A | N/A |  | 11/7/2019 |  | 4/1/2011 | 4/1/2011 | 4/1/2011 | N | No
W3-003 | East Flemington-Frenchtown 34.5kV | Quakertown Solar Farm #1 | NJ | Hunterdon | In Service | JCPL | 10 | 10 | 0 | 10 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2010 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 10/30/2018 | N | No
W3-004 | Ridgefield 13kV |  | NJ | Bergen | Withdrawn | PSEG | 1.3 | 1.261 | 0.479 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/3/2010 | N/A | N/A |  | 3/11/2011 | Customer Initiated Withdrawal | 1/15/2011 |  |  | N | No
W3-005 | Fostoria Central-Galion (FE) 345kV |  | OH | Huron | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3005_imp.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/3/2010 | N/A | N/A |  | 6/18/2014 | Customer Initiated Withdrawal | 11/30/2013 |  |  | N | No
W3-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 6 | 5 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3006_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/5/2010 | N/A | N/A |  | 3/7/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W3-007 | Reed 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-008 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-009 | Fairton |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2010 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-010 | Hans Meadow 12.47KV |  | VA | Montgomery | Withdrawn | AEP | 0.3 | 0.34 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3010_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 6/16/2011 | Customer Milestone Not Met | 8/1/2010 |  |  | Y | No
W3-011 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 9/2/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-012 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-013 | Miami |  | OH | Miami | Withdrawn | Dayton | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 3/16/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-014 | Galion-Fostoria Central 345kV |  | OH | Crawford | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-015 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3015_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 3/1/2011 |  |  | N | No
W3-016 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-017 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/21/2011 |  |  | N | No
W3-018 | Deepwater-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2010 | N/A | N/A |  | 8/23/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-019 | Fentress-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3019_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/20/2010 | N/A | N/A |  | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-021 | Jacksons Ferry-Peak Creek 138kV |  | VA | Pulaski | Withdrawn | AEP | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2010 | N/A | N/A |  | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
W3-021A | Corry East 115kV |  | PA | Crawford | Withdrawn | PENELEC | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3021a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3021a_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2010 | N/A | N/A |  | 10/1/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-022 | Frackville-Eldred #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_022_csa.pdf | Document Posted | N/A | N/A |  | 8/25/2010 | N/A | N/A |  | 3/25/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W3-023 | Frackville-Eldred #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2010 | N/A | N/A |  | 10/3/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W3-024 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 149.4 | 149.4 | 19.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3024_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2010 | N/A | N/A |  | 4/25/2013 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
W3-025 | Wrightstown 34.5kV | Saylors Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 2.1 | 2.06 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3025_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-026 | Burlington 13kV | 1900 River Road | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3026_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3026_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 7/23/2013 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
W3-027 | Meadowbrook 500kV |  | VA | Frederick | Withdrawn | APS | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w3027_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 12/9/2013 | Customer Initiated Withdrawal | 6/1/2011 |  |  | S | No
W3-028 | Cedar 230kV | New Jersey Offshore Wind Project | NJ | Atlantic | Withdrawn | AEC | 348 | 348 | 45 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_028_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2010 | N/A | N/A |  | 5/12/2016 | Customer Initiated Withdrawal | 1/1/2019 | 1/1/2019 |  | N | No
W3-029 | Buckeye-Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.4 | 8.4 | 3.2 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3029_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/4/2018 | N | No
W3-030 | Southampton 13kV | 1626 Route 70 | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3030_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 3/7/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W3-031 | Medford 69kV |  | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 10/27/2010 | Customer Initiated Withdrawal | 2/6/2012 |  |  | N | No
W3-032 | Stewartsville-West Portal 34.5kV | New Village Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3032_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/30/2010 | N/A | N/A |  | 12/24/2013 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-032A | Cartanza 230kV | Garrison Energy Center | DE | New Castle | In Service | DPL | 309.2 | 309.2 | 309.2 | 309.2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3032a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3032a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3032a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_032a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_032a_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 5/21/2015 | N | No
W3-033 | Egg Harbor Township 1 |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3033_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/1/2014 | Customer Initiated Withdrawal | 3/31/2018 | 3/31/2018 |  | N | No
W3-034 | Egg Harbor Township 2 |  | NJ | Atlantic | Withdrawn | AEC | 10 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3034_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 8/10/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-035 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 7 | 7 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/23/2011 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
W3-036 | Pemberton 12kV |  | MD | Wicomico | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 3/2/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-037 | Delmar 12kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-038 | Lumberton 13kV | Trotter Property | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3038_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/9/2012 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
W3-039 | Bayonne 26kV |  | NJ | Hudson | Withdrawn | PSEG | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3039_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 6/3/2013 | Customer Initiated Withdrawal | 10/10/2012 | 10/10/2012 |  | N | No
W3-040 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 3.8 | 3.8 | 3.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3040_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 4/22/2011 | Customer Milestone Not Met | 1/30/2012 |  |  | N | No
W3-041 | Burlington 26kV | Springfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3041_wmpa.pdf |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/2/2013 | Customer Milestone Not Met | 7/1/2012 | 7/1/2012 |  | N | No
W3-042 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-043 | Pendleton 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 11/30/2017 |  |  | N | No
W3-044 | Washington 34.5kV | McCullough Road Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 8.8 | 3.34 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3044_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3044_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A | 6/27/2019 |  |  | 6/30/2019 | 6/30/2019 | 6/27/2019 | N | No
W3-045 | Fairfield 12kV | Fairfield at Howell Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3045_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 10/28/2016 |  | 9/1/2014 | 9/1/2014 |  | N | No
W3-046 | Powerton 345kV |  | IL | Mason | Withdrawn | ComEd | 207.5 | 207.5 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3046_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/17/2018 |  | 12/31/2015 | 12/31/2015 |  | N | No
W3-047 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 1464 | 39 | 60 | 39 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_047_csa.pdf | Document Posted | N/A | N/A | 11/15/2013 | 8/31/2010 | N/A | N/A | 8/11/2014 |  |  | 9/30/2015 | 9/30/2015 | 10/30/2014 | N | No
W3-048 | Hope Creek 500kV | Hope Creek Generating Station | NJ | Salem | In Service | PSEG | 1275 | 50 | 50 | 50 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3048_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2010 | N/A | N/A |  |  |  | 6/1/2012 |  | 1/23/2013 | N | No
W3-049 | Carneys Point 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/23/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W3-050 | Kelford 34.5kV |  | NC | Bertie | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3050_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 12/14/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W3-051 | Dorton 138kV |  | KY | Pike | Withdrawn | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 9/30/2013 |  |  | N | No
W3-052 | Tazewell-Kendall 345kV |  | IL | Woodford | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-053 | Trowbridge 230kV |  | NC | Washington | Withdrawn | Dominion | 260 | 260 | 33.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 2/25/2011 | Customer Initiated Withdrawal | 9/30/2013 |  |  | N | No
W3-054 | Mackeys-Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3054_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3054_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 5/28/2012 | Customer Initiated Withdrawal | 9/30/2013 |  |  | N | No
W3-054A | Oak Hall 138kV |  | VA | Accomack | Withdrawn | ODEC | 95 | 95 | 12.35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3054a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3054a_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2010 | N/A | N/A |  | 1/22/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W3-055 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3055_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 9/7/2011 | Customer Initiated Withdrawal | 11/30/2011 |  |  | N | No
W3-056 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3056_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 3/1/2013 | 3/1/2013 |  | N | No
W3-057 | Lumberton 69kV | Warfield II | NJ | Burlington | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3057_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/1/2010 | N/A | N/A |  | 1/5/2016 | Customer Initiated Withdrawal | 10/1/2015 | 10/1/2015 |  | N | No
W3-058 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-059 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3059_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-059A_AT6 | Avery-Greenfield 138kV |  | OH | Erie | Withdrawn | ATSI | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3059a_at6_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3059a_at6_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3059a_at6_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 11/7/2014 | Customer Initiated Withdrawal | 9/9/2017 | 9/9/2017 |  | N | No
W3-059B_AT7 | Allen Junction-Lyons 138kV |  | OH | Fulton | Withdrawn | ATSI | 97.6 | 97.6 | 12.69 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3059b_at7_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 2/2/2012 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
W3-059C_AT8 | Allen Junction 138kV |  | OH | Fulton | Withdrawn | ATSI | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3059c_at8_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2010 | N/A | N/A |  | 6/15/2011 | Customer Initiated Withdrawal | 12/31/2010 |  |  | N | No
W3-060 | Kendallville 138kV |  | IN | Noble | Withdrawn | AEP | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3060_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2010 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 11/1/2012 |  |  | N | No
W3-061 | Church 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2010 | N/A | N/A |  | 2/28/2011 | Customer Initiated Withdrawal | 5/31/2011 |  |  | N | No
W3-062 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2010 | N/A | N/A | [6 empty] | S | No
W3-063 | South Fultonham 4kV | Zanesville Energy | OH | Muskingum | Deactivated | AEP | 0.9 | 0.85 | 0 | 0.85 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3063_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/17/2010 | N/A | N/A |  | 9/8/2018 |  | 5/31/2011 | 5/31/2011 | 5/31/2011 | N | No
W3-064 | Hunterstown 115kV V |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-065 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/w3065_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2010 | N/A | N/A |  | 4/4/2013 |  |  |  |  | EE | No
W3-066 | Shawboro 230kV | Hales Lake Energy Center | NC | Camden | Withdrawn | Dominion | 300 | 300 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3066_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3066_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_066_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2010 | N/A | N/A |  | 8/1/2016 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
W3-067 | Gardners-Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2010 | N/A | N/A |  | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-068 | Cumberland-W. Shore 3 #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2010 | N/A | N/A |  | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-069 | Cumberland-W. Shore 3 #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2010 | N/A | N/A |  | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-070 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 52 | 52 | 50 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3070_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2010 | N/A | N/A |  | 3/25/2013 | Customer Initiated Withdrawal | 10/31/2013 |  |  | N | No
W3-071 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 12.5 | 12.54 | 4.77 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3071_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 3/21/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-072 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3072_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W3-073 | West Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 8/12/2011 | Customer Milestone Not Met | 3/1/2011 |  |  | N | No
W3-075 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 8/12/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
W3-076 | Morris Park-Stewartsville 34.5kV | South Main Street Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3076_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W3-077 | Broadway-Stewartsville 34.5kV | Franklin Township Solar Farm | NJ | Warren | In Service | JCPL | 15 | 15 | 5.7 | 8.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3077_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A | 12/4/2019 |  |  | 1/31/2020 | 1/31/2020 | 1/10/2020 | N | No
W3-078 | Twin Rivers-Windsor 34.5kV | East Windsor Solar Farm | NJ | Mercer | Withdrawn | JCPL | 13 | 13 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3078_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3078_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 10/21/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-079 | Allenwood-Larabee 34.5kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 7 | 2.6 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3079_wmpa.pdf |  | Not Required | N/A | N/A | 3/11/2016 | 9/30/2010 | N/A | N/A |  |  |  | 10/6/2016 | 10/6/2016 | 4/19/2016 | N | No
W3-080 | Burlington 26kV | Cedar Lane | NJ | Burlington | In Service | PSEG | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3080_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2010 | N/A | N/A |  |  |  | 11/15/2016 | 11/15/2016 | 12/29/2016 | N | No
W3-081 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3081_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 7/26/2011 | Customer Milestone Not Met | 2/15/2012 |  |  | N | No
W3-082 | Woodbine Township |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3082_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2010 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-083 1650070 | AMIL-PJM |  | N/A | N/A | Confirmed | Ameren Energy Marketing Company | 84 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1650070_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1650070_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/8/2010 | 10/1/2011 | 10/1/2016 | [6 empty] | FF | No
W3-084 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16.6 | 16.6 | 6.31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2010 | N/A | N/A |  | 12/3/2010 | Customer Initiated Withdrawal | 12/1/2011 |  |  | N | No
W3-085 | Chatfield-South Tiffin 138kV |  | OH | Crawford | Withdrawn | AEP | 185 | 185 | 24 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2010 | N/A | N/A |  | 5/7/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W3-086 | Townsend 138kV |  | DE | New Castle | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-087 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2010 | N/A | N/A |  | 3/15/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-088 | South West Lima 345kV | Long Prairie Wind I, LLC | OH | Van Wert | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_088_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 10/28/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
W3-089 | Carneys Point 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W3-090 | Carneys Point 12kV 1 |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-092 | Carneys Point 12kV 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2010 | N/A | N/A |  | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-093 | Lyon Station |  | PA | Berks | Withdrawn | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3093_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/25/2010 | N/A | N/A |  | 3/5/2012 | Customer Initiated Withdrawal | 10/1/2011 |  |  | N | No
W3-095 | Broadway-Stewartsville#2 34.5kV | Stewartsville Solar Farm | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3095_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 9/18/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-096 | Perkiomen |  | PA | Montgomery | Withdrawn | PECO | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W3-097 | Russelville OH |  | OH | Brown | Withdrawn | AEP | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 10/10/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
W3-098 | Hillsboro-Kenton (KU) 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2010 | N/A | N/A |  | 10/24/2011 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
W3-099 | Erie East-Erie South 230 kV | Greenfield Wind Farm | PA | Erie | Withdrawn | PENELEC | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3099_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3099_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_099_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2010 | N/A | N/A |  | 9/10/2018 |  | 12/31/2019 | 12/31/2019 |  | N | No
W3-100 | Daretown Road 12kV |  | NJ | Salem | Withdrawn | AEC | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 3/3/2011 | Customer Initiated Withdrawal | 6/30/2012 |  |  | N | No
W3-101 | East Elmer Road 12kV | Elmer Road | NJ | Cumberland | Withdrawn | AEC | 3.2 | 3.2 | 1.21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3101_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3101_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 9/15/2012 |  |  | N | No
W3-102 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3102_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2010 | N/A | N/A |  | 5/19/2011 | Customer Initiated Withdrawal | 5/30/2011 |  |  | N | No
W3-103 | Upper Deerfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3103_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/16/2011 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
W3-104 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3104_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-105 | Dickerson 230kV | Dickerson CT1 (D-CT1) | MD | Montgomery | In Service | PEPCO | 18 | 5 | 5 | 5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3105_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w3_105_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 8/23/2011 | N | No
W3-106 | Sussex-Wykertown 34.5kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 9.9 | 0 | 9.9 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3106_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3106_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3106_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
W3-107 | Ringoes-Texas Eastern 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3107_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3107_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-108 | Ringoes #2 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3108_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3108_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/21/2011 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-109 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 0.6 | 0.625 | 0.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3109_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/3/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-110 | Sussex | Wantage Solar Farm | NJ | Sussex | In Service | JCPL | 7.5 | 7.5 | 2.85 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3110_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3110_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/15/2013 | N | No
W3-111 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3111_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3111_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_111_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_111_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2017 | 4/16/2017 |  | N | No
W3-112 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 35 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3112_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3112_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_112_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2018 | 4/16/2018 |  | N | No
W3-113 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 49.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3113_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3113_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_113_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2018 |  | 4/16/2019 | 4/16/2019 |  | N | No
W3-113A 1685913 | PJM-TVA |  | N/A | N/A | Retracted | NextEra | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1685913_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/29/2010 | 1/1/2012 | 1/1/2017 |  | 2/9/2011 |  |  |  |  | FF | No
W3-114 | Venango I |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3114_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-115 | Venango II |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-116 | Venango III |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-117 | Clarion |  | PA | Clarion | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-118 | Venango IV |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-119 | Venango V |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/17/2010 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W3-120 | Cookstown-Great Adventure 34.5kV | Polizzi Solar Farm | NJ | Ocean | Withdrawn | JCPL | 17 | 17 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3120_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3120_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/16/2014 |  | 12/31/2014 | 12/31/2014 |  | N | No
W3-121 | Queen Anne County 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3121_fea.pdf | Document Posted |  | Withdrawn |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W3-122 | Brandon Shores-Riverside 230kV |  | MD | Unknown | Withdrawn | BGE | 236 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3122_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/w3122_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w3_122_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 12/1/2014 | 12/1/2014 |  | S | No
W3-123 | Brandon Shores |  | MD | Unknown | Withdrawn | BGE |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/w3123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/w3123_imp2.pdf | Interim Study |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/w3_123_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/20/2013 | Customer Initiated Withdrawal | 7/26/2011 | 7/26/2011 | 2/29/2012 | S | No
W3-124 | Devils Brook 13kV | Matrix-Stults Road | NJ | Middlesex | In Service | PSEG | 2.9 | 2.85 | 1.08 | 2.85 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3124_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3124_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 6/30/2011 | 6/30/2011 | 6/17/2011 | N | No
W3-125 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 195 | 27.9 | 27.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/8/2011 | Customer Milestone Not Met | 6/1/2011 |  |  | N | No
W3-126 | Branchville-Holiday Lakes 34.5kV | Syncarpha Ty Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3126_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3126_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/3/2014 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-127 | City of Columbus 14.4kV |  | OH | Franklin | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3127_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/3/2012 | Customer Initiated Withdrawal | 12/1/2010 |  |  | N | No
W3-128 | Sporn-Waterford 345kV |  | OH | Meigs | Withdrawn | AEP | 652 | 652 | 652 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/22/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
W3-129 | Beaver Brook 13kV | Blackwood Solar | NJ | Camden | Withdrawn | PSEG | 7.3 | 7.3 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3129_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3129_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W3-130 | Crosswicks 13kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 8.3 | 8.3 | 3.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3130_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3130_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 6/30/2012 | 6/30/2012 |  | N | No
W3-131 | Alpha #2 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 7.6 | 7.6 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/21/2010 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
W3-132 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 19.4 | 7.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3132_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/30/2013 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-133 | Kewanee |  | IL | Stark | Withdrawn | ComEd | 19.5 | 19.5 | 2.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/15/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-134 | South Joliet 34.5kV | Brandon Road Lock & Dam | IL | Will | Under Construction | ComEd | 10.6 | 10.6 | 10.6 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3134_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3134_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A | 10/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
W3-135 | Goose Lake 34.5kV | Dresden Island Lock & Dam | IL | Grundy | Under Construction | ComEd | 12.1 | 12.1 | 12.1 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3135_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3135_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A | 10/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
W3-136 | Andover-Kittatinny #2 34.5kV | Hibler Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3136_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3136_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-137 | Furnace Brook 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3137_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/25/2011 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
W3-138 | Blairstown-Kittatinny 34.5kV | Stillwater Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3138_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3138_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2012 | 9/1/2012 |  | N | No
W3-139 | Broadway-Stewartsville #3 34.5kV | Broadway Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3139_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 1/17/2018 | Customer Initiated Withdrawal | 5/31/2017 | 5/31/2017 |  | N | No
W3-140 | Sussex #2 | Roy Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3140_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3140_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-141 | Knowlton #1 12kV |  | NJ | Warren | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3141_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
W3-142 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 18 | 18 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3142_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/25/2011 | Customer Initiated Withdrawal | 3/31/2012 |  |  | N | No
W3-143 | Knowlton #2 |  | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/3/2012 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-144 | Pequest-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3144_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/11/2012 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
W3-145 | Branchville-Newton 34.5kV | Hampton Township Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3145_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-146 | Andover-Kittatinny 34.5kV | Kerrs Corner Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3146_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3146_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/15/2014 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-147 | Baptistown-Frenchtown #2 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3147_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/30/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
W3-148 | Baptistown 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6 | 6 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3148_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/25/2011 | Customer Milestone Not Met | 11/15/2011 |  |  | N | No
W3-149 | Frenchtown-Rosemont 34.5kV | Route 519 Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3149_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3149_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W3-150 | Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3150_fea.pdf | Document Posted |  | Withdrawn |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 3/15/2012 |  |  | N | No
W3-151 | Phillipsburg 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 16 | 16 | 6.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3151_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/16/2011 | Customer Milestone Not Met | 3/15/2012 |  |  | N | No
W3-152 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3152_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/21/2011 | Customer Milestone Not Met | 4/1/2011 |  |  | N | No
W3-153 | Heaton 34kV |  | PA | Montgomery | Withdrawn | PECO | 2.6 | 2.6 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3153_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/2/2011 | Customer Milestone Not Met | 6/4/2011 |  |  | N | No
W3-154 | Broadway 12kV | Schanzlin Solar Farm | NJ | Warren | Withdrawn | JCPL | 1.6 | 1.6 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3154_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 9/1/2014 | 9/1/2014 |  | N | No
W3-155 | Alabama 13.8kV |  | DC | N/A | Withdrawn | PEPCO | 20 | 20 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3155_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2013 | Customer Milestone Not Met | 2/28/2014 |  |  | N | No
W3-156 | Englishtown-Texas Road 34.5kV | Swayles Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3156_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3156_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
W3-157 | Stow Creek Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.7 | 1.7 | 0.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3157_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-158 | Great Adventure-Great Adventure Tap 34kV | Millstone Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3158_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3158_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W3-159 | Hornerstown-Windsor 34kV | Monmouth West Solar I | NJ | Monmouth | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3159_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3159_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 5/5/2016 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
W3-160 | Worcester 25kV | Worcester Solar Facility | MD | Worcester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3160_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3160_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 9/24/2015 | Customer Initiated Withdrawal | 10/31/2017 | 10/31/2017 |  | N | No
W3-161 | Kanawha River 138kV |  | WV | Fayette | Withdrawn | AEP | 13 | 13 | 13 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3161_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/16/2012 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W3-162 | Baker 345kV | Riverside Generating Stations | KY | Lawrence | In Service | AEP | 993 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3162_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w3_162_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  |  |  | 2/8/2010 | 2/8/2010 | 9/9/2011 | N | No
W3-163 | Upper Pittsgrove 138kV 1 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3163_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-164 | Upper Pittsgrove 138kV 2 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3164_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-165 | Upper Pittsgrove 138kV 3 |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3165_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 8/15/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-166 | Nottingham I |  | PA | Chester | Withdrawn | PECO | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3166_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/22/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W3-167 | Nottingham II |  | PA | Chester | Withdrawn | PPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3167_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 7/26/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W3-168 | Germantown 13.2 kV |  | PA | Adams | Withdrawn | ME | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3168_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-169 | North Hanover 12.5kV |  | PA | Adams | Withdrawn | ME | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3169_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W3-170 | Buckskin 69kV |  | OH | Putnam | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3170_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3170_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 11/12/2014 | Customer Milestone Not Met | 9/30/2015 | 9/30/2015 |  | N | No
W3-171 | Levittown 13kV | Rancocas Road Solar Project | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w3171_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/10/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W3-172 | Hay Road 230kV 1 |  | DE | New Castle | Withdrawn | DPL | 402 | 402 | 402 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3172_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
W3-173 | Hay Road 230kV 2 |  | DE | New Castle | Withdrawn | DPL | 218 | 218 | 218 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3173_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
W3-174 | Churchtown 230kV 1 |  | NJ | Salem | Withdrawn | AEC | 193.5 | 193.5 | 193.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3174_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 4/15/2013 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
W3-175 | Churchtown 230kV 2 | Deepwater | NJ | Salem | Withdrawn | AEC | 371 | 371 | 371 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w3175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w3175_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w3175_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w3_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w3_175_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2010 | N/A | N/A |  | 2/7/2019 |  | 12/1/2021 | 12/1/2021 |  | N | No
W4-001 | Clover |  | VA | Halifax | Withdrawn | Dominion | 7 | 7 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2010 | N/A | N/A |  | 1/20/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-001A_AT9 | Lowellville 69kV | Carbon Limestone Landfil Gas to Electricity Facility | OH | Mahoning | In Service | ATSI | 24 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4001a_at9_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4001a_at9_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_001a_at9_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2010 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 9/19/2012 | N | No
W4-003 | Marengo-Pleasant Valley |  | IL | McHenry | Withdrawn | ComEd | 164 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2010 | N/A | N/A |  | 11/28/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
W4-004 | Madison-Tanners Creek 138kV | Flat Rock-WF-1 | IN | Henry | Withdrawn | AEP | 90 | 90 | 11.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4004_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4004_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/W4_004_csa.pdf | Document Posted | N/A | N/A |  | 11/10/2010 | N/A | N/A |  | 10/22/2018 |  | 7/1/2021 | 7/1/2021 |  | N | No
W4-004A_AT10 | Oberlin Road 69kV | Lorain | OH | Lorain | In Service | ATSI | 19.2 | 19.2 | 19.2 | 19.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4004a_at10_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4004a_at10_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4004a_at10_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/12/2010 | N/A | N/A |  |  |  | 9/1/2012 | 9/1/2012 | 5/31/2012 | N | No
W4-004B_AT11 | Perry 345kV | Perry Nuclear Power Plant | OH | Lake | In Service | ATSI | 1297.8 | 16 | 16 | 16 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4004b_at11_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4004b_at11_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_004B_at11_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/15/2010 | N/A | N/A | [5 empty] | 4/26/2013 | N | No
W4-005 | Blue Mound-Latham | Radford's Run Wind Farm | IL | Macon | Partially in Service - Under Construction | ComEd | 351 | 351 | 45.6 | 306 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4005_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4005_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/17/2010 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 12/14/2017 | N | No
W4-006 | S. Hicksville-Lockwood Road 138kV |  | OH | Defiance | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2010 | N/A | N/A |  | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-007 | Afton 138kV |  | WV | Preston | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2010 | N/A | N/A |  | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-008 | Madison-Tanners Creek 138kV | Flat Rock - WF-1 | IN | Henry | Withdrawn | AEP | 180 | 90 | 11.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4008_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4008_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_008_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_008_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  | 10/22/2018 |  | 7/1/2021 | 7/1/2021 |  | N | No
W4-009 | Raritan River 230kV | Woodbridge Energy Center | NJ | Middlesex | In Service | JCPL | 725 | 725 | 725 | 725 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4009_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_009_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_009_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
W4-010 | White Oak |  | MD | Montgomery | In Service | PEPCO | 53 | 29.1 | 0 | 29.1 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_010_csa.pdf | Document Posted | N/A | N/A |  | 11/22/2010 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 5/8/2014 | N | No
W4-011 | Larabee 34.5kV | Solar Wind Energy Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4011_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 2/22/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
W4-012 | Whetstone 115kV |  | PA | Elk | Withdrawn | PENELEC | 120 | 120 | 15.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4012_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-013 | Frack-Orwigsburg 69kV |  | PA | Schuylkill | Withdrawn | PPL | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4013_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2010 | N/A | N/A |  | 11/13/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-014 | Stewartsville-Captive Plastics 34.5kV | Stewartsville II Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4014_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4014_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 1/21/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-015 | Mickleton 230kV 1 | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 860 | 210 | 136 | 210 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/2010 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 1/16/2015 | N | No
W4-016 | Mickleton 230kV 2 | West Deptford Energy Station | NJ | Gloucester | Withdrawn | AEC | 1095 | 235 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4016_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4016_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_016_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_016_csa.pdf | Document Posted | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 11/20/2018 |  | 6/1/2019 | 6/1/2019 |  | N | No
W4-017 | Kings Creek-Crisfield 69kV |  | MD | Somerset | Withdrawn | DPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2010 | N/A | N/A |  | 11/27/2012 | Customer Initiated Withdrawal | 12/1/2013 |  |  | N | No
W4-018 | Monroeville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 3/15/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
W4-019 | Mendota |  | IL | Bureau | Withdrawn | ComEd | 40 | 40 | 9.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 1/30/2012 | Customer Initiated Withdrawal | 10/1/2012 |  |  | N | No
W4-020 | Mt. Zion 13.8kV |  | MD | Montgomery | Withdrawn | PEPCO | 10.1 | 10.08 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/18/2012 | Customer Milestone Not Met | 8/1/2011 |  |  | N | No
W4-021 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 738.4 | 738.4 | 738.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4021_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4021_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/11/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
W4-021A | Richland & Crawford |  | OH | Richland | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4021a_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2010 | N/A | N/A |  | 9/18/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
W4-022 | Hunterstown 230kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
W4-023 | Kearny 138kV |  | NJ | Hudson | Withdrawn | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 5/21/2012 |  | 5/31/2014 |  |  | N | No
W4-024 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2010 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
W4-025 | Cookstown-Fort Dix 34.5kV | North Run Solar | NJ | Burlington | In Service | JCPL | 7 | 7 | 2.6 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_025_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2010 | N/A | N/A |  |  |  | 5/29/2014 | 5/29/2014 | 2/4/2015 | N | No
W4-026 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2010 | N/A | N/A |  | 11/28/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W4-027 | Minotola 12kV | Minotola 2 Solar Facility | NJ | Atlantic | Withdrawn | AEC | 7.9 | 7.9 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4027_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4027_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/15/2010 | N/A | N/A |  | 5/20/2016 | Customer Initiated Withdrawal | 6/1/2018 | 6/1/2018 |  | N | No
W4-028 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2010 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 6/30/2011 |  |  | N | No
W4-029 | Medford 13kV | Reeve's Station North | NJ | Burlington | Withdrawn | PSEG | 2.4 | 2.4 | 0.91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4029_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/17/2010 | N/A | N/A |  | 10/31/2018 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-030 | Jessup |  | MD | Howard | Withdrawn | BGE | 0 | 0.008 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4030_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/20/2010 | N/A | N/A |  | 7/20/2012 | Customer Initiated Withdrawal | 3/1/2012 | 3/1/2012 |  | N | No
W4-031 | Perryville 12.5kV | Pattenburg Quarry Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2.6 | 2.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4031_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4031_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/22/2010 | N/A | N/A |  | 11/23/2015 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-032 | West Portal 4.8kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4032_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 4/4/2012 | Customer Initiated Withdrawal | 12/22/2011 |  |  | N | No
W4-033 | Wilmington | Lincoln Solar | IL | Will | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4033_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4033_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 12/8/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W4-034 | Essex 26.4kV |  | NJ | Essex | Withdrawn | PSEG | 3 | 3 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4034_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 9/1/2011 | Customer Milestone Not Met | 3/1/2011 |  |  | N | No
W4-035 | Martinsville |  | OH | Clinton | Withdrawn | Dayton | 20 | 20 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 12/12/2011 | Customer Initiated Withdrawal | 5/31/2012 |  |  | N | No
W4-036 | Buckskin 12kV | Ohio Solar I | OH | Ross | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4036_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4036_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/28/2010 | N/A | N/A |  | 1/2/2018 |  | 1/31/2019 | 1/31/2019 |  | N | No
W4-037 | Bismark 500kV | New Creek Mountain Energy Storage | WV | Grant | Withdrawn | Dominion | 160 | 32 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4037_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4037_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_037_csa.pdf | Document Posted | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 11/5/2018 |  | 12/31/2018 | 12/31/2018 | 12/26/2016 | N | No
W4-038 | Hudson 230kV | Hudson Generating Station | NJ | Hudson | Deactivated | PSEG | 677.5 | 24 | 24 | 12 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/30/2010 | N/A | N/A |  |  |  | 8/31/2018 | 8/31/2018 | 11/1/2012 | N | No
W4-039 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 6/22/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
W4-040 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 9.7 | 9.7 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 6/2/2014 | Customer Initiated Withdrawal | 5/13/2012 |  |  | N | No
W4-041 | Carlls Corner 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4041_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 1/31/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
W4-042 | McConnellsburg 34.5kV | Cove Creek Solar Project | PA | Fulton | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4042_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/30/2010 | N/A | N/A |  | 7/23/2013 | Customer Initiated Withdrawal | 12/15/2014 | 12/15/2014 |  | N | No
W4-043 | Roberts 34.5kV |  | OH | Marion | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2010 | N/A | N/A |  | 1/18/2011 |  | 9/1/2012 |  |  | N | No
W4-044 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 1450 | 725 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4044_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 1/5/2011 | N/A | N/A |  | 7/31/2013 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
W4-045 | Great Adventure-Great Adventure Tap 34.5kV | Red Valley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4045_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/11/2011 | N/A | N/A |  | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
W4-046 | Washington-Mobile Chemical 34.5kV | Hengst Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 3.8 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4046_wmpa.pdf |  | Not Required | N/A | N/A | 6/17/2016 | 1/11/2011 | N/A | N/A | 6/29/2016 |  |  | 11/28/2016 | 11/28/2016 | 7/13/2016 | N | No
W4-047 1855230 | PJM-LGEE |  | N/A | N/A | Withdrawn | Shell Energy North America (US), LP | 700 |  |  |  | Energy | Long-Term Firm Transmission | [7 empty] | Withdrawn |  |  |  | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2024 |  | 3/1/2011 |  |  |  |  | FF | No
W4-048 | Doremus Place 13kV |  | NJ | Essex | Withdrawn | PSEG | 1.1 | 1.05 | 0.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4048_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/18/2011 | N/A | N/A |  | 6/27/2011 | Customer Initiated Withdrawal | 6/30/2011 |  |  | N | No
W4-049 1878104 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1878104_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1878104_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
W4-050 1878108 | CPLE-PJM |  | N/A | N/A | Annulled | North Carolina Electric Membership | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1878108_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1878108_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
W4-051 | Packer 13kV |  | PA | Philadelphia | Withdrawn | PECO | 12 | 12 | 10.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4051_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2011 | N/A | N/A |  | 11/3/2011 | Customer Milestone Not Met | 9/1/2011 |  |  | N | No
W4-052 1885494 | TVA-PJM |  | N/A | N/A | Retracted | Magnolia Energy, LP | 900 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1885494_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/1885494_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2014 | [6 empty] | FF | No
W4-053 | Rocktown 4.8kV | Green Power West Amwell Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4053_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4053_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/24/2011 | N/A | N/A |  | 10/20/2015 |  | 12/31/2014 | 12/31/2014 |  | N | No
W4-054 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 12 | 12 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4054_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2011 | N/A | N/A |  | 5/24/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-054A 1893487 | EKPC-PJM |  | N/A | N/A | Retracted | American Municipal Power, Inc. | 42 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/1893487_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2014 |  | 4/21/2011 |  |  |  |  | FF | No
W4-055 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 12/13/2011 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
W4-056 | Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 4/15/2012 |  |  | N | No
W4-057 | Pittsgrove 2 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 4/15/2012 |  |  | N | No
W4-058 | Lawrence 13kV | Rider University | NJ | Mercer | In Service | PSEG | 0.7 | 0.702 | 0.267 | 0.702 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4058_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2011 | 12/31/2011 | 12/16/2011 | N | No
W4-059 | Kuller Road 13kV | Metro Division Headquarters | NJ | Passaic | In Service | PSEG | 0.6 | 0.6 | 0.228 | 0.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4059_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 6/30/2012 | 6/30/2012 | 7/5/2012 | N | No
W4-060 | Midland-Werner 34.5kV | Old Bridge Solar Farm | NJ | Middlesex | In Service | JCPL | 10 | 10 | 3.8 | 8.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4060_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4060_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 8/4/2018 | N | No
W4-061 | Lawrence 26kV |  | NJ | Mercer | Withdrawn | PSEG | 9 | 9 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4061_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/27/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | N | No
W4-062 | Tabernacle 69kV |  | NJ | Burlington | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W4-063 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 25 | 5 | 0.65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4063_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/w4063_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/w4_063_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_063_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 3/12/2019 |  | 1/27/2019 | 1/27/2019 |  | N | No
W4-064 | N. Newton 12kV | Augusta Solar Farm | NJ | Sussex | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4064_wmpa.pdf |  | Not Required | N/A | N/A | 5/10/2016 | 1/31/2011 | N/A | N/A | 5/13/2016 |  |  | 6/12/2016 | 6/12/2016 | 5/31/2016 | N | No
W4-065 | Sussex 12kV | Layton Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4065_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
W4-066 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4066_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-067 | Vernon 12kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
W4-068 | Hazen-Pequest River 34.5kV | White Township Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4068_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4068_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-069 | Lycoming |  | PA | Lycoming | Withdrawn | PPL | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 4/29/2011 | Customer Initiated Withdrawal | 4/1/2012 |  |  | N | No
W4-070 | Morgantown |  | PA | Berks | Withdrawn | PPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4070_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/27/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-071 | Garrett |  | PA | Somerset | Withdrawn | PENELEC | 2.3 | 2.25 | 0.29 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/17/2011 | Customer Milestone Not Met | 3/30/2012 |  |  | N | No
W4-072 | Englishtown-Rt. 33 Sw Point 34.5kV | Big Hill Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4072_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 10/23/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-073 | Phillipsburg 34.5kV | Hamptons at Pohatcong Solar Farm | NJ | Warren | In Service | JCPL | 8 | 8 | 3.04 | 8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4073_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A | 12/31/2019 |  |  | 12/31/2019 | 12/31/2019 | 1/10/2020 | N | No
W4-074 | Cox’s Corner 13kV | CleanLight Medford Solar Project | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4074_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 4/30/2012 | 4/30/2012 |  | N | No
W4-075 | Trenton 26kV | CleanLight Mansfield Solar Project | NJ | Burlington | Withdrawn | PSEG | 9 | 9 | 3.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4075_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/7/2012 |  | 6/30/2012 | 6/30/2012 |  | N | No
W4-076 | Ritchie |  | MD | Prince George's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4076_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/7/2011 | Customer Milestone Not Met | 11/1/2011 |  |  | N | No
W4-078 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
W4-079 | Lebanon |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4079_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/30/2012 | Customer Milestone Not Met | 10/31/2011 |  |  | N | No
W4-080 | Metuchen 26.4kV | IRL Landfill Solar Project | NJ | Middlesex | Withdrawn | PSEG | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4080_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/4/2016 |  | 11/30/2012 | 11/30/2012 |  | N | No
W4-081 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/2/2011 | Customer Milestone Not Met | 10/31/2011 |  |  | N | No
W4-082 | Libertyville 12kV | Countryside Landfill | IL | Lake | In Service | ComEd | 8 | 7.99 | 7.99 | 7.99 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 4/1/2001 |  | 7/16/2012 | N | No
W4-083 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4083_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-084 | Dixon 12kV | Dixon/Lee Landfill | IL | Lee | Deactivated | ComEd | 4 | 3.95 | 3.95 | 3.95 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/1/2001 |  | 4/16/2013 | N | No
W4-085 | Grays Ferry |  | PA | Philadelphia | Withdrawn | PECO | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4085_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/17/2014 | Customer Initiated Withdrawal | 5/15/2011 |  |  | N | No
W4-086 | Goose Lake 34.5kV | Morris Landfill | IL | Grundy | Deactivated | ComEd | 2.1 | 2.1 | 2.1 | 2.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4086_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_086_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 3/1/2001 |  | 5/16/2013 | N | No
W4-087 | South Holland |  | IL | Cook | Withdrawn | ComEd | 3.1 | 3.07 | 3.07 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 12/13/2012 | Customer Initiated Withdrawal | 4/1/1998 |  |  | N | No
W4-088 | Salem-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
W4-089 | Vineland #1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4089_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-090 | Vineland #2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.3 | 1.34 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
W4-091 | Andover-Kittatinny 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/1/2011 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
W4-092 | Englishtown 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 6/3/2011 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
W4-093 | Frenchtown 34.5kV | Dotoli Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 7 | 7 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4093_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4093_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
W4-094 | Millhurst-Raceway Mall 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 6 | 6 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 1/11/2012 | Customer Initiated Withdrawal | 3/15/2012 |  |  | N | No
W4-095 | Beckett 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5.2 | 5.2 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/29/2011 | Customer Milestone Not Met | 3/31/2013 |  |  | N | No
W4-096 | Piney Grove 25kV |  | MD | Wicomico | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/18/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
W4-097 | Hawks 12.5kV | Wetteland Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 3 | 1.1 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4097_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 1/6/2016 | N | No
W4-098 | U.S. Silica #1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4098_Imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 11/18/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
W4-099 | U.S. Silica #2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 2/22/2011 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
W4-100 | Exxon-NewYork Life 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4100_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 7/8/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-101 | Limecrest-Newton 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2011 | N/A | N/A |  | 7/6/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
W4-102 | Lappans 34.5kV | Lappans 34.5kV Project | MD | Washington | In Service | APS | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/w4_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/w4_102_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 11/29/2012 | N | No
W4-103 | Burlington 26kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 7 | 2.66 | 7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/w4103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/w4103_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/w4103_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2011 | N/A | N/A |  |  |  | 8/15/2016 | 8/15/2016 | 3/3/2016 | N | No
X1-001 | South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1001_fea.pdf | Document Posted |  | Withdrawn |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2011 | N/A | N/A |  | 10/4/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-003 | Belvidere |  | NJ | Warren | Withdrawn | JCPL | 1.9 | 1.9 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1003_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 4/27/2012 | Customer Milestone Not Met | 3/30/2012 |  |  | N | No
X1-004 | Asbury |  | NJ | Hunterdon | Withdrawn | JCPL | 9.7 | 9.7 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1004_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-005 | Port Murray | Meadows at Mansfield Solar Farm | NJ | Warren | Withdrawn | JCPL | 9.7 | 9.7 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1005_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1005_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 11/21/2013 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-006 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4.8 | 4.8 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1006_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-007 | Hackettstown |  | NJ | Burlington | Withdrawn | JCPL | 5.8 | 5.8 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-008 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 7.8 | 7.8 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 1/31/2012 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-009 | Sterling 69kV |  | OH | Allen | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1009_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2011 | N/A | N/A |  | 9/19/2011 | Customer Initiated Withdrawal | 12/1/2012 |  |  | N | No
X1-012 | Branchville-Sussex 34.5kV | Frankford Solar Farm | NJ | Sussex | In Service | JCPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1012_wmpa.pdf |  | Not Required | N/A | N/A | 3/2/2016 | 2/22/2011 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 3/3/2016 | N | No
X1-013 | N. Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 1018 | 1018 | 951 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1013_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2011 | N/A | N/A |  | 12/2/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
X1-014 | Peters Mountain 13kV |  | WV | Monroe | Withdrawn | AEP | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2011 | N/A | N/A |  | 9/19/2011 | Customer Milestone Not Met | 3/15/2013 |  |  | N | No
X1-015 | Kenney-Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 360 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x1015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x1015_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
X1-016 | Upper Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 9/16/2011 | Customer Milestone Not Met | 1/1/2013 |  |  | N | No
X1-017 | Cedar 230kV |  | NJ | Atlantic | Withdrawn | AEC | 720 | 720 | 93 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 2/7/2012 | Customer Initiated Withdrawal | 9/30/2016 |  |  | N | No
X1-018 | Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 75 | 75 | 9.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 1/10/2012 | Customer Milestone Not Met | 8/15/2013 |  |  | N | No
X1-019 | Sunbury-Dauphin 69kV |  | PA | Dauphin | Withdrawn | PPL | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 8/29/2011 | Customer Milestone Not Met | 8/15/2013 |  |  | N | No
X1-020 | Dumont-Greentown 765kV |  | IN | Cass | Withdrawn | AEP | 1500 | 1500 | 195 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 7/25/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
X1-021 | Deptford 13kV | Deptford Solar | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 10/27/2017 |  | 9/1/2017 | 9/1/2017 |  | N | No
X1-022 | Park Hall |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-023 | Mechanicsville |  | MD | St. Mary's | Withdrawn | PEPCO | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-024 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 9/21/2011 | Customer Milestone Not Met | 4/30/2012 |  |  | N | No
X1-025 | Leonardtowne |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2011 | N/A | N/A |  | 4/8/2011 | Queue Not Required | 4/30/2012 |  |  | N | No
X1-026 | Brick |  | NJ | Ocean | Withdrawn | JCPL | 6.3 | 6.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2011 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-027 | Hanging Rock 138kV |  | OH | Scioto | Withdrawn | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 6/30/2014 |  |  | N | No
X1-027A_AT12 | Davis Besse-Beaver 345kV | Emerson Creek Wind Farm | OH | Huron | Withdrawn | ATSI | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1027a_at12_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1027a_at12_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1027a_at12_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x1_027a_at12_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_027A_at12_csa.pdf | Document Posted | N/A | N/A |  | 3/3/2011 | N/A | N/A |  | 7/18/2018 |  | 4/1/2018 | 4/1/2018 |  | N | No
X1-028 | Upton 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2011 | N/A | N/A |  | 11/29/2011 | Customer Initiated Withdrawal | 11/30/2012 |  |  | N | No
X1-029 | Dorchester County |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2011 | N/A | N/A |  | 9/30/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-030 1998623 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 500 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2019 | [6 empty] | FF | No
X1-031 1998624 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 500 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2014 | 6/1/2019 |  | 4/20/2011 |  |  |  |  | FF | No
X1-032 | Costen 25kV | Somerset Solar Project | MD | Worcester | In Service | DPL | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1032_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1032_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/16/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/9/2013 | N | No
X1-033 | NCEC Sycamore 69/12.47kV |  | OH | Wyandot | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2011 | N/A | N/A |  | 11/27/2012 | Customer Milestone Not Met | 3/31/2012 |  |  | N | No
X1-034 | Stoney Brook 12kV | Renaissance at Hanover Solar Farm | NJ | Morris | Withdrawn | JCPL | 1.3 | 1.25 | 0.475 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1034_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1034_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/22/2011 | N/A | N/A |  | 4/9/2013 |  | 12/21/2014 | 12/21/2014 |  | N | No
X1-035 | Piney 34.5kV I |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1035_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/24/2011 | N/A | N/A |  | 5/22/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-036 | Piney 34.5kV II |  | PA | Venango | Withdrawn | PENELEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1036_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/24/2011 | N/A | N/A |  | 5/22/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X1-037 | Howell | Howell Solar Farm | NJ | Middlesex | In Service | JCPL | 17 | 17 | 6.46 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1037_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/28/2011 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 11/20/2014 | N | No
X1-038 | Union Camp 115kV | Franklin Mill Power Facility | VA | City of Franklin | In Service | Dominion | 35 | 35 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_038_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 6/6/2012 | N | No
X1-039 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 190 | 22.9 | 22.9 | 22.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 9/6/2012 | 9/6/2012 | 9/6/2012 | N | No
X1-040 | Collingwood-Hiple 345kV |  | IN | DeKalb | Withdrawn | AEP | 360 | 360 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2011 | N/A | N/A |  | 3/5/2013 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X1-041 | Dumont-Sorensen 345kV |  | IN | Marshall | Withdrawn | AEP | 252 | 262 | 32.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2011 | N/A | N/A |  | 5/14/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X1-042 | Watervliet | Orchard Hills | MI | Berrien | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1042_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/29/2011 | N/A | N/A |  |  |  | 11/30/2012 | 11/30/2012 | 3/4/2013 | N | No
X1-043 | Cox's Corner 13kV | All American Self Storage | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1043_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/30/2011 | N/A | N/A |  | 1/10/2013 | Customer Milestone Not Met | 3/31/2012 | 3/31/2012 |  | N | No
X1-044 | Minotola 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2011 | N/A | N/A |  | 9/23/2011 | Customer Milestone Not Met | 4/6/2012 |  |  | N | No
X1-045 | Dresden | Dresden Nuclear Generation Station, Units 2 & 3 | IL | Grundy | In Service | ComEd | 1917 | 3 | 3 | 3 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  |  |  | 12/1/2012 |  | 8/13/2013 | N | No
X1-046 | Branchville-N Newton #1 34kV | Morris Solar Farm | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1046_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-047 | Delaware City 69kV |  | DE | New Castle | Withdrawn | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 12/16/2011 | Customer Initiated Withdrawal | 6/1/2011 |  |  | N | No
X1-048 | Kenvil 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/19/2011 |  | 12/31/2012 |  |  | N | No
X1-049 | Englishtown 12.5kV | Monroe Sun Club | NJ | Middlesex | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1049_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1049_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/13/2017 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-050 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1050_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-051 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1051_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-052 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-053 | Suffolk 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/19/2011 | Customer Milestone Not Met | 12/1/2011 |  |  | N | No
X1-054 | Burlington 26kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1054_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 3/5/2013 | Customer Initiated Withdrawal | 3/31/2013 | 3/31/2013 |  | N | No
X1-055 | Robbinsville |  | NJ | Mercer | Withdrawn | JCPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1055_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2011 | N/A | N/A |  | 9/8/2011 | Customer Milestone Not Met | 10/1/2011 |  |  | N | No
X1-056 2079795 | LGEE-PJM |  | N/A | N/A | Withdrawn | Owensboro Municipal Utilities | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2079795_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2079795_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-057 2079798 | LGEE-PJM |  | N/A | N/A | Withdrawn | Owensboro Municipal Utilities | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2079798_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2079798_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-058 2079800 | LGEE-PJM |  | N/A | N/A | Withdrawn | Owensboro Municipal Utilities | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2079800_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2079800_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 6/1/2012 | 6/1/2017 |  | 5/14/2019 |  |  |  |  | FF | No
X1-058A_DK2 | Todhunter 69kV |  | OH | Butler | Withdrawn | Duke | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1058a_dk2_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/5/2011 | N/A | N/A |  | 2/22/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X1-059 2103861 | PJM-DUK |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103861_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103861_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-060 2103863 | PJM-CPLE |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103863_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103863_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-061 2103865 | PJM-DUK |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103865_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103865_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-062 2103868 | PJM-CPLE |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103868_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103868_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-063 2103869 | PJM-DUK |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103869_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103869_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-064 2103870 | PJM-CPLE |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2103870_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2103870_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [6 empty] | 1/1/2013 | 1/1/2018 |  | 2/17/2012 |  |  |  |  | FF | No
X1-064A_AT13 | Barberton-Star 138kV |  | OH | Summit | Withdrawn | ATSI | 268 | 268 | 268 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1064a_at13_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1064a_at13_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/11/2011 | N/A | N/A |  | 1/16/2013 | Customer Initiated Withdrawal | 1/10/2014 |  |  | N | No
X1-065 2120850 | EKPC-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 70 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2120850_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2120850_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/12/2011 | 6/1/2012 | 6/1/2019 | [6 empty] | FF | No
X1-066 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1066_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2011 | N/A | N/A |  | 7/11/2013 | Customer Initiated Withdrawal | 9/1/2011 |  |  | N | No
X1-067 | Plymouth |  | NC | Washington | Withdrawn | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1067_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/19/2011 | N/A | N/A |  | 11/21/2012 | Customer Milestone Not Met | 9/30/2013 | 9/30/2013 |  | N | No
X1-068 | Red Oak 230kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1068_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_068_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/20/2011 | N/A | N/A |  |  |  | 4/19/2011 |  | 12/3/2012 | N | No
X1-069 | Frenchtown |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2011 | N/A | N/A |  | 10/20/2011 | Customer Milestone Not Met | 6/1/2013 |  |  | N | No
X1-070 | Levittown 138kV | Mill Creek | NJ | Burlington | In Service | PSEG | 3.5 | 3.5 | 1.33 | 3.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1070_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 1/9/2012 | 1/9/2012 | 9/15/2011 | N | No
X1-071 | Cinnaminson 138kV | Southern Division Headquarters | NJ | Burlington | In Service | PSEG | 0.9 | 0.93 | 0.35 | 0.93 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/25/2011 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 10/7/2013 | N | No
X1-072 | Hackensack 4kV | Hackensack Solar Farm | NJ | Bergen | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1072_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/26/2011 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 1/11/2013 | N | No
X1-073 | Alpha-Gilbert 34kV | Pohatcong II Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1073_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X1-074 | Hay Road 230kV | Edge Moor Units EM6, EM7; Hay Road Units 5,6,7,8 | DE | New Castle | Withdrawn | DPL | 856 | 291 | 291 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_074_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 11/14/2017 | Customer Initiated Withdrawal | 6/18/2018 |  |  | N | No
X1-075 | Sussex 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2011 | N/A | N/A |  | 9/7/2011 | Customer Milestone Not Met | 12/30/2011 |  |  | N | No
X1-076 | East Greenwich Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 18 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1076_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-077 | Wrightstown 34.5kV | Saylos Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 2.1 | 0 | 0.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1077_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014 | 9/1/2014 |  | N | No
X1-078 | Deans (Poseidon) 500kV | Poseidon | NJ | Middlesex | Withdrawn | PSEG | 525 |  |  |  | Energy | Merchant Transmission |  | DC | F/TWR 525 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x1078_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x1078_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/x1_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/x1_078_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 4/23/2018 |  | 5/1/2020 | 5/1/2020 |  | S | No
X1-079 | Baptistown-Frenchtown #2 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1079_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 3/5/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-080 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1080_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1080_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 6/25/2014 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
X1-081 | Andover 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 9/8/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X1-082 | Hazen Switch Point-Warren 34kV | Quarry Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-083 | Salem 12kV |  | NJ | Salem | Withdrawn | AEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2011 | N/A | N/A |  | 1/17/2012 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
X1-084 | Altavista 115kV | Altavista Power Station | VA | Campbell | In Service | Dominion | 60 | 60 | 60 | 60 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 5/7/2013 | N | No
X1-085 | Hornerstown-Windsor 34kV | Upper Freehold Solar | NJ | Monmouth | In Service | JCPL | 5 | 5 | 1.9 | 2.7 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1085_wmpa.pdf |  | Not Required | N/A | N/A | 5/12/2016 | 4/29/2011 | N/A | N/A | 5/13/2016 |  |  | 2/29/2016 | 2/29/2016 | 5/18/2016 | N | No
X1-086 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 9.7 | 9.7 | 3.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1086_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 1/10/2012 | Customer Milestone Not Met | 3/31/2012 |  |  | N | No
X1-087 | Stillman Valley | Orchard Hills Renewable Energy Station | IL | Ogle | In Service | ComEd | 15.3 | 15.3 | 15.3 | 15.3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1087_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1087_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 11/17/2016 | N | No
X1-088 | Franklin #2 | Flemington Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 17 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1088_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/13/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-089 | Franklin #3 |  | NJ | Warren | Withdrawn | JCPL | 17 | 17 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1089_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/1/2011 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-090 | Yardville 138kV | BKB Properties | NJ | Mercer | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1090_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/18/2012 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
X1-091 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.9 | 1.91 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1091_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X1-092 | Newport 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.9 | 1.91 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 10/6/2011 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X1-093 | Pequest 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1093_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-094 | Flanders-Saxton Fall 34kV | Mount Olive Solar Farm | NJ | Morris | Withdrawn | JCPL | 17 | 17 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1094_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1094_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1094_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/18/2015 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
X1-095 | Bernardsville 12kV | Bernards Township Solar Farm | NJ | Somerset | In Service | JCPL | 3 | 3 | 1.14 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1095_wmpa.pdf |  | Not Required | N/A | N/A | 9/8/2016 | 4/29/2011 | N/A | N/A | 9/8/2016 |  |  | 9/20/2017 | 9/20/2017 | 10/3/2016 | N | No
X1-096 | Loretto-Kings Creek 138kV | Great Bay Wind Farm | MD | Somerset | Withdrawn | DPL | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1096_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1096_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x1_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_096_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/26/2015 |  | 12/31/2018 | 12/31/2018 | 12/28/2017 | N | No
X1-097 | Red Lion 138kV | Red Lion Energy Center | DE | New Castle | In Service | DPL | 27 | 27 | 27 | 27 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_097_csa.pdf | Document Posted | N/A | N/A | 12/12/2012 | 4/29/2011 | N/A | N/A | 12/12/2012 |  |  | 3/15/2013 | 3/15/2013 | 12/12/2012 | N | No
X1-098 | Cook Road 13kV | Montgomery Recycling | NJ | Essex | Withdrawn | PSEG | 0.5 | 0.5 | 0.5 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1098_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 3/31/2012 | 3/31/2012 |  | N | No
X1-099 | Woodhill 12kV |  | IL | Will | Withdrawn | ComEd | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1099_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 11/22/2013 | Customer Initiated Withdrawal | 7/1/2012 |  |  | N | No
X1-100 | Branchville 12kV | Mattison Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1100_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 3/7/2014 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-101 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 3/1/2012 |  |  | N | No
X1-102 | Stewartsville-Captive Plastics 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 9.5 | 9.5 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/29/2011 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
X1-103 | Branchville-Sussex 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1103_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/9/2011 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-104 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.5 | 2.45 | 0.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/6/2011 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-105 | Branchville-Holiday Lakes 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 11.2 | 11.2 | 4.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1105_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/25/2012 | Customer Milestone Not Met | 2/28/2012 |  |  | N | No
X1-106 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16.8 | 16.8 | 6.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1106_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 4/11/2012 | Customer Milestone Not Met | 1/31/2012 |  |  | N | No
X1-107 | Hopatcong |  | NJ | Sussex | Withdrawn | JCPL | 2.8 | 2.8 | 1.06 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1107_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/6/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X1-108 | Martins Creek 230kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 600 | 33 | 33 | 33 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1108_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1108_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 1/31/2013 | 1/31/2013 | 12/15/2012 | N | No
X1-109 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1109_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1109_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x1_109_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2011 | N/A | N/A |  |  |  | 2/29/2016 | 2/29/2016 | 3/28/2016 | N | No
X1-110 | Lower Township 12kV | Lower Township, NJ | NJ | Cape May | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x1110_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1110_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 11/23/2015 | Customer Milestone Not Met | 12/1/2014 | 12/1/2014 |  | N | No
X1-111 | Jackson |  | NJ | Ocean | Withdrawn | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 9/14/2011 | Customer Milestone Not Met | 7/1/2011 |  |  | N | No
X1-112 | Pennsville 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 20 | 4.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1112_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X1-113 | Lawrence 26kV | Bristol-Myers | NJ | Mercer | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1113_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/25/2012 | Customer Initiated Withdrawal | 12/1/2013 | 12/1/2013 |  | N | No
X1-114 | Holiday Lakes 12kV | Sandyston Solar Farm | NJ | Sussex | Withdrawn | JCPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1114_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 5/3/2016 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X1-115 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1115_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-116 | Branchville-N Newton #2 34kV | Frankford Solar Farm | NJ | Sussex | Withdrawn | JCPL | 7 | 7 | 2.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x1116_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X1-117 | Hampton |  | NJ | Sussex | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-118 | Hampton #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X1-119 | Andover #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2011 | N/A | N/A |  | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X2-001 | Howell |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 2/14/2012 | Customer Milestone Not Met | 5/13/2012 |  |  | N | No
X2-002 | Somerville 13kV |  | NJ | Somerset | Withdrawn | PSEG | 11.2 | 11.2 | 4.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2002_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 11/4/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X2-003 | East Rutherford 13kV |  | NJ | Bergen | Withdrawn | PSEG | 2.1 | 2.1 | 0.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2011 | N/A | N/A |  | 9/14/2011 | Customer Initiated Withdrawal | 2/28/2012 |  |  | N | No
X2-004 | Cumberland-W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2004_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2011 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 12/15/2012 |  |  | N | No
X2-005 | Cumberland-W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2011 | N/A | N/A |  | 11/14/2011 | Customer Milestone Not Met | 12/15/2012 |  |  | N | No
X2-006 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 999 | 0 | 0 | 0 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_006_csa.pdf | Document Posted | N/A | N/A |  | 5/6/2011 | N/A | N/A |  | 2/22/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
X2-007 | Peckville-Varden 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2007_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2007_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/12/2011 | N/A | N/A |  | 8/3/2012 | Customer Initiated Withdrawal | 6/30/2012 |  |  | N | No
X2-008 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/16/2011 | N/A | N/A |  | 5/17/2012 |  | 12/31/2013 |  |  | N | No
X2-009 | Cedar Grove-Clifton 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x2009_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/17/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X2-011 | Fairlawn 138kV | Elmwood | NJ | Bergen | In Service | PSEG | 73 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2011_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x2_011_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 9/28/2012 | N | No
X2-012 | Clinton 230kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 850 | 850 | 765 | 850 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2012_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2012_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_012_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 7/30/2016 | 7/30/2016 | 7/13/2016 | N | No
X2-013 | Thorofare 13kV | Mantua Creek Frequency Regularor | NJ | Gloucester | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_013_csa.pdf | Document Posted | N/A | N/A |  | 5/19/2011 | N/A | N/A |  |  |  | 12/31/2012 | 12/31/2012 | 1/17/2013 | N | No
X2-014 | Trenton 26kV | Hedding Road Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2014_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2014_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/23/2011 | N/A | N/A |  | 8/9/2012 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
X2-015 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 2.3 | 2.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2015_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/23/2011 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 10/15/2011 |  |  | N | No
X2-016 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 5/17/2013 |  |  | N | No
X2-017 | Elk Township 12kV #1 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 2/28/2013 |  |  | N | No
X2-018 | Elk Township 12kV #2 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2018_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 2/28/2013 |  |  | N | No
X2-019 | Silver Lake 345kV |  | IL | Lake | Withdrawn | ComEd | 225 | 225 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2019_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2011 | N/A | N/A |  | 7/8/2013 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
X2-020 | Erie East 230 kV |  | PA | Erie | Withdrawn | PENELEC | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2011 | N/A | N/A |  | 5/25/2012 | Customer Initiated Withdrawal | 10/31/2014 |  |  | N | No
X2-021 | Erie East 230kV |  | PA | Erie | Withdrawn | PENELEC | 153.8 | 153.75 | 19.98 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2021_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2011 | N/A | N/A |  | 1/18/2013 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
X2-022 | Brokaw-Lanesville | Hilltopper Wind Farm | IL | Logan | In Service | ComEd | 250 | 187.5 | 0 | 187.5 | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_022_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 11/1/2018 | N | No
X2-023 | North Mashoppen-Mehoopany 115kV |  | PA | Sullivan | Withdrawn | PENELEC | 51 | 51 | 6.63 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2023_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 1/22/2013 | Customer Milestone Not Met | 10/15/2013 |  |  | N | No
X2-024 | Lower Alloways Creek 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 11/1/2011 |  |  | N | No
X2-025 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 416 | 416 | 416 | 416 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2025_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_025_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X2-026 | Leola |  | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 7/12/2011 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X2-027 | Quinton 12kV | Quinton-Alloway | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2027_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_027_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 12/15/2017 |  | 11/1/2016 | 11/1/2016 |  | N | No
X2-028 | Quinton Township 12kV |  | NJ | Salem | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2028_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 2/20/2014 | Customer Initiated Withdrawal | 3/15/2012 |  |  | N | No
X2-029 | Danville-East Danville 138kV |  | VA | Pittsylvania | Withdrawn | AEP | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2029_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 8/7/2014 | Customer Initiated Withdrawal | 1/30/2014 | 1/30/2014 |  | S | No
X2-030 | Morgantown-Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 830 | 830 | 830 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 2/1/2012 | Customer Milestone Not Met | 1/1/2016 |  |  | N | No
X2-031 | Krayn 115kV | Highland III Wind Farm | PA | Cambria | Withdrawn | PENELEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_031_csa.pdf | Document Posted | N/A | N/A |  | 5/31/2011 | N/A | N/A |  | 11/29/2016 |  | 12/31/2015 | 12/31/2015 |  | N | No
X2-032 |  |  | N/A | N/A | Withdrawn | JCPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2011 | N/A | N/A |  | 9/26/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-033 | Trenton 26kV | Ward Avenue Solar | NJ | Burlington | Withdrawn | PSEG | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2033_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2033_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/3/2011 | N/A | N/A |  | 1/4/2013 | Customer Initiated Withdrawal | 6/30/2013 | 6/30/2013 |  | N | No
X2-034 | Laplume |  | PA | Lackawanna | Withdrawn | PPL | 0 | 0.032 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2034_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/3/2011 | N/A | N/A |  | 1/18/2012 | Customer Initiated Withdrawal |  |  |  | N | No
X2-035 | Sunnymeade Road 13kV) | Valley Road Solar | NJ | Somerset | Withdrawn | PSEG | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2035_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2035_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/6/2011 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 7/31/2013 | 7/31/2013 |  | N | No
X2-036 | Whitehouse |  | NJ | Hunterdon | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2011 | N/A | N/A |  | 1/5/2012 | Customer Milestone Not Met | 12/31/2011 |  |  | N | No
X2-037 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 350 | 45.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/8/2011 | N/A | N/A |  | 2/15/2012 | Customer Initiated Withdrawal |  |  |  | N | No
X2-038 | Halfway 12.5kV | Washington County Renewable Energy Project | MD | Washington | Withdrawn | APS | 2 | 2 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2038_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2038_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/10/2011 | N/A | N/A |  | 1/14/2016 | Customer Initiated Withdrawal | 10/31/2013 | 10/31/2013 |  | N | No
X2-039 | Brookside-Cloverdale 138kV |  | OH | Ashland | Withdrawn | ATSI | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2039_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2011 | N/A | N/A |  | 12/9/2011 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X2-040 | Wurno 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2040_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 6/22/2011 | N/A | N/A |  | 3/15/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X2-041 2403941 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2403941_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 6/1/2022 |  | 9/12/2011 |  |  |  |  | FF | No
X2-042 2403944 | CIN-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2403944_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2403944_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 9/1/2019 | [6 empty] | FF | No
X2-043 2403946 | MECS-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2403946_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/24/2011 | 6/1/2012 | 6/1/2022 |  | 9/12/2011 |  |  |  |  | FF | No
X2-044 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2044_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2011 | N/A | N/A |  | 1/3/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X2-045 | Kenney-Mt. Olive 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2045_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/27/2011 | N/A | N/A |  | 5/21/2012 |  | 6/30/2013 |  |  | N | No
X2-046 | Sussex County |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2046_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/27/2011 | N/A | N/A |  | 5/8/2012 | Customer Milestone Not Met | 1/1/2013 |  |  | N | No
X2-047 | Oldmans Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2047_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
X2-048 | South Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2048_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 11/30/2011 |  |  | N | No
X2-049 | S. Reading-Birdsboro 64kV |  | PA | Berks | Withdrawn | ME | 9.6 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2049_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 1/3/2012 | Customer Initiated Withdrawal | 3/1/2012 |  |  | N | No
X2-050 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 705 | 705 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A | 2/1/2016 | 6/28/2011 | N/A | N/A |  | 11/20/2013 | Customer Initiated Withdrawal | 5/31/2016 | 5/31/2016 |  | N | No
X2-051 |  |  | OH | Unknown | Withdrawn | AEP | 8 | 6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2011 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-052 | Dumont-Olive 345kV | St. Joseph Energy Center, LLC | MI | St. Joseph | In Service | AEP | 675 | 675 | 675 | 675 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2052_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2052_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_052_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 6/29/2011 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
X2-053 | Amsterdam 69kV |  | OH | Jefferson | Withdrawn | AEP | 6.4 | 6.4 | 6.4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2053_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/29/2011 | N/A | N/A |  | 5/15/2012 | Customer Milestone Not Met | 1/31/2013 |  |  | N | No
X2-054 | Franklin | Quakertown Solar Farm #2 | NJ | Hunterdon | Withdrawn | JCPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2054_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/15/2016 | Customer Initiated Withdrawal | 4/13/2016 | 4/13/2016 |  | N | No
X2-055 | Cedar Grove-Clifton "B" 230kV |  | VA | Fairfax | Withdrawn | PSEG | 206 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x2055_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x2055_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 12/18/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X2-056 | Greenwich 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.9 | 1.94 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 1/11/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-057 | White |  | NJ | Warren | Withdrawn | JCPL | 4.1 | 4.1 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2057_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 11/21/2011 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-058 | Buckley Road 138kV |  | OH | Hancock | Withdrawn | AEP | 149.5 | 149.5 | 19.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/10/2013 | Customer Milestone Not Met | 11/15/2012 |  |  | N | No
X2-059 | Freehold | Cloverleaf Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2059_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 7/15/2015 | Customer Milestone Not Met | 12/31/2014 | 12/31/2014 |  | N | No
X2-060 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | City of Covington | In Service | Dominion | 30 | 30 | 0 | 30 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_060_csa.pdf | Document Posted | N/A | N/A |  | 6/30/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
X2-061 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 15 | 4 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 12/14/2011 | Customer Initiated Withdrawal | 6/1/2012 | 6/1/2012 |  | N | No
X2-062 | North Hanover |  | NJ | Burlington | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2062_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2011 | N/A | N/A |  | 11/18/2011 | Customer Milestone Not Met | 10/30/2012 |  |  | N | No
X2-063 2459943 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 220 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2459943_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2012 | 6/1/2013 |  | 10/12/2011 |  |  |  |  | FF | No
X2-064 2459958 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 720 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2013 | 6/1/2015 |  | 8/5/2011 |  |  |  |  | FF | No
X2-065 2459960 | TVA-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 720 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2459960_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/6/2011 | 6/1/2013 | 6/1/2017 |  | 10/12/2011 |  |  |  |  | FF | No
X2-066 | S. Harrington-N. Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 312 | 312 | 309 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2066_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2066_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/18/2011 | N/A | N/A |  | 1/15/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
X2-067 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 309 | 309 | 309 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2067_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/18/2011 | N/A | N/A |  | 2/26/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
X2-068 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 11/30/2011 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X2-069 | Swedesboro |  | NJ | Gloucester | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2069_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 1/3/2012 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X2-070 | Hightstown |  | NJ | Mercer | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 8/15/2011 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
X2-071 | Beckett |  | NJ | Salem | Withdrawn | AEC | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2071_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 1/3/2012 |  | 5/31/2013 |  |  | N | No
X2-072 |  |  | N/A | N/A | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/19/2011 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-073 2533204 | PJM-CPLE |  | N/A | N/A | Withdrawn | NextEra Energy Power Marketing, LLC | 120 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2533204_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/21/2011 | 1/1/2013 | 1/1/2033 |  | 9/23/2011 |  |  |  |  | FF | No
X2-074 | Gibbsboro 12kV |  | NJ | Camden | Withdrawn | AEC | 1 | 1 | 0.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2011 | N/A | N/A |  | 5/8/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X2-075 | Flemington | Junction Road Solar Farm | NJ | Hunterdon | In Service | JCPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2075_wmpa.pdf |  | Not Required | N/A | N/A | 5/3/2016 | 7/26/2011 | N/A | N/A | 5/18/2016 |  |  | 6/12/2017 | 6/12/2017 | 5/19/2016 | N | No
X2-076 | Carson-Wake 500kV | Brunswick Combined Cycle Power Station | VA | Brunswick | In Service | Dominion | 1525.5 | 1525.5 | 1376 | 1525.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x2_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_076_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2011 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 3/7/2016 | N | No
X2-077 | Hursch Road 69kV |  | OH | Darke | Withdrawn | Dayton | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 2/14/2012 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X2-078 | Ringoes |  | NJ | Hunterdon | Withdrawn | JCPL | 0.4 | 0.38 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 5/11/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X2-079 |  |  | N/A | N/A | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 9/27/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-080 |  |  | NJ | Cumberland | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 9/27/2013 | Customer Milestone Not Met |  |  |  | N | No
X2-081 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 1.5 | 1.5 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 2/1/2012 |  |  | N | No
X2-082 | Chesterfield 230kV |  | VA | Chesterfield | Withdrawn | Dominion | 1575 | 1575 | 1420 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2082_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pub/planning/project-queues/isa/x2_082_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x2_082_csa.pdf | Document Posted | N/A | N/A |  | 7/28/2011 | N/A | N/A |  | 12/5/2012 | Customer Initiated Withdrawal | 12/1/2015 |  |  | N | No
X2-083 | Newark 12kV | Brookside Energy Center | DE | New Castle | In Service | DPL | 3 | 3 | 3 | 3 | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2083_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x2083_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2083_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 8/15/2012 | 8/15/2012 | 6/21/2012 | N | No
X2-084 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 19.6 | 19.6 | 7.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2084_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 5/10/2012 | Customer Milestone Not Met | 10/1/2012 |  |  | N | No
X2-085 | Barberton–Seiberling 23kV | Barberton Solar | OH | Summit | Withdrawn | ATSI | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2085_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 6/12/2014 | Customer Initiated Withdrawal | 6/30/2014 | 6/30/2014 |  | N | No
X2-086 | Mt. Storm 115kV |  | WV | Grant | Withdrawn | Dominion | 77 | 77 | 74 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2086_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/9/2012 | Customer Milestone Not Met | 12/1/2014 |  |  | N | No
X2-087 | Doremus 13kV | Food Bank Solar | NJ | Union | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2087_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2087_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 8/18/2012 | N | No
X2-088 | Devils Brook 13kV | Black Rock Solar | NJ | Middlesex | In Service | PSEG | 2.4 | 2.356 | 0.895 | 2.356 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2088_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 3/26/2012 | N | No
X2-089 | Pierson Avenue 13kV | Summit Associates Solar | NJ | Middlesex | In Service | PSEG | 2 | 2 | 0.76 | 2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2089_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2089_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  |  |  | 9/30/2012 | 9/30/2012 | 12/31/2011 | N | No
X2-090 | Dewey-Inez 69kV |  | KY | Martin | Withdrawn | AEP | 21 | 19 | 11.4 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/12/2012 | Customer Milestone Not Met | 8/31/2012 |  |  | N | No
X2-091 | Hegewisch 34kV |  | IL | Cook | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2091_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-092 | Cornell 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2092_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-093 | Pontiac-Midpoint 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2093_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013 |  |  | N | No
X2-094 | Green Brook 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/12/2012 | Customer Milestone Not Met | 1/31/2013 |  |  | N | No
X2-095 | Cape May Court House 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.8 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X2-096 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-097 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-098 | Lopatcong #2 |  | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 8/23/2011 | Customer Milestone Not Met | 7/31/2013 |  |  | N | No
X2-099 | Sparta-Woodruff's Gap 34kV | Sparta Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x2099_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 3/14/2013 | Customer Initiated Withdrawal | 12/31/2014 | 12/31/2014 |  | N | No
X2-100 | Woodstown-Laurel 69kV |  | NJ | Salem | Withdrawn | AEC | 14.4 | 14.4 | 1.87 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2100_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/18/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X2-101 | Upper Pittsgrove 138kV |  | NJ | Salem | Withdrawn | AEC | 18 | 18 | 2.34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x2101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x2101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2011 | N/A | N/A |  | 1/18/2012 | Customer Milestone Not Met | 9/1/2012 |  |  | N | No
X3-001 | West Melrose 34.5kV | Edgewood | OH | Hancock | Withdrawn | AEP | 1.8 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3001_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/1/2011 | N/A | N/A |  | 11/10/2016 | Customer Initiated Withdrawal | 7/15/2014 | 7/15/2014 |  | N | No
X3-002 | Greenville 12kV | Greenville Solar | OH | Darke | Withdrawn | Dayton | 3.4 | 3.38 | 1.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3002_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3002_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/1/2011 | N/A | N/A |  | 9/17/2018 |  | 12/31/2017 | 12/31/2017 |  | N | No
X3-002A 2590376 | MECS-PJM |  | N/A | N/A | Withdrawn | DTE Energy Trading | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2590376_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/2/2011 | 1/1/2013 | 1/1/2014 |  | 10/25/2011 |  |  |  |  | FF | No
X3-003 | Mehoopany II 115 kV | Mehoopany Plant | PA | Wyoming | In Service | PENELEC | 64 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_003_csa.pdf | Document Posted | N/A | N/A |  | 8/3/2011 | N/A | N/A |  |  |  | 10/17/2013 | 10/17/2013 | 11/15/2013 | N | No
X3-004 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 710 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_004_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 8/8/2011 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
X3-005 | Wildwood 12kV | City Solar | IL | Cook | In Service | ComEd | 9 | 9 | 3.4 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3005_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_005_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/8/2011 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 9/26/2013 | N | No
X3-006 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 800 | 150 | 110 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3006_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2011 | N/A | N/A |  | 2/13/2014 | Customer Milestone Not Met | 6/1/2014 |  |  | N | No
X3-007 | Bustleton 13kV | LB Solar | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3007_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3007_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/8/2011 | N/A | N/A |  | 1/28/2015 | Customer Milestone Not Met | 9/30/2014 | 9/30/2014 |  | N | No
X3-008 | Todd 69kV | Dorchester County Solar 1 Project | MD | Anne Arundel | Under Construction | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3008_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3008_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3008_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/12/2011 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
X3-009 | New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2011 | N/A | N/A |  | 8/24/2012 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
X3-010 | Franklin #1 |  | NJ | Warren | Withdrawn | JCPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 8/30/2013 |  |  | N | No
X3-011 | Franklin #2 | Beidelman Solar Farm | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3011_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 7/21/2015 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
X3-012 2654202 | AMIL-PJM |  | N/A | N/A | Retracted | Homefield Energy | 315 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/15/2011 | 1/1/2012 | 1/1/2017 | [6 empty] | FF | No
X3-013 | Wildwood Crest 12kV |  | NJ | Cape May | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2011 | N/A | N/A |  | 3/12/2012 | Customer Initiated Withdrawal | 11/1/2012 |  |  | N | No
X3-014 | South Harrington-North Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2011 | N/A | N/A |  | 4/27/2012 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
X3-015 | West Cambridge-Vienna 69kV | Linkwood Solar | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.41 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3015_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x3_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_015_csa.pdf | Document Posted | N/A | N/A |  | 8/22/2011 | N/A | N/A |  | 10/10/2017 |  | 9/1/2017 | 9/1/2017 |  | N | No
X3-016 | Carneys Point Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2011 | N/A | N/A |  | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2011 |  |  | N | No
X3-017 | Elsinboro Township 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
X3-018 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 10/11/2011 | Customer Initiated Withdrawal | 11/1/2011 |  |  | N | No
X3-019 2713235 | LGEE-PJM |  | N/A | N/A | Withdrawn | Bluegrass Generating Company LLC | 485 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2713235_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/26/2011 | 6/1/2014 | 6/1/2019 |  | 10/27/2011 |  |  |  |  | FF | No
X3-020 2722964 | AMIL-PJM |  | N/A | N/A | Confirmed | Tilton Energy, LLC | 180 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2722964_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2722964_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 8/29/2011 | 6/1/2014 | 6/1/2019 | [6 empty] | FF | No
X3-021 2723695 | MECS-PJM |  | N/A | N/A | Annulled | Renaissance Power, LLC | 660 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2723695_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2723695_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 8/29/2011 | 6/1/2016 | 6/1/2023 | [6 empty] | FF | No
X3-022 | Hunterstown-Jackson 138kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/22/2012 | Customer Milestone Not Met | 12/31/2014 |  |  | N | No
X3-023 | S. Greenwich-Willard 69kV | 6011 Greenwich Windpark, LLC | OH | Huron | Withdrawn | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3023_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 8/5/2016 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
X3-024 | Cape May Court House |  | NJ | Cape May | Withdrawn | AEC | 1.8 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X3-025 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 4.3 | 1.82 | 0.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3025_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/14/2012 | Customer Milestone Not Met | 6/1/2012 |  |  | N | No
X3-026 | Buena Vista Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 3/12/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-027 | Ocean |  | NJ | Ocean | Withdrawn | AEC | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3027_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2011 | N/A | N/A |  | 5/2/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-028 | X3-028 Sullivan 345 kV |  | IN | Sullivan | Withdrawn | AEP | 3500 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 1500; NFTIR 2000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3028_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 9/30/2019 |  | 12/31/2016 |  |  | S | No
X3-029 | Belvidere | CHP Belvidere Generation Facility | NJ | Warren | In Service | JCPL | 11.2 | 11.15 | 0 | 11.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_029_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2011 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/17/2013 | N | No
X3-030 | Shelby-S.W. Lima 345kV |  | OH | Marion | Withdrawn | Dayton | 245 | 245 | 31.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 5/30/2013 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
X3-031 | Southwest Lima-West Moulton 138kV |  | OH | Allen | Withdrawn | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2011 | N/A | N/A |  | 5/31/2013 | Customer Initiated Withdrawal | 9/30/2015 |  |  | N | No
X3-032 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 155 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3032_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3032_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 6/25/2014 | Customer Milestone Not Met | 6/1/2015 | 6/1/2015 |  | N | No
X3-033 | Green |  | NJ | Sussex | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3033_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 2/7/2012 | Customer Initiated Withdrawal | 5/1/2013 |  |  | N | No
X3-034 | Hunterstown-Jackson 130kV |  | PA | Washington | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3034_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 9/27/2012 | Customer Milestone Not Met | 8/1/2012 |  |  | N | No
X3-035 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 3/23/2012 | Customer Milestone Not Met | 7/4/2012 |  |  | N | No
X3-036 | William 138kV |  | WV | Grant | Withdrawn | APS | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 3/22/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
X3-037 | Krendale-Seneca 138kV |  | OH | Richland | Withdrawn | APS | 46 |  |  |  | Energy | Merchant Transmission |  |  | AC | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3037_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 8/14/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-038 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 2/10/2012 | Customer Milestone Not Met | 9/30/2013 |  |  | N | No
X3-039 | Geneva 115kV |  | PA | Crawford | Withdrawn | PENELEC | 96 | 96 | 96 |  | Capacity | Generation Interconnection | Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 6/19/2013 | Customer Initiated Withdrawal | 7/7/2014 |  |  | N | No
X3-040 | Weirwood-Eastville 69kV |  | VA | Northampton | Withdrawn | ODEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 8/13/2014 | Customer Initiated Withdrawal | 6/30/2016 | 6/30/2016 |  | N | No
X3-041 | Milton | Milton | DE | Sussex | Withdrawn | DPL | 14.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3041_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2011 | N/A | N/A |  | 12/19/2014 | Customer Initiated Withdrawal | 9/2/2018 | 9/2/2018 |  | N | No
X3-042 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2011 | N/A | N/A |  | 9/29/2011 |  |  |  |  | N | No
X3-043 | Lumberton 69kV | Warfield I | NJ | Burlington | Withdrawn | AEC | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3043_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/12/2011 | N/A | N/A |  | 1/5/2015 | Customer Initiated Withdrawal | 10/15/2015 | 10/15/2015 |  | N | No
X3-044 | Three Mile Island |  | PA | Dauphin | Withdrawn | ME | 860 | 15 | 15 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3044_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 7/16/2014 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
X3-045 | Dresden |  | IL | Grundy | Withdrawn | ComEd | 1984 | 32 | 32 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3045_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
X3-046 | Quad Cities |  | IL | Rock Island | Withdrawn | ComEd | 1984 | 32 | 32 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3046_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2011 | N/A | N/A |  | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014 | 6/1/2014 |  | N | No
X3-047 | Bayview 25kV |  | VA | Northampton | Withdrawn | ODEC | 5 | 5 | 0.65 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2011 | N/A | N/A |  | 4/12/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-048 2852305 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2852305_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2013 | 6/1/2014 |  | 12/20/2011 |  |  |  |  | FF | No
X3-049 2852306 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2852306_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2012 | 6/1/2013 |  | 12/20/2011 |  |  |  |  | FF | No
X3-050 2852309 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/2852309_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/2852309_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 9/26/2011 | 6/1/2015 | 6/1/2020 |  | 2/1/2018 |  |  |  |  | FF | No
X3-051 | Flatlick 765kV |  | OH | Unknown | Withdrawn | AEP | 1460 | 610 | 610 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3051_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3051_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/27/2011 | N/A | N/A |  | 5/23/2016 | Customer Milestone Not Met | 3/1/2017 | 3/1/2017 |  | N | No
X3-052 | Essex 26.4kV | Essex County Correctional Facility | NJ | Essex | In Service | PSEG | 6.2 | 3 | 0 | 3 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_052_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2011 | N/A | N/A |  |  |  | 5/31/2013 | 5/31/2013 | 9/10/2014 | N | No
X3-053 | Homer-Seville 69kV |  | OH | Medina | Withdrawn | ATSI | 17.7 | 17.68 | 6.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3053_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 8/2/2012 | Customer Milestone Not Met | 7/1/2013 |  |  | N | No
X3-054 | Sussex | Hough Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4.9 | 4.9 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3054_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 11/13/2013 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X3-055 | Occoquan 34.5kV |  | VA | Fairfax | Withdrawn | Dominion | 10 | 10 | 0 |  | Energy | Generation Interconnection | Diesel |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2011 | N/A | N/A |  | 11/14/2011 | Queue Not Required | 2/28/2013 |  |  | N | No
X3-056 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3056_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2011 | N/A | N/A |  | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011 |  |  | N | No
X3-057 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 1310 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3057_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2011 | N/A | N/A |  | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011 |  |  | N | No
X3-058 2890646 | PJM-DUK |  | N/A | N/A | Retracted | NextEra Energy Power Marketing, LLC | 120 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/5/2011 | 1/1/2013 | 1/1/2033 |  | 11/8/2011 |  |  |  |  | FF | No
X3-059 | Roberts 34.5kV |  | OH | Marion | Withdrawn | ATSI | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3059_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 10/16/2012 | Customer Initiated Withdrawal | 9/1/2012 |  |  | N | No
X3-060 | Fairfield Twp 1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-061 | Fairfield Twp 2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2011 | N/A | N/A |  | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-062 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3062_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-063 2919169 | PJM-DUK |  | N/A | N/A | Withdrawn | Constellation | 500 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/11/2011 | 1/1/2015 | 1/1/2018 |  | 10/28/2011 |  |  |  |  | FF | No
X3-064 | Fredericksburg-Mine Road 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 237 | 237 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3064_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-065 | Bristers-Ox 500kV |  | VA | Fauquier | Withdrawn | Dominion | 183 | 183 | 0 |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x3065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x3065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x3065_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 10/12/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | S | No
X3-066 | Church Hill 69kV | Church Hill Solar Farm | MD | Queen Anne's | In Service | DPL | 6 | 6 | 2.28 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3066_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3066_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3066_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/13/2011 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 5/19/2016 | N | No
X3-067 | Church Hill 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/2011 | N/A | N/A |  | 2/29/2012 | Customer Initiated Withdrawal | 9/30/2012 |  |  | N | No
X3-068 | Graceton 230kV |  | PA | York | Withdrawn | BGE | 678 | 678 | 678 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3068_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/14/2011 | N/A | N/A |  | 6/4/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X3-069 | Hamilton |  | N/A | N/A | Withdrawn | JCPL | 4 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2011 | N/A | N/A |  | 11/4/2011 |  |  |  |  | N | No
X3-070 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 72 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x3_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 12/12/2013 | N | No
X3-071 | Sussex County 12kV | Burbage Property | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3071_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 11/12/2013 | Customer Milestone Not Met | 10/31/2018 | 10/31/2018 |  | N | No
X3-072 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 10.5 | 10.5 | 3.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3072_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 3/7/2012 | Customer Milestone Not Met | 3/1/2013 |  |  | N | No
X3-073 | Massey 69kV |  | MD | Kent | Withdrawn | DPL | 9.8 | 9.8 | 3.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 3/12/2012 | Customer Milestone Not Met | 3/31/2013 |  |  | N | No
X3-074 | Chestertown 69kV |  | MD | Kent | Withdrawn | DPL | 11.9 | 11.9 | 4.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 8/15/2012 | Customer Initiated Withdrawal | 3/31/2013 |  |  | N | No
X3-075 | Runnemede 13kV | Owens Corning Solar | NJ | Camden | In Service | PSEG | 3 | 3 | 0 | 3 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3075_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2011 | N/A | N/A |  |  |  | 2/16/2017 | 2/16/2017 | 5/11/2017 | N | No
X3-076 | Loudoun-Meadowbrook 500kV |  | VA | Fauquier | Withdrawn | Dominion | 1270 | 510 | 412 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2011 | N/A | N/A |  | 6/7/2013 | Customer Initiated Withdrawal | 5/1/2015 |  |  | N | No
X3-077 | Sussex County 12kV | Baxter Property | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3077_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/12/2013 | Customer Milestone Not Met | 10/31/2018 | 10/31/2018 |  | N | No
X3-078 | Harrisburg 12kV |  | PA | Dauphin | Withdrawn | PPL | 4 | 4 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/11/2012 | Customer Initiated Withdrawal | 8/15/2014 |  |  | N | No
X3-079 | Oyster Creek-Waretown 34kV | Volunteer Way Solar Farm | NJ | Ocean | Withdrawn | JCPL | 16 | 16 | 6.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3079_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3079_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 12/21/2012 |  | 6/30/2015 | 6/30/2015 |  | N | No
X3-080 | Fairton Township |  | NJ | Cumberland | Withdrawn | AEC | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X3-081 | Upper Darby 13kV | Astra Foods | PA | Delaware | Withdrawn | PECO | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 8/27/2018 |  | 12/30/2012 | 12/30/2012 |  | N | No
X3-082 | Marble Hill-Morris Park 34kV | Lopatcong Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3082_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 6/30/2015 | 6/30/2015 |  | N | No
X3-083 | Andover-Kittatinny 34kV | Andover Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3083_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x3083_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 4/29/2016 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
X3-084 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 3/9/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X3-085 | Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 2/27/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
X3-086 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/17/2011 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X3-087 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Engineering and Procurement | PEPCO | 894 | 894 | 744 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x3087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x3087_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x3_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x3_087_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2011 | N/A | N/A |  |  |  | 3/1/2022 | 3/1/2022 |  | N | No
X3-088 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 440 | 440 | 440 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 6/21/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
X3-089 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 744 | 744 | 744 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3089_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 5/3/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
X3-090 3023526 | PJM-DUK |  | N/A | N/A | Retracted | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023526_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3023526_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 8/29/2012 |  |  |  |  | FF | No
X3-091 3023529 | PJM-DUK |  | N/A | N/A | Retracted | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023529_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-092 3023530 | PJM-DUK |  | N/A | N/A | Retracted | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023530_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-093 3023531 | PJM-DUK |  | N/A | N/A | Retracted | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023531_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-094 3023533 | PJM-DUK |  | N/A | N/A | Retracted | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023533_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2017 |  | 1/13/2012 |  |  |  |  | FF | No
X3-095 3023618 | AMIL-PJM |  | N/A | N/A | Retracted | Homefield Energy | 338 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023618_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-096 3023630 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 268 | 268 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023630_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3023630_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 12/15/2019 |  | 12/15/2019 |  |  |  |  | FF | No
X3-097 3023634 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 202 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023634_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3023634_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
X3-098 3023635 | AMIL-PJM |  | N/A | N/A | Withdrawn | Homefield Energy | 94 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023635_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3023635_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2015 | 6/1/2020 |  | 10/18/2019 |  |  |  |  | FF | No
X3-099 3023636 | AMIL-PJM |  | N/A | N/A | Retracted | Homefield Energy | 602 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023636_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-100 3023637 | AMIL-PJM |  | N/A | N/A | Retracted | Homefield Energy | 336 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023637_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-101 3023638 | AMIL-PJM |  | N/A | N/A | Retracted | Homefield Energy | 259 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3023638_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2011 | 6/1/2012 | 6/1/2017 |  | 1/30/2012 |  |  |  |  | FF | No
X3-102 | Burches Hill-Possum Point 500kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 971.2 | 937 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x3102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 6/20/2012 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
X3-103 | Oakgrove-Morgantown 230kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 971.2 | 971.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2011 | N/A | N/A |  | 11/18/2011 | Queue Not Required | 6/1/2016 |  |  | N | No
X4-001 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4001_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X4-002 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4002_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
X4-003 | Mill Creek-Riverview 138kV |  | OH | Washington | Withdrawn | AEP | 56 | 56 | 56 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4003_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 11/26/2012 | Customer Initiated Withdrawal | 3/31/2015 |  |  | N | No
X4-004 | Woodbury 26.4kV | Johnson Matthey | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x4_004_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2011 | N/A | N/A |  | 6/7/2016 | Customer Initiated Withdrawal | 12/31/2012 | 12/31/2012 |  | N | No
X4-005 | Raritan River 230kV |  | NJ | Middlesex | In Service | JCPL | 785 | 60 | 0 | 60 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4005_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/facilities/x4005_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_005_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 12/4/2015 | N | No
X4-006 | Kelson Ridge 230kV | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 785 | 60 | 0 | 35 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_006_csa.pdf | Document Posted | N/A | N/A |  | 11/3/2011 | N/A | N/A |  |  |  | 11/1/2016 | 11/1/2016 | 1/28/2017 | N | No
X4-007 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 785 | 60 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4007_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4007_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/3/2011 | N/A | N/A |  | 7/31/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
X4-008 3131895 | MECS-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/16/2011 | 6/1/2013 | 6/1/2023 |  | 12/19/2011 |  |  |  |  | FF | No
X4-009 | Cumberland - W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4009_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 7/1/2013 | Customer Initiated Withdrawal | 7/1/2014 | 7/1/2014 |  | N | No
X4-010 | Cumberland - W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 5/29/2012 | Customer Initiated Withdrawal | 12/15/2012 |  |  | N | No
X4-011 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4011_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/17/2011 | N/A | N/A |  | 8/16/2013 | Customer Initiated Withdrawal | 12/15/2012 |  |  | N | No
X4-012 | Branchville-Sussex 34kV | Plains Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x4012_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/21/2011 | N/A | N/A |  | 3/17/2015 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | No
X4-013 | Pleasant View-Edwards Ferry 230kV |  | VA | Prince William | Withdrawn | Dominion | 200 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4013_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 1/2/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
X4-014 | Kellam - Bayview 69kV |  | VA | Northampton | Withdrawn | ODEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4014_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2011 | N/A | N/A |  | 7/3/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X4-015 | Cookstown-Fort Dix 34kV | Jacobstown III Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4015_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x4015_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/28/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 9/28/2015 | N | No
X4-016 | Bayonne 138kV | Bayonne Cogen | NJ | Hudson | Deactivated | PSEG | 168 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4016_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x4_016_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/29/2011 | N/A | N/A |  |  |  | 9/30/2013 | 9/30/2013 | 9/30/2013 | N | No
X4-017 | Fruitland 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 7/24/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
X4-018 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 660 | 110 | 110 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 6/5/2012 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
X4-019 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 643 | 227 | 227 | 227 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4019_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4019_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_019_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/18/2018 | N | No
X4-020 | Peach Bottom-TMI #1 500kV I |  | PA | York | Withdrawn | PPL | 800 | 800 | 760 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4020_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X4-021 | Peach Bottom-TMI #2 500kV II |  | PA | York | Withdrawn | PPL | 320 | 320 | 304 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4021_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4021_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
X4-022 | Mount Storm 230kV |  | WV | Grant | Withdrawn | Dominion | 358 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012 |  |  | S | No
X4-023 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 155 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4023_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/x4_023_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 3/28/2014 |  | 6/1/2015 |  |  | S | No
X4-024 | Rock Springs 500kV |  | MD | Cecil | Withdrawn | NAEA | 109 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/x4024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/x4024_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/x4024_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 8/21/2013 | Customer Initiated Withdrawal | 7/1/2013 |  |  | S | No
X4-025 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4025_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_025_csa.pdf | Document Posted | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 9/18/2017 |  | 12/31/2018 | 12/31/2018 |  | N | No
X4-026 | Aquasco 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 792 | 792 | 650 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4026_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2011 | N/A | N/A |  | 8/2/2012 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
X4-027 | Linwood 230kV | Phillips Island CT1, CT2,CT3 & ST4 | PA | Delaware | In Service | PECO | 852 | 12 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x4_027_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/8/2011 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 6/1/2018 | N | No
X4-028 | Northerly Island |  | IL | Cook | Withdrawn | ComEd | 0.1 | 0.103 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 12/13/2011 | N/A | N/A |  | 8/30/2012 | Customer Milestone Not Met | 12/12/2011 |  |  | Y | No
X4-029 | Upper Deerfield 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2011 | N/A | N/A |  | 6/8/2012 | Customer Initiated Withdrawal | 1/2/2013 |  |  | N | No
X4-029A 3396286 | ALTE-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
X4-029B 3396289 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2013 | 6/1/2014 | [6 empty] | FF | No
X4-029C 3396292 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3396292_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
X4-029D 3396293 | ALTE-PJM |  | N/A | N/A | Confirmed | Calpine Energy Services, L.P. | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3396293_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3396293_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 12/29/2011 | 6/1/2015 | 6/1/2016 | [6 empty] | FF | No
X4-030 | Freemont 69kV |  | OH | Sandusky | Withdrawn | AEP | 13.8 | 13.75 | 5.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2011 | N/A | N/A |  | 8/27/2012 | Customer Milestone Not Met | 4/1/2013 | 4/1/2013 |  | N | No
X4-031 | Bennett-Farmingdale 34kV | Skudera Solar Farm | NJ | Monmouth | In Service | JCPL | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4031_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x4031_wmpa.pdf |  | Not Required | N/A | N/A |  | 12/30/2011 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 6/17/2015 | Y | No
X4-032 | Zach |  | PA | Montgomery | Withdrawn | PECO | 10 | 4 | 4 |  | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4032_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2011 | N/A | N/A |  | 12/31/2012 | Customer Milestone Not Met | 5/1/2012 |  |  | N | No
X4-033 | Braid 24kV BR-1-Cook 765kV |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2012 | N/A | N/A |  | 11/12/2012 |  |  |  |  | EE | No
X4-034 | Dravosburg–Rankin 23kV |  | PA | Allegheny | Withdrawn | DL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4034_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 1/19/2012 | N/A | N/A |  | 11/16/2012 |  | 8/31/2013 |  |  | N | No
X4-035 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 735.5 | 735.5 | 735.5 | 735.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4035_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4035_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_035_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2012 | N/A | N/A |  |  |  | 6/15/2018 | 6/15/2018 | 5/21/2018 | N | No
X4-036 | Braidwood-Cook |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4036_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-037 | Dresden-DEOK Zone |  | N/A | N/A | Withdrawn | ComEd | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4037_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 9/3/2014 |  |  |  |  | EE | No
X4-038 | TMI-PPL |  | N/A | N/A | Withdrawn | PPL | 500 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/x4038_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/x4038_arr-fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 11/18/2014 |  |  |  |  | EE | No
X4-039 | Pleasant View-Brambleton 230kV | Stonewall Energy Park | VA | Loudoun | In Service | Dominion | 800 | 800 | 750 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4039_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4039_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_039_csa.pdf | Document Posted | N/A | N/A |  | 1/30/2012 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/28/2017 | N | No
X4-040 | Sussex County 12kV |  | DE | Sussex | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4040_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/30/2012 | N/A | N/A |  | 12/8/2014 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | Y | No
X4-041 3618197 | AMIL-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 143 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3618197_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3618197_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | https://www.pjm.com/pub/planning/project-queues/ltf-phase-4/3618197_ltf4.pdf | Executed Agreement and/or Study | https://www.pjm.com/pub/planning/project-queues/ltf-phase-4/3618197_ltf4.pdf | Executed Agreement and/or Study |  | 1/31/2012 | 1/1/2015 | 1/1/2024 | [5 empty] | 4/9/2013 | FF | No
X4-042 | Footedale 12kV |  | PA | Fayette | Withdrawn | APS | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4042_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 7/17/2013 | Customer Milestone Not Met | 5/31/2013 |  |  | N | No
X4-043 | Clinton | Allerton Road Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4043_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x4043_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 9/19/2012 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | No
X4-044 | Aldene 230kV | EF Kenilworth LLC | NJ | Union | In Service | PSEG | 17.9 | 17.9 | 9.9 | 17.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/x4_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_044_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 6/11/2015 | N | No
X4-045 | Southwark 13kV |  | PA | Philadelphia | Withdrawn | PECO | 0.5 | 0.5 | 0.07 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 4/29/2013 | Customer Initiated Withdrawal | 5/1/2012 |  |  | N | No
X4-046 | E Street (Sub 18) 13kV |  | DC | N/A | In Service | PEPCO | 19.5 | 19.5 | 0 | 5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/x4046_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 9/1/2015 | 9/1/2015 | 2/4/2019 | N | No
X4-047 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2012 | N/A | N/A |  | 5/30/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
X4-048 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1000 | 1000 | 1000 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/x4048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/x4048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/x4048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/x4_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/x4_048_csa.pdf | Document Posted | N/A | N/A |  | 1/31/2012 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/8/2018 | N | No
Y1-001 | BL England 138kV | B.L. England Station | NJ | Cape May | Withdrawn | AEC | 452 | 452 | 447 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_001_csa.pdf | Document Posted | N/A | N/A |  | 2/3/2012 | N/A | N/A | 6/1/2021 | 12/18/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
Y1-002 3641682 | NIPS-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 575 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3641682_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3641682_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/3/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-003 | Deep Creek-Penn Mar 115kV | Winding Ridge Wind Farm | MD | Garrett | Withdrawn | APS | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1003_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1003_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_003_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_003_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2012 | N/A | N/A |  | 1/25/2017 |  | 10/31/2017 | 10/31/2017 |  | N | No
Y1-004 3673272 | TVA-PJM |  | N/A | N/A | Confirmed | Calpine Energy Services, L.P. | 720 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3673272_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3673272_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/7/2012 | 6/1/2023 | 6/1/2028 | [6 empty] | FF | No
Y1-005 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 2729 | 350 | 350 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1005_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2012 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 4/10/2016 |  |  | N | No
Y1-006 | Jubal Early-Austinville 138kV | Poplar Camp | VA | Carroll | Suspended | AEP | 72 | 72 | 9.36 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_006_csa.pdf | Document Posted | N/A | N/A |  | 2/14/2012 | N/A | N/A |  |  |  | 3/1/2023 | 3/1/2023 |  | N | No
Y1-007 3721881 | TVA-PJM |  | N/A | N/A | Confirmed | Calpine Energy Services, L.P. | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/3721881_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/3721881_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/14/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1008_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2012 | N/A | N/A |  | 3/26/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Y1-009 | Yardville 13kV |  | NJ | Mercer | Withdrawn | PSEG | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/21/2012 | N/A | N/A |  | 9/26/2012 | Customer Milestone Not Met | 11/30/2012 |  |  | N | No
Y1-010 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 3.9 | 1.9 | 1.9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2012 | N/A | N/A |  | 9/12/2012 | Customer Milestone Not Met | 5/17/2012 |  |  | N | No
Y1-011 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 520 | 520 | 520 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2012 | N/A | N/A |  | 9/11/2012 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y1-012 | Geneva | Geneva Renewable Energy Facility | OH | Ashtabula | In Service | ATSI | 6.5 | 6.48 | 6.48 | 6.48 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1012_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/23/2012 | N/A | N/A |  |  |  | 8/1/2013 | 8/1/2013 | 7/22/2013 | N | No
Y1-013 | McAlpin 12kV |  | WV | Harrison | Withdrawn | APS | 4.8 | 4.8 | 4.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2012 | N/A | N/A |  | 3/28/2012 | Customer Initiated Withdrawal | 9/9/2013 |  |  | N | No
Y1-014 | Worton 12kV |  | MD | Kent | Withdrawn | DPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1014_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2012 | N/A | N/A |  | 8/17/2012 | Customer Initiated Withdrawal | 6/15/2012 |  |  | N | No
Y1-015 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 1000 | 1000 | 870 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/24/2012 | N/A | N/A |  | 7/29/2014 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
Y1-016 | Baker-Hardy 138kV |  | WV | Hardy | Withdrawn | APS | 50 | 50 | 6.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1016_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 4/4/2013 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
Y1-017 | Tabernacle |  | NJ | Burlington | Withdrawn | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1017_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 8/27/2012 | Customer Initiated Withdrawal | 12/31/2013 |  |  | N | No
Y1-018 | Conesville #5 | Conesville #5 | OH | Muskingum | Deactivated | AEP | 405 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/1/2013 | N | No
Y1-019 | Conesville #6 | Conesville #6 | OH | Muskingum | Deactivated | AEP | 405 | 5 | 5 | 5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_019_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 6/1/2013 |  | 6/1/2013 | N | No
Y1-020 | Sussex 34kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 0 | 3.72 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1020_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1020_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/28/2012 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 1/22/2016 | N | No
Y1-021 | Fredericksburg-Cranes Corner 230kV |  | VA | City of Fredericksburg | Withdrawn | Dominion | 64 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 3/28/2012 |  | 6/1/2013 |  |  | S | No
Y1-022 | Cooper |  | PA | York | Withdrawn | PECO | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1022_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 6/21/2013 | Customer Initiated Withdrawal | 10/21/2013 |  |  | N | No
Y1-023 | Felicity 69kV |  | OH | Unknown | Withdrawn | Duke | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1023_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013 |  |  | N | No
Y1-024 | Felicity 12.5kV |  | OH | Unknown | Withdrawn | Duke | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1024_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2012 | N/A | N/A |  | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013 |  |  | N | No
Y1-025 | Raritan River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 785 | 785 | 725 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1025_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 6/4/2013 | Customer Initiated Withdrawal | 5/15/2015 |  |  | N | No
Y1-026 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 180 | 0 | 160 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1026_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1026_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/1/2012 |  | 6/1/2018 | N | No
Y1-027 | Belmon 12.5kV | Westmoreland Landfill Gas Plant | PA | Fayette | Withdrawn | APS | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1027_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 7/11/2016 |  | 12/31/2016 | 12/31/2016 |  | N | No
Y1-028 | Lewis Run 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 125 | 16.25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1028_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 10/19/2012 | Customer Milestone Not Met | 12/1/2014 |  |  | N | No
Y1-029 | Waynesboro-Dooms 115kV |  | VA | Accomack | Withdrawn | Dominion | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 8/29/2012 | Customer Initiated Withdrawal | 9/15/2014 |  |  | N | No
Y1-030 | Forest 69kV |  | OH | Wyandot | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1030_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 2/18/2015 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y1-031 | Erie East 230kV |  | PA | Clarion | Withdrawn | PENELEC | 101.5 | 101.47 | 13.19 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 3/13/2013 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
Y1-032 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | PENELEC | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1032_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 5/8/2013 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Y1-033 | Penn Mar-Rock Wood 115kV |  | PA | Somerset | In Service | PENELEC | 38.3 | 38.3 | 4.98 | 38.3 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1033_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_033_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2012 | N/A | N/A |  |  |  | 3/27/2017 | 3/27/2017 | 12/14/2016 | N | No
Y1-034 | Everson 23kV | Purdys Run Plant | WV | Harrison | Withdrawn | APS | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1034_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1034_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/29/2012 | N/A | N/A |  | 6/7/2016 | Customer Initiated Withdrawal | 1/1/2015 | 1/1/2015 |  | N | No
Y1-035 | Eastlake 138kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | 462 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1035_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1035_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/8/2012 | N/A | N/A |  | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
Y1-036 | Eastlake 345kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | 462 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1036_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/8/2012 | N/A | N/A |  | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017 | 6/1/2017 |  | N | No
Y1-037 |  |  | NJ | Unknown | Withdrawn | JCPL | 6 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2012 | N/A | N/A |  | 4/4/2012 | Customer Milestone Not Met |  |  |  | N | No
Y1-038 | Sparta |  | NJ | Sussex | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1038_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2012 | N/A | N/A |  | 8/28/2012 | Customer Milestone Not Met | 8/31/2013 |  |  | N | No
Y1-039 | Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 5.2 | 5.2 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1039_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2012 | N/A | N/A |  | 9/12/2012 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
Y1-039A_EKPC1 | JK Smith 138 KV |  | KY | Clark | Withdrawn | EKPC | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1039a_ekpc1_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2012 | N/A | N/A |  | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y1-040 4012244 | PJM-LGEE |  | N/A | N/A | Withdrawn | Cargill Power Markets, LLC | 103 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/26/2012 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
Y1-041 4019603 | ALTE-PJM |  | N/A | N/A | Confirmed | Calpine Energy Services, L.P. | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4019603_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4019603_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/27/2012 | 6/1/2016 | 6/1/2017 | [6 empty] | FF | No
Y1-042 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 3.5 | 3.5 | 1.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1042_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 8/28/2012 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y1-043 | Mackeys-Creswell 115kV |  | NC | Washington | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 3/26/2013 | Customer Initiated Withdrawal | 5/31/2015 |  |  | N | No
Y1-044 | Belmont 138kV | Willow Island Hydro Generation Project | WV | Pleasants | In Service | APS | 43.2 | 6.8 | 6.8 | 6.8 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1044_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 7/31/2015 | 7/31/2015 | 11/15/2015 | N | No
Y1-045 | Friendship Manor |  | MD | Howard | Withdrawn | BGE | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1045_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 8/16/2018 |  | 9/1/2017 | 9/1/2017 |  | Y | No
Y1-046 | New Prospect Road 12kV |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 8 | 3.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2012 | N/A | N/A |  | 6/18/2012 | Customer Initiated Withdrawal | 3/13/2013 |  |  | N | No
Y1-047 | North Meshoppen 34.5kV | Roundtop Energy Project | PA | Wyoming | In Service | PENELEC | 15.4 | 15.4 | 15.4 | 15.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_047_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y1-048 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | Withdrawn | Dominion | 372 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/2/2012 | N/A | N/A |  | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
Y1-049 | Wurno 34.5kV | New River Resource Authority Waste Management Facility IRD LEG-E | VA | Pulaski | In Service | AEP | 6 | 6 | 6 | 6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1049_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_049_csa.pdf | Document Posted | N/A | N/A |  | 4/6/2012 | N/A | N/A |  |  |  | 3/31/2013 | 3/31/2013 | 12/1/2014 | N | No
Y1-050 4089954 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2013 | 6/1/2015 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-051 4089967 | CIN-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2014 | 6/1/2023 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-052 4089969 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/6/2012 | 6/1/2014 | 6/1/2022 |  | 5/16/2012 |  |  |  |  | FF | No
Y1-053 4126399 | PJM-NYIS |  | N/A | N/A | Retracted | Invenergy LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4126399_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/11/2012 | 1/1/2014 | 1/1/2019 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-054 | Rochelle 138kV | Rochelle Plant | OH | Hamilton | In Service | DEOK | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/16/2012 | N/A | N/A |  |  |  | 5/1/2013 |  | 5/30/2013 | N | No
Y1-055 | Brick-Lanes Mill 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1055_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2012 | N/A | N/A |  | 8/10/2012 | Customer Milestone Not Met | 6/30/2015 |  |  | N | No
Y1-056 | TMI |  | PA | York | Withdrawn | ME | 879 | 19 | 19 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1056_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2012 | N/A | N/A |  | 6/10/2013 | Customer Initiated Withdrawal | 6/30/2013 |  |  | N | No
Y1-057 | Barbadoes 34kV | Barbadoes Energy Storage Unit | PA | Montgomery | Deactivated | PECO | 2 | 1 | 0.1 | 1 | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_057_csa.pdf | Document Posted | N/A | N/A | 9/4/2013 | 4/25/2012 | N/A | N/A |  |  |  | 12/1/2013 | 12/1/2013 | 9/30/2013 | N | No
Y1-058 4231012 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 33 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4231012_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4231012_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/25/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-059 4231038 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 33 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4231038_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4231038_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/25/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-060 | Aulander 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 15 | 15 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1060_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/25/2012 | N/A | N/A |  | 1/18/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y1-061 4239695 | CPLE-PJM |  | N/A | N/A | Retracted | North Carolina Electric Membership Corporation | 55 |  |  | 55 | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4239695_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2013 | 6/1/2015 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-062 4239873 | CPLE-PJM |  | N/A | N/A | Retracted | North Carolina Electric Membership Corporation | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4239873_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2013 | 6/1/2014 |  | 7/9/2012 |  |  |  |  | FF | No
Y1-063 | Trenton 34.5kV |  | OH | Delaware | In Service | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1063_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 3/31/2014 | 3/31/2014 | 3/31/2014 | N | No
Y1-064 | Berkshire 34.5kV | Berkshire 3.4kV | OH | Delaware | Withdrawn | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1064_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  | 10/31/2013 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y1-065 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 834.1 | 834.1 | 805 | 834.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1065_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_065_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 9/21/2017 | 9/21/2017 | 7/26/2017 | N | No
Y1-066 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | In Service | Dominion | 182 | 0 | 13.3 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1066_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1066_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_066_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 9/1/2013 | N | No
Y1-067 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 64.6 | 8.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2012 | N/A | N/A |  | 11/30/2012 | Customer Milestone Not Met | 11/1/2013 |  |  | N | No
Y1-068 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | Unknown | In Service | Dominion | 50 | 20 | 0 | 20 | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_068_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 10/15/2013 | N | No
Y1-069 | Bay Shore-Fostoria Central 345kV & Bayshore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 799 | 799 | 799 | 799 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_069_csa.pdf | Document Posted | N/A | N/A | 3/15/2016 | 4/27/2012 | N/A | N/A | 3/9/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
Y1-070 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 825 | 825 | 825 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1070_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 4/24/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Y1-071 | Burma 25kV | Kelly Generation Facility | PA | Lawrence | Withdrawn | APS | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 3/10/2017 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | No
Y1-072 | Glen Gardner 12kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 0 | 0.76 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/23/2011 |  | 5/30/2013 | N | No
Y1-073 | Riders Creek |  | NC | Tyrell | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1073_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/4/2012 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Y1-074 | Martin 12kV |  | OH | Summit | Withdrawn | ATSI | 7.8 | 7.8 | 2.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 2/25/2013 | Customer Initiated Withdrawal | 11/1/2013 |  |  | N | No
Y1-075 | Medford 13kV | Reeve's Station South | NJ | Burlington | In Service | PSEG | 1 | 1 | 0.38 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1075_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 12/19/2013 | N | No
Y1-076 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 452 | 18.1 | 18.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 5/29/2012 |  | 6/1/2015 |  |  | N | No
Y1-077 | BL England 138kV | Cape May Energy Center (CMEC) | NJ | Cape May | Withdrawn | AEC | 486 | 34 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_077_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A | 6/1/2023 | 12/18/2019 |  | 6/1/2021 | 6/1/2021 |  | N | No
Y1-078 | Crawford 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1078_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 2/7/2014 | Customer Initiated Withdrawal | 12/31/2012 |  |  | N | No
Y1-079 | Wye Mills 69kV | Wye Mills Solar Site | MD | Talbot | In Service | DPL | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1079_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1079_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 7/29/2016 | 7/29/2016 | 8/24/2016 | N | No
Y1-080 | Dorchester 12kV | Constellation Solar Maryland II, LLC Solar Facility | MD | Dorchester | In Service | DPL | 3.4 | 3.38 | 1.28 | 3.38 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1080_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1080_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 4/30/2015 | 4/30/2015 | 4/30/2015 | N | No
Y1-081 | Wye Mills 12kV |  | MD | Talbot | Withdrawn | DPL | 3.4 | 3.38 | 1.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1081_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/10/2012 | Customer Initiated Withdrawal | 11/1/2013 |  |  | N | No
Y1-082 | Longwood-Wye Mills 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y1082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y1082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y1_082_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 5/2/2016 | S | No
Y1-084 | East Newton–Blairstown 34.5kV | Fredon Solar Farm | NJ | Sussex | Withdrawn | JCPL | 2 | 1.99 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y1084_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 5/16/2017 |  | 5/30/2015 | 5/30/2015 |  | N | No
Y1-085 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 4.4 | 4.4 | 0 |  | Energy | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1085_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 10/4/2012 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y1-086 | Morgans Corner | Morgan's Corner Solar | NC | Pasquotank | In Service | Dominion | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y1086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y1_086_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2012 | N/A | N/A |  |  |  | 1/30/2016 | 1/30/2016 | 12/26/2015 | N | No
Y1-087 | New Hope |  | MD | Wicomico | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y1087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2012 | N/A | N/A |  | 9/6/2012 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y1-088 4273094 | AMIL-PJM |  | N/A | N/A | Withdrawn | Ameren | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2013 | 6/1/2018 | [6 empty] | FF | No
Y1-089 4273103 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 61 | 61 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4273103_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4273103_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 12/15/2019 |  | 12/15/2019 |  |  |  |  | FF | No
Y1-090 4273104 | AMIL-PJM |  | N/A | N/A | Confirmed | Homefield Energy | 105 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4273104_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4273104_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y1-091 4273111 | AMIL-PJM |  | N/A | N/A | Withdrawn | Homefield Energy | 57 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4273111_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4273111_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/30/2012 | 6/1/2015 | 6/1/2020 |  | 10/18/2019 |  |  |  |  | FF | No
Y2-001 | Gosport | SPSA Navy Power Plant | VA | City of Portsmouth | In Service | Dominion | 53.8 | 3.8 | 40 | 3.8 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/2/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 5/22/2014 | N | No
Y2-002 |  |  | N/A | N/A | Withdrawn | PPL | 350 |  |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2012 | N/A | N/A |  | 5/24/2012 | Customer Milestone Not Met |  |  |  | N | No
Y2-003 | Chicago Battery |  | IL | Unknown | Withdrawn | ComEd | 0.6 | 0.6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2003_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/16/2012 | N/A | N/A |  | 3/28/2016 | Customer Milestone Not Met | 8/31/2014 | 8/31/2014 |  | Y | No
Y2-004 4392716 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4392716_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4392716_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 6/1/2022 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-005 4392723 | AMIL-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 117 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4392723_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4392723_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 1/1/2022 | [6 empty] | FF | No
Y2-006 4392735 | IPL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 237 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4392735_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4392735_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2016 | 6/1/2021 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-007 4393092 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4393092_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4393092_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 5/16/2012 | 6/1/2013 | 6/1/2015 |  | 10/25/2013 |  |  |  |  | FF | No
Y2-008 4393106 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4393106_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/16/2012 | 1/1/2013 | 1/1/2015 |  | 8/19/2013 |  |  |  |  | FF | No
Y2-009 4436881 | MECS-PJM |  | N/A | N/A | Withdrawn | Cargill-Alliant LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4436881_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/22/2012 | 1/1/2013 | 1/1/2015 |  | 7/30/2012 |  |  |  |  | FF | No
Y2-010 | Olive-Meadow Lake 345kV |  | IN | White | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2010_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/23/2012 | N/A | N/A |  | 2/6/2014 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y2-011 | Brunot Island I 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 20 | 15 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 5/24/2012 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
Y2-012 | Brunot Island II 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 20 | 15 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | Withdrawn |  | Not Required |  | Not Required |  | Not Required | N/A |  | Not Required | N/A | N/A |  | 5/24/2012 | N/A | N/A |  | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | No
Y2-013 | Linden VFT-Tosco 230kV |  | NJ | Union | Withdrawn | PSEG | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2013_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2012 | N/A | N/A |  | 5/20/2013 | Customer Initiated Withdrawal | 5/1/2017 |  |  | N | No
Y2-014 4465462 | MECS-PJM |  | N/A | N/A | Retracted | JP Morgan Ventures Energy Corporation | 542 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4465462_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/30/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-015 | Eldred-Frackville #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 344 | 337 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2015_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 5/31/2012 | N/A | N/A |  | 10/2/2017 |  | 12/31/2018 | 12/31/2018 |  | N | No
Y2-016 |  |  | N/A | N/A | Withdrawn | PENELEC | 68 |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2012 | N/A | N/A |  | 6/12/2012 | Customer Initiated Withdrawal |  |  |  | N | No
Y2-017 4469835 | WEC-PJM |  | N/A | N/A | Withdrawn | Dominion Energy Marketing, Inc. | 578 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4469835_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/11/2012 | 1/1/2014 | 6/1/2019 |  | 8/16/2012 |  |  |  |  | FF | No
Y2-018 | Pequest River 34.5kV | Warren County Landfill | NJ | Warren | In Service | JCPL | 3.8 | 3.8 | 2.3 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/20/2012 | N/A | N/A |  |  |  | 5/31/2016 | 5/31/2016 | 5/12/2014 | N | No
Y2-019 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 755 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_019_csa.pdf | Document Posted | N/A | N/A | 7/15/2014 | 6/21/2012 | N/A | N/A |  |  |  | 3/31/2016 | 3/31/2016 | 6/29/2015 | N | No
Y2-020 4474313 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4474313_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/26/2012 | 6/1/2016 | 6/1/2017 | [6 empty] | FF | No
Y2-021 4474676 | TVA-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 160 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-022 4474678 | TVA-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-023 4474686 | TVA-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-024 4474688 | TVA-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 13 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-025 4474691 | DUK-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 160 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-026 4474692 | DUK-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-027 4474693 | DUK-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 75 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-028 4474695 | DUK-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 38 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/29/2012 | 7/1/2014 | 7/1/2019 |  | 7/6/2012 |  |  |  |  | FF | No
Y2-029 | Ringoes 12kV |  | N/A | N/A | Withdrawn | JCPL | 0.4 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2012 | N/A | N/A |  | 8/16/2012 |  |  |  |  | N | No
Y2-030 4476631 | LGEE-PJM |  | N/A | N/A | Confirmed | Bluegrass Generating Company LLC | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4476631_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4476631_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-031 4476636 | LGEE-PJM |  | N/A | N/A | Confirmed | Bluegrass Generating Company LLC | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4476636_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4476636_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-032 4476638 | LGEE-PJM |  | N/A | N/A | Confirmed | Bluegrass Generating Company LLC | 167 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4476638_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4476638_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 7/3/2012 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
Y2-033 4476971 | TVA-PJM |  | N/A | N/A | Confirmed | Brookfield Energy Marketing LP | 93 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4476971_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4476971_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/4/2012 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Y2-034 4476972 | DUK-PJM |  | N/A | N/A | Confirmed | Brookfield Energy Marketing LP | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4476972_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4476972_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 7/4/2012 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Y2-035 4479078 | DUK-PJM |  | N/A | N/A | Confirmed | Southern Company Services, Inc. | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4479078_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4479078_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/10/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-036 4479079 | DUK-PJM |  | N/A | N/A | Confirmed | Southern Company Services, Inc. | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4479079_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4479079_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 7/10/2012 | 6/1/2015 | 6/1/2020 | [6 empty] | FF | No
Y2-037 | Tuscarora 12kV #1 | Blythe Township Solar Farm #1 | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2037_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/11/2012 | N/A | N/A |  | 9/10/2013 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | N | Yes
Y2-038 | Tuscarora 12kV #2 |  | PA | Schuylkill | Withdrawn | PPL | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2012 | N/A | N/A |  | 8/23/2012 | Customer Milestone Not Met | 12/31/2012 |  |  | N | No
Y2-039 4480171 | PJM-NYIS |  | N/A | N/A | Retracted | PP&amp;L Energy Plus | 6 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/13/2012 | 9/1/2012 | 9/1/2017 | [6 empty] | FF | No
Y2-040 4480173 | MECS-PJM |  | N/A | N/A | Withdrawn | Renaissance Power LLC | 660 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4480173_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/13/2012 | 6/1/2014 | 6/1/2019 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-041 4482430 | PJM-NYIS |  | N/A | N/A | Withdrawn | PP&amp;L Energy Plus | 6 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/20/2012 | 9/1/2012 | 9/1/2013 | [6 empty] | FF | No
Y2-042 | Oxbow 25kV | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 18.3 | 18.3 | 18.3 | 18.3 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2042_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/23/2012 | N/A | N/A | 10/31/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Y2-043 | Kickapoo | Grand Ridge Battery Storage | IL | Lasalle | In Service | ComEd | 15.7 | 4.5 | 0 | 1.5 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_043_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/30/2012 | N/A | N/A | 12/21/2012 |  |  | 12/31/2012 |  | 12/21/2012 | N | No
Y2-044 4485276 | NYIS-PJM |  | N/A | N/A | Withdrawn | Castleton Commodities Merchant Trading L.P. | 83 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4485276_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4485276_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 7/31/2012 | 6/1/2016 | 6/1/2021 |  | 6/18/2018 |  |  |  |  | FF | No
Y2-045 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 999 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2045_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/2/2012 | N/A | N/A |  |  |  | 7/8/2015 | 7/8/2015 | 1/8/2016 | N | No
Y2-046 4486124 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 800 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4486124_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 8/3/2012 | 1/1/2014 | 1/1/2024 | [6 empty] | FF | No
Y2-047 | Peach Bottom-BGE |  | N/A | N/A | Withdrawn | PECO | 200 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/y2047_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2012 | N/A | N/A |  | 7/15/2015 |  | 1/1/2013 |  |  | EE | No
Y2-048 | Haumesser Road |  | IL | DeKalb | Withdrawn | ComEd | 240 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2012 | N/A | N/A |  | 11/5/2013 | Customer Initiated Withdrawal | 3/29/2013 |  |  | N | No
Y2-049 4487235 | MECS-PJM |  | N/A | N/A | Withdrawn | JP Morgan Ventures Energy Corporation | 542 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4487235_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4487235_ltf2.pdf | Revised |  | Withdrawn |  | N/A | N/A | [5 empty] | 8/8/2012 | 6/1/2015 | 6/1/2020 |  | 9/18/2014 |  |  |  |  | FF | No
Y2-050 | Tidd–Canton Central | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 742 | 742 | 672 | 742 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2050_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y2_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_050_csa.pdf | Document Posted | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 11/1/2017 | 11/1/2017 | 9/25/2017 | N | No
Y2-051 | Brick-Lane Mill 34.5kV | French's Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2051_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2051_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/22/2014 | N | Yes
Y2-052 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 704 | 0 | 34.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2012 | N/A | N/A |  | 7/17/2013 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | N | No
Y2-053 | Lemoyne 138kV |  | OH | Wood | Withdrawn | ATSI | 675 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2053_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 8/15/2012 | N/A | N/A |  | 1/6/2015 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | No
Y2-054 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 13.7 | 13.7 | 13.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2054_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_054_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/15/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/10/2014 | N | No
Y2-055 | Elm Street 34.5kV | United Refining Company Oil Refinery | PA | Warren | Withdrawn | PENELEC | 29 | 29 | 29 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2055_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2055_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2055_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/16/2012 | N/A | N/A |  | 2/15/2019 |  | 1/1/2018 | 1/1/2018 |  | N | No
Y2-056 4489283 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 468 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4489283_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4489283_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 8/17/2012 | 6/1/2017 | 6/1/2022 |  | 6/4/2014 |  |  |  |  | FF | No
Y2-057 | Wyandot 13kV |  | OH | Wyandot | Withdrawn | AEP | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2012 | N/A | N/A |  | 9/14/2012 | Customer Milestone Not Met | 10/1/2013 |  |  | N | No
Y2-058 | Broadford-Jackson's Ferry 765kV |  | VA | Unknown | Withdrawn | AEP | 762 | 762 | 668 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2058_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2012 | N/A | N/A |  | 6/2/2015 | Customer Initiated Withdrawal | 5/15/2017 |  |  | N | No
Y2-059 | Kingston-Westover 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2059_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2012 | N/A | N/A |  | 3/11/2013 | Customer Initiated Withdrawal | 9/1/2015 |  |  | N | No
Y2-060 | North Meshoppen 34.5kv II | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 18.9 | 3.5 | 3.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_060_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2012 | N/A | N/A |  |  |  | 4/1/2015 | 4/1/2015 | 10/15/2015 | N | No
Y2-061 | Cumberland-West Shore 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2061_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2012 | N/A | N/A |  | 3/19/2013 | Customer Initiated Withdrawal | 7/1/2014 |  |  | N | Yes
Y2-062 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2012 | N/A | N/A |  | 1/14/2013 | Customer Initiated Withdrawal | 12/1/2014 |  |  | N | No
Y2-063 | Eldred-Frackville #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 344 | 337 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2063_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2063_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/20/2012 | N/A | N/A |  | 4/14/2015 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y2-064 | Printz | Liberty Electric | PA | Delaware | In Service | PECO | 606.5 | 65.5 | 19 | 65.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_064_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/24/2012 | N/A | N/A |  |  |  | 9/30/2014 | 9/30/2014 | 10/5/2015 | N | No
Y2-065 | Valley-Raccoon 138kV |  | PA | Beaver | Withdrawn | DL | 205 | 205 | 97 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2065_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2012 | N/A | N/A |  | 3/26/2013 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Y2-066 | Suffolk 34.5kV | Suffolk Landfill Units 1-10 | VA | City of Suffolk | Withdrawn | Dominion | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_066_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2012 | N/A | N/A |  | 6/5/2015 | Customer Initiated Withdrawal | 6/1/2015 | 6/1/2015 |  | N | Yes
Y2-067 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 626 | 12 | 12 | 12 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2067_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_067_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2012 | N/A | N/A |  |  |  | 11/1/2012 |  | 3/28/2014 | N | No
Y2-068 4504469 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Inc. | 3081 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4504469_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4504469_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/12/2012 | 6/1/2016 | 6/1/2022 |  | 5/19/2014 |  |  |  |  | FF | No
Y2-069 4505354 | MECS-PJM |  | N/A | N/A | Withdrawn | Renaissance Power LLC | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4505354_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-070 4505355 | MECS-PJM |  | N/A | N/A | Withdrawn | Renaissance Power LLC | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4505355_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-071 4505356 | MECS-PJM |  | N/A | N/A | Withdrawn | Renaissance Power LLC | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4505356_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-072 4505357 | MECS-PJM |  | N/A | N/A | Withdrawn | Renaissance Power LLC | 165 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4505357_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/15/2012 | 6/1/2015 | 6/1/2020 |  | 8/15/2013 |  |  |  |  | FF | No
Y2-073 4505680 | NYISJK-PJM-NYISBC |  | N/A | N/A | Withdrawn | PSEG Energy Resources &amp; Trade LLC | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4505680_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4505680_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/16/2012 | 6/1/2017 | 6/1/2022 |  | 1/8/2013 |  |  |  |  | FF | No
Y2-074 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 8 | 8 | 8 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2074_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_074_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/19/2012 | N/A | N/A |  |  |  | 6/1/2013 | 6/1/2013 | 6/1/2013 | N | No
Y2-075 | Solar City |  | MD | Frederick | Withdrawn | APS | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2075_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/19/2012 | N/A | N/A |  | 5/13/2013 | Customer Milestone Not Met | 4/5/2013 |  |  | Y | Yes
Y2-076 | Clover 230kV | Clover Power Station Unit 1 | VA | Halifax | In Service | Dominion | 445 | 4 | 13.7 | 4 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2012 | N/A | N/A |  |  |  | 6/1/2014 | 6/1/2014 | 6/1/2014 | N | No
Y2-077 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 401 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2077_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_077_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2012 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 12/20/2017 | N | No
Y2-078 | Lakewood #1 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_078_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 6/1/2015 | N | No
Y2-079 | Lakewood #2 230kV | Ocean Peaking Power | NJ | Ocean | In Service | JCPL | 395.6 | 200 | 200 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_079_csa.pdf | Document Posted | N/A | N/A |  | 10/25/2012 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 6/1/2015 | N | No
Y2-080 | Rhodes Lane 500kV |  | PA | Westmoreland | Withdrawn | APS | 1065 | 1065 | 1065 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2080_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2012 | N/A | N/A |  | 11/23/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Y2-081 | Deptford 13kV | Deptford (Kinsley Solar)13kV | NJ | Gloucester | In Service | PSEG | 5 | 5 | 1.9 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2012 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 1/14/2015 | N | Yes
Y2-082 4510276 | MECS-PJM |  | N/A | N/A | Annulled | New Covert Generating Company, LLC | 1200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4510276_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4510276_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/30/2012 | 6/1/2019 | 6/1/2024 |  | 5/18/2016 |  |  |  |  | FF | No
Y2-083 | Essex 138kV |  | NJ | Essex | Withdrawn | PSEG | 218 | 218 | 198 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2083_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 5/29/2013 | Customer Initiated Withdrawal | 5/31/2016 |  |  | N | No
Y2-084 | Dequine 345kV |  | IN | Tippecance | Withdrawn | AEP | 64 | 64 | 3.33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 3/14/2014 | Customer Initiated Withdrawal | 2/28/2014 |  |  | N | No
Y2-085 | Sammis–Star 345kV |  | OH | Carroll | Withdrawn | ATSI | 1050 | 1050 | 1050 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2085_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 7/3/2013 | Customer Initiated Withdrawal | 1/1/2017 |  |  | N | No
Y2-086 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2086_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2012 | N/A | N/A |  | 11/10/2014 | Customer Initiated Withdrawal | 1/1/2015 |  |  | N | No
Y2-087 | Raystown-Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 150.4 | 150.4 | 19.55 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 8/28/2014 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
Y2-088 | Garards Fort 25kV | Bayles-Garards Fort 25kV | PA | Greene | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2088_imp.pdf | Document Posted |  | Withdrawn | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2088_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | Yes
Y2-089 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1370 | 370 | 370 | 370 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_089_csa.pdf | Document Posted | N/A | N/A | 9/30/2017 | 10/31/2012 | N/A | N/A | 3/1/2018 |  |  | 4/1/2019 | 4/1/2019 | 10/2/2018 | N | No
Y2-090 4510751 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/31/2012 | 6/1/2017 | 6/1/2018 | [6 empty] | FF | No
Y2-091 | Toledo Solar |  | OH | Lucas | Withdrawn | ATSI | 0.3 | 0.332 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/13/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
Y2-092 | Walbridge Solar |  | OH | Wood | Withdrawn | ATSI | 0.3 | 0.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 1/13/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
Y2-093 | Easton-Easton Tap 69kV |  | PA | Northampton | Withdrawn | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 12/7/2012 | Queue Not Required | 6/1/2013 |  |  | S | No
Y2-094 | 4 Quad Cities-1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 250 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/y2094_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Y2-095 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 1211 | 1211 | 1211 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013 |  |  | N | No
Y2-096 | Balenger Sewage-Thomas Bakery 34.5kV |  | MD | Frederick | Withdrawn | APS | 47.2 | 47.2 | 47.2 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 12/2/2014 | Customer Initiated Withdrawal | 8/18/2016 |  |  | N | No
Y2-097 | Brunswick 500kV |  | VA | Brunswick | Withdrawn | Dominion | 3102 | 1551 | 1376 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 11/18/2013 | Customer Initiated Withdrawal | 12/1/2018 |  |  | N | No
Y2-098 | Freemansburg #1 12kV | Bethlehem Landfill | PA | Northampton | Deactivated | PPL | 5 | 5 | 5 | 5 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2098_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_098_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  |  |  | 11/1/2012 |  | 8/10/2016 | N | No
Y2-099 | Warrenton 34.5kV | Fauquier County Landfill Units 1 & 2 | VA | Fauquier | Withdrawn | Dominion | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y2_099_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 3/11/2016 | Customer Initiated Withdrawal | 6/1/2016 | 6/1/2016 |  | N | Yes
Y2-100 | Otter Point 34.5kV | Eastern Landfill Gas | MD | Baltimore County | In Service | BGE | 4 | 4 | 4 | 3 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2012 | N/A | N/A |  |  |  | 4/30/2013 | 4/30/2013 | 11/18/2016 | N | No
Y2-101 | Freemansburg #2 12kV |  | PA | Northampton | Withdrawn | PPL | 3.2 | 3.2 | 3.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2012 | N/A | N/A |  | 4/4/2013 | Customer Milestone Not Met | 12/31/2013 |  |  | N | No
Y2-102 | Deepwater 138kV |  | NJ | Salem | Withdrawn | AEC | 193 | 193 | 193 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2102_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 7/10/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Y2-103 | Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 945 | 360 | 360 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2103_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 12/24/2019 |  | 6/1/2016 |  |  | N | No
Y2-104 | Russell Hill-N. Meshoppen 34.5kV |  | PA | Wyoming | Withdrawn | PENELEC | 6.6 | 6.6 | 6.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2012 | N/A | N/A |  | 7/25/2013 | Customer Initiated Withdrawal | 3/1/2014 |  |  | N | No
Y2-105 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 253 | 63 | 50 | 63 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2105_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y2105_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y2_105_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2012 | N/A | N/A |  |  |  | 6/1/2016 |  | 3/25/2015 | N | No
Y2-106 4511112 | ALTE-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/1/2012 | 6/1/2017 | 6/1/2018 | [6 empty] | FF | No
Y2-107 | Robison Park-Argenta 345 kV |  | IN | LeGrange | Withdrawn | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2107_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/19/2013 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
Y2-108 | Crisfield 25kV |  | MD | Somerset | Withdrawn | DPL | 12 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2108_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 12/11/2014 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y2-109 | Bayview 25kV | Bayview | VA | Northampton | In Service | ODEC | 12.5 | 0.5 | 0.5 | 0.5 | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 7/19/2013 | 7/19/2013 | 7/19/2013 | N | No
Y2-110 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 565 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2110_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 3/7/2016 | Customer Initiated Withdrawal | 1/1/2016 |  |  | N | No
Y2-111 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 12 | 12 | 0 | 12 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2111_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_111_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 3/27/2014 | 3/27/2014 | 8/27/2013 | N | Yes
Y2-112 | Keystone 345kV |  | IN | Wells | Withdrawn | AEP | 12 | 12 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2112_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/21/2013 | Customer Milestone Not Met | 3/1/2013 |  |  | N | No
Y2-113 | Morris 138kV | Morris Cogen | IL | Grundy | In Service | ComEd | 120 | 12.6 | 12.6 | 12.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y2_113_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  |  |  | 10/31/2012 |  | 3/14/2014 | N | No
Y2-114 4511399 | CIN-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing, LLC | 95 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4511399_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4511399_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 11/2/2012 | 6/1/2016 | 1/1/2024 | [6 empty] | FF | No
Y2-115 4511400 | TVA-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing, LLC | 102 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4511400_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4511400_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 11/2/2012 | 6/1/2016 | 1/1/2024 |  | 2/1/2019 |  |  |  |  | FF | No
Y2-116 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2116_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013 |  |  | N | No
Y2-117 | Perryman Solar | Perryman Solar Farm | MD | Harford | Withdrawn | BGE | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y2117_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y2117_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/2/2012 | N/A | N/A |  | 8/2/2018 |  | 12/31/2017 | 12/31/2017 |  | N | No
Y3-001 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 705 | 705 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3001_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/5/2012 | N/A | N/A |  | 1/21/2014 | Customer Milestone Not Met | 5/31/2017 | 5/31/2017 |  | N | No
Y3-002 4512681 | MECS-PJM |  | N/A | N/A | Retracted | Cargill Power Markets, LLC | 103 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/6/2012 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
Y3-003 4514773 | PJM-LGEE |  | N/A | N/A | Retracted | AEP Energy Partners, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/12/2012 | 1/1/2015 | 1/1/2016 | [6 empty] | FF | No
Y3-004 4520247 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 468 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/30/2012 | 6/1/2017 | 6/1/2018 |  | 4/1/2013 |  |  |  |  | FF | No
Y3-005 4520326 | PJM-LGEE |  | N/A | N/A | Retracted | AEP Energy Partners, Inc. | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/30/2012 | 1/1/2015 | 1/1/2021 |  | 4/1/2013 |  |  |  |  | FF | No
Y3-006 4522077 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing, LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4522077_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2014 | 1/1/2024 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-007 4522091 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing, LLC | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4522091_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2014 | 1/1/2024 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-008 4522102 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing, LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4522102_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2015 | 1/1/2023 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-009 4522107 | AMIL-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing, LLC | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4522107_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/7/2012 | 1/1/2015 | 1/1/2023 |  | 12/27/2013 |  |  |  |  | FF | No
Y3-010 | Brush Junction-Millheim 46kV |  | PA | Centre | Withdrawn | APS | 70 | 70 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3010_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2012 | N/A | N/A |  | 9/23/2013 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y3-011 4524473 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 468 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4524473_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/17/2012 | 6/1/2017 | 6/1/2018 |  | 12/26/2013 |  |  |  |  | FF | No
Y3-012 | Huron 69kV | Marina Thermal Facility | NJ | Atlantic | In Service | AEC | 15.5 | 7.5 | 0 | 7.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_012_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2012 | N/A | N/A |  |  |  | 12/31/2013 | 12/31/2013 | 1/31/2014 | N | Yes
Y3-013 | Zion Energy Center |  | IL | Lake | Active | ComEd | 585 | 0 | 90 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3013_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 12/27/2012 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 |  | N | No
Y3-014 4526965 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4526965_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-015 4526966 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4526966_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-016 4526971 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4526971_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-017 4526972 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4526972_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-018 4526973 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 38 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4526973_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/28/2012 | 1/1/2015 | 1/1/2024 |  | 3/8/2013 |  |  |  |  | FF | No
Y3-019 4530042 | AMIL-PJM |  | N/A | N/A | Withdrawn | Homefield Energy | 275 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4530042_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-020 4530044 | AMIL-PJM |  | N/A | N/A | Withdrawn | Homefield Energy | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4530044_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-021 4530045 | AMIL-PJM |  | N/A | N/A | Withdrawn | Homefield Energy | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4530045_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 1/9/2013 | 6/1/2015 | 6/1/2020 |  | 3/21/2013 |  |  |  |  | FF | No
Y3-022 4531285 | PJM-LGEE |  | N/A | N/A | Retracted | AEP Energy Partners, Inc. | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4531285_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4531285_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 1/14/2013 | 1/1/2015 | 1/1/2021 | [6 empty] | FF | No
Y3-023 | Country Side 12kV | Wabash Valley Power Association, Inc. | IN | Elkhart | In Service | AEP | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3023_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3023_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-024 | Bluff Point 12kV | Wabash Valley Power Association, Inc. | IN | Jay | In Service | AEP | 3.2 | 3.2 | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3024_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3024_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/18/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/1/2015 | N | Yes
Y3-025 | Bridge-South Park 12kV | Charleston Clean Energy | WV | Kanawha | In Service | AEP | 3.2 | 3.18 | 3.18 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_025_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/22/2013 | N/A | N/A |  |  |  | 5/29/2015 | 5/29/2015 | 5/29/2019 | N | No
Y3-026 | Burlington 26kV | Burlington (L&D Solar) 26kV | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_026_csa.pdf | Document Posted | N/A | N/A |  | 1/25/2013 | N/A | N/A |  |  |  | 9/24/2015 | 9/24/2015 | 1/26/2016 | N | Yes
Y3-027 | Camden 26kV | Camden (Cinnaminson Solar) 26kV | NJ | Burlington | Withdrawn | PSEG | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3027_wmpa.pdf |  | Not Required | N/A | N/A |  | 1/25/2013 | N/A | N/A |  | 2/18/2015 | Customer Initiated Withdrawal | 5/28/2015 | 5/28/2015 |  | N | Yes
Y3-028 4534356 | CIN-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4534356_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4534356_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 1/25/2013 | 6/1/2017 | 6/1/2022 |  | 7/14/2014 |  |  |  |  | FF | No
Y3-029 | Damascus-Mt. Airy 34.5kV | Hickory Plains Hydroponics | MD | Frederick | Withdrawn | APS | 4.4 | 4.375 | 4.375 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3029_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3029_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/1/2013 | N/A | N/A |  | 4/4/2018 |  | 12/31/2017 | 12/31/2017 |  | N | Yes
Y3-030 | Sandy Springs-High Ridge 230kV |  | MD | Unknown | Withdrawn | BGE | 127 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3030_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3030_fac.pdf | Document Posted |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 2/4/2013 | N/A | N/A |  | 4/3/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
Y3-031 | Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 130.9 | 130.9 | 17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3031_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2013 | N/A | N/A |  | 9/16/2013 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
Y3-031A_EKPC2 | Flemingsburg 138 KV |  | KY | Unknown | Withdrawn | EKPC | 150.3 | 150.28 | 19.53 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3031a_ekpc2_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3031a_ekpc2_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2013 | N/A | N/A |  | 5/1/2014 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
Y3-032 4540149 | MECS-PJM |  | N/A | N/A | Annulled | CMS Energy Resource Management Company | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4540149_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4540149_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 2/19/2013 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Y3-033 | Chestertown-Millington 69kV | Mills Branch Wind Farm | MD | Kent | Withdrawn | DPL | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3033_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_033_csa.pdf | Document Posted | N/A | N/A |  | 2/19/2013 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 4/30/2018 | 4/30/2018 |  | N | No
Y3-034 | Eldred-Pine Grove 690kV | Stonegate Renewable Energy | PA | Schuylkill | In Service | PPL | 10.5 | 0 | 1.8 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/20/2013 | N/A | N/A |  |  |  | 12/31/2013 |  | 12/26/2013 | N | No
Y3-035 | Mole Creek 345kV |  | IL | Marshall | Withdrawn | ComEd | 97.5 | 97.5 | 12.675 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2013 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
Y3-036 | Gavin Unit 2 | Gavin Unit #2 | OH | Gallia | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A | 10/1/2020 |  |  | 12/31/2014 | 12/31/2014 | 1/14/2015 | N | No
Y3-037 | Amos Unit 3 | John Amos Generating Plant Unit No. 3 | WV | Putnam | In Service | AEP | 1336 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 4/1/2015 | N | No
Y3-038 | Rockport Unit 1 | Rockport Unit #1 | IN | Spencer | In Service | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 6/30/2017 | N | No
Y3-039 | Clinch River Unit 1 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 4/15/2016 | 4/15/2016 | 5/27/2016 | N | No
Y3-040 | Clinch River Unit 2 | Clinch River Power Plant | VA | Russell | In Service | AEP | 250 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/6/2016 | 6/6/2016 | 5/23/2016 | N | No
Y3-041 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 62 | 62 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3041_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 1/29/2015 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
Y3-042 | Elrama 69kV |  | PA | Washington | Withdrawn | DL | 460 | 460 | 460 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 10/22/2013 | Customer Initiated Withdrawal | 6/1/2015 |  |  | N | No
Y3-043 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 760 | 760 | 760 | 760 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_043_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
Y3-044 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 206 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_044_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-045 | Bergen | Bergen Genertating Station | NJ | Bergen | In Service | PSEG | 1235 | 0 | 5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_045_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-046 | Linden | Linden Generating Station | NJ | Union | Withdrawn | PSEG | 178 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_046_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 6/30/2017 |  | 3/31/2015 | 3/31/2015 | 2/13/2015 | N | No
Y3-047 | Essex |  | NJ | Essex | Withdrawn | PSEG | 299 | 10 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3047_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pub/planning/project-queues/isa/y3_047_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
Y3-048 | Burlington | Burlington Generating Station | NJ | Burlington | In Service | PSEG | 207 | 2 | 3 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_048_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-049 | Edison |  | NJ | Middlesex | Withdrawn | PSEG | 582 | 0 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3049_fea.pdf | Document Posted |  |  |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_049_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2013 | N/A | N/A |  | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013 |  |  | N | No
Y3-050 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 497 | 24 | 21 | 24 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3050_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/21/2015 | N | No
Y3-051 | Linden | Linden Generating Station | NJ | Union | In Service | PSEG | 1626 | 47 | 4 | 47 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3051_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3051_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 8/29/2016 | N | No
Y3-052 | Bergen |  | NJ | Bergen | In Service | PSEG | 1285 | 50 | 10 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3052_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3052_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 3/31/2015 | 3/31/2015 | 10/29/2015 | N | No
Y3-053 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 537 | 40 | 13 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3053_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_053_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2013 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 10/21/2015 | N | No
Y3-054 | Milford 138kV | Milford Solar | DE | Kent | Withdrawn | DPL | 12 | 12 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3054_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/5/2013 | N/A | N/A |  | 5/16/2016 |  | 12/31/2014 | 12/31/2014 |  | N | No
Y3-055 4543017 | PJM-TVA |  | N/A | N/A | Retracted | Tennessee Valley Authority | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4543017_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/5/2013 | 1/1/2015 | 1/1/2017 |  | 5/16/2013 |  |  |  |  | FF | No
Y3-056 | Pioneer Crossing 69kV | Pioneer Crossing | PA | Berks | In Service | ME | 8 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/12/2013 | N/A | N/A |  |  |  | 10/31/2013 | 10/31/2013 | 9/1/2013 | N | No
Y3-057 | Forest Park |  | MD | Charles | Withdrawn | PEPCO | 12 | 12 | 4.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2013 | N/A | N/A |  | 4/12/2013 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y3-058 | Rockawalkin 69kV | Rockfish Solar Power Plant | MD | Wicomico | In Service | DPL | 15 | 15 | 5.7 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3058_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/13/2013 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 2/22/2016 | N | No
Y3-059 4545202 | PJM-MECS |  | N/A | N/A | Confirmed | Constellation | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4545202_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4545202_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 3/14/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Y3-060 4545220 | PJM-CPLE |  | N/A | N/A | Withdrawn | Southeastern Power Administration | 89 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4545220_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/14/2013 | 1/1/2014 | 1/1/2019 | [6 empty] | FF | No
Y3-061 4545319 | DUK-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 409 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/14/2013 | 6/1/2016 | 6/1/2021 |  | 4/8/2013 |  |  |  |  | FF | No
Y3-062 | Erie East 34.5kV | North East Wind Farm | PA | Erie | Withdrawn | PENELEC | 18.7 | 18.7 | 2.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3062_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/18/2013 | N/A | N/A |  | 12/17/2014 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | No
Y3-063 | State Line 138kV |  | IN | Lake | Withdrawn | ComEd | 1161 | 1161 | 1161 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3063_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2013 | N/A | N/A |  | 9/9/2013 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Y3-064 | Pierce-Beckjord 138kV |  | OH | Clermont | Engineering and Procurement | DEOK | 160 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 155 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3064_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_064_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2013 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 |  | S | No
Y3-065 4548142 | PJM-CIN |  | N/A | N/A | Retracted | AEP Energy Partners, Inc | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/26/2013 | 1/1/2015 | 1/1/2021 |  | 4/18/2013 |  |  |  |  | FF | No
Y3-066 4548245 | AMIL-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 580 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4548245_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/26/2013 | 6/1/2017 | 6/1/2022 |  | 6/7/2013 |  |  |  |  | FF | No
Y3-067 4548247 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4548247_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4548247_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/26/2013 | 6/1/2016 | 6/1/2017 |  | 7/23/2014 |  |  |  |  | FF | No
Y3-068 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 525 | 525 | 525 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_068_csa.pdf | Document Posted | N/A | N/A |  | 3/29/2013 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
Y3-069 4549810 | NIPS-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 233 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4549810_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4549810_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/2/2013 | 6/1/2017 | 1/1/2024 | [6 empty] | FF | No
Y3-070 4549811 | NIPS-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4549811_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/2/2013 | 1/1/2015 | 1/1/2024 |  | 6/10/2013 |  |  |  |  | FF | No
Y3-071 4549812 | NIPS-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 35 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4549812_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/2/2013 | 1/1/2015 | 1/1/2024 |  | 6/10/2013 |  |  |  |  | FF | No
Y3-072 4549813 | NIPS-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 233 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4549813_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4549813_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/2/2013 | 6/1/2017 | 1/1/2024 | [6 empty] | FF | No
Y3-073 | W.H. Zimmer Station |  | OH | Clermont | Withdrawn | DEOK | 1350 | 50 | 50 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3073_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/10/2013 | N/A | N/A |  | 2/24/2016 | Customer Initiated Withdrawal | 6/1/2013 |  |  | N | No
Y3-074 | Ashton 480V |  | MD | Montgomery | In Service | BGE | 0.4 | 0.372 | 0 | 0.37 | Energy | Generation Interconnection | Hydro |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3074_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/12/2013 | N/A | N/A |  |  |  | 7/1/2014 | 7/1/2014 | 10/1/2014 | Y | No
Y3-075 4553095 | CIN-PJM |  | N/A | N/A | Withdrawn | Union Power Partners L.P. | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2015 | 6/1/2016 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-076 4553097 | CIN-PJM |  | N/A | N/A | Withdrawn | Union Power Partners L.P. | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-077 4553099 | CIN-PJM |  | N/A | N/A | Withdrawn | Union Power Partners L.P. | 250 |  |  |  | Energy | Long-Term Firm Transmission | [9 empty] | Not Required |  | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-078 4553101 | CIN-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 500 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/15/2013 | 6/1/2016 | 6/1/2021 |  | 4/29/2013 |  |  |  |  | FF | No
Y3-079 4553350 | DUK-PJM |  | N/A | N/A | Retracted | Calpine Energy Services | 409 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/16/2013 | 6/1/2017 | 6/1/2022 |  | 5/7/2013 |  |  |  |  | FF | No
Y3-080 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 20 | 8 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3080_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_080_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 3/27/2014 | 3/27/2014 | 9/24/2013 | N | No
Y3-081 |  |  | N/A | N/A | Withdrawn | ATSI | 0.1 |  |  |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2013 | N/A | N/A |  | 4/25/2013 |  |  |  |  | N | No
Y3-082 | Easton-Trappe Tap 69kV |  | MD | Talbot | In Service | DPL | 63 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3082_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_082_csa.pdf | Document Posted | N/A | N/A |  | 4/19/2013 | N/A | N/A |  |  |  | 6/1/2014 |  | 1/29/2016 | S | No
Y3-083 4554680 | MECS-PJM |  | N/A | N/A | Withdrawn | CMS Energy Resource Management Company | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4554680_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4554680_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/22/2013 | 6/1/2016 | 6/1/2017 |  | 5/12/2015 |  |  |  |  | FF | No
Y3-084 4555130 | AMIL-PJM |  | N/A | N/A | Retracted | Biogas Energy Solutions, LLC | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4555130_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-085 4555141 | AMIL-PJM |  | N/A | N/A | Retracted | Biogas Energy Solutions, LLC | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4555141_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-086 4555143 | MEC-PJM |  | N/A | N/A | Retracted | Biogas Energy Solutions, LLC | 4 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4555143_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/24/2013 | 6/1/2014 | 6/1/2019 |  | 6/11/2013 |  |  |  |  | FF | No
Y3-087 | Beaverbrook 13kV | Beaverbrook (Kinsley Solar) | NJ | Gloucester | In Service | PSEG | 3.8 | 3.8 | 1.44 | 3.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_087_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 6/30/2015 |  | 1/14/2015 | N | No
Y3-088 | Kendall I | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1158.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-089 | Kendall II | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1178.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-090 | Kendall III | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1198.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_090_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-091 | Kendall IV | Kendall Energy Center | IL | Grundy | In Service | ComEd | 1218.8 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3091_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_091_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 12/1/2015 | 12/1/2015 | 5/23/2017 | N | No
Y3-092 | Erie West 345kV | ITC Lake Erie Connector | PA | Erie | Engineering and Procurement | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; NF/TWR 1000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/y3092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-isa/y3_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/y3_092_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2013 | N/A | N/A |  |  |  | 3/31/2024 | 3/31/2024 |  | S | No
Y3-093 | Erie West 345kV |  | PA | Erie | Withdrawn | PENELEC | 1000 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 1000; F/TWR 1000 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3093_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2013 | N/A | N/A |  | 10/9/2013 | Customer Initiated Withdrawal | 1/1/2017 | 1/1/2017 |  | S | No
Y3-094 4556115 | CIN-PJM |  | N/A | N/A | Annulled | Union Power Partners, L.P. | 223 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4556115_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4556115_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/29/2013 | 6/1/2017 | 6/1/2022 |  | 8/23/2016 |  |  |  |  | FF | No
Y3-095 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 5/24/2013 | Customer Initiated Withdrawal | 9/25/2013 |  |  | N | No
Y3-096 | Hanging Rock 765kV |  | OH | Lawrence | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3096_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 4/23/2015 | Customer Initiated Withdrawal | 3/31/2015 | 3/31/2015 |  | N | No
Y3-097 | Trent (Jug St.) 34.5kV |  | OH | Delaware | Withdrawn | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3097_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 9/30/2015 |  |  | N | Yes
Y3-098 | Printz |  | PA | Delaware | Withdrawn | PECO | 735 | 735 | 735 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/26/2013 | Customer Initiated Withdrawal | 10/1/2017 |  |  | N | No
Y3-099 | Beckjord 2 MW-1 | Beckjord Battery #1 | OH | Clermont | In Service | DEOK | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_099_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2013 | N/A | N/A |  |  |  | 5/1/2015 | 5/1/2015 | 1/21/2015 | N | No
Y3-100 | Beckjord 2 MW-2 | Beckjord Battery #2 | OH | Clermont | In Service | DEOK | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_100_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2013 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
Y3-101 | Cedar 12kV |  | NJ | Ocean | Withdrawn | AEC | 5.7 | 5.7 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2013 | N/A | N/A |  | 9/30/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Y3-102 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1000 | 166 | 135 | 166 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3102_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_102_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 8/21/2017 | 8/21/2017 | 7/27/2017 | N | No
Y3-103 | Valley-Raccoon 138kV | Pennsylvania Chemicals Generating Facility | PA | Beaver | Under Construction | DL | 205 | 205 | 97 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3103_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3103_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/y3_103_csa.pdf | Document Posted | N/A | N/A | 11/12/2019 | 4/30/2013 | N/A | N/A | 9/1/2020 |  |  | 4/30/2020 | 4/30/2020 |  | N | No
Y3-104 | Sullivan Trail-Stanton 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3104_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3104_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 1/22/2015 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
Y3-105 | Belvidere-Gilbert-115kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3105_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 10/1/2013 | Customer Milestone Not Met | 1/1/2015 |  |  | N | No
Y3-106 | Belleville-Rutland 138kV | Belleville Hydroelectric Plant | WV | Wood | In Service | AEP | 49 | 7 | 7 | 3 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3106_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/y3_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 12/31/2014 | N | No
Y3-107 | Bergen 230kV |  | NJ | Bergen | In Service | PSEG | 1220 | 35 | 45 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/y3107_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/y3_107_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  |  |  | 4/1/2015 |  | 10/29/2015 | N | No
Y3-108 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 1420 | 110 | 107 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 11/20/2013 | Customer Initiated Withdrawal | 3/1/2014 |  |  | N | No
Y3-109 | Nyswaner 25kV | Red Glen Generator | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3109_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/y3109_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 1/25/2018 |  | 12/31/2016 | 12/31/2016 |  | N | Yes
Y3-110 | North Salisbury-Worcester 69kV |  | MD | Wicomico | Withdrawn | DPL | 15.7 | 15.7 | 15.7 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 10/9/2013 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Y3-111 | Harborcreek Township 34kV |  | PA | Erie | Withdrawn | PENELEC | 18.7 | 18.7 | 2.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 9/22/2013 | Customer Milestone Not Met | 4/1/2014 |  |  | N | No
Y3-112 | Butler-Shanor Manor 138kV |  | PA | Armstrong | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/y3112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/y3112_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 4/25/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Y3-113 | Russell Hill-W. Meshoppen |  | PA | Wyoming | Withdrawn | PENELEC | 10 | 3.4 | 3.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 7/25/2013 | Customer Initiated Withdrawal | 9/1/2014 |  |  | N | No
Y3-114 |  |  | N/A | N/A | Withdrawn | PENELEC | 19.9 |  |  |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 4/30/2013 | Customer Initiated Withdrawal |  |  |  | N | No
Y3-115 4556438 | PJM-WEC |  | N/A | N/A | Withdrawn | Invenergy LLC | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4556438_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4556438_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 5/1/2014 |  |  |  |  | FF | No
Y3-116 4556441 | PJM-AMIL |  | N/A | N/A | Retracted | Invenergy LLC | 75 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4556441_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-117 4556443 | PJM-NIPS |  | N/A | N/A | Retracted | Invenergy LLC | 175 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4556443_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-118 4556445 | PJM-AMIL |  | N/A | N/A | Retracted | Invenergy LLC | 250 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4556445_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/30/2013 | 6/1/2015 | 6/1/2020 |  | 7/10/2013 |  |  |  |  | FF | No
Y3-119 | E. Lynchburg-Peaks View 34.5kV |  | VA | City of Lynchburg | Withdrawn | AEP | 19 | 19 | 7 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/y3119_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 11/12/2014 | Customer Milestone Not Met | 9/30/2015 |  |  | N | Yes
Y3-120 | Conowingo 230kV |  | MD | Harford | Withdrawn | PECO | 617 | 45 | 45 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/y3120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2013 | N/A | N/A |  | 9/27/2013 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-001 | Blairsville East-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | APS | 15.7 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2013 | N/A | N/A |  | 9/3/2013 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z1-002 4558624 | DUK-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 409 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4558624_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/8/2013 | 6/1/2017 | 6/1/2022 |  | 7/30/2013 |  |  |  |  | FF | No
Z1-003 4558888 | NYIS-PJM |  | N/A | N/A | Retracted | Castleton Commodities Merchant Trading L.P. | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/9/2013 | 1/1/2016 | 1/1/2023 |  | 5/30/2013 |  |  |  |  | FF | No
Z1-004 |  |  | N/A | N/A | Withdrawn | Unknown |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/10/2013 | N/A | N/A |  | 5/14/2013 | Queue Not Required |  |  |  | S | No
Z1-005 4559728 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services, L.P. | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4559728_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/13/2013 | 6/1/2014 | 6/1/2015 |  | 7/30/2013 |  |  |  |  | FF | No
Z1-006 | NIPSCO-BOCGASE2 |  | N/A | N/A | Withdrawn | AEP | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [5 empty] | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2014 | N/A | N/A |  | 5/29/2015 |  |  |  |  | EE | No
Z1-007 4561037 | CIN-PJM |  | N/A | N/A | Annulled | American Municipal Power, Inc. | 87 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4561037_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4561037_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2017 | 6/1/2022 |  | 2/21/2017 |  |  |  |  | FF | No
Z1-008 4561044 | LGEE-PJM |  | N/A | N/A | Retracted | American Municipal Power, Inc. | 59 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2021 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-009 4561079 | NIPS-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2015 | 1/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-010 4561082 | NIPS-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2017 | 6/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-011 4561084 | CIN-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2023 |  | 6/30/2013 |  |  |  |  | FF | No
Z1-012 4561085 | CIN-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2016 | 1/1/2023 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-013 4561088 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 44 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 6/1/2016 | 6/1/2022 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-014 4561089 | ALTE-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/17/2013 | 1/1/2016 | 1/1/2021 |  | 6/7/2013 |  |  |  |  | FF | No
Z1-015 | Springdale 3, 4, 5 | Springdale | PA | Allegheny | In Service | APS | 590 | 0 | 26 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/20/2013 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/21/2015 | N | No
Z1-016 | Hanna-Juniper 345kV |  | OH | Portage | Withdrawn | ComEd | 140 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 6/13/2013 | Queue Not Required |  |  |  | S | No
Z1-017 | Limerick-Peach Bottom |  | PA | Montgomery | Withdrawn | PECO | 181 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1017_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2013 | N/A | N/A |  | 2/20/2014 | Customer Milestone Not Met | 6/1/2014 |  |  | S | No
Z1-018 | Richland III 138kV |  | OH | Defiance | Withdrawn | ATSI | 591 | 591 | 591 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1018_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/29/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 5/15/2016 |  |  | N | No
Z1-019 4566427 | NYIS-PJM |  | N/A | N/A | Withdrawn | Castleton Commodities Merchant Trading L.P. | 600 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4566427_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4566427_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 6/5/2013 | 1/1/2016 | 1/1/2023 |  | 6/18/2018 |  |  |  |  | FF | No
Z1-020 | Richland I 138kV |  | OH | Defiance | Withdrawn | ATSI | 48 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/22/2014 | Customer Milestone Not Met | 4/30/2014 |  |  | N | No
Z1-021 | Richland II 138kV |  | OH | Defiance | Withdrawn | ATSI | 390 | 36 | 36 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/22/2014 | Customer Milestone Not Met | 4/30/2014 |  |  | N | No
Z1-022 | Stryker 138kV |  | OH | Defiance | Withdrawn | ATSI | 22 | 5 | 5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1022_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 4/30/2014 |  |  | N | No
Z1-023 4566738 | TVA-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4566738_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4566738_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 6/6/2013 | 1/1/2016 | 1/1/2024 |  | 5/12/2014 |  |  |  |  | FF | No
Z1-024 4566952 | PJM-AMIL |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-025 4566958 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 206 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4566958_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4566958_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 6/7/2013 | 6/1/2017 | 6/1/2022 |  | 2/1/2019 |  |  |  |  | FF | No
Z1-026 4566959 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-027 4566961 | NIPS-PJM |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 124 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4566961_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4566961_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 6/7/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-028 4566962 | NIPS-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/7/2013 |  |  |  | 6/30/2013 |  |  |  |  | FF | No
Z1-029 4567977 | CIN-PJM |  | N/A | N/A | Annulled | American Municipal Power, Inc. | 59 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4567977_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4567977_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/11/2013 | 6/1/2016 | 6/1/2021 |  | 2/21/2017 |  |  |  |  | FF | No
Z1-030 | Bay Shore 138kV |  | OH | Lucas | Withdrawn | ATSI | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1030_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2013 | N/A | N/A |  | 4/1/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-031 | Lake Nelson-Middlesex 230kV |  | NJ | Unknown | Withdrawn | JCPL | 56 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1031_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2013 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 7/31/2014 |  |  | S | No
Z1-032 4571836 | PJM-IPL |  | N/A | N/A | Confirmed | Southern Indiana Gas &amp; Electric | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 4/1/2015 | 4/1/2020 | [6 empty] | FF | No
Z1-033 | Hudson 230kV |  | NJ | Unknown | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | DC | F/TIR 400; F/TWR 410 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/2/2013 | N/A | N/A |  | 12/18/2013 | Customer Initiated Withdrawal | 10/30/2017 |  |  | S | No
Z1-034 | Niles 138kV |  | OH | Trumbull | Withdrawn | ATSI | 217 | 217 | 217 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2013 | N/A | N/A |  | 7/31/2013 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-035 | Lake Erie Wind 138kV |  | OH | Unknown | Active | ATSI | 18 | 18 | 2.34 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1035_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 7/5/2013 | N/A | N/A |  |  |  | 9/30/2017 |  |  | N | No
Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | Suspended | Dominion | 300.3 | 300.3 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_036_csa.pdf | Document Posted | N/A | N/A |  | 7/23/2013 | N/A | N/A | 10/31/2020 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
Z1-037 | Krendale-Shanor Manor 138kV |  | PA | Butler | Withdrawn | APS | 43 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1037_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2013 | N/A | N/A |  | 5/6/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | S | No
Z1-038 | Florey Knob 34.5kV | Florey Knob Generating Station | PA | Wyoming | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_038_csa.pdf | Document Posted | N/A | N/A |  | 8/1/2013 | N/A | N/A |  | 2/21/2019 |  | 3/31/2017 | 3/31/2017 |  | N | No
Z1-039 4582175 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 260 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/6/2013 | 6/1/2017 | 6/1/2023 | [6 empty] | FF | No
Z1-040 4582207 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 260 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/6/2013 | 1/1/2017 | 1/1/2022 |  | 8/22/2013 |  |  |  |  | FF | No
Z1-041 | Rock Springs 500kV | Rock Springs Units #1 & #2 | MD | Cecil | In Service | Essential Power | 327 | 2 | 2 | 2 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_041_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/14/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/28/2015 | N | No
Z1-042 | Belleville/New Holland-Logan 46kV |  | PA | Mifflin | Withdrawn | PENELEC | 46 | 46 | 9.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2013 | N/A | N/A |  | 11/3/2014 | Customer Initiated Withdrawal | 12/31/2015 | 12/31/2015 |  | N | No
Z1-043 4585350 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing, LLC | 260 | 260 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4585350_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4585350_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 8/22/2013 | 6/1/2017 | 6/1/2022 |  | 10/18/2019 |  |  |  |  | FF | No
Z1-044 4586363 | PJM-MECS |  | N/A | N/A | Withdrawn | First Energy Solutions | 894 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2016 | 6/1/2021 | [6 empty] | FF | No
Z1-045 4586409 | PJM-MECS |  | N/A | N/A | Retracted | FirstEnergy Solutions Corp. | 894 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4586409_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4586409_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2016 | 6/1/2021 |  | 6/11/2014 |  |  |  |  | FF | No
Z1-046 4586438 | TVA-PJM |  | N/A | N/A | Confirmed | Dynegy Power Marketing, LLC | 240 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4586438_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4586438_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 8/27/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-047 | Albright |  | PA | Mifflin | Withdrawn | PENELEC | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1047_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Z1-048 | Rivesville |  | WV | Marion | Withdrawn | APS | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/28/2014 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
Z1-049 | Willow Island |  | WV | Pleasants | Withdrawn | APS | 464 | 464 | 464 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
Z1-050 | Kittatinny 230kV | Yards Creek Pumped Storage Hydro-electric Generating Station | NJ | Warren | In Service | JCPL | 420 | 20 | 20 | 20 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 3/1/2014 |  | 5/1/2014 | N | No
Z1-051 | D.C. Cook Unit 2 | D.C. Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 1192 | 102 | 83 | 102 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 11/18/2016 | 11/18/2016 | 1/14/2017 | N | No
Z1-052 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | Partially in Service - Under Construction | PEPCO | 800 | 64.5 | 44.5 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_052_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_052_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2013 | N/A | N/A |  |  |  | 8/15/2018 | 8/15/2018 | 7/23/2018 | N | No
Z1-053 | Monocacy 12.47 KV - Worman Mill Feeder |  | MD | Frederick | Withdrawn | APS | 0.3 | 0.3 | 0 | 20 | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/5/2013 | N/A | N/A |  | 9/25/2013 | Customer Initiated Withdrawal | 4/15/2014 |  |  | Y | No
Z1-054 | Byron-Cherry Valley |  | IL | Ogle | Withdrawn | ComEd | 26 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z1054_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2013 | N/A | N/A |  | 4/9/2015 | Customer Initiated Withdrawal | 9/30/2014 |  |  | S | No
Z1-055 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 714 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1055_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_055_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-056 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 6 | 6 | 6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/11/2013 | N/A | N/A |  |  |  | 6/1/2016 |  | 1/31/2017 | N | No
Z1-057 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 15.9 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_057_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 10/1/2013 |  | 5/6/2014 | N | No
Z1-058 | Linden 1 - 138kV | Linden Generating Station | NJ | Union | In Service | PSEG | 491 | 23 | 36 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1058_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1058_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 8/29/2016 | N | No
Z1-059 | Linden 2 - 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 800 | 23 | 18 | 23 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1059_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/29/2016 | N | No
Z1-060 4593055 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 101 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4593055_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-061 4593064 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 61 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4593064_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-062 4593068 | NYIS-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 139 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4593068_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/30/2013 | 6/1/2018 | 6/1/2023 |  | 12/10/2013 |  |  |  |  | FF | No
Z1-063 | Kirk 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-064 | Shannon 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1064_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-065 | Wiley 34.5kV | Willey Energy Storage Project | OH | Hamilton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/1/2015 | N | Yes
Z1-066 | Arnold 34.5kV | Green Mountain Battery | PA | Somerset | In Service | PENELEC | 10.4 | 10.4 | 0 | 8 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1066_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/30/2013 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 12/30/2015 | N | No
Z1-067 4593370 | DUK-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 50 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4593370_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4593370_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 10/1/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-068 | Birdneck 34.5kV |  | VA | City of Virginia Beach | Under Construction | Dominion | 12 | 12 | 1.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1068_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1068_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/10/2013 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | Yes
Z1-069 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 70 | 70 | 13.3 | 70 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_069_csa.pdf | Document Posted | N/A | N/A |  | 10/24/2013 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
Z1-070 4598661 | AMIL-PJM |  | N/A | N/A | Retracted | Exelon Generation Company LLC | 1045 | 1045 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4598661_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4598661_ltf2.pdf | Executed Agreement and/or Study | https://www.pjm.com/pub/planning/project-queues/ltf-phase-3/4598661_ltf3.pdf | Executed Agreement and/or Study |  | N/A | N/A |  | Withdrawn |  | Withdrawn |  | 10/25/2013 | 6/1/2017 | 6/1/2022 |  | 6/28/2016 |  |  |  |  | FF | No
Z1-071 4598677 | TVA-PJM |  | N/A | N/A | Confirmed | Pentacles Electric, LLLP | 82 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4598677_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4598677_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/25/2013 | 6/1/2017 | 6/1/2022 | [6 empty] | FF | No
Z1-072 | Crescent Ridge | Crescent Ridge Wind Farm | IL | Bureau | In Service | ComEd | 54.5 | 0 | 9.7 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1072_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 6/1/2016 | N | No
Z1-073 | Mendota Hills |  | IL | Lee | In Service | ComEd | 50.4 | 0 | 5.2 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1073_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_073_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2013 | N/A | N/A |  |  |  | 12/31/2014 | 12/31/2014 | 8/5/2015 | N | No
Z1-074 | Garrett-Jenning 34.5kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 2.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1074_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2013 | N/A | N/A |  | 4/23/2014 | Customer Milestone Not Met | 12/18/2015 |  |  | N | No
Z1-075 4599518 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
Z1-076 | Stockton 1 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 14 | 5.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1076_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
Z1-077 | Stockton 2 69kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
Z1-078 | Broadford-Jackson Ferry Phase II 765kV |  | VA | Unknown | Withdrawn | AEP | 777 | 777 | 777 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 11/10/2014 | Customer Initiated Withdrawal | 6/15/2018 |  |  | N | No
Z1-079 | Todhunter-Foster 345kV | Middletown Energy Center | OH | Butler | In Service | DEOK | 513 | 513 | 513 | 513 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_079_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 6/1/2018 |  | 2/6/2018 | N | No
Z1-080 | Clinton County 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 6 | 6 | 0 | 6 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1080_fea.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_080_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | Yes
Z1-081 | Church 25kV | Sunfish Solar Project | MD | Queen Anne's | Withdrawn | DPL | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1081_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1081_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1081_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/3/2017 | Customer Initiated Withdrawal | 7/15/2017 | 7/15/2017 |  | N | Yes
Z1-082 | Lawnside 13kV | Lawnside Battery | NJ | Camden | In Service | PSEG | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1082_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1082_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 8/1/2014 | 8/1/2014 | 1/13/2015 | Y | Yes
Z1-083 | Salem Unit 1-PSEG Zone |  | NJ | Salem | Withdrawn | PSEG | 300 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1083_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 9/2/2015 |  |  |  |  | EE | No
Z1-084 | Quad Cities 1-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 475 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1084_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-085 | Quad Cities 2-NI Hub |  | N/A | N/A | Withdrawn | ComEd | 525 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z1085_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  | 3/27/2015 |  |  |  |  | EE | No
Z1-086 | Heritage-Carson | Greensville Generating Facility | VA | Greensville | In Service | Dominion | 1681 | 1681 | 1630 | 1681 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_086_csa.pdf | Document Posted | N/A | N/A | 1/21/2018 | 10/30/2013 | N/A | N/A | 7/20/2018 |  |  | 6/1/2019 | 6/1/2019 | 12/8/2018 | N | No
Z1-087 | Glade 230kV | Seneca Pumped Storage Generating Station | PA | Warren | In Service | PENELEC | 485 | 17 | 17 | 13 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1087_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_087_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 4/21/2017 | N | No
Z1-088 | Allegheny Dam 5 | Allegheny River Lock & Dam # 5 | PA | Armstrong | In Service | APS | 8 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1088_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_088_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-089 | Allegheny Dam 6 138kV | Allegheny River Lock & Dam #6 | PA | Armstrong | In Service | APS | 9 | 0 | 5 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1089_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_089_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 3/25/2015 | N | No
Z1-090 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1024 | 381 | 381 | 381 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_090_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2013 | N/A | N/A |  |  |  | 3/18/2018 | 3/18/2018 | 3/24/2018 | N | No
Z1-091 | Lenox 34kV | Hop Bottom Generating Station | PA | Lackawanna | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1091_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1091_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 12/15/2018 |  | 3/31/2017 | 3/31/2017 |  | N | No
Z1-092 | Milan 34kV | Milan Energy | PA | Lackawanna | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A | 2/20/2017 |  |  | 2/2/2017 | 2/2/2017 | 2/20/2017 | N | No
Z1-093 | Woodville Battery 34.5kV |  | OH | Sandusky | Withdrawn | ATSI | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1093_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 10/31/2014 | Customer Initiated Withdrawal | 12/30/2014 |  |  | N | No
Z1-094 | Jugg 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1094_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 10/5/2016 | Customer Milestone Not Met | 5/18/2018 | 5/18/2018 |  | N | Yes
Z1-095 | North Woodcock 34.5kV |  | OH | Allen | Withdrawn | AEP | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/27/2015 | Customer Initiated Withdrawal | 12/30/2014 |  |  | N | No
Z1-096 | Trenton 26kV | Parkland Solar | NJ | Burlington | In Service | PSEG | 7.8 | 7.84 | 2.98 | 7.84 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1096_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1096_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/15/2014 |  | 1/14/2015 | N | Yes
Z1-097 | Adkins 345kV | Darby Generating Station Unites, 1,2,3,4,5,6 | OH | Madison | In Service | AEP | 564 | 0 | 30 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 12/15/2014 | N | No
Z1-098 | Peckville-Jackson 69kV | Valley View Flywheel Station | PA | Lackawanna | Withdrawn | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1098_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1098_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_098_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 11/6/2015 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | Yes
Z1-099 | North Street 69kV | City of Dover Generating Facilities | DE | Kent | In Service | DPL | 182 | 7 | 7 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 9/22/2016 | N | No
Z1-100 | Oak Hall | Oak Hal lProject A | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1100_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_100_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
Z1-101 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1101_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1101_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_101_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_101_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
Z1-102 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1102_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1102_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-103 | Oak Hall |  | VA | Unknown | In Service | DPL | 20 | 0 | 4.162 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_103_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
Z1-104 | Somerset County 25kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1104_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 4/30/2013 |  |  | N | No
Z1-105 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1105_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 2/27/2015 | Customer Initiated Withdrawal | 7/1/2015 |  |  | N | Yes
Z1-106 | West Chicago 34kV | West Chicago Energy Storage | IL | Du Page | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1106_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 9/22/2015 | N | Yes
Z1-107 | Joliet 34kV |  | IL | Will | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1107_fea.pdf | Document Posted |  |  |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1107_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 8/26/2015 | N | Yes
Z1-108 | McHenry 34kV | McHenry Energy Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1108_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1108_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | Yes
Z1-109 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 208 | 208 | 208 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1109_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1109_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 3/16/2016 | Customer Initiated Withdrawal | 6/30/2016 |  |  | N | No
Z1-110 | Grover 34kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1110_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/5/2016 | 10/31/2013 | N/A | N/A | 5/5/2016 |  |  | 12/31/2016 | 12/31/2016 | 6/7/2016 | N | No
Z1-111 4600025 | AMIL-PJM |  | N/A | N/A | Retracted | Constellation | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4600025_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 10/31/2013 | 1/1/2015 | 1/1/2017 |  | 1/16/2014 |  |  |  |  | FF | No
Z1-112 4600034 | MEC-PJM |  | N/A | N/A | Withdrawn | Acciona Energy North America Corporation | 108 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4600034_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4600034_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/31/2013 | 6/1/2015 | 6/1/2020 |  | 5/30/2019 |  |  |  |  | FF | No
Z1-113 | West Winchester 13kV | HP Hood Generation Facility | VA | Rockingham | In Service | APS | 12 | 12 | 5 | 12 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z1113_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 3/30/2015 | 3/30/2015 | 5/11/2015 | N | Yes
Z1-114 | Oxford 13kV |  | PA | York | Withdrawn | ME | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1114_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | N | Yes
Z1-115 | Crescentville 13kV |  | PA | Philadelphia | Withdrawn | PECO | 2 | 2 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1115_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/13/2014 | Customer Milestone Not Met | 12/31/2014 |  |  | N | Yes
Z1-116 | Metuchen 230kV | CPV Keasbey Energy Center | NJ | Middlesex | Engineering and Procurement | PSEG | 675 | 675 | 671 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1116_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1116_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_116_csa.pdf | Document Posted | N/A | N/A | 8/1/2021 | 10/31/2013 | N/A | N/A | 1/1/2024 |  |  | 1/1/2024 | 1/1/2024 |  | N | No | This project slid to the next queue
Z1-117 | Pocomoke 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1117_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-118 | Pocomoke 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1118_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-119 | Pocomoke 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1119_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-120 | Loretto 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1120_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-121 | Loretto 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-122 | Loretto 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1122_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-123 | Piney Grove 1 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-124 | Piney Grove 2 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1124_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-125 | Piney Grove 3 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1125_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-126 | Piney Grove 4 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 10 | 5.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1126_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
Z1-127 | University Park |  | IL | Will | Partially in Service - Active | ComEd | 320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1127_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1127_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_127_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 10/31/2013 | N/A | N/A |  |  |  | 10/31/2013 |  | 2/10/2014 | N | No
Z2-001 | Burlington 26 kV | Recovery Road Solar Farm | NJ | Burlington | Withdrawn | PSEG | 7.1 | 7.1 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2001_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2001_wmpa.pdf |  | Not Required | N/A | N/A |  | 11/1/2013 | N/A | N/A |  | 3/29/2018 |  | 6/30/2018 | 6/30/2018 |  | N | No
Z2-002 | Linden 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 1049 | 61 | 54 | 61 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2002_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2002_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_002_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/1/2013 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 5/16/2018 | N | No
Z2-003 4601556 | DUK-PJM |  | N/A | N/A | Withdrawn | Brookfield Energy Marketing, Inc. | 299 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/7/2013 | 7/1/2014 | 7/1/2015 | [6 empty] | FF | No
Z2-004 | Mantua Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2004_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/8/2013 | N/A | N/A |  | 9/24/2014 | Customer Initiated Withdrawal | 8/4/2014 |  |  | N | Yes
Z2-005 4604093 | PJM-MEC |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/19/2013 | 1/1/2015 | 1/1/2022 |  | 12/12/2013 |  |  |  |  | FF | No
Z2-006 4604623 | PJM-MECS |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2013 | 3/1/2015 | 3/1/2023 |  | 12/14/2013 |  |  |  |  | FF | No
Z2-007 | East Palmerton-Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 212.5 | 212.5 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2007_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/22/2013 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 6/1/2015 |  |  | N | No
Z2-008 | East Palmerton-Wagner 69kV |  | PA | Carbon | Withdrawn | PPL | 99 | 99 | 12.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2013 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
Z2-009 | East Hazelton-Harwood 69kV |  | PA | Luzerne | Withdrawn | PPL | 52 | 52 | 6.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2009_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2009_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 12/23/2013 | N/A | N/A |  | 1/14/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-010 4612032 | PJM-MEC |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4612032_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/24/2013 | 1/1/2014 | 1/1/2020 |  | 3/13/2014 |  |  |  |  | FF | No
Z2-011 | Canton 34.5kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2011_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2011_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_011_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_011_csa.pdf | Document Posted | N/A | N/A | 2/20/2017 | 12/30/2013 | N/A | N/A | 2/27/2017 |  |  | 6/30/2017 | 6/30/2017 | 2/27/2017 | N | No
Z2-012 | Weirwood-Eastville 69kV | Hecate Energy Cherrydale | VA | Northampton | In Service | ODEC | 20 | 20 | 7.6 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2012_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_012_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_012_csa.pdf | Document Posted | N/A | N/A |  | 12/31/2013 | N/A | N/A |  |  |  | 4/1/2017 | 4/1/2017 | 9/7/2017 | N | No
Z2-013 | Frostburg 138kV | Twin Ridges Wind Farm | PA | Somerset | Partially in Service - Under Construction | APS | 200 | 0 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_013_csa.pdf | Document Posted | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2014 |  | 12/15/2014 | N | No
Z2-014 | St. Benedict-Patton | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30 | 0 | 5.25 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/9/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 2/13/2015 | N | No
Z2-015 | Dans Mountain 138kV |  | PA | Allegheny | Withdrawn | APS | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2014 | N/A | N/A |  | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2014 |  |  | N | No
Z2-016 | Blairsville-Social Hall 138kV |  | PA | Westmoreland | Withdrawn | PENELEC | 15.7 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z2016_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | S | No
Z2-017 | Bristers Ox 500kV |  | VA | Unknown | In Service | Dominion | 237 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 733 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/z2017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/z2017_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/z2_017_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 3/25/2015 | S | No
Z2-018 | South Canton-Harmon 345kV |  | OH | Unknown | Withdrawn | ATSI | 82 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2014 | N/A | N/A |  | 4/21/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
Z2-019 | Fairborn 12.47kV | Dovetail Biogas Facility | OH | Greene | Withdrawn | ATSI | 0.9 | 0.85 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2019_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/7/2014 | N/A | N/A |  | 7/7/2015 | Customer Initiated Withdrawal | 6/30/2015 | 6/30/2015 |  | Y | No
Z2-020 | New Franklin 12.47kV |  | OH | Summit | Withdrawn | ATSI | 0.9 | 0.85 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2020_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/7/2014 | N/A | N/A |  | 11/10/2017 |  | 6/30/2015 | 6/30/2015 |  | Y | No
Z2-021 4626426 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
Z2-022 4626428 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
Z2-023 4626437 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/11/2014 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
Z2-024 4626439 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/11/2014 | 6/1/2014 | 6/1/2015 | [6 empty] | FF | No
Z2-025 4626594 | PJM-MECS |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2014 | 1/1/2015 | 1/1/2016 | [6 empty] | FF | No
Z2-026 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 800 | 800 | 800 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2026_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2014 | N/A | N/A |  | 4/8/2016 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Z2-027 | Pasquotank 34.5kV | Elizabeth City Solar Park | NC | Pasquotank | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2027_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_027_csa.pdf | Document Posted | N/A | N/A |  | 2/20/2014 | N/A | N/A |  |  |  | 2/15/2015 | 2/15/2015 | 12/31/2014 | N | No
Z2-028 | Highland-Sammis 345kV & Highland-Mansfield 345kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 800 | 800 | 800 | 800 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_028_csa.pdf | Document Posted | N/A | N/A | 9/12/2017 | 2/21/2014 | N/A | N/A | 12/22/2017 |  |  | 12/28/2018 | 12/28/2018 | 8/15/2018 | N | No
Z2-029 | Stuart 4 | Stuart Electric Generating Station | OH | Brown | Deactivated | Dayton | 585 | 20.5 | 20.5 | 20.5 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_029_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/25/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 10/1/2015 | N | No
Z2-030 | Double Toll Gate 34.5kV | Double Tollgate Solar Project | VA | Clarke | In Service | APS | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2030_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/26/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 7/12/2017 | N | No
Z2-031 4630443 | PJM-MECS |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/26/2014 | 6/1/2015 | 6/1/2023 |  | 3/19/2014 |  |  |  |  | FF | No
Z2-032 | Clean River Power MR-1 (Devola) |  | OH | Washington | Withdrawn | AEP | 5.2 | 5.21 | 5.21 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2032_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-033 | Clean River Power MR-2 (Lowell) |  | OH | Washington | Withdrawn | AEP | 5.2 | 5.21 | 5.21 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2033_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-034 | Clean River Power MR-3 (Beverly) |  | OH | Washington | Withdrawn | AEP | 4 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2034_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
Z2-035 | Clean River Power MR-5 (Malta) |  | OH | Morgan | Withdrawn | AEP | 4 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2035_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-036 | Clean River Power MR-6 (Rokeby) |  | OH | Morgan | Withdrawn | AEP | 4 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-037 | Clean River Power MR-7 (Philo) |  | OH | Muskingum | Withdrawn | AEP | 4 | 3.95 | 3.95 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | Yes
Z2-038 | Ridgeley-Frostburg 138kV | Dan's Mountain Solar Project | MD | Allegany | Withdrawn | APS | 19.9 | 19.9 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_038_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 12/22/2017 |  | 3/31/2018 | 3/31/2018 |  | N | No
Z2-039 | PF Hydro | Warren Hydro Station; Newport Hydro Station; Luray Hydro Station; Shenandoah Hydro Station | VA | Warren | In Service | APS | 4.6 | 0 | 2.82 | 0 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2039_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2039_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 5/31/2015 | 5/31/2015 | 5/13/2015 | N | No
Z2-040 | PF Hydro | Dam 4 Hydro Generation Facility; Dam 5 Hydro Generation Facility; Millville Hydroelectric Facility | WV | Jefferson | In Service | APS | 5.8 | 0 | 3.5 | 5.75 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/27/2014 | N/A | N/A |  |  |  | 3/31/2014 |  | 4/17/2015 | N | No
Z2-041 | Silver Lake |  | IL | McHenry | Withdrawn | ComEd | 455 | 455 | 435 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2014 | N/A | N/A |  | 10/2/2014 | Customer Initiated Withdrawal | 5/1/2018 |  |  | N | No
Z2-042 | Wurno-Clayor 138kV |  | VA | Pulaski | Withdrawn | AEP | 180 | 180 | 23.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2042_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/28/2014 | N/A | N/A |  | 10/25/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
Z2-043 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 20 | 20 | 14 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2043_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2043_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_043_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-044 | Whitakers 34.5kV | Whitakers Solar Park | NC | Nash | In Service | Dominion | 12 | 12 | 8.4 | 12 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_044_csa.pdf | Document Posted | N/A | N/A |  | 3/5/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | Yes
Z2-045 | Cedar Grove-Roseland 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-046 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 1050 | 900 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_046_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 2/20/2018 | N | No
Z2-047 | Steel City 230kV |  | PA | Northampton | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2014 | N/A | N/A |  | 6/9/2014 | Customer Initiated Withdrawal | 7/1/2014 |  |  | S | No
Z2-048 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 545 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2048_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_048_csa.pdf | Document Posted | N/A | N/A |  | 3/26/2014 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
Z2-049 | Cedar Grove-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 21 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-050 | Easton-Trappe Tap 69kV |  | MD | Talbot | Withdrawn | DPL | 13 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-051 | Red Lion-Cedar Creek 230kV |  | DE | New Castle | Withdrawn | DPL | 83 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-052 | Preston-Tanyard 69kV |  | MD | Caroline | Withdrawn | DPL | 20 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 8/29/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-053 | Bridgewater-S. River |  | N/A | N/A | Withdrawn | PSEG | 156.1 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2053_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-054 | Roseland-Williams 230kV |  | NJ | Unknown | Withdrawn | PSEG | 44 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-055 | Cedar Grove-Clifton 230kV |  | NJ | Unknown | Withdrawn | PSEG | 42 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 3/31/2015 |  |  | S | No
Z2-056 | Crossmans-Werner 34.5kV |  | NJ | Middlesex | In Service | JCPL | 20 | 0.5 | 0 | 0.5 | Energy | Generation Interconnection | Solar |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_056_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 8/4/2016 | Y | No
Z2-057 4637968 | AMIL-PJM |  | N/A | N/A | Withdrawn | American Municipal Power, Inc. | 35 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-058 4637969 | AMIL-PJM |  | N/A | N/A | Withdrawn | American Municipal Power, Inc. | 6 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-059 4637970 | AMIL-PJM |  | N/A | N/A | Withdrawn | American Municipal Power, Inc. | 37 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/31/2014 | 6/1/2015 | 6/1/2021 |  | 5/5/2014 |  |  |  |  | FF | No
Z2-060 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Engineering and Procurement | PEPCO | 927 | 33 | 116 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_060_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2014 | N/A | N/A |  |  |  | 3/1/2022 | 3/1/2022 |  | N | No
Z2-061 | Spurlock-Zimmer 345kV |  | KY | Mason | Withdrawn | DEOK | 88 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2014 | N/A | N/A |  | 4/1/2014 |  |  |  |  | S | No
Z2-062 | Gloucester 26kV | Camden County Energy Recovery Associates | NJ | Camden | In Service | PSEG | 24.5 | 0 | 3 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/2/2014 | N/A | N/A |  |  |  | 5/1/2015 |  | 11/19/2014 | N | No
Z2-063 4639216 | PJM-WEC |  | WI | Unknown | Withdrawn | WPPI Energy | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4639216_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4639216_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/7/2014 | 6/1/2017 | 6/1/2027 |  | 6/1/2015 |  |  |  |  | FF | No
Z2-064 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 651 | 651 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2064_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/10/2014 | N/A | N/A |  | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
Z2-065 4641473 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4641473_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4641473_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-066 4641474 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4641474_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4641474_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-067 4641475 | CPLE-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership Corporation | 55 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4641475_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4641475_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-068 4641477 | DUK-PJM |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 87 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/17/2014 | 6/1/2019 | 6/1/2024 |  | 4/24/2014 |  |  |  |  | FF | No
Z2-069 | Bridgewater-Hoboken |  | N/A | N/A | Withdrawn | PSEG | 105 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2069_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-070 | Worcester-Ocean Pines 69kV |  | MD | Worcester | Withdrawn | DPL | 25 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-071 | Piney Grove-New Church 138kV |  | MD | Wicomico | Withdrawn | DPL | 55 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 12/5/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | S | No
Z2-072 | Indian River-New Church |  | N/A | N/A | Withdrawn | DPL | 204.6 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/z2072_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 7/14/2015 |  |  |  |  | EE | No
Z2-073 | Chestertown West 25kV |  | MD | Kent | Withdrawn | DPL | 5 | 5 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-074 | Chestertown East 25kV |  | MD | Kent | Withdrawn | DPL | 6 | 6 | 4.03 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-075 | Lynch East 25kV |  | MD | Kent | Withdrawn | DPL | 5.5 | 5.5 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-076 | Worcester South 25kV | Worcester South | MD | Worcester | In Service | DPL | 6 | 6 | 3.99 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2076_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2076_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 5/29/2019 | N | Yes
Z2-077 | Worcester North 25kV | Worcester North | MD | Worcester | In Service | DPL | 6 | 6 | 3.99 | 6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2077_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2077_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2077_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/22/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/15/2019 | N | No
Z2-078 4642907 | DUK-PJM |  | N/A | N/A | Annulled | North Carolina Electric Membership Corporation | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4642907_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4642907_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/24/2014 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
Z2-079 | Pleasant View - Edwards Ferry 230kV |  | VA | Loudoun | Withdrawn | Dominion | 31 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/25/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
Z2-080 4643119 | PJM-NIPS |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/25/2014 | 1/1/2015 | 1/1/2022 | [6 empty] | FF | No
Z2-081 | Streator 34.5kV | Livingston Landfill Gas to Energy Facility | IL | Livingston | In Service | ComEd | 13.3 | 13.3 | 13.3 | 12 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2081_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_081_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2014 | N/A | N/A |  |  |  | 12/1/2014 |  | 4/4/2017 | N | No
Z2-082 | Cape May County 12kV | Cape May County Municipal Utilities Authority Landfill | NJ | Cape May | In Service | AEC | 2 | 0 | 0.3 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 6/1/2015 | N | No
Z2-083 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 1104 | 9 | 9 | 9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_083_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A |  | 11/20/2018 |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
Z2-084 | JK Smith 345kV |  | KY | Nelson | Withdrawn | EKPC | 207.8 | 207.8 | 207.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2084_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2014 | N/A | N/A |  | 10/7/2014 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
Z2-085 | Mahoning Valley Hydro 25kV | Mahoning Creek Hydroelectric Plant | PA | Clarion | In Service | APS | 7.5 | 1.5 | 1.5 | 7.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2085_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_085_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2014 | N/A | N/A |  |  |  | 11/1/2014 | 11/1/2014 | 10/10/2014 | N | No
Z2-086 |  |  | N/A | N/A | Withdrawn | ComEd | 200 |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2014 | N/A | N/A |  | 5/21/2014 | Customer Milestone Not Met |  |  |  | N | No
Z2-087 | Pontiac MidPoint-Brokaw 345kV | Bright Stalk Wind Farm | IL | Livingston | In Service | ComEd | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2087_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_087_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2014 | N/A | N/A | 12/16/2019 |  |  | 12/30/2019 | 12/30/2019 | 12/16/2019 | N | No
Z2-088 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 80 | 30.4 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_088_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
Z2-089 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 568 | 541 | 568 | Capacity | Generation Interconnection | Natural Gas; Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_089_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 5/2/2018 | N | No
Z2-090 | Blackhawk 12.5kV |  | IL | Winnebago | Withdrawn | ComEd | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2090_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2090_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 6/13/2016 | Customer Initiated Withdrawal | 10/1/2014 |  |  | N | Yes
Z2-091 | Woodsdale Road |  | OH | Butler | Withdrawn | DEOK | 36 | 36 | 36 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/19/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-092 | Bennett-Farmingdale 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 4 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2092_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
Z2-093 | Hawks 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6.5 | 3.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/29/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-094 | Washington-Mobile Chemical 34kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 7/15/2014 | Customer Initiated Withdrawal | 12/31/2014 |  |  | N | No
Z2-095 | Branchville-Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 20 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2095_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 10/1/2014 | Customer Milestone Not Met | 12/31/2015 | 12/31/2015 |  | N | No
Z2-096 | Lynch West 25kV |  | MD | Kent | Withdrawn | DPL | 10 | 10 | 7.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2096_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | No
Z2-097 | Church 25kV | Church | MD | Kent | Withdrawn | DPL | 5 | 5 | 3.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2097_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2097_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2097_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/z2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 3/5/2019 |  | 9/28/2019 | 9/28/2019 |  | N | Yes
Z2-099 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 8.5 | 8.5 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2099_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 1/25/2018 |  | 5/31/2019 | 5/31/2019 |  | N | No
Z2-100 | Boykin 115kV |  | VA | Unknown | Withdrawn | Dominion | 20 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/9/2014 | Customer Initiated Withdrawal |  |  |  | N | No
Z2-101 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 67.5 | 67.5 | 8.78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2101_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 5/15/2015 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
Z2-102 | Argonne-New Lisbon 34.5kV | Dix Solar Farm | NJ | Burlington | In Service | JCPL | 13 | 13 | 4.94 | 13 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2102_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2102_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 8/24/2017 | 8/24/2017 | 7/13/2017 | N | No
Z2-103 | North Meshoppen 34.5kV III | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 19.9 | 1 | 1 | 1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 1/28/2016 | N | No
Z2-104 | Oxbow 25kV II | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 19.9 | 1.6 | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2104_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2104_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A | 10/30/2019 |  |  | 10/30/2019 | 10/30/2019 | 11/16/2019 | N | No
Z2-105 | Bell-Mariana 25kV | Ten Mile Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2105_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 2/25/2015 | Customer Initiated Withdrawal | 7/1/2016 | 7/1/2016 |  | N | Yes
Z2-106 | Washington-Bell 25kV | Amity Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2106_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 1/29/2019 |  | 6/30/2017 | 6/30/2017 |  | N | Yes
Z2-107 | East Carbondale-Lackawanna 69kV | Waymart Battery Energy Storage System | PA | Wayne | Suspended | PPL | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z2107_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z2_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_107_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2020 | 12/15/2020 |  | N | No
Z2-108 | Meyersdale North 115kV | Meyersdale Wind Farm & Battery Energy Storage System | PA | Somerset | In Service | PENELEC | 48 | 18 | 0 | 18 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/17/2015 | N | No
Z2-109 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 460 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z2_109_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2014 | N/A | N/A |  | 3/21/2019 |  | 5/16/2019 | 5/16/2019 |  | N | No
Z2-110 4644137 | PJM-DUK |  | N/A | N/A | Withdrawn | Invenergy LLC | 78 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4644137_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/30/2014 | 1/1/2016 | 1/1/2021 |  | 7/9/2014 |  |  |  |  | FF | No
Z2-111 4644159 | PJM-WEC |  | N/A | N/A | Withdrawn | Invenergy LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4644159_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4644159_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/30/2014 | 6/1/2018 | 6/1/2023 |  | 11/20/2014 |  |  |  |  | FF | No
Z2-112 | Waterford 345kV |  | OH | Washington | In Service | AEP | 1007 | 97 | 64.5 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/z2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/15/2015 | N | No
Z2-113 | Watervliet 12.47kV | Watervliet Solar Facility | MI | Berrien | In Service | AEP | 4.6 | 4.6 | 2.3 | 4.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2113_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/z2113_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 11/8/2016 | N | Yes
Z2-114 | Olive 12.47kV | Olive Solar Facility | IN | St. Joseph | In Service | AEP | 5 | 5 | 2.5 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2114_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/z2114_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 12/15/2016 | 12/15/2016 | 8/26/2016 | N | Yes
Z2-115 | Deer Creek 12.47kV | Deer Creek Solar Facility | IN | Grant | In Service | AEP | 2.5 | 2.5 | 1.25 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2115_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 3/1/2016 | 3/1/2016 | 1/6/2016 | N | Yes
Z2-116 | Twin Branch 12.47kV | Twin Branch Solar Facility | IN | St. Joseph | In Service | AEP | 2.6 | 2.6 | 1.3 | 2.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z2116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/z2116_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/z2116_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2014 | N/A | N/A |  |  |  | 7/31/2016 | 7/31/2016 | 8/18/2016 | N | No
AA1-001 4645310 | AMIL-PJM |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 78 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4645310_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4645310_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 5/5/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-002 4645653 | MECS-PJM |  | N/A | N/A | Retracted | CMS Energy Resource Management Co. | 65 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4645653_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4645653_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 5/7/2014 | 6/1/2017 | 6/1/2023 |  | 4/27/2015 |  |  |  |  | FF | No
AA1-003 4646885 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 575 | 575 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4646885_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4646885_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 5/10/2016 |  |  |  |  | FF | No
AA1-004 4646887 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 225 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4646887_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4646887_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 2/1/2019 |  |  |  |  | FF | No
AA1-005 4646888 | CIN-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 550 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4646888_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4646888_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 5/13/2014 | 1/1/2016 | 1/1/2025 |  | 5/21/2015 |  |  |  |  | FF | No
AA1-006 | Erie County Landfill | Erie County Landfill | OH | Erie | In Service | ATSI | 2.3 | 0.8 | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1006_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/2/2014 | N/A | N/A |  |  |  | 9/30/2015 | 9/30/2015 | 12/31/2015 | N | No
AA1-007 | Smith Gap Regional Landfill |  | VA | Roanoke | Withdrawn | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 6/19/2014 | N/A | N/A |  | 1/7/2016 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
AA1-008 4656596 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-009 4656601 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-010 4656602 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-011 4656605 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-012 4656606 | AMIL-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/20/2014 | 1/1/2016 | 1/1/2025 |  | 7/9/2014 |  |  |  |  | FF | No
AA1-013 | Hanging Rock 765kV | Cornu | OH | Lawrence | In Service | AEP | 1250 | 10 | 10 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1013_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_013_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-014 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 625 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 10/1/2015 | 10/1/2015 | 11/1/2015 | N | No
AA1-015 | Fayette II | Fayette Energy Facility | PA | Fayette | In Service | APS | 661 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_015_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/23/2014 | N/A | N/A |  |  |  | 1/1/2016 | 1/1/2016 | 12/14/2015 | N | No
AA1-016 | Portland 1 |  | PA | Monroe | Withdrawn | ME | 158 | 158 | 158 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/25/2014 | N/A | N/A |  | 11/18/2015 | Customer Milestone Not Met | 6/1/2017 | 6/1/2017 |  | N | No
AA1-017 | Portland 2 |  | PA | Monroe | Withdrawn | ME | 243 | 243 | 243 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1017_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 6/25/2014 | N/A | N/A |  | 11/18/2015 | Customer Milestone Not Met | 6/1/2017 | 6/1/2017 |  | N | No
AA1-018 | Powerton-Goodings Grove | Otter Creek Wind Farm | IL | Livingston | In Service | ComEd | 150 | 150 | 19.5 | 150 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1018_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1018_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_018_csa.pdf | Document Posted | N/A | N/A |  | 6/25/2014 | N/A | N/A | 12/20/2019 |  |  | 1/17/2020 | 1/17/2020 | 1/9/2020 | N | No
AA1-019 | Beaverbrook 13kV | Gloucester Solar Farm | NJ | Camden | Withdrawn | PSEG | 7.3 | 7.3 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1019_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/9/2014 | N/A | N/A |  | 7/27/2017 | Customer Initiated Withdrawal | 9/30/2015 | 9/30/2015 |  | N | Yes
AA1-020 | Andersontown Road #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-021 | Andersontown Rd #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-022 | Andersontown Rd #3 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 8/18/2014 | Customer Initiated Withdrawal |  |  |  | Y | No
AA1-023 | Andersontown Rd #4 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/10/2014 | N/A | N/A |  | 11/25/2014 | Customer Initiated Withdrawal | 6/30/2015 |  |  | Y | No
AA1-024 4661444 | DUK-PJM |  | N/A | N/A | Withdrawn | Ingenco Wholesale Power LLC | 6 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4661444_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/10/2014 | 6/1/2018 | 6/1/2023 |  | 9/18/2014 |  |  |  |  | FF | No
AA1-025 | Oak Hall A |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1025_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_025_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 10/15/2016 | 10/15/2016 | 12/8/2016 | N | No
AA1-026 | Oak Hall B |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_026_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2016 | 12/30/2016 | 12/8/2016 | N | No
AA1-027 | Oak Hall C |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1027_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-028 | Oak Hall D |  | VA | Unknown | In Service | DPL | 20 | 0 | 3.7 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1028_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_028_csa.pdf | Document Posted | N/A | N/A |  | 7/11/2014 | N/A | N/A |  |  |  | 12/30/2017 | 12/30/2017 | 12/8/2016 | N | No
AA1-029 | Carson Rawlings 500kV |  | VA | Brunswick | Withdrawn | Dominion | 315 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 9/8/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-030 | Zion-Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 133 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2014 | N/A | N/A |  | 4/3/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA1-031 4662618 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation | 3000 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4662618_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/15/2014 | 6/1/2017 | 6/1/2022 |  | 9/11/2014 |  |  |  |  | FF | No
AA1-032 | Kingsport Mill | Kingsport Mill | TN | Sullivan | In Service | AEP | 50 | 0 | 45 | 0 | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1032_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_032_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/21/2014 | N/A | N/A |  |  |  | 6/1/2015 | 6/1/2015 | 5/24/2017 | N | No
AA1-033 | Hay Road 230kV |  | DE | New Castle | Withdrawn | DPL | 371 | 80 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2014 | N/A | N/A |  | 10/21/2015 | Customer Initiated Withdrawal | 6/18/2018 |  |  | N | No
AA1-034 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 880 | 120 | 70 | 72.4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1034_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_034_csa.pdf | Document Posted | N/A | N/A |  | 7/24/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/11/2018 | N | No
AA1-035 | Edgecomb-Roanoke Valley |  | N/A | N/A | Withdrawn | Dominion | 60 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1035_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2014 | N/A | N/A |  | 3/31/2016 |  |  |  |  | EE | No
AA1-036 | Mountain 230kV |  | PA | Luzerne | Withdrawn | UGI | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/11/2014 | N/A | N/A |  | 4/6/2016 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA1-037 | Piney Hydro 34.5kV | Piney Station (Piney 1-3) | PA | Clarion | In Service | PENELEC | 33.3 | 5.26 | 5.26 | 5.26 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/13/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 6/19/2015 | N | No
AA1-038 | Lexington-Low Moor 230kV |  | VA | Botetourt | Engineering and Procurement | Dominion | 76.6 | 76.6 | 9.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_038_csa.pdf | Document Posted | N/A | N/A |  | 8/19/2014 | N/A | N/A |  |  |  | 6/12/2021 | 6/12/2021 |  | N | No
AA1-039 | Bergen 230kV |  | NJ | Bergen | Withdrawn | PSEG | 660 |  |  |  | Energy | Merchant Transmission |  | DC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1039_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2014 | N/A | N/A |  | 3/30/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA1-040 | Morris | Morris Cogen | IL | Grundy | In Service | ComEd | 140 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1040_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_040_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 1/28/2016 | N | No
AA1-041 | Tioga 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1041_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2014 | N/A | N/A |  | 4/2/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-042 | Ontelaunee |  | PA | Bradford | Withdrawn | ME | 574 | 0 | 52.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1042_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2014 | N/A | N/A |  | 11/18/2015 | Customer Initiated Withdrawal | 11/4/2016 |  |  | N | No
AA1-043 | Ontelaunee 230kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 591.1 | 34.1 | 19.6 | 34.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1043_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_043_csa.pdf | Document Posted | N/A | N/A |  | 8/27/2014 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 9/30/2017 | N | No
AA1-044 | Shenango-Hoytdale 345kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 1000 | 870 | 1000 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_044_csa.pdf | Document Posted | N/A | N/A | 4/22/2019 | 8/27/2014 | N/A | N/A | 11/15/2019 |  |  | 3/30/2020 | 3/30/2020 | 10/31/2019 | N | No
AA1-045 | McConnellsburg-Guilford 138kV |  | PA | Venango | Withdrawn | APS | 308 | 308 | 308 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1045_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 11/3/2015 | Customer Milestone Not Met | 12/18/2015 |  |  | N | No
AA1-046 | Somerset-Allegheny 115kV | Kimberly Run Wind Farm | PA | Somerset | Withdrawn | PENELEC | 80 | 80 | 10.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_046_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 6/21/2018 |  | 12/29/2018 | 12/29/2018 |  | N | No
AA1-047 | Hazelton-Jennings 138kV | Garrett County Wind Facility | MD | Garrett | Withdrawn | APS | 69.1 | 69.1 | 9.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1047_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_047_csa.pdf | Document Posted | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 1/12/2020 |  | 12/1/2018 | 12/1/2018 |  | N | No
AA1-048 | Kendall |  | IL | Grundy | Withdrawn | ComEd | 800 | 800 | 780 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1048_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2014 | N/A | N/A |  | 4/13/2015 | Customer Milestone Not Met | 12/1/2018 |  |  | N | No
AA1-049 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1049_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1049_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_049_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2014 | N/A | N/A |  | 6/5/2017 | Customer Milestone Not Met | 11/30/2019 | 11/30/2019 |  | N | No
AA1-050 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 0 | 25.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1050_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_050_csa.pdf | Document Posted | N/A | N/A |  | 8/30/2014 | N/A | N/A |  |  |  | 11/30/2015 | 11/30/2015 | 12/21/2015 | N | No
AA1-051 4671936 | PJM-WEC |  | N/A | N/A | Confirmed | Constellation | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4671936_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4671936_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-052 4671937 | PJM-IPL |  | N/A | N/A | Confirmed | Constellation | 400 | 400 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4671937_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4671937_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-053 4671938 | PJM-MEC |  | N/A | N/A | Withdrawn | Constellation | 700 | 700 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4671938_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4671938_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2017 | 6/1/2022 |  | 1/23/2017 |  |  |  |  | FF | No
AA1-054 4671939 | PJM-CIN |  | N/A | N/A | Confirmed | Constellation | 700 | 700 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4671939_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4671939_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-055 4671943 | PJM-AMIL |  | N/A | N/A | Withdrawn | Constellation | 1100 | 1100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4671943_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4671943_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 9/3/2014 | 6/1/2017 | 6/1/2022 |  | 2/26/2018 |  |  |  |  | FF | No
AA1-056 | Bay Shore-Fostoria 345kV & Bay Shore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 960 | 161 | 46 | 8.8571 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1056_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_056_isa.pdf | Document Posted | N/A |  |  | N/A | N/A | 3/15/2016 | 9/10/2014 | N/A | N/A | 6/22/2017 |  |  | 5/15/2017 | 5/15/2017 | 6/23/2017 | N | No
AA1-057 | Sunbury-Milton 69kV | Northumberland Wood Fired Power Plant | PA | Northumberland | Withdrawn | PPL | 16 | 16 | 16 |  | Capacity | Generation Interconnection | Wood |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1057_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_057_csa.pdf | Document Posted | N/A | N/A |  | 9/10/2014 | N/A | N/A |  | 9/30/2019 |  | 9/30/2019 | 9/30/2019 |  | N | No
AA1-058 4675070 | CPLE-PJM |  | N/A | N/A | Withdrawn | Ingenco Wholesale Power LLC | 6 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4675070_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4675070_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/15/2014 | 6/1/2016 | 6/1/2018 |  | 6/1/2018 |  |  |  |  | FF | No
AA1-059 | Crisfield 25kV | Ibis | MD | Somerset | Withdrawn | DPL | 6 | 6 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1059_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1059_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/16/2014 | N/A | N/A |  | 5/23/2018 |  | 6/30/2020 | 6/30/2020 |  | N | No
AA1-060 | Great Adventure 34.5kV | Plumsted Energy Storage Facility | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_060_csa.pdf | Document Posted | N/A | N/A |  | 9/22/2014 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 12/11/2018 | N | Yes
AA1-061 | Jacktown-East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1061_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2014 | N/A | N/A |  | 4/24/2018 |  | 12/31/2016 |  |  | N | No
AA1-062 | Williams 138kV | Mt. Storm Wind Force | WV | Grant | Suspended | APS | 150 | 150 | 22.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1062_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1062_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_062_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 |  | N | No
AA1-063 | Huntsville (Cabin Creek) 69kV |  | IN | Randolph | Withdrawn | AEP | 3.6 | 3.6 | 3.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1063_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/26/2014 | N/A | N/A |  | 4/6/2016 | Customer Initiated Withdrawal | 3/31/2016 |  |  | N | No
AA1-063A | Carolina–Seaboard 115kV | Spuds Lane Solar Park | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 50.9 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1063a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1063a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1063a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_063a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_063a_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2014 | N/A | N/A |  |  |  | 8/17/2018 | 8/17/2018 | 11/8/2018 | N | No
AA1-064 | Carson-Wake 500kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1064_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2014 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 12/31/2015 |  |  | N | No
AA1-065 | Earleys 230kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 80 | 80 | 53.6 | 80 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_065_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A | 1/9/2019 |  |  | 12/31/2018 | 12/31/2018 | 1/9/2019 | N | No
AA1-066 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 0 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_066_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/31/2018 | N | No
AA1-067 | Everetts 34.5kV | Williamston Speight Solar | NC | Martin | In Service | Dominion | 15 | 15 | 10.5 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1067_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_067_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2014 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 1/24/2017 | N | No
AA1-068 | Wilson 34.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1068_fea.pdf | Document Posted |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/1/2014 | N/A | N/A |  | 6/17/2015 | Customer Initiated Withdrawal | 5/1/2016 |  |  | N | Yes
AA1-070 | Hatfield 500kV | Hatfield Ferry, Units 1, 2, and 3 | PA | Greene | Withdrawn | APS | 1710 | 1710 | 1590 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_070_csa.pdf | Document Posted | N/A | N/A |  | 10/6/2014 | N/A | N/A |  | 11/23/2016 | Customer Initiated Withdrawal | 6/1/2019 | 6/1/2019 |  | N | No
AA1-071 4680722 | MEC-PJM |  | N/A | N/A | Confirmed | Acciona Energy North America Corporation | 72 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4680722_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4680722_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 10/13/2014 | 6/1/2018 | 6/1/2023 | [6 empty] | FF | No
AA1-072 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 23.1 | 3.1 | 2.1 | 3.1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_072_csa.pdf | Document Posted | N/A | N/A |  | 10/13/2014 | N/A | N/A |  |  |  | 12/31/2015 | 12/31/2015 | 12/31/2015 | N | No
AA1-073 | Metuchen 26kV | Middlesex Plant | NJ | Middlesex | Withdrawn | PSEG | 5.6 | 5.6 | 3.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1073_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/14/2014 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 12/16/2016 | 12/16/2016 |  | N | Yes
AA1-074 4681626 | PJM-MECS |  | N/A | N/A | Confirmed | NRG Power Marketing, LLC | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4681626_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4681626_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/16/2014 | 6/1/2018 | 6/1/2025 | [6 empty] | FF | No
AA1-075 | Huron 23kV |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | 7.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2014 | N/A | N/A |  | 5/29/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | Yes
AA1-076 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1050 | 1050 | 1000 | 1050 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_076_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2014 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AA1-077 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1483 | 113 | 34 | 113 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1077_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1077_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_077_csa.pdf | Document Posted | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 4/1/2019 | 4/1/2019 | 1/21/2019 | N | No
AA1-078 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 560 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1078_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/23/2014 | N/A | N/A |  |  |  | 10/14/2015 |  | 6/1/2016 | N | No
AA1-079 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 1342 | 74 | 74 | 74 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 6/1/2015 |  | 9/13/2016 | N | No
AA1-080 | Wilson 34.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1080_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1080_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  | 3/3/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-081 | Cooksville 13kV |  | MD | Howard | Withdrawn | BGE | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1081_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  | 5/1/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | Yes
AA1-082 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 907.5 | 57.5 | 0 | 57.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_082_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2014 | N/A | N/A |  |  |  | 1/29/2016 | 1/29/2016 | 8/25/2016 | N | No
AA1-083 | Four Rivers 230kV | Doswell Facility | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1083_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_083_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/31/2015 | N | No
AA1-084 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 252 | 0 | 10 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/27/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/19/2015 | N | No
AA1-085 | Moshannon-Milesburg 230kV | Centre County Wind Facility | PA | Centre | Withdrawn | APS | 82 | 82 | 10.66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1085_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1085_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_085_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 12/11/2018 |  | 6/1/2019 | 6/1/2019 |  | N | No
AA1-086 | Blue Mound-Latham |  | IL | Macon | Withdrawn | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1086_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 2/23/2016 | Customer Milestone Not Met | 10/1/2017 |  |  | N | No
AA1-087 | Timblin-Trade City 115kV |  | PA | Jefferson | Withdrawn | PENELEC | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1087_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/12/2015 | Customer Milestone Not Met | 6/1/2016 | 6/1/2016 |  | S | No
AA1-088 | USAP-Woodville 138kV |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-089 | Dravosburg-W Mifflin |  | PA | Allegheny | Withdrawn | DL | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa1089_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 11/11/2015 | Customer Initiated Withdrawal | 6/1/2015 |  |  | S | No
AA1-090 | Cheswick 24kV Unit 1-AEP-Dayton HUB |  | N/A | N/A | Withdrawn | DL | 565 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1090_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 5/25/2016 |  |  |  |  | EE | No
AA1-091 | Dover 12kV |  | DE | Kent | Withdrawn | DPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1091_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/29/2014 | N/A | N/A |  | 3/6/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | Y | Yes
AA1-092 | Halfway 34.5kV | Perennial Solar Project | MD | Washington | Engineering and Procurement | APS | 12 | 12 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1092_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 12/1/2020 |  |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-093 | Clear Spring 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1093_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1093_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 10/18/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-094 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1094_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/19/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | Yes
AA1-095 | Halfway-Marlowe 34.5kV | Pinesburg Solar Project | MD | Washington | Under Construction | APS | 4.3 | 4.25 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1095_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_095_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_095_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 4/24/2020 |  |  | 1/16/2020 | 1/16/2020 |  | N | Yes
AA1-096 | Wilson 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 3.5 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1096_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1096_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/7/2019 |  | 10/31/2016 | 10/31/2016 |  | N | Yes
AA1-097 | Oyster Creek 230kV |  | NJ | Ocean | Withdrawn | JCPL | 186 | 100 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1097_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 4/14/2015 | Customer Milestone Not Met | 6/1/2018 |  |  | N | No
AA1-098 | Raritan River-Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 560 | 560 | 560 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1098_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 11/2/2016 | Customer Initiated Withdrawal | 5/30/2018 |  |  | N | No
AA1-099 | Clinton Co. 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 10 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 8/29/2016 | N | No
AA1-100 | Warrior Run 138kV | AES Warrior Run Energy Storage | PA | Allegheny | In Service | APS | 11 | 11 | 0 | 11 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_100_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 10/31/2015 | 10/31/2015 | 10/15/2015 | N | No
AA1-101 | Tait 69kV |  | OH | Montgomery | Withdrawn | Dayton | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1101_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_101_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 12/13/2017 |  | 5/1/2018 | 5/1/2018 |  | N | No
AA1-102 | Kings Creek-Loretto 138kV | Perry Road Solar | MD | Somerset | Partially in Service - Under Construction | DPL | 150 | 150 | 57 | 97 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1102_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1102_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 12/28/2017 | N | No
AA1-103 | Harwood-Siegfried 230kV |  | PA | Carbon | Withdrawn | PPL | 208.5 | 208.5 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1103_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1103_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 9/15/2016 | Customer Milestone Not Met | 6/1/2016 |  |  | N | No
AA1-104 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1104_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 11/20/2018 |  | 6/30/2017 | 6/30/2017 |  | N | No
AA1-105 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1105_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/19/2015 | Customer Initiated Withdrawal | 11/1/2015 |  |  | N | Yes
AA1-106 | Grover II 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1106_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1106_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa1106_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 2/2/2019 |  | 12/31/2016 |  |  | N | No
AA1-107 | Kings Creek-Pocomoke 138kV |  | MD | Somerset | Withdrawn | DPL | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 3/31/2015 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AA1-108 | Churchtown 230kV | Deepwater | NJ | Salem | Withdrawn | AEC | 529 | 158 | 158 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1108_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1108_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_108_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A |  | 2/7/2019 |  | 12/1/2021 | 12/1/2021 |  | N | No
AA1-109 | Cotoctin-Troutville Junction 34.5kV | Frederick Road Solar | MD | Frederick | In Service | APS | 9 | 9 | 4.5 | 9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_109_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_109_csa.pdf | Document Posted | N/A | N/A | 10/13/2017 | 10/31/2014 | N/A | N/A |  |  |  | 10/31/2017 | 10/31/2017 | 10/23/2017 | N | Yes
AA1-110 | Massey 25kV | Blue Star Solar Project | MD | Kent | Withdrawn | DPL | 6 | 6 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1110_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1110_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa1110_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 8/17/2017 |  | 10/17/2019 | 10/17/2019 |  | N | Yes
AA1-111 | Moshannon-East Towanda 230kV |  | PA | Clinton | Active | PENELEC | 463 | 463 | 463 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1111_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No | This project slid to the next queue
AA1-112 | Westmoreland 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 7.2 | 7.2 | 4 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1112_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017 | 8/16/2017 |  | N | Yes
AA1-113 | Frackville-Hauto 69kV |  | PA | Schuylkill | Withdrawn | PPL | 68 | 68 | 8.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/7/2015 | Customer Milestone Not Met | 12/30/2017 |  |  | N | No
AA1-114 | Harwood-East Hazelton #2 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 60 | 7.72 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1114_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1114_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 9/20/2016 | Customer Initiated Withdrawal | 12/30/2017 |  |  | N | No
AA1-115 | Thirty First Street 115kV |  | PA | Blair | Withdrawn | PENELEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1115_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1115_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/17/2016 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-116 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 18.4 | 18.4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1116_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pub/planning/project-queues/isa/aa1_116_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_116_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/11/2018 |  | 6/1/2016 |  |  | N | No
AA1-117 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1117_imp.pdf | Document Posted |  | Withdrawn | https://www.pjm.com/pub/planning/project-queues/isa/aa1_117_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_117_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/11/2018 |  | 9/1/2016 | 9/1/2016 |  | N | No
AA1-118 | Picway 69kV |  | OH | Pickaway | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1118_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 5/15/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA1-119 | Sunset Lake-Mardela |  | N/A | N/A | Withdrawn | DPL | 139 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1119_arr-imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/30/2017 |  |  |  |  | EE | No
AA1-120 | Fowler-LaPorte |  | N/A | N/A | Withdrawn | AEP | 64 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/aa1120_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/8/2017 |  |  |  |  | EE | No
AA1-121 | South Granville 12kV | Denison University | OH | Licking | Withdrawn | AEP | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1121_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1121_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/18/2017 | Customer Initiated Withdrawal | 1/31/2018 | 1/31/2018 |  | N | No
AA1-122 | Antietam 34.5kV |  | MD | Washington | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 11/3/2015 | Customer Milestone Not Met | 9/2/2016 |  |  | N | Yes
AA1-123 | Highland-Sammis 345kV | South Field Energy Power Plant | OH | Columbiana | Under Construction | ATSI | 1152 | 1152 | 1105 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1123_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1123_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_123_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 1/29/2021 |  |  | 7/29/2021 | 7/29/2021 |  | N | No
AA1-124 | Englishtown-Monroe 34kV |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 1.5 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/13/2015 | Customer Initiated Withdrawal | 8/1/2016 |  |  | N | Yes
AA1-125 | Seaman 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1125_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/7/2015 | Customer Initiated Withdrawal | 10/1/2016 |  |  | N | No
AA1-126 | Hillcrest 138kV |  | OH | Brown | Withdrawn | DEOK | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1126_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/5/2015 | Customer Milestone Not Met | 10/1/2016 |  |  | N | No
AA1-127 | Andersontown Road 25kV |  | MD | Caroline | Withdrawn | DPL | 6 | 6 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1127_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 4/24/2015 | Customer Initiated Withdrawal | 8/1/2016 |  |  | N | Yes
AA1-128 | Glen Lyn |  | VA | Giles | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/24/2015 | Customer Initiated Withdrawal | 10/1/2016 |  |  | N | No
AA1-129 | Northbrook-Skokie |  | IL | Cook | Withdrawn | ComEd | 27 | 27 | 27 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1129_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 7/1/2016 | Customer Milestone Not Met | 6/1/2018 |  |  | N | No
AA1-130 | St. Claire 13kV |  | OH | Franklin | Withdrawn | AEP | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1130_fea.pdf | Document Posted |  | Withdrawn |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 3/31/2016 | Customer Milestone Not Met | 11/1/2015 |  |  | N | No
AA1-131 | N. Towanda 34.5kV | Bradford Natural Gas Facility | PA | Bradford | Withdrawn | PENELEC | 8 | 8 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1131_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa1131_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/3/2015 | Customer Initiated Withdrawal | 12/1/2016 | 12/1/2016 |  | N | No
AA1-132 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 80 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1132_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1132_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_132_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/5/2017 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-133 | Hickory-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1133_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1133_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 10/31/2015 |  |  | N | No
AA1-134 | Sunbury-WinFall 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1134_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_134_isa2.pdf | Interim Study | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 2/15/2017 | Customer Initiated Withdrawal | 10/31/2015 |  |  | N | No
AA1-135 | Earleys-Everetts 230kV | Aulander Earleys Solar | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1135_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_135_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 5/11/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AA1-136 | Cashie-E. Trowbridge 230kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-137 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Milestone Not Met | 10/31/2015 |  |  | N | No
AA1-138 | Earleys-Suffolk 230kV | Haslett Solar Park | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1138_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1138_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_138_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 6/7/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AA1-139 | Hickory-Shawboro 230kV | Summit Farms Solar and Ranchland Solar | NC | Currituck | In Service | Dominion | 120 | 120 | 84 | 120 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1139_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa1_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_139_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 2/28/2018 | 2/28/2018 | 3/6/2018 | N | No
AA1-140 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1140_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1140_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/27/2017 |  | 6/30/2018 | 6/30/2018 |  | N | No
AA1-141 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1141_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1141_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/27/2017 |  | 10/31/2016 |  |  | N | No
AA1-142 | Vienna-Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1142_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
AA1-143 | Easton-Wye Mills 69kV |  | MD | Talbot | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1143_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016 |  |  | N | No
AA1-144 | East Towanda-Grover 230kV | Gateway Bradford Plant | PA | Bradford | Engineering and Procurement | PENELEC | 163 | 163 | 163 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1144_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1144_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_144_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_144_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A | 4/30/2021 |  | Customer Milestone Not Met | 4/30/2020 | 4/30/2020 |  | N | No
AA1-145 | Four Rivers 230kV | Doswell SC Units 2 & 3 | VA | Hanover | In Service | Dominion | 340 | 340 | 340 | 340 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1145_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1145_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_145_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 7/1/2018 | 7/1/2018 | 5/30/2018 | N | No
AA1-146 | Nelson |  | IL | Lee | Active | ComEd | 190 | 190 | 157 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1146_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  |  |  | 6/1/2024 | 6/1/2024 |  | N | No
AA1-147 | Marion 345kV |  | NJ | Camden | Withdrawn | PSEG | 400 |  |  |  | Energy | Merchant Transmission |  | AC | TWR/400 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2014 | N/A | N/A |  | 12/1/2014 | Customer Initiated Withdrawal | 6/1/2018 |  |  | S | No
AA2-001 | Reusens 34.5kV |  | VA | Campbell | Withdrawn | AEP | 12.5 | 12.5 | 2 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2014 | N/A | N/A |  | 9/10/2015 | Customer Milestone Not Met | 12/8/2014 |  |  | N | No
AA2-002 4686172 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, LP | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2016 | 6/1/2017 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-003 4686173 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, LP | 312 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2017 | 6/1/2018 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-004 4686175 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, LP | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2016 | 6/1/2017 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-005 4686176 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, LP | 456 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/3/2014 | 6/1/2018 | 6/1/2019 |  | 11/24/2014 |  |  |  |  | FF | No
AA2-006 4686643 | PJM-DUK |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 150 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4686643_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/5/2014 | 1/1/2017 | 1/1/2032 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-007 4686662 | PJM-DUK |  | N/A | N/A | Retracted | Avangrid Renewables, LLC | 58 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4686662_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/5/2014 | 1/1/2017 | 1/1/2032 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-008 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 907 | 57 | 0 | 57 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2008_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_008_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/6/2014 | N/A | N/A |  |  |  | 9/1/2016 | 9/1/2016 | 9/1/2016 | N | No
AA2-009 4691199 | AMIL-PJM |  | N/A | N/A | Withdrawn | Exelon Generation Company LLC | 1045 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4691199_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/21/2014 | 6/1/2016 | 6/1/2017 |  | 2/3/2015 |  |  |  |  | FF | No
AA2-010 4691202 | AMIL-PJM |  | N/A | N/A | Withdrawn | Exelon Generation Company LLC | 1045 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/21/2014 | 6/1/2017 | 6/1/2018 |  | 2/3/2015 |  |  |  |  | FF | No
AA2-011 | Winslow Township |  | NJ | Camden | Withdrawn | AEC | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2011_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/24/2014 | N/A | N/A |  | 9/9/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-012 4692026 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services LP | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4692026_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2016 | 6/1/2017 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-013 4692027 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services LP | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4692027_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-014 4692029 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services LP | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4692029_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/24/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-015 4692036 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 12/11/2014 |  |  |  |  | FF | No
AA2-016 4692037 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 12/11/2014 |  |  |  |  | FF | No
AA2-017 | East Palmerton-Acahela 69kV | Penn Forest Wind Project | PA | Carbon | Suspended | PPL | 98 | 98 | 12.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2017_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2017_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_017_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_017_csa.pdf | Document Posted | N/A | N/A |  | 11/26/2014 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AA2-018 4694146 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services LP | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4694146_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/3/2014 | 6/1/2018 | 6/1/2019 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-019 4694147 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services LP | 156 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4694147_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/3/2014 | 6/1/2019 | 6/1/2020 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-020 | Albright-Cross School 138kV |  | MD | Garrett | Withdrawn | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2020_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2014 | N/A | N/A |  | 10/29/2015 | Customer Milestone Not Met | 5/30/2017 |  |  | N | No
AA2-021 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 7 | 7 | 2.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2021_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2014 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-022 4694704 | CPLE-PJM |  | N/A | N/A | Retracted | Virginia Power | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4694704_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 12/5/2014 | 1/1/2015 | 1/1/2026 |  | 3/9/2015 |  |  |  |  | FF | No
AA2-023 4695929 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/11/2014 | 6/1/2015 | 6/1/2016 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-024 4696138 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2015 | 6/1/2016 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-025 4696140 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 156 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2017 | 6/1/2018 |  | 1/22/2015 |  |  |  |  | FF | No
AA2-026 4696144 | AMIL-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 24 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2016 | 6/1/2017 |  | 1/13/2015 |  |  |  |  | FF | No
AA2-027 4696146 | AMIL-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 24 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/12/2014 | 6/1/2017 | 6/1/2018 |  | 1/13/2015 |  |  |  |  | FF | No
AA2-028 4696147 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-029 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 28 | 8 | 5.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2029_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/18/2014 | N/A | N/A |  | 10/2/2015 | Customer Initiated Withdrawal | 12/15/2015 |  |  | N | No
AA2-030 | Nelson |  | IL | Lee | Active | ComEd | 190 | 190 | 157 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2030_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2014 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 |  | N | No
AA2-031 4697572 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-032 4697573 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 1/13/2015 |  |  |  |  | FF | No
AA2-033 4698486 | NYIS-PJM |  | N/A | N/A | Retracted | Castleton Commodities Merchant Trading L.P. | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4698486_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4698486_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 12/23/2014 | 1/1/2016 | 1/1/2023 |  | 12/11/2015 |  |  |  |  | FF | No
AA2-034 4698488 | NYIS-PJM |  | N/A | N/A | Retracted | Castleton Commodities Merchant Trading L.P. | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4698488_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4698488_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 12/23/2014 | 1/1/2017 | 1/1/2024 |  | 12/11/2015 |  |  |  |  | FF | No
AA2-035 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1098.3 | 1019.3 | 1019.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2035_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2014 | N/A | N/A |  | 10/15/2018 |  | 6/30/2019 |  |  | N | No
AA2-036 | West Cambridge 12kV |  | MD | Dorchester | Withdrawn | DPL | 14 | 14 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2036_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-037 | Preston 12kV |  | MD | Caroline | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/9/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/31/2015 |  |  | N | No
AA2-038 4703464 | ALTE-PJM |  | N/A | N/A | Retracted | Calpine Energy Services LP | 312 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4703464_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4703464_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 1/16/2015 | 6/1/2016 | 6/1/2021 |  | 1/20/2016 |  |  |  |  | FF | No
AA2-039 | Kewanee 138 kV |  | IL | Henry | Withdrawn | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2039_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2015 | N/A | N/A |  | 4/16/2020 |  | 12/1/2016 |  |  | N | No
AA2-040 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion |  |  |  |  | Energy | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2015 | N/A | N/A |  | 2/24/2015 | Customer Milestone Not Met | 8/31/2015 |  |  | N | No
AA2-041 | Tidd-Collier |  | OH | Jefferson | Withdrawn | AEP | 225 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 3/16/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AA2-042 | Conastone-Northwest 230kV |  | MD | Harford | Withdrawn | BGE | 102 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2042_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 9/21/2015 |  | 6/1/2016 |  |  | S | No
AA2-043 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 718 | 67 | 99 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2015 | N/A | N/A |  | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AA2-044 | Sherman Avenue 69kV |  | NJ | Cumberland | Withdrawn | AEC | 13.5 | 13.5 | 7.3 |  | Capacity | Generation Interconnection | Solar; Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2044_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/6/2015 | N/A | N/A |  | 8/30/2017 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
AA2-045 4709031 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-046 4709032 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-047 4709033 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [9 empty] | 2/12/2015 |  |  |  |  | FF | No
AA2-048 | Allenwood-Larrabee 34kV | Lakewood-Farmingdale Road Solar Farm & Storage Facility | NJ | Monmouth | Engineering and Procurement | JCPL | 7 | 7 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2048_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/18/2015 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AA2-049 | Atlantic-Oceanview 34kV | Tinton Falls Solar & Storage Facility | NJ | Monmouth | Withdrawn | JCPL | 19.9 | 3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2049_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_049_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_049_csa.pdf | Document Posted | N/A | N/A |  | 2/18/2015 | N/A | N/A |  | 1/6/2020 |  | 6/30/2017 | 6/30/2017 |  | N | No
AA2-050 | Penrose #1 230klV |  | PA | Philadelphia | Withdrawn | PECO | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/18/2015 | N/A | N/A |  | 3/10/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-051 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2015 | N/A | N/A |  | 3/10/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-052 | Essex 26kV |  | NJ | Essex | In Service | PSEG | 3 | 0 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_052_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/20/2015 | N/A | N/A |  |  |  | 2/12/2015 |  | 9/11/2015 | N | No
AA2-053 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 74.9 | 74.9 | 52.4 | 74.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2053_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_053_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A | 7/10/2019 |  |  | 6/19/2019 | 6/19/2019 | 7/10/2019 | N | No
AA2-054 | Pumphrey 230kV |  | MD | Anne Arundel | In Service | BGE | 155 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 65.7 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/aa2054_imp.pdf | Document Posted |  | Not Required |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/aa2_054_csa.pdf | Document Posted | N/A | N/A |  | 2/23/2015 | N/A | N/A |  |  |  | 1/1/2016 |  | 6/7/2017 | S | No
AA2-055 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2015 | N/A | N/A |  | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-056 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2015 | N/A | N/A |  | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AA2-057 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 66 | 66 | 44.7 | 66 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2057_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2057_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_057_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 2/26/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-058 | Mount Rose 13kV | Hopewell Valley Solar | NJ | Mercer | Partially in Service - Under Construction | PSEG | 1 | 1 | 0.3 | 0.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2058_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2058_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 12/30/2015 | N | No
AA2-059 | Edenton 15kV | Edenton Solar | NC | Chowan | Withdrawn | Dominion | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2059_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2059_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa2059_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/5/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AA2-060 | Branchville-Sussex #1 34kV | Plains Road Battery Storage Facility | NJ | Sussex | Engineering and Procurement | JCPL | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_060_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A | 10/31/2020 |  |  | 6/30/2017 | 6/30/2017 |  | N | No
AA2-061 | Branchville-Sussex #2 34.5kV | Mohawk Battery Storage Facility | NJ | Sussex | Engineering and Procurement | JCPL | 8 | 8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_061_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A | 10/31/2020 |  |  | 6/23/2017 | 6/23/2017 |  | N | No
AA2-062 | Branchville-N. Newton #1 34.kV |  | NJ | Sussex | Withdrawn | JCPL | 7 | 7 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2062_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 5/6/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-063 | Branchville-N. Newton #2 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2063_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 5/6/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-064 | Branchville-N. Newton #3 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 17 | 17 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2064_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/3/2017 | Customer Milestone Not Met | 12/1/2015 |  |  | N | No
AA2-065 | Hazen Switch Point-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2065_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 9/2/2016 | Customer Milestone Not Met | 12/1/2015 |  |  | N | Yes
AA2-066 | Penns Neck 13kV | Princeton Hospital NRG Energy Center | NJ | Mercer | In Service | PSEG | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2066_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2066_wmpa.pdf |  | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  |  |  | 6/1/2016 | 6/1/2016 | 8/16/2017 | Y | No
AA2-067 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 11/29/2016 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-068 | South Justice 115kV | N301 Solar | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2068_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2068_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa2068_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 4/3/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
AA2-069 | Cartanza 230kV | Garrison Energy Center | DE | New Castle | Suspended | DPL | 760.2 | 451 | 451 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_069_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2015 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AA2-069A | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 64.6 | 8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2015 | N/A | N/A |  | 3/26/2015 |  |  |  |  | N | No
AA2-070 | Smith Mountain 138kV | Smith Mountain Hydro | VA | Henry | In Service | AEP | 649 | 34 | 34 | 34 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_070_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/28/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
AA2-071 4714642 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing, LLC | 700 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4714642_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/2/2015 | 1/1/2017 | 1/1/2024 |  | 5/21/2015 |  |  |  |  | FF | No
AA2-072 | Kingsville 13kV | Kingsville Solar | MD | Harford | In Service | BGE | 1.1 | 1.1 | 0 | 1.1 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2072_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/9/2015 | N/A | N/A |  |  |  | 5/1/2016 | 5/1/2016 | 6/14/2016 | Y | No
AA2-073 4716842 | PJM-MEC |  | N/A | N/A | Retracted | NRG Power Marketing, LLC | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4716842_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 3/9/2015 | 6/1/2016 | 6/1/2021 |  | 5/21/2015 |  |  |  |  | FF | No
AA2-074 4717004 | CPLE-PJM |  | N/A | N/A | Confirmed | Virginia Power | 45 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4717004_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4717004_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/10/2015 | 1/1/2015 | 1/1/2026 | [6 empty] | FF | No
AA2-075 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 250 | 250 | 33 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2075_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2015 | N/A | N/A |  | 1/27/2017 | Customer Initiated Withdrawal | 3/14/2022 |  |  | N | No
AA2-076 | Linwood 230kV | Phillips Island CT1, CT2, CT3 & ST4 | PA | Delaware | Partially in Service - Under Construction | PECO | 852 | 0 | 18 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2076_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_076_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2015 | N/A | N/A |  |  |  | 5/31/2018 |  |  | N | No | This project slid to the next queue
AA2-077 | Penrose #1 230kV |  | PA | Philadelphia | Withdrawn | PECO | 220 | 220 | 220 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2077_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2077_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/27/2015 | N/A | N/A |  | 5/31/2018 |  | 5/1/2018 |  |  | N | No
AA2-078 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2078_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2015 | N/A | N/A |  | 11/12/2015 | Customer Milestone Not Met | 5/1/2018 |  |  | N | No
AA2-079 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 668 | 28 | 0 | 28 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2079_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_079_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2015 | N/A | N/A |  |  |  | 10/31/2016 | 10/31/2016 | 7/27/2016 | N | No
AA2-080 | Ellsworth-Eppler Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2080_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 12/2/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-081 | Niles Valley 34.5kV | Niles Valley 34.5kV | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2081_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2081_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_081_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_081_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 3/15/2018 |  | 8/28/2018 | 8/28/2018 |  | N | No
AA2-082 | Alpha 34.5kV | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2082_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_082_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 10/20/2018 | 10/20/2018 | 1/28/2019 | N | No
AA2-083 | South Troy 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2083_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-084 | Lappans Road 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2084_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 9/20/2016 | Customer Initiated Withdrawal | 11/2/2016 |  |  | N | No
AA2-085 | General Office 12.5kV |  | MD | Washington | Withdrawn | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2085_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_085_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 9/6/2019 |  | 9/5/2016 |  |  | N | No
AA2-086 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 13 | 4.5 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2086_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2086_wmpa.pdf |  | Not Required | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 1/25/2018 |  | 10/31/2017 | 10/31/2017 |  | N | No
AA2-087 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2015 | N/A | N/A |  | 10/5/2015 | Customer Milestone Not Met | 9/5/2016 |  |  | N | No
AA2-088 | Boykins-Handsome 115kV | Newsoms Solar | VA | Washington | In Service | Dominion | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_088_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2015 | N/A | N/A |  |  |  | 12/1/2017 | 12/1/2017 | 12/15/2017 | N | No
AA2-089 4725077 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 200 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725077_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4725077_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2017 | 1/1/2025 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-090 4725079 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725079_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4725079_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2018 | 1/1/2025 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-091 4725081 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 15 | 15 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725081_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/14/2015 | 1/1/2018 | 1/1/2025 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-092 4725288 | PJM-AMIL |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725288_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4725288_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 4/15/2015 | 1/1/2016 | 1/1/2024 |  | 12/8/2015 |  |  |  |  | FF | No
AA2-093 4725500 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 20 | 20 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725500_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-094 4725501 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 22 | 22 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725501_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-095 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [14 empty] | FF | No
AA2-096 4725504 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 16 | 16 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725504_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-097 4725505 | CIN-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 21 | 21 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4725505_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 4/16/2015 | 1/1/2017 | 1/1/2024 |  | 3/31/2016 |  |  |  |  | FF | No
AA2-098 | George Washington (Moundsville) |  | WV | Marshall | Withdrawn | AEP | 565 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AA2-099 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 0 | 32 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2099_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2099_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_099_csa.pdf | Document Posted | N/A | N/A |  | 4/21/2015 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 | 6/5/2018 | N | No
AA2-100 | Brown 34.5kV | Bio Energy Landfill Facility | OH | Brown | In Service | DEOK | 4.8 | 4.8 | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2100_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2100_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa2100_wmpa.pdf | Not Required | N/A | N/A |  | 4/22/2015 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 5/10/2017 | N | No
AA2-101 4726899 | PJM-MECS |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4726899_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4726899_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/22/2015 | 6/1/2019 | 6/1/2025 | [6 empty] | FF | No
AA2-102 4726900 | PJM-MECS |  | N/A | N/A | Confirmed | NRG Power Marketing LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4726900_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4726900_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/22/2015 | 6/1/2019 | 6/1/2025 | [6 empty] | FF | No
AA2-103 | Backbone Mountain 138kV | Backbone Mountain Energy Storage | WV | Tucker | Suspended | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2103_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2103_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_103_csa.pdf | Document Posted | N/A | N/A |  | 4/24/2015 | N/A | N/A |  |  |  | 7/31/2019 | 7/31/2019 |  | N | No
AA2-104 | Bigby 115kV |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 7/27/2016 | Customer Milestone Not Met | 12/30/2016 |  |  | N | No
AA2-105 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2105_fea.pdf | Document Posted |  | Withdrawn |  |  | https://www.pjm.com/pub/planning/project-queues/isa/aa2_105_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017 | 3/31/2017 |  | N | No
AA2-106 | Bluff Point 69kV |  | IN | Jay | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2106_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 3/13/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AA2-107 | Waterman 34kV |  | IL | DeKalb | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2107_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/24/2015 | N/A | N/A |  | 10/22/2018 |  | 12/1/2016 |  |  | N | No
AA2-108 | Plano 765kV |  | IL | Kendall | Withdrawn | ComEd | 2060 |  |  |  | Energy | Merchant Transmission |  | DC | 2060 FTIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/aa2108_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 10/26/2015 | Customer Milestone Not Met | 9/30/2021 |  |  | S | No
AA2-109 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 1100 | 1100 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2109_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-110 | Eddystone 230kV |  | PA | Delaware | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-111 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AA2-112 | Tiffany 34.5kV |  | PA | Susquehanna | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2112_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2112_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/27/2015 | N/A | N/A |  | 11/14/2017 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AA2-113 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2113_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017 | 3/31/2017 |  | N | No
AA2-114 | Furnace Brook-Hazen Switch Point 34kV |  | NJ | Union | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2114_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 5/2/2016 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | Yes
AA2-115 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 450 | 450 | 450 | 450 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2115_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2115_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_115_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2015 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AA2-116 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 994 | 994 | 994 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2116_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2116_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_116_csa.pdf | Document Posted | N/A | N/A | 6/7/2021 | 4/28/2015 | N/A | N/A | 10/28/2021 |  |  | 7/30/2021 | 7/30/2021 |  | N | No
AA2-117 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16 | 16 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2117_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2015 | N/A | N/A |  | 6/2/2016 | Customer Milestone Not Met | 5/2/2016 |  |  | N | No
AA2-118 | Murphy-Tunis 115kV |  | NC | Hertford | Withdrawn | Dominion | 35.2 | 35.2 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/6/2015 | Customer Initiated Withdrawal | 6/30/2017 |  |  | N | No
AA2-119 | Glenn Falls 138kV | Glen Falls Facility | WV | Harrison | Suspended | APS | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2119_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2119_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_119_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2015 | N/A | N/A | 7/30/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AA2-120 | Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2120_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/25/2016 | Customer Milestone Not Met | 6/1/2020 |  |  | N | No
AA2-121 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Engineering and Procurement | APS | 685 | 685 | 685 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2121_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2121_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_121_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_121_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2015 | N/A | N/A | 12/31/2022 |  |  | 8/3/2021 | 8/3/2021 |  | N | No
AA2-122 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 143.5 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2122_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 5/24/2016 | Customer Milestone Not Met | 5/1/2016 |  |  | N | No
AA2-123 | Marengo 34kV | Marengo Battery Storage | IL | McHenry | In Service | ComEd | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2123_wmpa.pdf |  | Not Required | N/A | N/A |  | 4/29/2015 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 11/19/2018 | N | No
AA2-124 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 576 | 576 | 553 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2124_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 9/10/2015 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AA2-125 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 580.1 | 580.08 | 504 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/29/2015 | N/A | N/A |  | 9/9/2015 | Customer Initiated Withdrawal | 5/31/2017 |  |  | N | No
AA2-126 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 6/5/2015 | Customer Initiated Withdrawal | 4/1/2016 |  |  | N | No
AA2-127 | Bear Garden 230kV | Bear Garden Facility | VA | Buckingham | In Service | Dominion | 682 | 7 | 32.2 | 7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_127_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 5/1/2016 | N | No
AA2-128 | Raritan River-Werner 115kV |  | NJ | Middlesex | Withdrawn | JCPL | 175 | 175 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2128_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/24/2017 | Customer Initiated Withdrawal | 6/27/2017 |  |  | N | No
AA2-129 | New Church 138kV |  | VA | Accomack | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2129_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 6/8/2018 |  | 12/31/2016 |  |  | N | No
AA2-130 | Kings Creek-Crisfield 69kV | CleanBay Biomass Generator | MD | Somerset | Withdrawn | DPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2130_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2130_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa2130_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/8/2019 |  | 9/25/2018 | 9/25/2018 |  | N | No
AA2-131 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 354 | 0 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2131_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_131_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 5/25/2018 | N | No
AA2-132 | Thompson 34.5kV | Thompson 34.5kV | PA | Susquehanna | Suspended | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2132_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2132_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_132_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 9/28/2018 | 9/28/2018 |  | N | No
AA2-133 | Wyalusing 34.5kV | Wyalusing 34.5kV | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2133_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2133_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_133_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/31/2019 | 5/31/2019 | 2/21/2019 | N | No
AA2-134 | Andrew Shaft-84 Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2134_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/29/2015 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-135 | East Towanda 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2135_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/17/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-136 | Kendall |  | IL | Kendall | Withdrawn | ComEd | 1228.8 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2136_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/2/2015 | Customer Milestone Not Met | 5/1/2016 |  |  | N | No
AA2-137 | Hanging Rock 765kV - Power Block 1 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2137_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_137_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 |  | 12/2/2016 | N | No
AA2-138 | Hanging Rock 765kV - Power Block 2 | Cornu | OH | Lawrence | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2138_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_138_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2019 | 5/1/2019 | 12/2/2016 | N | No
AA2-139 | Ronco 500kV | Fayette Energy Facility | PA | Fayette | In Service | APS | 706 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2139_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_139_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_139_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 10/1/2017 | 10/1/2017 | 4/21/2017 | N | No
AA2-140 | Printz 230kV | Liberty Electric | PA | Delaware | Partially in Service - Under Construction | PECO | 641.5 | 35 | 35 | 25 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2140_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_140_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 5/1/2016 |  | 6/30/2017 | N | No
AA2-141 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 670 | 45 | 45 | 45 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 8/31/2016 | 8/31/2016 | 12/2/2016 | N | No
AA2-142 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 1377 | 1377 | 1278 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2142_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AA2-143 | Catoctin 12.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2143_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/26/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-144 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-145 | Catoctin 34.5kV | Hessong Birdge Solar Facility | MD | Frederick | Withdrawn | APS | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2145_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_145_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/22/2019 |  | 9/15/2017 | 9/15/2017 |  | N | No
AA2-146 | Catoctin 34.5kV |  | MD | Frederick | Withdrawn | APS | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2146_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/13/2016 | Customer Milestone Not Met | 9/15/2016 |  |  | N | No
AA2-147 | Todd 12kV |  | MD | Dorchester | Withdrawn | DPL | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-148 | Madison-Tanners Creek 138kV |  | IN | Fayette | Active | AEP | 175 | 174.2 | 22.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 |  | N | No
AA2-149 | Carolina-Seaboard 115kV |  | NC | Northhampton | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2149_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/6/2015 | Customer Milestone Not Met | 12/15/2015 |  |  | N | No
AA2-150 | Trappe 12kV |  | MD | Talbot | Withdrawn | DPL | 10 | 10 | 6.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2150_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-151 | Delano-Scioto Trail 138kV |  | OH | Ross | Withdrawn | AEP | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/18/2015 |  | 6/30/2016 |  |  | N | No
AA2-152 | Keeney-Steel 230kV |  | MD | Caroline | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/20/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-153 | Yellow Springs 34.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2153_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/22/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-154 | Watkins Corner 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2154_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/2/2015 | Customer Initiated Withdrawal | 11/30/2015 |  |  | N | No
AA2-155 | Mt. Lena 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2155_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/19/2016 | Customer Initiated Withdrawal | 9/15/2016 |  |  | N | No
AA2-156 | Aydlett-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-157 | Cashie-Trowbridge 230kV |  | NC | Martin | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-158 | Louisa 34.5kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-159 | Downsville 34.5kV | Route 632 Washington Solar Facility | MD | Washington | Engineering and Procurement | APS | 16 | 16 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2159_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_159_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_159_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 6/30/2021 |  |  | 9/15/2017 | 9/15/2017 |  | N | No
AA2-160 | Bridgeville 12kV |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/18/2015 |  | 11/30/2015 |  |  | N | No
AA2-161 | Yukon-Robbins 138kV | Allegheny Energy Center LLC | PA | Allegheny | Engineering and Procurement | APS | 541 | 541 | 513 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2161_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2161_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_161_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 6/1/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
AA2-162 | Elizabeth City-Shawboro 230kV |  | NC | Camden | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met |  |  |  | N | No
AA2-163 | Wakefield 12.5kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-164 | Murphy 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 11/30/2015 |  |  | N | No
AA2-165 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 74.9 | 8.9 | 5.3 | 8.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_165_csa.pdf | Document Posted | N/A | N/A | 9/1/2019 | 4/30/2015 | N/A | N/A | 11/18/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/26/2019 | N | No
AA2-166 | Shenango-Bedford 69kV |  | PA | Lawrence | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2166_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-167 | East Sayre 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2167_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AA2-168 | Prince George's County |  | MD | Prince George's | Withdrawn | PEPCO | 4 | 4 | 1.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 8/27/2015 | Customer Milestone Not Met | 12/31/2016 |  |  | N | No
AA2-169 | Five Forks 115kV | Five Forks Solar | NC | Warren | Withdrawn | Dominion | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2169_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2169_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/aa2169_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/aa2169_wmpa.pdf | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 4/3/2018 |  | 8/31/2018 | 8/31/2018 |  | N | No
AA2-170 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Engineering and Procurement | PEPCO | 1038.1 | 111.1 | 92 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2170_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2170_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_170_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/1/2022 | 3/1/2022 |  | N | No
AA2-171 | Sunbury #1 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 1121 | 97 | 60 | 97 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2171_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_171_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/30/2015 | N/A | N/A |  |  |  | 3/15/2018 | 3/15/2018 | 6/1/2018 | N | No
AA2-172 | ATSI-PSEG |  | N/A | N/A | Withdrawn | PSEG | 115 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 7/8/2015 |  |  |  |  | EE | No
AA2-173 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | Under Construction | APS | 515 | 515 | 515 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2173_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2173_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_173_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 2/1/2021 |  |  | 5/9/2021 | 5/9/2021 |  | N | No
AA2-174 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 79.9 | 5 | 2.4 | 5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2174_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2174_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 7/10/2019 |  |  | 4/22/2019 | 4/22/2019 | 7/10/2019 | N | No
AA2-175 | Suffolk-Sunbury 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-176 | Indian River-Piney Grove 230kV |  | DE | Sussex | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/21/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-177 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2177_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2177_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_177_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_177_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 10/13/2017 |  | 11/15/2021 | 11/15/2021 |  | N | No
AA2-178 | Mackeys 230kV | Ablemarle Beach Solar | NC | Washington | Under Construction | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2178_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2178_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_178_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_178_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 8/1/2020 |  |  | 9/30/2020 | 9/30/2020 |  | N | No
AA2-179 | Creswell-Mackeys 115kV |  | NC | Washington | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2015 |  |  | N | No
AA2-180 | Hickory 34.5kV | Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2180_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2180_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_180_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_180_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/29/2016 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
AA2-181 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/22/2015 | Customer Milestone Not Met | 6/30/2016 |  |  | N | No
AA2-182 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 1030 | 1030 | 977 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2182_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2182_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/4/2020 |  | 9/2/2019 |  |  | N | No
AA2-183 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 234 | 234 | 230 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2183_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 2/11/2016 |  | 6/1/2019 |  |  | N | No
AA2-184 | Atlantic-Red Bank 34kV | Atlantic-RedBank 34.5kV Solar | NJ | Monmouth | In Service | JCPL | 20 | 20 | 0 | 20 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/aa2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_184_csa.pdf | Document Posted | N/A | N/A |  | 4/30/2015 | N/A | N/A | 11/30/2019 |  |  | 12/5/2019 | 12/5/2019 | 12/31/2019 | N | No
AA2-185 | Independent Hill 115kV |  | VA | Prince William | Withdrawn | Dominion | 1.9 | 1.6 | 0 |  | Energy | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 9/15/2015 | Customer Initiated Withdrawal | 1/31/2016 |  |  | Y | No
AA2-186 | Forest 69kV |  | OH | Hardin | Withdrawn | AEP | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2186_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/30/2015 | N/A | N/A |  | 5/11/2017 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-001 | Absecon 12 kV | Oak Street Landfill Solar Project | NJ | Atlantic | Engineering and Procurement | AEC | 2.3 | 2.3 | 0.87 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1001_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1001_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1001_wmpa.pdf | Not Required | N/A | N/A |  | 5/1/2015 | N/A | N/A | 11/1/2020 |  |  | 3/30/2020 | 3/30/2020 |  | Y | No
AB1-002 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 909 | 909 | 765 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2015 | N/A | N/A |  | 4/25/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AB1-003 | Keystone-Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 1474 | 1474 | 1474 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2015 | N/A | N/A |  | 4/18/2016 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AB1-004 | Solar Holler, LLC |  | N/A | N/A | Withdrawn | AEP | 0.4 | 0.4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2015 | N/A | N/A |  | 5/19/2015 |  | 10/1/2015 |  |  | Y | No
AB1-005 | Harrisonville 13kV |  | MD | Baltimore County | Under Construction | BGE | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1005_wmpa.pdf |  | Not Required | N/A | N/A |  | 5/18/2015 | N/A | N/A | 10/1/2020 |  |  | 12/1/2015 | 12/1/2015 |  | Y | No
AB1-006 | Meadow Lake 345kV | Meadow Lake Wind Farm VI | IN | White | In Service | AEP | 200 | 200 | 26 | 200 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1006_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1006_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_006_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_006_csa.pdf | Document Posted | N/A | N/A |  | 5/22/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/21/2018 | N | No
AB1-007 4735313 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketin, LLC | 58 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4735313_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-008 4735314 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing LLC | 85 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4735314_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-009 4735315 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing, LLC | 95 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4735315_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 5/26/2015 | 1/1/2018 | 1/1/2025 |  | 8/24/2015 |  |  |  |  | FF | No
AB1-010 | Quakertown |  | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 | Customer Milestone Not Met | 4/1/2015 |  |  | N | No
AB1-011 | Bear Branch 13kV |  | MD | Prince George's | Withdrawn | BGE | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 |  | 5/15/2015 |  |  | N | No
AB1-012 | Hackettstown |  | NJ | Warren | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/27/2015 | N/A | N/A |  | 6/18/2015 | Customer Milestone Not Met | 4/1/2015 |  |  | N | No
AB1-013 | Riders Creek 115kV | Little Alligator Windfarm | NC | Tyrell | Withdrawn | Dominion | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1013_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_013_csa.pdf | Document Posted | N/A | N/A |  | 5/29/2015 | N/A | N/A |  | 5/22/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AB1-014 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | Under Construction | DEOK | 125 | 125 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1014_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1014_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_014_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 6/8/2015 | N/A | N/A | 9/8/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB1-015 | Evergreen 138kV | Warren Natural Gas Generation Faciility | OH | Trumbull | In Service | ATSI | 16.5 | 16.5 | 0 | 16.5 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_015_csa.pdf | Document Posted | N/A | N/A |  | 6/16/2015 | N/A | N/A | 10/10/2016 |  |  | 10/1/2017 | 10/1/2017 | 10/10/2016 | N | No
AB1-016 4740070 |  |  | N/A | N/A | Withdrawn |  |  | 90 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2016 | 1/1/2025 |  | 6/22/2015 |  |  |  |  | FF | No
AB1-017 | Highland-Sammis 345 kV & Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 940 | 140 | 64 | 140 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1017_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1017_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_017_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/18/2015 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 8/11/2018 | N | No
AB1-018 4740256 | TVA-PJM |  | N/A | N/A | Retracted | Associated Electric Cooperative Inc | 90 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4740256_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 6/18/2015 | 1/1/2016 | 1/1/2021 |  | 3/31/2016 |  |  |  |  | FF | No
AB1-019 | Newlinville 230 kV |  | PA | Chester | Withdrawn | PECO | 100 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1019_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab1019_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2015 | N/A | N/A |  | 4/12/2018 |  | 6/1/2018 |  |  | S | No
AB1-020 | Cold Spring 240v |  | MD | Baltimore City | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1020_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | Partially in Service - Under Construction | PSEG | 2 | 2 | 0.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 6/1/2018 | N | No
AB1-022 | Columbia 115kV |  | VA | Louisa | Withdrawn | Dominion | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1022_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/6/2015 | N/A | N/A |  | 4/6/2020 |  | 3/31/2017 | 3/31/2017 |  | Y | No
AB1-023 4743994 | LGEE-PJM |  | N/A | N/A | Withdrawn | American Municipal Power, Inc. | 120 | 120 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4743994_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 7/7/2015 | 6/1/2017 | 6/1/2022 |  | 8/18/2016 |  |  |  |  | FF | No
AB1-024 | Loretto-Wilton Ctr |  | IL | Livingston | Withdrawn | ComEd | 50 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2015 | N/A | N/A |  | 8/25/2016 |  | 6/1/2017 |  |  | S | No
AB1-025 | Lumberton 13kV | Lumberton Solar | NJ | Burlington | In Service | PSEG | 6.8 | 6.8 | 2.6 | 6.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/AB1025_wmpa.pdf |  | Not Required | N/A | N/A |  | 7/21/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 8/22/2016 | N | No
AB1-026 | Westmoreland 34.5kV | Montross Solar | VA | Westmoreland | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1026_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1026_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_026_isa.pdf | Document Posted | N/A |  | Withdrawn | N/A | N/A |  | 7/22/2015 | N/A | N/A |  | 5/25/2017 | Customer Milestone Not Met | 11/15/2020 | 11/15/2020 |  | N | No
AB1-027 | Old Church 34.5 KV |  | VA | Hanover | Under Construction | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1027_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1027_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_027_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_027_csa.pdf | Document Posted | N/A | N/A |  | 7/22/2015 | N/A | N/A | 8/1/2020 |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AB1-028 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2015 | N/A | N/A |  | 8/14/2015 |  | 8/31/2016 |  |  | N | No
AB1-029 | Loretto-Pontiac |  | IL | Livingston | Withdrawn | ComEd | 35 |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2015 | N/A | N/A |  | 3/10/2017 |  | 6/1/2017 |  |  | S | No
AB1-030 | Huron 69kV |  | NJ | Atlantic | Withdrawn | AEC | 23 | 7.5 | 3.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1030_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/28/2015 | N/A | N/A |  | 6/28/2016 | Customer Milestone Not Met | 12/1/2016 |  |  | N | No
AB1-031 | North Wales 34kV |  | PA | Montgomery | Withdrawn | PECO | 9 | 9 | 0 |  | Energy | Generation Interconnection | Diesel |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2015 | N/A | N/A |  | 7/29/2015 |  |  |  |  | N | No
AB1-031A | LAKEWOOD 18 KV OCEAN C1-ATLANTIC 230 KV REACTR |  | NJ | Unknown | Withdrawn | JCPL | 25 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1031a_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2015 | N/A | N/A |  | 3/3/2017 |  |  |  |  | EE | No
AB1-032 | Lee Station Southwest 12kV |  | OH | Athens | Withdrawn | AEP | 3.3 | 3.3 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1032_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 7/31/2015 | N/A | N/A |  | 8/1/2017 | Customer Initiated Withdrawal | 12/31/2016 | 12/31/2016 |  | N | No
AB1-033 | North Wales 34.5kV | Morris Road | PA | Montgomery | Partially in Service - Under Construction | PECO | 6 | 4 | 4.1 | 1.5 | Capacity | Generation Interconnection | Diesel |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1033_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1033_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_033_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_033_csa.pdf | Document Posted | N/A | N/A |  | 8/12/2015 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 2/25/2019 | N | No
AB1-034 | Maintou 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 0.6 | 0.6 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1034_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/12/2015 | N/A | N/A |  | 4/8/2016 | Customer Milestone Not Met | 9/1/2015 |  |  | N | No
AB1-035 | Mill Creek 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1035_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-036 | Howard 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1036_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-037 | Ridgeview 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1037_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-038 | Shadyside 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1038_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-039 | Lipins Corner 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1039_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-040 | Glendale 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1040_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-041 | Hunt Club 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1041_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-042 | Wall Cove 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1042_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-043 | Riva Road 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1043_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-044 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1044_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-045 | East Towson 240v |  | MD | Baltimore County | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1045_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-046 | Sudbrook Park 240v |  | MD | Baltimore County | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1046_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 8/15/2015 |  |  | BB | No
AB1-047 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1047_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-048 | Texas 240v |  | MD | Baltimore County | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1048_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-049 | Friendship Manor 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1049_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-050 | High Ridge 240v |  | MD | Howard | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1050_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/14/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-051 | Lutherville 240v |  | MD | Baltimore County | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1051_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-052 | Bengies 240v |  | MD | Baltimore County | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1052_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-053 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 10 | 10 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 1/13/2017 | Customer Initiated Withdrawal | 11/15/2017 | 11/15/2017 |  | N | No
AB1-054 | Boykins 115kV |  | VA | Southampton | Withdrawn | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1054_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2015 | N/A | N/A |  | 12/13/2016 | Customer Initiated Withdrawal | 12/31/2018 | 12/31/2018 |  | N | No
AB1-055 | Balls Gap 34.5kV | Balls Gap Battery Facility | WV | Cabell | In Service | AEP | 2 | 2 | 0 | 2 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1055_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1055_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1055_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 3/1/2017 | N | No
AB1-056 | Indian River 230kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 247.8 | 247.8 | 64.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1056_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_056_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2015 | N/A | N/A | 9/1/2023 |  |  | 10/31/2021 | 10/31/2021 |  | N | No
AB1-057 | Indian River 230kV II |  | DE | Sussex | Withdrawn | DPL | 251.8 | 251.8 | 65.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1057_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1057_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 8/16/2018 |  | 3/1/2020 |  |  | N | No
AB1-058 | Gavin Unit #1 765kV | Gavin #1 | OH | Gallia | In Service | AEP | 1331 | 11 | 11 | 11 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 12/31/2017 | N | No
AB1-059 | Old Church 34.5kV |  | VA | Hanover | Withdrawn | Dominion | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1059_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 3/31/2016 | Customer Initiated Withdrawal | 1/1/2017 |  |  | N | No
AB1-060 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-061 | Fieldale-Thornton-Franklin 138kV & Danville-East Danville 138kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-062 | Graceton-Safe Harbor |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 9/3/2015 | Customer Initiated Withdrawal | 6/1/2016 |  |  | S | No
AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | Partially in Service - Under Construction | PSEG | 0.4 | 0.4 | 0 | 0.2 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1063_wmpa.pdf |  | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 2/15/2017 | N | No
AB1-064 | Monessen 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 11.2 | 4 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1064_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1064_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1064_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017 | 8/16/2017 |  | N | No
AB1-065 | Jennings-Hoyes 34.5kV | CleanLight Power Solar Facility | MD | Garrett | Suspended | APS | 10.9 | 10.9 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1065_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1065_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1065_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2015 | N/A | N/A |  |  |  | 10/31/2019 | 10/31/2019 |  | N | No
AB1-066 | Lime Kiln-Aqueduct 34.5kV |  | MD | Frederick | Withdrawn | APS | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 3/2/2016 | Customer Initiated Withdrawal | 12/15/2016 |  |  | N | No
AB1-067 | Unionville 12.5kV |  | VA | Orange | Withdrawn | Dominion | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2015 | N/A | N/A |  | 4/4/2016 | Customer Milestone Not Met | 9/26/2016 |  |  | N | No
AB1-068 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 364 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1068_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2015 | N/A | N/A |  | 10/2/2017 |  | 5/1/2019 | 5/1/2019 |  | N | No
AB1-069 | Wylie Ridge 500kV | Beech Hollow Energy Center | PA | Washington | Suspended | APS | 1025 | 1025 | 950 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_069_csa.pdf | Document Posted | N/A | N/A |  | 9/9/2015 | N/A | N/A | 12/31/2021 |  |  | 6/1/2022 | 6/1/2022 |  | N | No
AB1-070 | Emporia-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2015 | N/A | N/A |  | 9/28/2015 | Customer Initiated Withdrawal | 12/15/2017 |  |  | N | No
AB1-071 | Greenbury Point 240V |  | MD | Anne Arundel | Withdrawn | BGE | 0 | 0.005 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1071_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/11/2015 | N/A | N/A |  | 9/27/2019 |  | 12/31/2015 | 12/31/2015 |  | BB | No
AB1-072 | Hancock-Marlowe 34.5kV |  | MD | Washington | Withdrawn | APS | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1072_fea..pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1072_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/14/2015 | N/A | N/A |  | 7/13/2016 | Customer Milestone Not Met | 7/1/2016 |  |  | N | No
AB1-073 | Eddystone 138kV |  | PA | Delaware | Withdrawn | PECO | 856 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1073_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-074 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 118 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1074_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-075 | Riverside 115kV |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1075_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 12/16/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-076 | Fourmile Ridge 138kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1076_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2015 | N/A | N/A |  | 11/9/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-077 | Suffolk-WinFall 230kV |  | NC | Perquimans | Withdrawn | Dominion | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1077_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2015 | N/A | N/A |  | 11/21/2016 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AB1-078 | Wilson 34.5kV |  | PA | Washington | Withdrawn | APS | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1078_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 9/22/2015 | N/A | N/A |  | 5/18/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-079 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 6.5 | 6.5 | 6.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1079_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2015 | N/A | N/A |  | 8/5/2016 | Customer Milestone Not Met | 12/29/2016 |  |  | N | No
AB1-080 | Dumont-Olive 345kV | St. Joseph's Energy Center, LLC | IN | St. Joseph | In Service | AEP | 715 | 40 | 40 | 40 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1080_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1080_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_080_csa.pdf | Document Posted | N/A | N/A | 7/1/2017 | 9/30/2015 | N/A | N/A | 12/28/2017 |  |  | 4/29/2018 | 4/29/2018 | 4/1/2018 | N | No
AB1-081 | Anaconda-Mayo Dunbar 115kV | Harts Mill Solar | NC | Edgecombe | Under Construction | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1081_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1081_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_081_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_081_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2015 | N/A | N/A | 11/1/2020 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AB1-082 | Potter 46kV | IMG Generation Potter Facility | PA | Potter | Suspended | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1082_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_082_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 |  | N | No
AB1-083 | McDowell-Sharon 69kV |  | PA | Susquehanna | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1083_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-084 | Greenfield-Elk Mountain 69kV |  | PA | Susquehanna | Withdrawn | PPL | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1084_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1084_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 6/14/2018 |  | 12/1/2017 |  |  | N | No
AB1-085 | North Aurora |  | IL | Kane | Withdrawn | ComEd | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 11/29/2016 | Customer Initiated Withdrawal | 9/1/2016 |  |  | N | No
AB1-086 | Pontiac Midpoint 345kV |  | IL | McLean | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1086_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 4/27/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AB1-087 | Sullivan 345kV #1 |  | IN | Sullivan | Active | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1087_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB1-088 | Sullivan 345kV #2 |  | IN | Sullivan | Active | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1088_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB1-089 | Byron-Wayne 345kV #1 |  | IL | Lee | Active | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1089_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB1-090 | Byron-Wayne 345kV #2 |  | IL | Lee | Withdrawn | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  | 10/18/2018 |  | 6/1/2019 |  |  | N | No
AB1-091 | Davis Creek 345kV |  | IL | Kankakee | Active | ComEd | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB1-092 | Moshannon-East Towanda 230kV |  | PA | Clinton | Active | PENELEC | 504 | 41 | 17 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2015 | N/A | N/A |  |  |  | 5/1/2019 |  |  | N | No
AB1-093 | Oakland |  | NJ | Bergen | Withdrawn | RE | 0.9 | 0.85 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2015 | N/A | N/A |  | 10/12/2015 |  | 12/1/2015 |  |  | N | No
AB1-094 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 0.9 | 0.85 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/5/2015 | N/A | N/A |  | 10/12/2015 |  | 12/1/2015 |  |  | N | No
AB1-095 | Rona 12kV | Dovetail Biogas Facility | OH | Greene | In Service | ATSI | 0.9 | 0.85 | 0 | 0.85 | Energy | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1095_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1095_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/6/2015 | N/A | N/A | 9/30/2016 |  |  | 12/31/2016 | 12/31/2016 | 9/30/2016 | Y | No
AB1-096 | Carroll-Mt. Airy 34.5kV | Union Bridge Solar Facility | MD | Carroll | Engineering and Procurement | APS | 9.9 | 8.2 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1096_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_096_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_096_csa.pdf | Document Posted | N/A | N/A |  | 10/7/2015 | N/A | N/A | 10/20/2020 |  |  | 10/20/2020 | 10/20/2020 |  | N | No
AB1-097 | Harrisonburg-Stauton 115kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1097_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/7/2015 | N/A | N/A |  | 4/26/2016 | Customer Initiated Withdrawal | 11/10/2017 |  |  | N | No
AB1-098 | Walkersville 12kV | Walkersville Solar Facility | MD | Frederick | Withdrawn | APS | 8.2 | 8.16 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1098_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1098_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1098_wmpa.pdf | Not Required | N/A | N/A |  | 10/8/2015 | N/A | N/A |  | 6/23/2017 | Customer Initiated Withdrawal | 1/1/2019 | 1/1/2019 |  | N | No
AB1-099 | Sunnymeade Road 13kV |  | NJ | Somerset | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Not Required |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1099_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/13/2015 | N/A | N/A |  | 6/16/2017 | Customer Initiated Withdrawal | 9/1/2016 | 9/1/2016 |  | Y | No
AB1-100 4764572 | NYIS-PJM |  | N/A | N/A | Withdrawn | Renovo Energy Center LLC | 480 | 480 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4764572_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4764572_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/14/2015 | 6/1/2020 | 6/1/2025 |  | 1/29/2018 |  |  |  |  | FF | No
AB1-101 | Cloverdale-Jacksons Ferry 765kV |  | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1101_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-102 | Graceton-Safe Harbor 230kV |  | N/A | N/A | Withdrawn | PPL |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1102_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-103 | Fieldale-Thornton & Danville-E. Danville 138kV | CMN | N/A | N/A | Withdrawn | AEP |  |  |  |  | Energy | Merchant Transmission |  | AC |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab1103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2015 | N/A | N/A |  | 9/20/2016 |  | 6/1/2016 |  |  | S | No
AB1-104 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 9.9 | 9.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2015 | N/A | N/A |  | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB1-105 | Highland-Hanna 345kV |  | OH | Trumbull | Active | ATSI | 940 | 940 | 850 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1105_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1105_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/21/2015 | N/A | N/A |  |  |  | 10/16/2020 |  |  | N | No
AB1-106 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 940 | 10 | 40 | 10 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1106_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1106_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_106_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/22/2015 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 11/18/2018 | N | No
AB1-107 | Bayshore-GM Powertrain 138 kV & Lallendorf 345kV | Cedar Point Energy Center | OH | Lucas | Engineering and Procurement | ATSI | 955 | 955 | 860 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1107_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_107_csa.pdf | Document Posted | N/A | N/A |  | 10/22/2015 | N/A | N/A | 11/30/2022 |  |  | 11/30/2022 | 11/30/2022 |  | N | No
AB1-108 | Lackawanna 500 kV |  | PA | Lackawanna | Withdrawn | PPL | 485 | 485 | 485 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1108_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2015 | N/A | N/A |  | 5/15/2019 |  | 6/19/2019 |  |  | N | No
AB1-109 | Mountaineer | Mountaineer #1 | WV | Unknown | Under Construction | AEP | 1356 | 36 | 36 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2015 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AB1-110 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 620 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AB1-111 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 1235 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 2/4/2016 |  | 6/1/2019 |  |  | N | No
AB1-112 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | Under Construction | APS | 535 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1112_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1112_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_112_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_112_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2015 | N/A | N/A | 5/31/2021 |  |  | 5/9/2021 | 5/9/2021 |  | N | No
AB1-113 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1113_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2015 | N/A | N/A |  | 3/24/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | N | No
AB1-114 | Masury-Maysvile 69kV |  | PA | Mercer | Withdrawn | ATSI | 12.5 | 12.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1114_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 3/2/2017 | Customer Milestone Not Met | 1/27/2017 |  |  | N | No
AB1-115 | Painesville 13kV | Lake County Generating Station | OH | Lake | Withdrawn | ATSI | 3.1 | 3.1 | 2.5 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1115_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1115_wmpa.pdf | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 2/8/2017 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
AB1-116 | Egg Harbor Road 12kV |  | NJ | Atlantic | In Service | AEC | 0.8 | 0.787 | 0 | 0.79 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1116_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 2/1/2018 | Y | No
AB1-117 | Cunningham 500kV |  | VA | Fluvanna | Withdrawn | Dominion | 920 | 17.3 | 17.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 11/4/2015 | Customer Initiated Withdrawal | 4/24/2016 |  |  | N | No
AB1-118 | Trenton 13kV |  | NJ | Mercer | Withdrawn | PSEG | 0.7 | 0.735 | 0.735 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 11/2/2015 | Customer Initiated Withdrawal | 1/31/2016 |  |  | N | No
AB1-119 | Tansboro Road 12kV | Tansboro Road | NJ | Camden | In Service | AEC | 0.7 | 0.735 | 0 | 0.74 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1119_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1119_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1119_wmpa.pdf | Not Required | N/A | N/A |  | 10/28/2015 | N/A | N/A |  |  |  | 7/1/2017 | 7/1/2017 | 2/1/2018 | Y | No
AB1-120 | King of Prussia |  | PA | Montgomery | Withdrawn | PECO | 0.8 | 0.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2015 | N/A | N/A |  | 4/22/2016 | Customer Initiated Withdrawal | 3/14/2016 |  |  | Y | No
AB1-121 | Byron 345kV |  | IL | Ogle | Withdrawn | ComEd | 1927 |  |  |  | Energy | Merchant Transmission |  | DC | FTIR 989/NFTIR 938 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ab1121_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 6/30/2017 |  | 12/1/2021 |  |  | S | No
AB1-122 | Kendall-Tazewell & Dresden-Mole Creek |  | IL | Grundy | Active | ComEd | 1160 | 1150 | 1150 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1122_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  |  |  | 3/1/2022 | 3/1/2022 |  | N | No
AB1-123 | Showalter 34.5kV | Mason Dixon Solar Center Facility | MD | Washington | Suspended | APS | 18.4 | 18.4 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1123_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1123_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1123_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1123_wmpa.pdf | Not Required | N/A | N/A |  | 10/29/2015 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 |  | N | No
AB1-124 | Carroll-Monocacy 34.5kV | Legore Bridge Solar Center Facility | MD | Frederick | Suspended | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1124_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1124_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1124_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1124_wmpa.pdf | Not Required | N/A | N/A |  | 10/29/2015 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 |  | N | No
AB1-125 | Carroll-Monocacy 34.5kV | Biggs Ford Solar Facility | MD | Frederick | Suspended | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1125_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1125_wmpa.pdf |  | Withdrawn | N/A | N/A |  | 10/29/2015 | N/A | N/A |  |  |  | 3/31/2019 | 3/31/2019 |  | N | No
AB1-126 | McConnellsburg-Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1126_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 7/12/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB1-127 | St. Thomas-Guilford 34.5kV | St. Thomas Township Solar Facility | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1127_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_127_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_127_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 6/1/2020 |  |  | 6/30/2020 | 6/30/2020 |  | N | No
AB1-128 | St. Thomas-Mercersburg 34.5kV | St. Thomas Township Solar Facility II | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1128_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_128_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_128_csa.pdf | Document Posted | N/A | N/A |  | 10/29/2015 | N/A | N/A | 7/31/2020 |  |  | 6/30/2020 | 6/30/2020 |  | N | No
AB1-129 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1129_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 7/12/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB1-130 | Loretto 69kV |  | MD | Somerset | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2015 | N/A | N/A |  | 11/17/2015 | Customer Initiated Withdrawal | 6/1/2017 |  |  | N | No
AB1-131 | South Joliet |  | IL | Will | Withdrawn | ComEd | 6 | 6 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/3/2016 |  | 6/1/2016 |  |  | N | No
AB1-132 | Thelma 230kV | Gaston Green Acres Solar | NC | Northhampton | Suspended | Dominion | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1132_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1132_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_132_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 12/15/2020 |  |  | 11/15/2021 | 11/15/2021 |  | N | No
AB1-133 | Chestertown 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-134 | Wye Mills-Centreville 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-135 | Chickahominy 34.5kV | Charles City Solar | VA | Unknown | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1135_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_135_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 6/7/2017 | Customer Milestone Not Met | 11/15/2019 | 11/15/2019 |  | N | No
AB1-136 | Picway Solar 138kV |  | OH | Franklin | Withdrawn | AEP | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/17/2015 | Customer Milestone Not Met | 11/1/2016 |  |  | N | No
AB1-137 | Frankford 25kV | Millsboro Solar | DE | Sussex | Engineering and Procurement | DPL | 6 | 6 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1137_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1137_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1137_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1137_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/26/2021 |  |  | 3/26/2021 | 3/26/2021 |  | N | No
AB1-138 | Navy 34.5kV | Lakehurst Solar Farm | NJ | Ocean | In Service | JCPL | 9.6 | 9.6 | 3.6 | 9.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1138_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_138_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_138_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/24/2020 |  |  | 8/18/2020 | 8/18/2020 | 3/24/2020 | N | No
AB1-139 | Metuchen 26kV | Nixon Lane Solar | NJ | Middlesex | In Service | PSEG | 6.6 | 6.6 | 2.5 | 6.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1139_wmpa.pdf |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/1/2016 | 12/1/2016 | 5/26/2017 | N | No
AB1-140 | George Washington 138kV I |  | WV | Marshall | Withdrawn | AEP | 575 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1140_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-141 | Church-Wye Mills 138 kV I | Bluegrass Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 19.8 | 19.8 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1141_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1141_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_141_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_141_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AB1-142 | Church-Wye Mills 138 kV II | Bluegrass Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 19.8 | 19.8 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1142_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1142_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_142_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AB1-143 | George Washington 138kV II |  | WV | Marshall | Withdrawn | AEP | 585 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1143_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-144 | Shawville 230kV | Shawville Generating Station | PA | Clearfield | In Service | PENELEC | 590 | 590 | 590 | 532 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1144_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_144_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_144_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/21/2017 | 12/21/2017 | 10/24/2016 | N | No
AB1-145 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1145_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1145_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 12/23/2016 |  |  | N | No
AB1-146 | Sabrooke 12kV |  | IL | Winnebago | Withdrawn | ComEd | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/21/2017 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AB1-147 | Hoytdale 138kV |  | PA | Beaver | Withdrawn | ATSI | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1147_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/25/2016 | Customer Initiated Withdrawal | 11/1/2016 |  |  | N | No
AB1-148 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 1745 | 368 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AB1-149 | Baker 138kV |  | WV | Hardy | Withdrawn | APS | 121.6 | 121.6 | 15.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1149_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AB1-150 | Grassy Falls 138kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 50.6 | 50.6 | 6.7 | 50.6 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1150_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_150_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_150_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/30/2020 |  |  | 4/30/2020 | 4/30/2020 | 3/14/2020 | N | No
AB1-151 | Paupack 230kV |  | PA | Wayne | Withdrawn | PPL | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1151_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/29/2016 | Customer Initiated Withdrawal | 6/1/2020 |  |  | N | No
AB1-152 | Culpeper 34.5kV | Stevensburg Solar | VA | Unknown | Withdrawn | Dominion | 15 | 15 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1152_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1152_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1152_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2019 | 10/31/2019 |  | N | No
AB1-153 | Hunterstown 500kV |  | PA | Adams | Withdrawn | ME | 1061.5 | 1061.5 | 985.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1153_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/10/2016 | Customer Initiated Withdrawal | 6/1/2020 |  |  | N | No
AB1-154 | Gilbert 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1092.2 | 1092.2 | 1028 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1154_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2154_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 8/16/2018 |  | 6/1/2020 |  |  | N | No
AB1-155 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/16/2015 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-156 | Sligo 34.5kV |  | NC | Camden | Withdrawn | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1156_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/7/2016 | Customer Milestone Not Met | 10/31/2017 |  |  | N | No
AB1-157 | George Washington 138kV III |  | WV | Marshall | Withdrawn | AEP | 595 | 10 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1157_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB1-158 | Thornville 34.5kV |  | OH | Perry | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/12/2015 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-159 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 5/3/2016 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB1-160 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 90 | 20 | 3.8 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1160_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_160_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 8/22/2019 |  |  | 10/31/2019 | 10/31/2019 | 11/20/2019 | N | No
AB1-161 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 1.3 | 1.34 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1161_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/21/2016 | Customer Initiated Withdrawal | 8/31/2016 |  |  | Y | No
AB1-162 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 16.7 | 16.7 | 6.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1162_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1162_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 7/1/2019 |  | 7/1/2017 |  |  | N | No
AB1-163 | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | Engineering and Procurement | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1163_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1163_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1163_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 6/30/2018 | 6/30/2018 |  | N | No
AB1-164 | Whiteley 25kV | Whitely - Greene Battery Storage Facility | PA | Greene | Withdrawn | APS | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1164_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1164_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1164_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/14/2017 | Customer Initiated Withdrawal | 7/31/2019 | 7/31/2019 |  | N | No
AB1-165 | Tabernacle 12kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1165_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 12/24/2016 |  |  | N | No
AB1-166 | Wilson 23kV | Wilson Battery Storage | PA | Allegheny | Withdrawn | DL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1166_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1166_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1166_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2015 | N/A | N/A |  | 5/30/2019 |  | 8/31/2019 | 8/31/2019 |  | N | No
AB1-167 | South Cumberland 69kV |  | OH | Noble | Withdrawn | AEP | 50 | 50 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1167_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/30/2017 |  | 8/31/2017 |  |  | N | No
AB1-168 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 4.5 | 4.5 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1168_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1168_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 12/11/2017 |  | 3/31/2017 |  |  | N | No
AB1-169 | Stuart 345kV | Mason Energy Center | KY | Mason | Engineering and Procurement | Dayton | 1150 | 1150 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1169_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1169_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_169_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 12/1/2022 |  |  | 6/30/2023 | 6/30/2023 |  | N | No
AB1-169A | Minotola 138 kV |  | NJ | Atlantic | Active | AEC | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1169a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1169a_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AB1-170 | LaSalle-Braidwood |  | IL | Grundy | Withdrawn | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 8/4/2016 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AB1-171 | Franklin 25kV | Franklin Generation Facility | PA | Greene | Withdrawn | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1171_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1171_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1171_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 10/22/2018 |  | 10/31/2019 | 10/31/2019 |  | N | No
AB1-172 | Joliet-Wilmington |  | IL | Will | Withdrawn | ComEd | 6.4 | 6.2 | 6.2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1172_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 6/29/2018 |  | 9/1/2017 |  |  | N | No
AB1-173 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | Suspended | Dominion | 19.8 | 19.8 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1173_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1173_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_173_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB1-173A | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | Suspended | Dominion | 39.6 | 19.8 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1173a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1173a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1173a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_173a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_173a_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB1-174 | Thornville12kV | Thornville 12kV | OH | Perry | Withdrawn | AEP | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1174_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1174_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1174_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 2/7/2018 |  | 12/31/2018 | 12/31/2018 |  | N | No
AB1-175 | Homer City-Mainesburg 345kV |  | PA | Clearfield | Withdrawn | PENELEC | 1000 | 989 | 960 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/19/2015 | Customer Initiated Withdrawal | 1/1/2020 |  |  | N | No
AB1-176 | Price 25kV II |  | MD | Queen Anne's | Active | DPL | 4 | 4 | 1.51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1176_fac.pdf | Document Posted | N/A |  | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2016 |  |  | N | No
AB1-177 | Ontario 23kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1177_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 4/4/2016 | Customer Initiated Withdrawal | 4/30/2016 |  |  | N | No
AB1-178 | Pidgeon 69kV |  | OH | Columbiana | Withdrawn | ATSI | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1178_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-179 | Sabinsville-Wellsboro 34kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1179_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB1-180 | Pine View 12kV | Seven Islands Environmental Solutions, LLC | WV | Unknown | In Service | AEP | 3.2 | 3.2 | 2.4 | 3.2 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1180_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1180_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1180_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 3/7/2017 | N | No
AB1-181 | Cunningham 500kV |  | VA | Fluvanna | In Service | Dominion | 1000 | 28 | 37.3 | 28 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A |  |  |  | 2/28/2017 | 2/28/2017 | 3/7/2017 | N | No
AB1-182 | Bear Creek | Bear Creek Energy Storage Facility | PA | Luzerne | Engineering and Procurement | PPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1182_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1182_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_182_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_182_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2015 | N/A | N/A | 12/1/2022 |  |  | 12/1/2022 | 12/1/2022 |  | N | No
AB1-183 | Kennedyville-Massey 69kV |  | MD | Kent | Withdrawn | DPL | 99 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1183_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 1/20/2017 | Customer Initiated Withdrawal | 10/28/2016 |  |  | N | No
AB1-184 | Centreville 12kV II |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 1.96 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1184_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2015 | N/A | N/A |  | 3/21/2016 | Customer Initiated Withdrawal | 11/11/2016 |  |  | Y | No
AB1-185 | 4 QUAD C18 KV QC-1-981 CRES 138KV PROVIDWF |  | N/A | N/A | Withdrawn | ComEd | 2 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1185_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 10/18/2018 |  | 6/1/2016 |  |  | EE | No
AB1-186 | REDLION 34.5 KV REDLINFC-KENT 13 KV DOVER2CT |  | N/A | N/A | Withdrawn | DPL | 3 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ab1186_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2015 | N/A | N/A |  | 11/26/2018 |  | 6/1/2016 |  |  | EE | No
AB2-001 | Ringoes-US Bronze 34kV | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | 3.8 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2001_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_001_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 11/2/2015 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/31/2016 | N | No
AB2-002 4768938 | TVA-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing LLC | 148 | 148 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/6/2015 | 1/1/2018 | 1/1/2028 |  | 12/1/2015 |  |  |  |  | FF | No
AB2-003 | Halfway-N=Milnor 34.5kV | Thornton Solar Facility | MD | Washington | Withdrawn | APS | 4.4 | 4.4 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_003_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 11/9/2015 | N/A | N/A |  | 12/19/2016 | Customer Initiated Withdrawal | 12/31/2017 | 12/31/2017 |  | N | No
AB2-004 | Halfway-Milnor 34.5kV | Hagerstown Solar Facility | MD | Washington | Withdrawn | APS | 5.4 | 5.4 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_004_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_004_csa.pdf | Document Posted | N/A | N/A |  | 11/13/2015 | N/A | N/A |  | 10/23/2017 |  | 3/31/2018 | 3/31/2018 |  | N | No
AB2-005 4771489 | TVA-PJM |  | N/A | N/A | Withdrawn | NRG Power Marketing (South Central) | 148 | 148 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4771489_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4771489_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 11/20/2015 | 1/1/2019 | 1/1/2030 |  | 4/28/2017 |  |  |  |  | FF | No
AB2-006 4771490 | TVA-PJM |  | N/A | N/A | Retracted | NRG Power Marketing (South Central) | 350 | 350 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4771490_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 11/20/2015 | 1/1/2021 | 1/1/2030 |  | 2/11/2016 |  |  |  |  | FF | No
AB2-007 4772393 | NYISJK-PJM-NYISABC |  | N/A | N/A | Withdrawn | PSEG Energy Resource &amp; Trade LLC | 1000 | 1000 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4772393_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4772393_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 11/24/2015 | 5/1/2017 | 5/1/2022 |  | 5/31/2017 |  |  |  |  | FF | No
AB2-008 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 105 | 105 | 96 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2008_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2015 | N/A | N/A |  | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-009 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 116 | 116 | 105 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2009_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2015 | N/A | N/A |  | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-010 | Saltville-Holston 34.5kV - Phase I | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Suspended | AEP | 5 | 5 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2010_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2010_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2010_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2015 | N/A | N/A |  |  |  | 12/1/2017 | 12/1/2017 |  | N | No
AB2-011 | Saltville-Holstone 34.5kV - Phase II | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Suspended | AEP | 5 | 5 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2011_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2011_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2011_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2015 | N/A | N/A |  |  |  | 12/1/2017 | 12/1/2017 |  | N | No
AB2-012 | Blooming Grove to West Damascus 69 kV |  | PA | Wayne | Withdrawn | PPL | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2012_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2012_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 12/9/2015 | N/A | N/A |  | 8/3/2018 |  | 6/1/2018 |  |  | N | No
AB2-013 4776359 | AMIL-PJM |  | N/A | N/A | Withdrawn | Illinois Power Marketing Company | 150 | 150 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4776359_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4776359_lft2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 12/15/2015 | 6/1/2020 | 6/1/2025 |  | 4/11/2019 |  |  |  |  | FF | No
AB2-014 | Lakewood 230kV | Lakewood Cogeneration Plant | NJ | Ocean | Partially in Service - Under Construction | JCPL | 280 | 0 | 8.1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_014_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 12/15/2015 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 11/16/2016 | N | No
AB2-015 | Franklin 115kV | Tidewater Solar Projects | VA | Southampton | Engineering and Procurement | Dominion | 91 | 91 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2015_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_015_csa.pdf | Document Posted | N/A | N/A |  | 12/21/2015 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AB2-016 | Maddox Creek 345kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2016_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2015 | N/A | N/A |  | 3/9/2018 |  | 12/31/2019 |  |  | N | No
AB2-017 |  |  | N/A | N/A | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/4/2016 | N/A | N/A |  | 1/27/2016 | Customer Milestone Not Met |  |  |  | Y | No
AB2-018 | Bethel-Carolina 12.kkV |  | NC | Unknown | Withdrawn | Dominion | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2016 | N/A | N/A |  | 2/9/2016 |  | 12/31/2016 |  |  | N | No
AB2-019 | Erie West 345kV |  | N/A | N/A | Engineering and Procurement | PENELEC | 28 |  |  |  | Energy | Merchant Transmission |  | DC | 28 NFTWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ab2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab2019_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-isa/ab2_019_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 2/3/2016 | N/A | N/A |  |  |  | 3/31/2024 | 3/31/2024 |  | S | No
AB2-020 | Roseland-Williams 230kV |  | N/A | N/A | In Service | PSEG | 40 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 62 | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab2020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab2020_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/ab2_020_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 11/22/2017 | S | No
AB2-021 | Keeney-Rock Springs 500kV |  | MD | Unknown | In Service | Essential Power | 100 |  |  |  | Energy | Merchant Transmission |  | AC | ICTR 705 | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ab2021_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-facilities/ab2021_fac.pdf | Document Posted |  | Not Required | N/A | https://www.pjm.com/pub/planning/project-queues/merch-csa/ab2_021_csa.pdf | Document Posted | N/A | N/A |  | 2/4/2016 | N/A | N/A |  |  |  | 6/1/2018 |  | 10/31/2018 | S | No
AB2-022 | Elizabeth City 34.5kV | Elizabeth City Solar | NC | Camden | Engineering and Procurement | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2022_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2022_wmpa.pdf | Not Required | N/A | N/A |  | 2/4/2016 | N/A | N/A | 12/1/2020 |  |  | 12/30/2020 | 12/30/2020 |  | N | No
AB2-023 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2016 | N/A | N/A |  | 3/30/2016 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-024 | Correctional 34.5kV |  | VA | New Kent | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2024_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2024_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2024_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/27/2017 | N | Yes
AB2-025 | Sapony 34.5kV |  | VA | Sussex | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2025_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2025_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2025_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-026 | Powhatan 34.5kV |  | VA | Powhatan | In Service | Dominion | 20 | 20 | 13.8 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2026_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2026_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2026_wmpa.pdf | Not Required | N/A | N/A |  | 2/8/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-027 | Maple Ave-Mount Lena 34.5kV | Funkstonw Solar Facility | MD | Washington | Suspended | APS | 8.8 | 8.8 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2027_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2027_wmpa.pdf | Not Required | N/A | N/A |  | 2/10/2016 | N/A | N/A |  |  |  | 11/30/2017 | 11/30/2017 |  | N | No
AB2-028 | Fall Creek-Desoto 345kV |  | IN | Henry | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2028_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2016 | N/A | N/A |  |  |  | 10/31/2018 |  |  | N | No
AB2-029 | Remington 34.5kV |  | VA | Fauquier | In Service | Dominion | 19.8 | 19.8 | 7.6 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2029_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2029_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2029_wmpa.pdf | Not Required | N/A | N/A |  | 2/11/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 10/1/2017 | N | No
AB2-030 | Tasley 25kV |  | VA | Accomack | Withdrawn | DPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2030_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2016 | N/A | N/A |  | 10/16/2017 |  | 12/1/2016 |  |  | N | No
AB2-031 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | Suspended | Dominion | 59.6 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_031_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/11/2016 | N/A | N/A | 5/31/2021 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB2-032 | Church-Wye Mills 138 kV | Bluegrass Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2032_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2032_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_032_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_032_csa.pdf | Document Posted | N/A | N/A |  | 2/11/2016 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AB2-033 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 10 | 10 | 7.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2033_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2016 | N/A | N/A |  | 3/20/2018 |  | 5/1/2017 |  |  | N | No
AB2-035 | Bethel-Carolina 12.5kV |  | NC | Pitt | Withdrawn | Dominion | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2035_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 2/23/2016 | N/A | N/A |  | 11/30/2018 |  | 12/31/2016 |  |  | N | No
AB2-036 | Church-Steele 138kV |  | MD | Caroline | Active | DPL | 92 | 92 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2036_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2016 | N/A | N/A |  |  |  | 11/30/2018 |  |  | N | No
AB2-037 | Keeney-Steele 230kV |  | MD | Caroline | Active | DPL | 202 | 202 | 76.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2037_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2037_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2016 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No
AB2-038 | Frostburg 138kV |  | PA | Somerset | Engineering and Procurement | APS | 200 | 0 | 4.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_038_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2016 | N/A | N/A | 12/15/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB2-039 | Bakers Pond-Ivor 115kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 85 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2039_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 7/7/2017 | Customer Milestone Not Met | 12/31/2018 | 12/31/2018 |  | N | No
AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | Suspended | Dominion | 80 | 80 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2040_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2040_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_040_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2016 | N/A | N/A | 12/31/2020 |  |  | 3/31/2020 | 3/31/2020 |  | N | No
AB2-041 | Frostburg 138kV | Mason Dixon Wind Farm | PA | Somerset | Engineering and Procurement | APS | 219.4 | 19.4 | 3.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2041_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_041_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/29/2016 | N/A | N/A | 12/15/2020 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AB2-042 | Smithfield-Surry 230kV |  | VA | Isle of Wight | Withdrawn | Dominion | 160 | 160 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2042_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 10/11/2016 | Customer Milestone Not Met | 9/30/2018 |  |  | N | No
AB2-043 | Chase City 115kV | Bluestone Farm Solar | VA | Mecklenburg | Under Construction | Dominion | 49.9 | 49.9 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2043_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2043_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_043_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 2/29/2016 | N/A | N/A | 10/15/2020 |  |  | 9/1/2020 | 9/1/2020 |  | N | No
AB2-044 |  |  | VA | Middlesex | Withdrawn | PSEG | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 3/17/2016 |  | 7/1/2017 |  |  | N | No
AB2-045 | Buckingham 34.5kV |  | VA | Buckingham | In Service | Dominion | 19.8 | 19.8 | 13.5 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2045_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2045_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2045_wmpa.pdf | Not Required | N/A | N/A |  | 2/29/2016 | N/A | N/A |  |  |  | 12/31/2017 | 12/31/2017 | 11/30/2017 | N | Yes
AB2-046 | Charleroi 12kV |  | OH | Washington | Withdrawn | APS | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/29/2016 | N/A | N/A |  | 6/27/2016 | Customer Initiated Withdrawal | 12/1/2016 |  |  | Y | No
AB2-047 | Brokaw-Pontiac Midpoint | Blooming Grove WF | IL | McLean | Engineering and Procurement | ComEd | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2047_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_047_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2016 | N/A | N/A | 12/1/2020 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AB2-048 | Grandin 12kV | Clinton Energy Storage System | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2048_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2048_wmpa.pdf | Not Required | N/A | N/A |  | 3/3/2016 | N/A | N/A |  | 7/31/2018 |  | 6/30/2019 | 6/30/2019 |  | Y | No
AB2-049 | Gloucester Township 12kV |  | NJ | Camden | Active | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2049_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2049_fac.pdf | Document Posted | N/A |  | N/A |  | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A |  |  |  | 12/1/2017 |  |  | N | No
AB2-050 | Four Rivers 230kV | Doswell Complex 5 & 6 | VA | Hanover | In Service | Dominion | 746 | 20 | 20 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/4/2016 | N/A | N/A |  |  |  | 3/1/2020 | 3/1/2020 | 2/28/2018 | N | No
AB2-051 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 840 | 840 | 765.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2051_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2051_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/14/2016 | N/A | N/A |  | 10/3/2018 |  | 1/1/2021 |  |  | N | No
AB2-052 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-053 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2053_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-054 | JK Smith 345kV |  | KY | Clark | Withdrawn | EKPC | 614 | 614 | 504 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2054_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 5/8/2017 | Customer Initiated Withdrawal | 3/1/2023 |  |  | N | No
AB2-055 | Bayonne 345kV |  | NJ | Hudson | Withdrawn | PSEG | 1041.4 | 1041.4 | 1041.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2055_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2016 | N/A | N/A |  | 9/20/2019 |  | 6/1/2021 |  |  | N | No
AB2-056 | Colora 34.5kV |  | MD | Cecil | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2056_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2016 | N/A | N/A |  | 5/24/2017 | Customer Initiated Withdrawal | 10/1/2018 |  |  | N | No
AB2-057 | Brunswick 26kV | New Road Solar | NJ | Middlesex | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2057_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2057_wmpa.pdf | Not Required | N/A | N/A |  | 3/24/2016 | N/A | N/A |  |  |  | 3/30/2018 | 3/30/2018 | 6/22/2018 | N | No
AB2-058 | Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 10 | 3.6 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2058_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_058_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/25/2016 | N/A | N/A |  |  |  | 12/31/2016 | 12/31/2016 | 12/6/2016 | N | No
AB2-059 | Benson-Dunbar 115kV | Moccasin Creek Solar | NC | Edgecombe | Under Construction | Dominion | 100 | 100 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2059_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_059_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 6/30/2020 |  |  | 6/15/2020 | 6/15/2020 |  | N | No
AB2-060 | Chase City-Lunenburg 115kV | Chase City Solar | VA | Mecklenburg | Under Construction | Dominion | 80 | 80 | 54.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_060_csa.pdf | Document Posted | N/A | N/A |  | 3/25/2016 | N/A | N/A | 5/15/2020 |  |  | 5/15/2020 | 5/15/2020 |  | N | No
AB2-061 | Meadow Road 13kV | Meadow Road Solar | NJ | Middlesex | Withdrawn | PSEG | 2.5 | 2.5 | 0.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2061_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2061_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2061_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2016 | N/A | N/A |  | 5/12/2017 | Customer Initiated Withdrawal | 6/30/2018 | 6/30/2018 |  | N | No
AB2-062 | Unionville 115kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2062_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2062_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 8/24/2018 |  | 2/1/2018 |  |  | N | No
AB2-063 | Price 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2063_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2063_fac.pdf | Document Posted |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 7/1/2019 |  | 12/31/2018 |  |  | N | No
AB2-064 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 40 | 40 | 15.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2064_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 9/22/2016 |  | 12/31/2018 |  |  | N | No
AB2-065 | Madison-Tanners Creek 138kV |  | IN | Rush | Withdrawn | AEP | 124.2 | 124.2 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2065_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2016 | N/A | N/A |  | 2/27/2018 |  | 12/31/2019 |  |  | N | No
AB2-066 | Crawfords Corner 23kV |  | NJ | Monmouth | Withdrawn | JCPL | 4.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2066_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Milestone Not Met | 7/31/2016 |  |  | N | No
AB2-067 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | Under Construction | AEP | 1100 | 1100 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2067_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_067_csa.pdf | Document Posted | N/A | N/A | 5/8/2021 | 3/31/2016 | N/A | N/A | 3/24/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AB2-068 | Chickahominy 500kV | C4GT | VA | Charles City | Engineering and Procurement | Dominion | 1060 | 1060 | 1060 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_068_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2016 | N/A | N/A | 5/1/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AB2-069 | Chase City-Kerr Dam 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49 | 49 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 10/11/2016 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-070 | Brokaw-Lanesville |  | IL | DeWitt | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2070_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AB2-071 | Hunterstown-Lincoln 115kV |  | PA | Adams | Withdrawn | ME | 100 | 100 | 68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2071_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 5/31/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-072 | Arnold's Corner 34.5kV |  | VA | King George | Withdrawn | Dominion | 18 | 18 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2072_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/31/2016 | N/A | N/A |  | 1/29/2019 |  | 9/15/2017 |  |  | N | No
AB2-073 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2016 | N/A | N/A |  | 5/27/2016 | Customer Milestone Not Met | 10/31/2016 |  |  | N | No
AB2-074 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 1143 | 113 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2074_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/1/2016 | N/A | N/A |  | 5/4/2020 |  | 9/2/2019 |  |  | N | No
AB2-075 4796024 | DUK-PJM |  | N/A | N/A | Retracted | Brookfield Energy Marketing LP | 42 | 42 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4796024_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4796024_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/5/2016 | 6/1/2020 | 6/1/2025 |  | 5/2/2017 |  |  |  |  | FF | No
AB2-076 4796025 | DUK-PJM |  | N/A | N/A | Retracted | Brookfield Energy Marketing LP | 51 | 51 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4796025_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4796025_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 4/5/2016 | 6/1/2020 | 6/1/2025 |  | 5/2/2017 |  |  |  |  | FF | No
AB2-077 | Buggs Island-Chase City 115kV | Otter Creek Solar Project | VA | Mecklenburg | Suspended | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2077_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2077_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_077_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_077_csa.pdf | Document Posted | N/A | N/A |  | 4/11/2016 | N/A | N/A | 4/1/2021 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AB2-078 | Buggs Island-Chase City 115kV | Otter Creek Solar Project | VA | Mecklenburg | Suspended | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2078_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2078_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_078_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_078_csa.pdf | Document Posted | N/A | N/A |  | 4/11/2016 | N/A | N/A | 4/1/2021 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AB2-079 | Buggs Island-Chase City 115kV | Otter Creek Solar Project | VA | Mecklenburg | Suspended | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_079_csa.pdf | Document Posted | N/A | N/A |  | 4/11/2016 | N/A | N/A | 4/1/2021 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AB2-080 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1200 | 1200 | 1200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/12/2016 | N/A | N/A |  | 10/4/2016 | Customer Milestone Not Met | 6/1/2021 |  |  | N | No
AB2-081 | Sligo 34.5kV |  | NJ | Camden | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/13/2016 | N/A | N/A |  | 5/3/2016 |  | 10/31/2017 |  |  | N | No
AB2-082 | Metuchen 230kv |  | NJ | Middlesex | Withdrawn | PSEG | 675 | 675 | 671 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2082_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2016 | N/A | N/A |  | 4/30/2019 |  | 6/1/2019 |  |  | N | No
AB2-083 | Delano 138kV |  | OH | Ross | Active | AEP | 40 | 40 | 27.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2083_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/14/2016 | N/A | N/A |  |  |  | 10/31/2017 |  |  | N | No
AB2-084 | Costen 25kV | Costen Solar Energy Center | MD | Somerset | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2084_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2084_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2084_wmpa.pdf | Not Required | N/A | N/A |  | 4/15/2016 | N/A | N/A |  | 2/1/2019 |  | 10/20/2019 | 10/20/2019 |  | N | No
AB2-085 | Adams 138kV |  | OH | Adams | Active | AEP | 80 | 80 | 54.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2085_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2016 | N/A | N/A |  |  |  | 10/31/2017 |  |  | N | No
AB2-086 | Grassfield 13.2kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2016 | N/A | N/A |  | 5/5/2016 | Customer Milestone Not Met | 10/31/2017 |  |  | N | No
AB2-087 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2016 | N/A | N/A |  | 11/27/2017 | Customer Initiated Withdrawal | 12/31/2016 |  |  | N | No
AB2-088 | Tarboro 12.5kV |  | NC | Edgecombe | Withdrawn | Dominion | 4 | 4 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2088_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/22/2016 | N/A | N/A |  | 11/30/2018 |  | 12/31/2016 |  |  | N | No
AB2-089 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_089_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_089_csa.pdf | Document Posted | N/A | N/A |  | 4/25/2016 | N/A | N/A |  | 7/24/2019 |  | 6/1/2017 |  |  | N | No
AB2-090 | Chase City 34.5kV |  | VA | Mecklenburg | Withdrawn | Dominion | 36 | 36 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2090_imp.pdf | Interim Study | https://www.pjm.com/pub/planning/project-queues/facilities/ab2090_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/25/2016 | N/A | N/A |  | 8/31/2018 |  | 6/12/2018 | 6/12/2018 |  | N | No
AB2-091 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 105 | 105 | 100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2091_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 4/21/2017 | Customer Initiated Withdrawal | 5/31/2020 |  |  | N | No
AB2-092 | Bergen 138kV | Bergen Generating Station | NJ | Bergen | Engineering and Procurement | PSEG | 1371.1 | 51.1 | 51.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_092_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2016 | N/A | N/A | 12/31/2025 |  |  | 12/5/2019 | 12/5/2019 |  | N | No
AB2-093 | Ormet 138kV | Hannibal Port Power Project | OH | Monroe | Under Construction | AEP | 485 | 485 | 485 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_093_csa.pdf | Document Posted | N/A | N/A |  | 4/26/2016 | N/A | N/A |  |  |  | 9/13/2021 | 9/13/2021 |  | N | No
AB2-094 | Warren Glen Switch Point 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/Combined with Feaas | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 11/23/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AB2-095 | Ocean Pines-Walston Switch 69kV |  | MD | Wicomico | Withdrawn | DPL | 30 | 30 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2095_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/26/2016 | N/A | N/A |  | 10/12/2016 | Customer Initiated Withdrawal | 10/31/2018 |  |  | N | No
AB2-096 | Silver Lake-Cherry Valley |  | IL | Boone | Active | ComEd | 450 | 350 | 350 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2096_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2016 | N/A | N/A |  |  |  | 6/1/2018 |  |  | N | No
AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | Under Construction | APS | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2097_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/27/2016 | N/A | N/A | 8/15/2020 |  |  | 2/28/2020 | 2/28/2020 |  | N | No
AB2-098 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2098_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2016 | N/A | N/A |  | 9/18/2019 |  | 12/30/2016 |  |  | N | No
AB2-099 | Ahoskie 34.5kV | Colice Hall Solar | NC | Hertford | Suspended | Dominion | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_099_csa.pdf | Document Posted | N/A | N/A | 5/1/2020 | 4/27/2016 | N/A | N/A | 6/1/2020 |  |  | 3/31/2020 | 3/31/2020 |  | N | No
AB2-100 | Clubhouse-Lakeview 230kV | Sadler Solar | VA | Greensville | Under Construction | Dominion | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2100_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_100_csa.pdf | Document Posted | N/A | N/A |  | 4/27/2016 | N/A | N/A | 11/1/2020 |  |  | 12/1/2021 | 12/1/2021 |  | N | No
AB2-101 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 626 | 31 | 31 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2101_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2016 | N/A | N/A |  | 5/16/2017 | Customer Initiated Withdrawal | 4/1/2019 |  |  | N | No
AB2-102 | Cumberland 230kV |  | NJ | Cumberland | Active | AEC | 230 | 230 | 225 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AB2-103 | Seaman 138kV |  | OH | Adams | Withdrawn | AEP | 40 | 40 | 27.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/26/2018 |  | 10/31/2017 |  |  | N | No
AB2-104 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I, LLC | WV | Brooke | Engineering and Procurement | APS | 750 | 65 | 65 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2104_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_104_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_104_csa.pdf | Document Posted | N/A | N/A |  | 4/28/2016 | N/A | N/A | 12/31/2021 |  |  | 8/3/2021 | 8/3/2021 |  | N | No
AB2-105 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2105_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 10/12/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-106 | Pierson Avenue 480V |  | NJ | Middlesex | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-107 | Burlington 480V |  | NJ | Burlington | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/30/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-108 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-109 | Reusens 34.5kV | Reusens Hydro Electric Generating Plant | VA | City of Lynchburg | In Service | AEP | 12.5 | 12.5 | 4 | 12.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 3/31/2018 | 3/31/2018 | 11/29/2017 | N | No
AB2-110 | Englishtown-Millhurst 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 11.1 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2110_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 4/19/2017 |  |  | N | No
AB2-111 | Millhurst-Rt 33 Switch Point 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 11.1 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2111_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 3/27/2017 | Customer Initiated Withdrawal | 4/20/2017 |  |  | N | No
AB2-112 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 485 | 35 | 35 | 35 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2112_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_112_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 2/7/2019 | N | No
AB2-113 | Cecil County 1 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2113_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-114 | Cecil County 2 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2114_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-115 | Cecil County 3 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2115_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/21/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-116 | Cecil County 4 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2116_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-117 | Cecil County 5 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2117_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-118 | Cecil County 6 |  | MD | Cecil | Withdrawn | DPL | 2 | 2 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2118_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017 |  |  | N | No
AB2-119 | Middle Township 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.5 | 1.5 | 0.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2119_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 5/24/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AB2-120 | Piney Grove-New Church 138kV |  | MD | Worcester | Active | DPL | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2120_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 12/14/2018 |  |  | N | No
AB2-121 | Burlington 26kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2121_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 2/14/2017 | Customer Milestone Not Met | 12/1/2017 |  |  | N | No
AB2-122 | Egg Harbor 12kV | Winzinger Egg Harbor Solar Project | NJ | Atlantic | Engineering and Procurement | AEC | 1.9 | 1.9 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2122_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2122_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2122_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2122_wmpa.pdf | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  |  |  | 9/4/2021 | 9/4/2021 |  | N | No
AB2-123 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2123_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-124 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-125 | Marriott Hill 34kV |  | MD | Anne Arundel | Withdrawn | BGE | 3.3 | 3.3 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-126 | Finksburg 34kV |  | MD | Baltimore County | Withdrawn | BGE | 3.8 | 3.8 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2126_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 12/31/2017 | 12/31/2017 |  | N | No
AB2-127 | Gilbert 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16 | 16 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2127_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 12/2/2016 | Customer Initiated Withdrawal | 6/29/2018 |  |  | N | No
AB2-128 | Clubhouse-Lakeview 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 57.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2128_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/17/2017 | Customer Initiated Withdrawal | 10/31/2017 |  |  | N | No
AB2-129 | Doubs 230kV | Potomac Solar, LLC | MD | Frederick | Suspended | APS | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2129_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2129_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_129_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_129_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 4/30/2020 | 4/30/2020 |  | N | No
AB2-130 | Laurel 69kV |  | DE | Sussex | Active | DPL | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2130_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB2-131 | Galion-Roberts South 138kV |  | OH | Marion | Active | ATSI | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2131_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AB2-132 | Haumesser Road |  | IL | Lee | Active | ComEd | 240 | 2.5 | 2.2 |  | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2132_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 12/15/2016 |  |  | N | No
AB2-133 | Chestertown-Church 69kV |  | MD | Kent | Active | DPL | 55.8 | 55.8 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 |  | N | No
AB2-134 | Hopewell-Surry 230kV | Colonial Trail West Solar | VA | Surry | In Service | Dominion | 142.4 | 142.4 | 71.8 | 142.4 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2134_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_134_csa.pdf | Document Posted | N/A | N/A | 10/3/2019 | 4/29/2016 | N/A | N/A | 11/7/2019 |  |  | 12/1/2019 | 12/1/2019 | 11/7/2019 | N | No
AB2-135 | Church-Kent 69kV |  | MD | Queen Anne's | Active | DPL | 64 | 64 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2135_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 5/1/2018 |  |  | N | No
AB2-136 | West Cambridge-Vienna 69kV |  | MD | Dorchester | Active | DPL | 51.1 | 51.1 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2136_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 5/1/2018 |  |  | N | No
AB2-137 | St. Clair 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 4 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/30/2016 | Customer Initiated Withdrawal | 11/1/2017 |  |  | N | No
AB2-138 | Clybourn 12.5kV |  | IL | Cook | Withdrawn | ComEd | 0.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met |  |  |  | Y | No
AB2-139 | Raceway Mall 34.5kV | Freemall Fuel Cell Facility | NJ | Monmouth | In Service | JCPL | 0.4 | 0.42 | 0 | 0.42 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2139_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2139_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/30/2017 | 6/30/2017 | 2/1/2018 | Y | No
AB2-140 | Rock Ridge 13kV |  | MD | Harford | Withdrawn | BGE | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2140_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/27/2017 | Customer Initiated Withdrawal | 10/31/2017 | 10/31/2017 |  | N | No
AB2-141 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 394 | 394 | 388.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2141_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/27/2019 |  | 4/1/2019 |  |  | N | No
AB2-142 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 13.4 | 13.4 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2142_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/24/2017 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-143 | Lynch 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2143_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 10/14/2016 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AB2-144 | Emmitsburg–Taneytown 2 34.5 kV |  | VA | Frederick | Withdrawn | APS | 13.8 | 13.8 | 5.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2144_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 11/9/2016 | Customer Milestone Not Met | 3/1/2017 |  |  | N | No
AB2-145 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 572 | 572 | 572 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2145_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/23/2018 |  | 1/1/2021 |  |  | N | No
AB2-146 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 382 | 382 | 382 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 10/3/2016 | Customer Initiated Withdrawal | 1/1/2021 |  |  | N | No
AB2-147 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 40 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-148 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 19.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/18/2016 | Customer Milestone Not Met | 10/30/2017 |  |  | N | No
AB2-149 | Myrtle-Windsor 115kV |  | VA | Isle of Wight | Withdrawn | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2149_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/21/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-150 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 40 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2150_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017 |  |  | N | No
AB2-151 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 19.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/18/2016 | Customer Milestone Not Met | 10/30/2017 |  |  | N | No
AB2-152 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 57.6 | 54 | 54 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2152_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/1/2017 | Customer Initiated Withdrawal | 6/30/2019 |  |  | N | No
AB2-153 | Church-Wye Mills 138 kV | Bluegrass Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2153_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2153_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_153_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_153_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AB2-154 | Kendall 345kV |  | IL | Kendall | Withdrawn | ComEd | 1283 | 65 | 65 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2154_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/27/2016 | Customer Initiated Withdrawal | 5/1/2017 |  |  | N | No
AB2-155 | Richland-Stryker |  | OH | Defiance | Withdrawn | ATSI | 379 | 25 | 25 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 11/4/2016 | Customer Milestone Not Met | 6/1/2017 |  |  | N | No
AB2-156 | W.H. Zimmer 345kV |  | OH | Clermont | Withdrawn | DEOK | 1350 | 50 | 50 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2156_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 6/1/2016 |  |  | N | No
AB2-157 | Prince George's County 12kV | Rollins Avenue Phoenix | MD | Prince George's | In Service | PEPCO | 2.5 | 2.5 | 0.8 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2157_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2157_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2157_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2157_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/19/2019 |  |  | 7/12/2019 | 7/12/2019 | 12/23/2019 | N | No
AB2-158 | Louisa-South Anna 230kV | Belcher Solar | VA | Louisa | Under Construction | Dominion | 88.2 | 88.2 | 61 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2158_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_158_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/1/2020 |  |  | 12/1/2020 | 12/1/2020 |  | N | No
AB2-159 | Lumberton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 8.1 | 1.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/11/2017 |  | 10/3/2016 |  |  | N | No
AB2-160 | Reams 115kV | Reams Solar | VA | Dinwiddie | Suspended | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2160_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_160_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_160_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/31/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AB2-161 | Waverly #2 DP 115kV | Waverly Solar | VA | Sussex | Suspended | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2161_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2161_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_161_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/31/2021 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB2-162 | Camden 480V |  | NJ | Camden | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Not Required |  | Not Required |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/30/2016 | Customer Milestone Not Met | 12/31/2016 |  |  | Y | No
AB2-163 | Sicklerville 12kV |  | NJ | Camden | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016 |  |  | Y | No
AB2-164 | Wattsville-Wallops Island 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2164_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AB2-165 | Tasley-Oak Hall 69kV I |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2165_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AB2-166 | Edgewood 12kV | Aydelotte Solar Project | MD | Wicomico | Withdrawn | DPL | 5.5 | 5.5 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2166_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2166_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2166_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 1/10/2019 |  | 3/31/2019 | 3/31/2019 |  | N | No
AB2-167 | Stockton 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 14 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2167_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 8/11/2017 | Customer Initiated Withdrawal | 11/1/2017 |  |  | N | No
AB2-168 | Perch 34.5kV | Crouse Solar Project | MD | Cecil | Withdrawn | DPL | 9 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2168_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2168_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2168_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2168_wmpa.pdf | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 3/9/2020 |  | 9/6/2022 | 9/6/2022 |  | N | No
AB2-169 | Pantago-Five Points 115kV | Wilkinson Solar Energy Center | NC | Hyde | Partially in Service - Under Construction | Dominion | 74 | 74 | 39 | 35 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2169_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2169_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_169_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_169_csa.pdf | Document Posted | N/A | N/A | 10/10/2019 | 4/29/2016 | N/A | N/A | 11/18/2019 |  |  | 6/30/2021 | 6/30/2021 | 11/20/2019 | N | No
AB2-170 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | Engineering and Procurement | AEP | 150 | 130 | 49.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2170_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2170_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_170_csa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_170_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AB2-171 | Handsome 115kV |  | VA | Southampton | Withdrawn | Dominion | 75 | 75 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2171_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AB2-172 | Todd 69kV |  | MD | Dorchester | Active | DPL | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2172_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AB2-173 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 206 | 16 | 28 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2173_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/24/2019 |  | 6/1/2018 |  |  | N | No
AB2-174 | Emporia-Trego 115kV | Greensville County Solar Project | VA | Greensville | Under Construction | Dominion | 80 | 80 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2174_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2174_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_174_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 12/1/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AB2-175 | Peach Bottom 500kV | Peach Bottom Units #2 & #3 | PA | York | Partially in Service - Under Construction | PECO | 2709.8 | 44 | 44 | 44 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2175_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_175_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 3/26/2019 | N | No
AB2-176 | Chase City 34.5kV |  | NC | Mecklenburg | Withdrawn | Dominion | 14 | 14 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2176_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 7/23/2018 |  | 6/1/2017 |  |  | N | No
AB2-177 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 6.6 | 6.6 | 2.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2177_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/9/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AB2-178 | Beckjord 138kV | 138kV Bus 5 Beckjord Battery | OH | Clermont | Withdrawn | DEOK | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2178_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_178_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_178_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 12/10/2019 |  | 11/30/2018 | 11/30/2018 |  | N | No
AB2-179 | Townsend 138kV | New Castle Solar | DE | New Castle | Engineering and Procurement | DPL | 50 | 50 | 37.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2179_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2179_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_179_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 12/16/2022 | 12/16/2022 |  | N | No
AB2-180 | Rockawalkin 69kV |  | MD | Wicomico | Active | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2180_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/30/2017 |  |  | N | No
AB2-181 | Catoctin 138kV |  | VA | Frederick | Withdrawn | APS | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 6/2/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-182 | Townsend 25kV |  | MD | Cecil | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-183 | Massey 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-184 | Monkton |  | MD | Baltimore County | Withdrawn | BGE | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/19/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-185 | Wye Mills 25kV |  | MD | Queen Anne's | Active | DPL | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 6/30/2017 |  |  | N | No
AB2-186 | South Hertford 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 5 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2186_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 1/28/2019 |  | 6/30/2017 |  |  | N | No
AB2-187 | Indian River-Nelson 138kV |  | VA | Sussex | Withdrawn | DPL | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-188 | Creswell 34.5kV |  | NC | Washington | Withdrawn | Dominion | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2188_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 2/20/2019 |  | 6/30/2017 |  |  | N | No
AB2-189 | Mackeys 230kV |  | WI | Washington | Withdrawn | Dominion | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 5/20/2016 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AB2-190 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Engineering and Procurement | Dominion | 160 | 160 | 112 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2190_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2190_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_190_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 5/15/2021 |  | Customer Milestone Not Met | 5/15/2021 | 5/15/2021 |  | N | No
AB2-191 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 70.4 | 20 | 8.4 | 20 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ab2_191_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A |  |  |  | 3/1/2019 | 3/1/2019 | 2/11/2019 | N | No
AB2-192 | Tasley-Oak Hall 69kV II |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2192_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2016 | N/A | N/A |  | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018 |  |  | N | No
AC1-001 | Delano 138kV |  | OH | Ross | Active | AEP | 80 | 80 | 54.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1001_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/5/2016 | N/A | N/A |  |  |  | 10/31/2017 |  |  | N | No
AC1-002 4804066 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing, LLC | 550 | 550 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4804066_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4804066_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 5/5/2016 | 6/1/2017 | 6/1/2022 |  | 10/24/2017 |  |  |  |  | FF | No
AC1-003 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Engineering and Procurement | APS | 830 | 80 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1003_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_003_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 5/9/2016 | N/A | N/A | 12/31/2021 |  |  | 8/3/2021 | 8/3/2021 |  | N | No
AC1-004 4804766 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4804766_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 5/10/2016 | 6/1/2017 | 6/1/2022 |  | 8/5/2016 |  |  |  |  | FF | No
AC1-005 | Zion-Stateline |  | IL | Cook | Withdrawn | ComEd | 1000 |  |  |  | Energy | Merchant Transmission |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2016 | N/A | N/A |  | 6/6/2016 |  | 12/31/2021 |  |  | S | No
AC1-006 | Aydlett 34.5kV |  | NC | Currituck | Withdrawn | Dominion | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2016 | N/A | N/A |  | 9/21/2016 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AC1-007 | Crittenden 34.5kV |  | VA | Isle of Wight | Withdrawn | Dominion | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1007_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2016 | N/A | N/A |  | 4/11/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | N | No
AC1-008 | Calvert Cliffs 500kV |  | MD | Calvert | Active | BGE | 1799.3 | 6.3 | 19.2 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1008_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/9/2016 | N/A | N/A |  |  |  | 3/8/2017 |  |  | N | No
AC1-009 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1009_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2016 | N/A | N/A |  | 3/29/2018 |  | 3/31/2019 |  |  | N | No
AC1-010 | Gloucester 26kV | National Park NJ | NJ | Gloucester | Suspended | PSEG | 6 | 6 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_010_csa.pdf | Document Posted | N/A | N/A |  | 6/20/2016 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 |  | N | No
AC1-011 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2016 | N/A | N/A |  | 4/21/2017 | Customer Milestone Not Met | 1/5/2018 |  |  | N | Yes
AC1-012 | Rupert 34.5kV | Tri-State Solar | WV | Greenbrier | Withdrawn | AEP | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1012_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1012_wmpa.pdf | Not Required | N/A | N/A |  | 6/23/2016 | N/A | N/A |  | 7/30/2018 |  | 10/31/2017 | 10/31/2017 |  | Y | No
AC1-013 | Clybourn 12.5kV | Western Avenue Battery | IL | Cook | Withdrawn | ComEd | 0.1 | 0.1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1013_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1013_wmpa.pdf | Not Required | N/A | N/A |  | 6/28/2016 | N/A | N/A |  | 5/7/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-014 | Farmingdale-Bennett I 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1014_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/8/2016 | N/A | N/A |  | 7/10/2017 | Customer Milestone Not Met | 5/30/2018 |  |  | N | Yes
AC1-015 | Farmingdale-Bennett II 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 0.4 | 0.4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1015_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/8/2016 | N/A | N/A |  | 7/10/2017 | Customer Milestone Not Met | 9/1/2017 |  |  | N | Yes
AC1-016 | Burlington 26 kV | Burlington 26 kV Solar | NJ | Burlington | Engineering and Procurement | PSEG | 8.8 | 8.8 | 3.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1016_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1016_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1016_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A | 3/31/2021 |  |  | 3/31/2021 | 3/31/2021 |  | N | No
AC1-017 | Levittown 13 kV | Levittown 13 kV Solar | NJ | Burlington | Under Construction | PSEG | 3.7 | 3.7 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1017_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1017_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1017_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A | 4/17/2020 |  |  | 3/31/2020 | 3/31/2020 |  | N | No
AC1-018 | Morris Park 12.47kV | Strykers Road Solar Farm | NJ | Warren | Suspended | JCPL | 1.4 | 1.4 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_018_csa.pdf | Document Posted | N/A | N/A |  | 7/13/2016 | N/A | N/A |  |  |  | 7/1/2019 | 7/1/2019 |  | N | Yes
AC1-019 | Lake Nelson 13 kV | Lake Nelson 13 kV Solar | NJ | Middlesex | Withdrawn | PSEG | 0.9 | 0.9 | 0.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1019_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1019_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1019_wmpa.pdf | Not Required | N/A | N/A |  | 7/13/2016 | N/A | N/A |  | 1/22/2018 |  | 11/30/2018 | 11/30/2018 |  | N | No
AC1-020 | Kittatinny-Newton 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 12.2 | 12.2 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1020_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 7/13/2016 | N/A | N/A |  | 5/31/2017 | Customer Milestone Not Met | 9/1/2016 |  |  | N | Yes
AC1-021 | Yukon Hatfield 500kV | Smithton Generation Station | PA | Westmoreland | In Service | APS | 1050 | 110 | 0 | 110 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1021_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_021_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/14/2016 | N/A | N/A |  |  |  | 3/1/2019 |  | 11/18/2018 | N | No
AC1-022 | N. Vienna 138kV |  | OH | Brown | Withdrawn | DEOK | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 8/3/2016 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC1-023 | Southwest Lima-East Lima 345kV |  | OH | Allen | Withdrawn | AEP | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 8/2/2016 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC1-024 | Frazeysburg 138kV |  | OH | Muskingum | Withdrawn | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2016 | N/A | N/A |  | 4/21/2017 | Customer Milestone Not Met | 12/1/2018 |  |  | N | No
AC1-025 | Dale Summit | State College Pumping Station Battery | PA | Centre | In Service | APS | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1025_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1025_wmpa.pdf | Not Required | N/A | N/A |  | 7/18/2016 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 | 2/14/2019 | Y | Yes
AC1-026 | Sayreville |  | N/A | N/A | Withdrawn | JCPL | 1.3 | 1.3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/18/2016 | N/A | N/A |  | 8/9/2016 |  |  |  |  | Y | No
AC1-027 | Pendleton 34.5kV | Oceana Solar Facility | VA | City of Virginia Beach | In Service | Dominion | 17.6 | 17.6 | 11.2 | 17.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1027_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1027_wmpa.pdf | Not Required | N/A | N/A |  | 7/26/2016 | N/A | N/A |  |  |  | 1/1/2018 | 1/1/2018 | 12/1/2017 | N | No
AC1-028 | North Salisbury 25kV |  | MD | Wicomico | Withdrawn | DPL | 3.8 | 3.8 | 3.8 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1028_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2016 | N/A | N/A |  | 4/5/2017 | Customer Initiated Withdrawal | 6/30/2017 |  |  | N | No
AC1-029 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 480 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1029_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_029_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/29/2016 | N/A | N/A |  | 11/27/2019 |  | 5/16/2019 | 5/16/2019 |  | N | No
AC1-030 | Cinnaminson 13kV | Pennsauken Solar 3 | NJ | Camden | In Service | PSEG | 2.5 | 2.5 | 0.95 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1030_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1030_wmpa.pdf | Not Required | N/A | N/A |  | 8/1/2016 | N/A | N/A |  |  |  | 12/29/2017 | 12/29/2017 | 12/13/2017 | N | Yes
AC1-031 | Hampstead 13 kV |  | MD | Carroll | Withdrawn | BGE | 2 | 2 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1031_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/1/2016 | N/A | N/A |  | 8/1/2017 | Customer Milestone Not Met | 6/30/2017 |  |  | N | No
AC1-032 | Wilmington |  | IL | Will | Withdrawn | ComEd | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2016 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 6/30/2017 |  |  | Y | No
AC1-033 | Kewanee |  | IL | Henry | Active | ComEd | 100.8 | 100.8 | 13.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1033_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2016 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC1-034 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 75 | 42.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1034_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2016 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AC1-035 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | PENELEC | 750 | 30 | 30 | 30 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_035_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_035_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2016 | N/A | N/A |  |  |  | 5/31/2018 | 5/31/2018 | 3/30/2018 | N | No
AC1-036 | Twittys Creek 34.5kV | Twittys Creek Solar | VA | Charlotte | Engineering and Procurement | Dominion | 13.8 | 13.75 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1036_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1036_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1036_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2016 | N/A | N/A |  |  |  | 7/31/2020 | 7/31/2020 |  | N | No
AC1-037 | Doremus 13kV | Hillside Battery | NJ | Union | Withdrawn | PSEG | 0.5 | 0.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1037_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1037_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2016 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 12/29/2017 | 12/29/2017 |  | N | No
AC1-038 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 293 | 13 | 13 | 13 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1038_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_038_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/30/2016 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC1-039 | Catoctin 34kV | Catoctin Furnace Solar Facility | MD | Frederick | Suspended | APS | 20 | 20 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1039_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_039_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 10/31/2018 | 10/31/2018 |  | N | No
AC1-040 | Rockport-Duff-Coleman 345 kV |  | IN | Spencer | Withdrawn | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1040_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 11/7/2018 |  | 12/31/2020 |  |  | N | No
AC1-041 | Mt. Olive 12kV |  | MD | Worcester | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1041_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 6/5/2018 |  | 5/1/2018 |  |  | N | No
AC1-042 | Altavista-Mt. Airy 69kV | Sycamore Solar I | VA | Pittsylvania | Engineering and Procurement | Dominion | 42 | 42 | 15.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1042_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_042_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_042_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 12/1/2022 | 12/1/2022 |  | N | No
AC1-043 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Suspended | Dominion | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1043_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1043_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_043_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 10/30/2021 | 10/30/2021 |  | N | No
AC1-044 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | Under Construction | AEP | 1650 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_044_csa.pdf | Document Posted | N/A | N/A | 5/8/2021 | 8/31/2016 | N/A | N/A | 3/24/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AC1-045 | King's Fork 34.5kV | TWE Myrtle Solar | VA | City of Suffolk | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1045_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1045_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 6/22/2018 |  | 11/15/2018 | 11/15/2018 |  | N | No
AC1-046 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Withdrawn | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1046_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1046_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 10/20/2017 |  | 11/15/2018 | 11/15/2018 |  | N | No
AC1-047 | Hickory 34.5kV | TWE Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1047_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1047_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1047_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 10/20/2017 |  | 11/15/2018 | 11/15/2018 |  | N | Yes
AC1-048 | Germantown 115kV | Brookview Solar I | PA | Adams | Suspended | ME | 35 | 35 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_048_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC1-049 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1049_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 12/6/2018 |  | 5/1/2018 |  |  | N | No
AC1-050 | Mardela 12kV | Mardela Springs | MD | Wicomico | Withdrawn | DPL | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1050_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1050_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1050_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 8/27/2018 |  | 5/1/2018 |  |  | N | No
AC1-051 | Willard-S. Greenwich 69kV |  | OH | Huron | Active | AEP | 60 | 60 | 7.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1051_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ac1_051_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 12/31/2017 |  |  | N | No
AC1-052 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 9 | 9 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1052_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  | 3/20/2018 |  | 5/1/2017 |  |  | N | No
AC1-053 | Lanesville-Brokaw |  | IL | Logan | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1053_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2016 | N/A | N/A |  |  |  | 12/1/2018 |  |  | N | No
AC1-054 | Kerr Dam–Eatons Ferry 115 kV | Hawtree Creek | NC | Warren | Engineering and Procurement | Dominion | 65 | 65 | 44.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1054_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1054_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_054_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_054_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2016 | N/A | N/A | 5/15/2021 |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AC1-055 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Suspended | APS | 580 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1055_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_055_csa.pdf | Document Posted | N/A | N/A |  | 9/9/2016 | N/A | N/A | 7/30/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-056 4831048 | PJM-AMIL |  | N/A | N/A | Confirmed | NRG Power Marketing (South Central) | 100 | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4831048_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4831048_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/12/2016 | 6/1/2018 | 6/1/2025 | [6 empty] | FF | No
AC1-057 4831050 | PJM-MECS |  | N/A | N/A | Retracted | NRG Power Marketing (South Central) | 200 | 200 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4831050_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4831050_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/12/2016 | 6/1/2018 | 6/1/2025 |  | 10/30/2017 |  |  |  |  | FF | No
AC1-058 4831663 | PJM-AMIL |  | N/A | N/A | Retracted | J. Aron &amp; Company | 300 | 300 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4831663_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 9/13/2016 | 6/1/2018 | 6/1/2023 |  | 11/14/2016 |  |  |  |  | FF | No
AC1-059 | Desoto-Tanners Creek 345kV |  | IN | Fayette | Withdrawn | AEP | 300 | 300 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1059_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2016 | N/A | N/A |  | 6/5/2018 |  | 12/15/2018 |  |  | N | No
AC1-060 | Providence Forge 34.5kV | Charles City 1 | VA | Charles City | In Service | Dominion | 24 | 0 | 2.5 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1060_feas.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_060_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/9/2017 | N | No
AC1-061 | Locks 34.5kV | Dinwiddie 2 | VA | Dinwiddie | In Service | Dominion | 3 | 0 | 0.2 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 6/1/2017 | N | No
AC1-062 | Jetersville 34.5kV | Amelia 1 | VA | Amelia | In Service | Dominion | 16 | 0 | 1.9 | 0 | Capacity | Generation Interconnection | Diesel; Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1062_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_062_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2017 | 6/1/2017 | 8/24/2018 | N | No
AC1-063 | Shackleford 34.5kV | King & Queen Landfill Facility | VA | King and Queen | In Service | Dominion | 14 | 0 | 2.2 | 0 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1063_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_063_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 6/1/2019 | 6/1/2019 | 5/9/2019 | N | No
AC1-064 | Route 16 34.5kV | Route 16 (Mountain View) 345kV (Upton 114) | PA | Franklin | In Service | APS | 15 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_064_csa.pdf | Document Posted | N/A | N/A |  | 9/20/2016 | N/A | N/A |  |  |  | 9/30/2017 | 9/30/2017 | 6/22/2017 | N | No
AC1-065 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Engineering and Procurement | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1065_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_065_isa.pdf | Document Posted | N/A |  | Document Posted | N/A | N/A |  | 9/20/2016 | N/A | N/A | 12/31/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AC1-066 | Linden 26 kV |  | NJ | Union | Withdrawn | PSEG | 5 | 5 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1066_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/21/2016 | N/A | N/A |  | 12/11/2017 |  | 9/1/2017 |  |  | N | No
AC1-067 | Davis Creek-Burnham |  | IL | Cook | Withdrawn | ComEd | 1254 | 1254 | 1092 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1067_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2016 | N/A | N/A |  | 3/27/2019 |  | 12/1/2021 |  |  | N | No
AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | Engineering and Procurement | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_068_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2016 | N/A | N/A | 12/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | Engineering and Procurement | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_069_csa.pdf | Document Posted | N/A | N/A |  | 9/26/2016 | N/A | N/A | 12/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-070 | Stuarts Draft 23kV |  | VA | Augusta | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1070_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2016 | N/A | N/A |  | 12/15/2017 |  | 10/1/2018 |  |  | N | Yes
AC1-071 | Paupack-Lackawanna 230kV | Waymart Wind II | PA | Wayne | Suspended | PPL | 67.3 | 67.25 | 8.74 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_071_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 10/15/2021 | 10/15/2021 |  | N | No
AC1-072 | Segreto (Covert) 345kV | Covert Generating Facility | MI | Van Buren | In Service | ITCI | 1055 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1072_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_072_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 6/18/2018 | 6/18/2018 | 5/9/2018 | N | No
AC1-073 | Laurel Mountain 138 kV | Laurel Mountain Wind Farm & Energy Storage Facility | WV | Barbour | Suspended | APS | 141.3 | 16.3 | 5.8 |  | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1073_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_073_csa.pdf | Document Posted | N/A | N/A |  | 9/28/2016 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 |  | N | No
AC1-074 | Jacksonville-Renaker 138kV I |  | KY | Harrison | Active | EKPC | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1074_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-075 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 38.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_075_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | Suspended | Dominion | 62.5 | 62.5 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_076_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-077 | Sayreville Storage |  | NJ | Middlesex | Withdrawn | JCPL | 0 | 0.38 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/27/2016 |  |  |  |  | Y | No
AC1-078 | Beatty-London 138kV |  | OH | Madison | Active | ATSI | 176 | 176 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1078_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC1-079 | Broadwell Solar |  | KY | Harrison | Withdrawn | EKPC | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/21/2016 |  | 6/1/2019 |  |  | N | No
AC1-080 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | Engineering and Procurement | Dominion | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1080_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1080_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_080_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_080_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-081 | Susquehanna-Lackawanna 500kV |  | PA | Luzerne | Withdrawn | PPL | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 4/7/2017 | Customer Initiated Withdrawal | 9/28/2020 |  |  | N | No
AC1-082 | Ravenswood-Hemlock 69kV |  | OH | Meigs | Active | AEP | 48 | 48 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1082_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  |  |  | 5/1/2018 |  |  | N | No
AC1-083 | Smith Mountain-Bearskin 138kV |  | VA | Pittsylvania | Active | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1083_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ac1_083_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  |  |  | 10/21/2017 |  |  | N | No
AC1-084 | Mt. Arlington Solar |  | NJ | Morris | Withdrawn | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2016 | N/A | N/A |  | 10/17/2016 |  | 3/31/2018 |  |  | N | No
AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | Engineering and Procurement | Dayton | 400 | 400 | 152 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1085_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1085_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_085_csa.pdf | Document Posted | N/A | N/A |  | 9/30/2016 | N/A | N/A | 11/1/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC1-086 | Thelma 230kV |  | NC | Northhampton | Active | Dominion | 300 | 180 | 123.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1086_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2016 | N/A | N/A |  |  |  | 12/31/2017 |  |  | N | No
AC1-087 | Siegfried-Hauto 69kV | PA Solar Park | PA | Carbon | Partially in Service - Under Construction | PPL | 20 | 10 | 3.8 | 2.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1087_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_087_csa.pdf | Document Posted | N/A | N/A |  | 10/11/2016 | N/A | N/A | 12/1/2019 |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AC1-088 | Strawton 138kV |  | IN | Madison | Withdrawn | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1088_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2016 | N/A | N/A |  | 5/8/2018 |  | 12/31/2017 |  |  | BB | No
AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | Suspended | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_089_csa.pdf | Document Posted | N/A | N/A |  | 10/13/2016 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 |  | N | No
AC1-090 | Hamilton Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1090_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2016 | N/A | N/A |  | 7/17/2017 | Customer Milestone Not Met | 10/1/2017 |  |  | BB | Yes
AC1-091 | Cedar Creek 138kV I |  | DE | New Castle | Active | DPL | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-092 | Cedar Creek 138kV II |  | DE | New Castle | Active | DPL | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-093 | Cedar Creek 138kV III |  | DE | New Castle | Active | DPL | 18.8 | 18.8 | 7.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1093_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-094 | Cedar Creek 138kV IV |  | DE | New Castle | Active | DPL | 15.9 | 15.9 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1094_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-095 | Cedar Creek 25kV |  | DE | New Castle | Withdrawn | DPL | 9.9 | 9.9 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1095_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2016 | N/A | N/A |  | 3/9/2020 |  | 6/30/2018 |  |  | N | No
AC1-096 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1277 | 1277 | 1277 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2016 | N/A | N/A |  | 2/23/2017 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AC1-097 | Hatfield 500kV | Renaissance Energy Center | PA | Greene | Withdrawn | APS | 1140 | 1140 | 1040 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1097_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1097_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_097_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_097_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2016 | N/A | N/A |  | 11/11/2019 |  | 6/1/2021 |  |  | N | No
AC1-098 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 60 | 60 | 37.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1098_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1098_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_098_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2016 | N/A | N/A |  |  |  | 11/1/2022 | 11/1/2022 |  | N | No
AC1-099 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1099_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1099_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_099_csa.pdf | Document Posted | N/A | N/A |  | 10/21/2016 | N/A | N/A |  |  |  | 11/1/2022 | 11/1/2022 |  | N | No
AC1-100 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 678 | 98 | 43.4 | 98 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1100_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_100_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/24/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/10/2017 | N | No
AC1-101 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1101_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-102 | Johns Creek-Excel 138kV II |  | KY | Pike | Active | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-103 | Nottingham 138kV |  | OH | Harrison | Active | AEP | 1050 | 1050 | 1026 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1103_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2016 | N/A | N/A |  |  |  | 10/21/2020 |  |  | N | No
AC1-104 | Deepwater-Penns Grove 69kV |  | NJ | Salem | Withdrawn | AEC | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/25/2016 | N/A | N/A |  | 11/6/2017 |  | 6/30/2018 |  |  | N | No
AC1-105 | Halifax-Mt. Laurel 115kV | Sunnybrook Farm Solar | VA | Halifax | Suspended | Dominion | 51 | 51 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1105_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1105_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_105_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 7/15/2022 | 7/15/2022 |  | N | No
AC1-106 | Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49.9 | 0 | 15.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1106_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2016 | N/A | N/A |  | 4/10/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-107 | Chickahominy 500kV | Chickahominy Power | VA | Charles City | Suspended | Dominion | 1600 | 1600 | 1600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1107_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1107_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_107_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_107_csa.pdf | Document Posted | N/A | N/A |  | 10/26/2016 | N/A | N/A | 3/1/2023 |  |  | 3/1/2023 | 3/1/2023 |  | N | No
AC1-108 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1100 | 50 | 100 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2016 | N/A | N/A | 9/13/2019 |  |  | 3/1/2021 | 3/1/2021 | 9/22/2019 | N | No
AC1-109 | Aurora 345kV |  | IL | Du Page | Active | ComEd | 980 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1109_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 6/1/2017 |  |  | N | No
AC1-110 | Aurora 138kV |  | IL | Du Page | Active | ComEd | 1010 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1110_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 6/1/2017 |  |  | N | No
AC1-111 | Aurora 138kV |  | IL | Du Page | Active | ComEd | 1046 | 36 | 36 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1111_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2016 | N/A | N/A |  |  |  | 6/1/2017 |  |  | N | No
AC1-112 | Old Church 34.5kV | Hollyfield Solar Facility | VA | King William | In Service | Dominion | 17 | 17 | 10.9 | 17 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1112_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1112_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1112_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 8/8/2018 | N | No
AC1-113 | Rockford |  | IL | Winnebago | Active | ComEd | 320 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1113_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 6/1/2017 |  |  | N | No
AC1-114 | Rockford II |  | IL | Winnebago | Active | ComEd | 173 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1114_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 6/1/2017 |  |  | N | No
AC1-115 | St. Johns 115kV |  | VA | Carolina | Withdrawn | Dominion | 14.9 | 14.9 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1115_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 12/29/2017 |  | 4/30/2018 |  |  | N | No
AC1-116 | Mount Eagle 34.5kV | Rivanna Solar | VA | Albemarle | Engineering and Procurement | Dominion | 12.5 | 12.5 | 4.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1116_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1116_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1116_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A | 6/30/2020 |  |  | 12/31/2022 | 12/31/2022 |  | N | Yes
AC1-117 | Stockton 34.5kV | Sol Systems, LLC Solar Facility | VA | Henry | Suspended | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1117_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1117_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1117_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | Yes
AC1-118 | Westmoreland 34.5kV | Montross Solar Facility | VA | Westmoreland | In Service | Dominion | 20 | 20 | 13.2 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1118_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1118_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1118_wmpa.pdf | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 12/12/2018 | N | No
AC1-119 | Deep Run |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 11/16/2016 |  | 4/30/2017 |  |  | N | No
AC1-120 | Mitchell-Mountain Run 115kV |  | VA | Culpeper | Active | Dominion | 60 | 60 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1120_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1120_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-121 | Mitchell-Mountain Run 115kV |  | VA | Culpeper | Active | Dominion | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1121_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1121_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC1-122 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | Engineering and Procurement | AEP | 60 | 60 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1122_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1122_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_122_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/30/2020 | 12/30/2020 |  | N | No
AC1-123 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | Engineering and Procurement | AEP | 80 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1123_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1123_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_123_csa.pdf | Document Posted | N/A | N/A |  | 10/27/2016 | N/A | N/A |  |  |  | 12/30/2020 | 12/30/2020 |  | N | No
AC1-124 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1124_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | No
AC1-125 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1125_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/27/2016 | N/A | N/A |  | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | No
AC1-126 4841985 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841985_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841985_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-127 4841988 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841988_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841988_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-128 4841989 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841989_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841989_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-129 4841990 | PJM-CPLE |  | N/A | N/A | Confirmed | North Carolina Electric Membership | 25 | 25 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841990_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841990_lft2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 | [6 empty] | FF | No
AC1-130 4841991 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 25 | 25 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 10/31/2016 |  |  |  |  | FF | No
AC1-131 4841992 | PJM-CPLE |  | N/A | N/A | Confirmed | North Carolina Electric Membership | 50 | 50 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841992_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841992_ltf2.pdf | Executed Agreement and/or Study |  | Not Required |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 | [6 empty] | FF | No
AC1-132 4841993 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 50 | 50 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841993_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841993_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-133 4841994 | PJM-CPLE |  | N/A | N/A | Withdrawn | North Carolina Electric Membership | 100 | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4841994_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4841994_ltf2.pdf | Executed Agreement and/or Study |  | Withdrawn |  | N/A | N/A | [5 empty] | 10/27/2016 | 1/1/2018 | 1/1/2023 |  | 2/13/2019 |  |  |  |  | FF | No
AC1-134 | Four Rivers 230kV | Doswell Facility (Doswell Complex 5 & 6) | VA | Hanover | In Service | Dominion | 746 | 0 | 50 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_134_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 2/28/2018 | N | No
AC1-135 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 1274 | 0 | 62 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/16/2016 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AC1-136 | Keriton 12kV |  | KY | Keaton | Withdrawn | DEOK | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-137 | Erlanger 12kV |  | KY | Boone | Withdrawn | DEOK | 1.9 | 1.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-138 | Bend Station 12kV |  | KY | Boone | Withdrawn | DEOK | 2.5 | 2.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC1-139 | Doubs 230kV |  | MD | Frederick | Withdrawn | APS | 102 | 102 | 38.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1139_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 10/31/2017 |  | 6/1/2019 |  |  | N | No
AC1-140 | North Longview 500 kV | Longview Power | WV | Monongalia | In Service | APS | 710 | 10 | 10 | 10 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1140_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_140_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_140_csa.pdf | Document Posted | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 6/30/2018 | 6/30/2018 | 5/14/2018 | N | No
AC1-141 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 1085 | 91 | 91 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/30/2020 | 10/28/2016 | N/A | N/A | 3/1/2021 |  |  | 7/30/2021 | 7/30/2021 |  | N | No
AC1-142 | Garner-Lancaster 115kV |  | VA | Lancaster | Withdrawn | Dominion | 100 | 100 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  | 6/12/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC1-142A | Joliet |  | IL | Will | Active | ComEd | 1100 | 64 | 64 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1142a_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2016 | N/A | N/A |  |  |  | 10/19/2016 |  |  | N | No
AC1-143 | Brandy-Remington 115kV |  | VA | Culpeper | Active | Dominion | 60 | 60 | 41.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1143_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-144 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 85 | 85 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/18/2018 |  | 10/1/2019 |  |  | N | No
AC1-145 | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | Engineering and Procurement | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1145_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1145_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_145_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/18/2020 | 12/18/2020 |  | N | No
AC1-146 | Chatham 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/8/2017 | Customer Initiated Withdrawal | 9/1/2018 |  |  | N | No
AC1-147 | Grassfield 34.5kV |  | VA | City of Chesapeake | Engineering and Procurement | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1147_fea.pdf | Document Posted |  | Not Required |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1147_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1147_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A | 12/30/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | Yes
AC1-148 | Granger-Twin Branch 138kV |  | IN | St. Joseph | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1148_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 3/16/2018 |  | 11/1/2018 |  |  | N | No
AC1-149 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-150 | Beaver 138kV |  | OH | Pike | Withdrawn | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-151 | Harwood-Berwick 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1151_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1151_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1151_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 9/23/2019 |  | 2/28/2019 |  |  | N | No
AC1-152 | Lawrenceburg 345kV PB I | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 1270 | 50 | 50 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1152_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_152_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-153 | Kendall-Tazewell-Dresden-Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 2460 | 1300 | 1250 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1153_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 8/10/2018 |  | 6/1/2021 |  |  | N | No
AC1-154 | I.B. Corners 12kV | Harris Project | MD | Queen Anne's | Withdrawn | DPL | 3.2 | 3.2 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1154_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1154_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1154_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/25/2018 |  | 11/8/2018 | 11/8/2018 |  | N | No
AC1-155 | Mt. Airy 34.5kV |  | VA | Wythe | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-156 | Morgan's Cut 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Milestone Not Met | 6/1/2019 |  |  | N | No
AC1-157 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC1-158 | Spotsylvania 500kV | Spotsylvania Energy Center | VA | Spotsylvania | Under Construction | Dominion | 500 | 500 | 347.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1158_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_158_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 10/31/2016 | N/A | N/A | 7/1/2020 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AC1-159 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 1250.1 | 250.1 | 369.1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 10/3/2018 |  | 1/1/2021 |  |  | N | No
AC1-160 | Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC1-161 | Septa 500kV |  | VA | Isle of Wight | Active | Dominion | 240 | 240 | 168.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1161_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AC1-162 | Briery-Clover 230kV |  | VA | Prince Edward | Withdrawn | Dominion | 240 | 240 | 168.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1162_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 2/26/2019 |  | 10/1/2019 |  |  | N | No
AC1-163 | Ahoskie 34.5KV |  | NC | Hertford | Withdrawn | Dominion | 16.9 | 16.94 | 11.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1163_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/1/2018 |  | 10/1/2019 |  |  | N | No
AC1-164 | Chickahominy 230kV | Keydet Solar Center One | VA | Charles City | Engineering and Procurement | Dominion | 320 | 320 | 220.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1164_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1164_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_164_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_164_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/30/2022 | 6/30/2022 |  | N | No
AC1-165 | Atlanta 69kV III | Pickaway County Solar III | OH | Pickaway | Engineering and Procurement | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_165_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 12/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | Engineering and Procurement | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1166_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1116_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_166_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 12/1/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC1-167 | Mark Center 69kV |  | OH | Defiance | Active | AEP | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1167_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/1/2019 |  |  | N | No
AC1-168 | Kewanee-Streator |  | IL | Putnam | Active | ComEd | 78.7 | 78.65 | 10.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1168_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 11/15/2019 |  |  | N | No
AC1-169 | Chicago Heights |  | IL | Will | Withdrawn | ComEd | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/4/2018 |  | 9/30/2017 |  |  | Y | No
AC1-170 | New Canton 12.47V |  | NJ | Mercer | Withdrawn | JCPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1170_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/28/2017 | Customer Initiated Withdrawal | 10/1/2017 |  |  | Y | Yes
AC1-171 | Powerton |  | IL | Tazewell | Active | ComEd | 79.1 | 79.1 | 10.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1171_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 11/15/2019 |  |  | N | No
AC1-172 | Lawrenceburg 345kV PB II | Lawrenceburg Generating Plant | IN | Dearborn | Partially in Service - Under Construction | AEP | 1320 | 50 | 50 | 4 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1172_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 | 11/13/2019 | N | No
AC1-173 | Logtown 138kV | Timber Road IV Wind Farm (Southern Phase) | OH | Paulding | In Service | AEP | 75.9 | 75.9 | 9.9 | 75.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1173_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_173_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_173_csa.pdf | Document Posted | N/A | N/A | 2/5/2020 | 10/31/2016 | N/A | N/A | 2/15/2020 |  |  | 3/31/2020 | 3/31/2020 | 3/27/2020 | N | No
AC1-174 | Losantville 345kV |  | IN | Randolph | Active | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1174_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 11/30/2019 |  |  | N | No
AC1-175 | Losantville 345kV |  | IN | Randolph | Active | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1175_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 11/30/2019 |  |  | N | No
AC1-176 | Timber Switch 138kV |  | OH | Paulding | Active | AEP | 58.7 | 58.7 | 7.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1176_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No
AC1-177 | Kings Creek 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1177_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/28/2019 |  | 1/1/2019 |  |  | N | No
AC1-178 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/5/2016 |  | 1/1/2019 |  |  | N | No
AC1-179 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/5/2016 |  | 1/1/2019 |  |  | N | No
AC1-180 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1180_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 3/20/2017 | Customer Initiated Withdrawal | 1/1/2019 |  |  | N | No
AC1-181 | Richland 138kV | Richland Power Plant | OH | Defiance | In Service | ATSI | 428 | 5 | 5 | 5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1181_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_181_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 8/8/2018 | N | No
AC1-182 | W.H. Zimmer Station 345kV | Zimmer Station | OH | Clermont | In Service | DEOK | 1320 | 20 | 20 | 20 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1182_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_182_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 |  | N | No
AC1-183 | Ontelaunee 230kV |  | PA | Berks | Withdrawn | ME | 608.1 | 12 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1183_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/15/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC1-184 | Printz |  | PA | Delaware | Withdrawn | PECO | 676.5 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1184_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/25/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC1-185 | Lee County | Lee Energy Facility | IL | Lee | Partially in Service - Under Construction | ComEd | 688 | 48 | 48 | 48 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1185_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1185_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2019 |  | 12/14/2018 | N | No
AC1-186 | Central City 115kV |  | PA | Somerset | Withdrawn | PENELEC | 138 | 138 | 17.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1186_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/11/2018 |  | 12/31/2019 |  |  | N | No
AC1-187 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | APS | 117 | 117 | 15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1187_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/20/2018 |  | 12/31/2019 |  |  | N | No
AC1-188 | Rio-Lick 138kV |  | OH | Jackson | Active | AEP | 70 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1188_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/Delay email sent 11/20/19 | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2017 |  |  | N | No
AC1-189 | Chinquapin-Everetts 230kV |  | NC | Pitt | Active | Dominion | 80 | 80 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1189_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2017 |  |  | N | No
AC1-190 | East New Market 69kV |  | MD | Dorchester | Active | DPL | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1190_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2017 |  |  | N | No
AC1-191 | Elmont 115kV |  | VA | Hanover | Active | Dominion | 80 | 80 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1191_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC1-192 | N/A-N/A |  | N/A | N/A | Withdrawn | PECO |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/2/2016 |  |  |  |  | EE | No
AC1-193 | Handsome DP-Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 130 | 55 | 20.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1193_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-194 | Elk 138kV |  | OH | Vinton | Active | AEP | 125 | 125 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1194_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AC1-195 | Dunkirk-Ada 69kV |  | OH | Hardin | Withdrawn | AEP | 75 | 75 | 9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1195_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/30/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC1-196 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/22/2016 | Customer Initiated Withdrawal | 6/30/2017 |  |  | Y | No
AC1-197 | Somerset 480v | Somerset 480v | NJ | Somerset | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1197_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1197_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1197_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1197_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-198 | Union 480v | Union 480v | NJ | Union | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1198_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1198_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1198_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1198_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-199 | Mercer 480v I | Mercer 480v I | NJ | Mercer | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1199_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1199_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1199_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1199_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 1/31/2018 | 1/31/2018 |  | Y | No
AC1-200 | Mercer 480v II | Mercer 480v II | NJ | Mercer | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1200_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1200_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1200_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1200_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 2/28/2018 | 2/28/2018 |  | Y | No
AC1-201 | Camden 480v II | Camden 480v II | NJ | Camden | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1201_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1201_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1201_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1201_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-202 | Cedar 12kV | The Home Depot Store #0951 | NJ | Ocean | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1202_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1202_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1202_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1202_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/12/2018 |  | 12/31/2018 | 12/31/2018 |  | Y | No
AC1-203 | Camden 480v III | Camden 480v III | NJ | Camden | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1203_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1203_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1203_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1203_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/3/2018 |  | 12/29/2017 | 12/29/2017 |  | Y | No
AC1-204 | Elwood | Jackson Generation | IL | Will | Under Construction | ComEd | 1200.9 | 1200.9 | 1115.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1204_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1204_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_204_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_204_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 11/1/2021 |  |  | 4/1/2022 | 4/1/2022 |  | N | No
AC1-205 | Madison Park |  | NJ | Middlesex | Withdrawn | JCPL | 10.3 | 10.3 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/17/2016 |  | 12/29/2017 |  |  | N | No
AC1-206 | Clubhouse 230kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 85 | 57.72 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1206_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 1/18/2018 |  | 10/1/2019 |  |  | N | No
AC1-207 | Monroe 34.5kV | Hoffman Station Road Solar | NJ | Middlesex | Engineering and Procurement | JCPL | 13.1 | 13.1 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1207_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_207_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_207_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 5/31/2020 |  |  | 5/26/2020 | 5/26/2020 |  | N | Yes
AC1-208 | Cox-Whitakers 115kV |  | NC | Halifax | Active | Dominion | 80 | 80 | 55.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1208_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1208_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1208_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/30/2018 |  |  | N | No
AC1-209 | Pine Grove Solar | Pine Grove Solar | PA | York | Withdrawn | PECO | 18 | 18 | 12.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1209_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1209_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1209_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 10/4/2019 |  | 9/30/2021 | 9/30/2021 |  | N | Yes
AC1-210 | Madison 69kV |  | OH | Madison | Withdrawn | AEP | 45 | 45 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1210_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/17/2018 |  | 6/30/2018 |  |  | N | No
AC1-211 | McConnellsburg 138kV |  | PA | Fulton | Withdrawn | APS | 70 | 70 | 48.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1211_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1211_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/6/2017 |  | 6/30/2018 |  |  | N | No
AC1-212 | Minster 69kV | Minster III ESS | OH | Auglaize | Engineering and Procurement | Dayton | 19.9 | 19.9 | 1.9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1212_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac1212_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac1212_wmpa.pdf | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A | 7/1/2020 |  |  | 4/30/2020 | 4/30/2020 |  | N | No
AC1-213 | North Salisbury 25kV |  | MD | Somerset | Active | DPL | 5.3 | 5.3 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1213_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1213_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 9/30/2017 |  |  | N | No
AC1-214 | Crescent Ridge | Lone Tree Wind | IL | Bureau | Engineering and Procurement | ComEd | 79.4 | 79.4 | 19 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1214_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1214_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1214_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_214_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_214_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC1-215 | Chase-City-Twittys Creek 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 100 | 100 | 68.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1215_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 6/21/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | No
AC1-216 | Hopewell-Surry 230kV | Spring Grove I Solar | VA | Surry | Under Construction | Dominion | 97.9 | 97.9 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1216_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1216_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1216_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_216_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_216_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 12/1/2020 | 12/1/2020 |  | N | No
AC1-217 | McConnellsburg-Texas Eastern 6 138kV |  | PA | Franklin | Withdrawn | APS | 55 | 55 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1217_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1217_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/29/2017 |  | 6/30/2018 |  |  | N | No
AC1-218 |  |  | NJ | Morris | Withdrawn | JCPL | 0.3 | 0.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/7/2016 |  | 1/31/2017 |  |  | Y | No
AC1-219 |  |  | NJ | Morris | Withdrawn | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 11/7/2016 |  | 1/31/2017 |  |  | Y | No
AC1-220 | Price 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 26.5 | 26.5 | 15.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1220_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1220_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 5/8/2018 |  | 9/30/2018 |  |  | N | No
AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | Engineering and Procurement | Dominion | 29.2 | 29.2 | 14.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1221_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1221_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_221_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 11/30/2021 | 11/30/2021 |  | N | No
AC1-222 | Crystal Hill-Halifax 115kV | Halifax County Solar | VA | Halifax | Engineering and Procurement | Dominion | 44.7 | 44.7 | 22.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1222_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1222_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1222_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_222_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_222_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AC1-223 | N/A-N/A |  | IL | Will | In Service | ComEd | 43.2 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ac1223_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ac1223_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ac1223_arr-csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A |  |  |  | 6/1/2020 |  | 12/12/2018 | EE | No
AC1-224 | Wye Mills 25kV |  | MD | Talbot | Withdrawn | DPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1224_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1224_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1224_fac.pdf | Document Posted |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/4/2018 |  | 2/1/2017 |  |  | Y | No
AC1-225 | Sorenson-Marysville 765kV |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 300.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1225_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1225_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/16/2018 |  | 12/31/2019 |  |  | N | No
AC1-226 | Wurno-Claytor 138kV |  | VA | Pulaski | Withdrawn | AEP | 200.1 | 200.1 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1226_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 4/3/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC1-227 | Low Moor-Lexington 230kV |  | VA | Botetourt | Withdrawn | Dominion | 96.6 | 96.6 | 12 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1227_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 7/13/2018 |  | 12/31/2019 |  |  | N | No
AC1-228 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1228_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 2/23/2018 |  | 3/31/2018 |  |  | N | No
AC1-229 | Omar 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1229_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2016 | N/A | N/A |  | 12/6/2018 |  | 3/31/2018 |  |  | N | No
AC2-001 |  |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 300.2 | 39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 12/31/2019 |  |  | N | No
AC2-002 |  |  | VA | Pulaski | Withdrawn | AEP | 179.4 | 179.4 | 23 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 12/31/2019 |  |  | N | No
AC2-003 |  |  | VA | Botetourt | Withdrawn | Dominion | 78.2 | 78 | 10 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 12/6/2016 | Queue Not Required | 10/12/2023 |  |  | N | No
AC2-004 | Meyersdale 115kV |  | PA | Somerset | Withdrawn | PENELEC | 98.8 | 50.75 | 6.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2004_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 7/12/2018 |  | 12/13/2019 |  |  | N | No
AC2-005 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 3 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 1/23/2017 |  | 3/31/2018 |  |  | N | No
AC2-006 | Oman 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 1/23/2017 |  | 3/31/2018 |  |  | N | No
AC2-007 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 20 | 20 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2007_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2016 | N/A | N/A |  | 7/5/2018 |  | 12/31/2017 |  |  | N | No
AC2-008 | Wildcat 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2016 | N/A | N/A |  | 6/5/2017 | Customer Initiated Withdrawal | 6/3/2019 |  |  | N | No
AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | Partially in Service - Under Construction | PSEG | 0.6 | 0.59 | 0.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2009_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2009_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2016 | N/A | N/A |  |  |  | 3/2/2018 | 3/2/2018 | 10/19/2017 | N | Yes
AC2-010 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2016 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 4/30/2018 |  |  | N | No
AC2-011 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Biomass |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/5/2016 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 7/31/2018 |  |  | N | No
AC2-012 | Grassfield-Great Bridge 115kV |  | VA | City of Chesapeake | Active | Dominion | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2012_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2016 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-013 | Ripley 69kV |  | MD | Charles | Withdrawn | PEPCO | 27.5 | 27.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2016 | N/A | N/A |  | 1/24/2017 | Customer Milestone Not Met | 11/30/2018 |  |  | N | No
AC2-014 | Ripley-Nanjemoy 69kV |  | MD | Charles | Withdrawn | PEPCO | 32.5 | 32.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2016 | N/A | N/A |  | 1/24/2017 | Customer Milestone Not Met | 11/30/2018 |  |  | N | No
AC2-015 | Chatfield-Howard 138kV |  | OH | Crawford | Active | AEP | 117 | 117 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2015_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2016 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-016 | Stemple 345kV | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 748 | 6 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2016_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_016_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 1/3/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 2/14/2020 | N | No
AC2-017 | Calvert Cliffs 500kV |  | MD | Calvert | Active | BGE | 1810.4 | 11.1 | 11.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2017_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/4/2017 | N/A | N/A |  |  |  | 3/8/2018 |  |  | N | No
AC2-018 | Rock Springs 500kV | Rock Springs Units #3 & #4 | MD | Cecil | In Service | Essential Power | 390 | 60 | 8 | 60 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2018_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_018_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/19/2017 | N/A | N/A |  |  |  | 6/1/2017 |  | 10/1/2017 | N | No
AC2-019 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2017 | N/A | N/A |  | 7/13/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC2-020 | Greenfield-Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2020_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2017 | N/A | N/A |  | 8/3/2018 |  | 12/31/2019 |  |  | N | No
AC2-021 | Albright-Cross School 138 kV |  | MD | Garrett | Active | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2021_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2021_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  |  |  | 1/15/2019 |  |  | N | No
AC2-022 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 100 | 100 | 70.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2022_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 11/1/2017 |  | 9/30/2019 |  |  | N | No
AC2-023 | Hebron 69kV |  | MD | Wicomico | Active | DPL | 45.8 | 45.8 | 26.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2023_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  |  |  | 9/30/2019 |  |  | N | No
AC2-024 | Edison 4kV |  | NJ | Middlesex | Withdrawn | PSEG | 1.2 | 1.2 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2024_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 1/29/2018 |  | 12/31/2017 |  |  | N | Yes
AC2-025 | Hatfield 500kV |  | PA | Greene | Withdrawn | APS | 1140 | 1140 | 1140 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2017 | N/A | N/A |  | 3/28/2017 | Customer Initiated Withdrawal | 6/1/2022 |  |  | N | No
AC2-026 | Wakefield 138kV |  | OH | Scioto | Withdrawn | AEP | 50 | 50 | 27.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2026_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2017 | N/A | N/A |  | 9/6/2017 | Customer Milestone Not Met | 6/30/2019 |  |  | N | No
AC2-027 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2017 | N/A | N/A |  | 7/19/2017 | Customer Initiated Withdrawal | 11/30/2018 |  |  | N | No
AC2-028 | Highland 13.2kV |  | OH | Highland | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2017 | N/A | N/A |  | 4/12/2017 | Customer Initiated Withdrawal | 10/31/2018 |  |  | N | No
AC2-029 | Circleville 138kV |  | OH | Pickaway | Active | AEP | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2029_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2017 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AC2-030 | East Beaver 69kV |  | OH | Pike | Withdrawn | AEP | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2030_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 12/6/2017 |  | 12/31/2018 |  |  | N | No
AC2-031 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2031_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/4/2017 |  | 10/1/2019 |  |  | N | No
AC2-032 | N/A-N/A |  | N/A | N/A | Withdrawn | BGE | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/3/2017 |  | 6/1/2018 |  |  | EE | No
AC2-033 | N/A-N/A |  | N/A | N/A | Withdrawn | BGE | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/24/2017 |  |  |  |  | EE | No
AC2-034 | N/A-N/A |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 3/24/2017 |  |  |  |  | EE | No
AC2-035 | Lick-Firebrick 69kV |  | OH | Jackson | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2035_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 2/25/2019 |  | 6/1/2019 |  |  | N | No
AC2-036 | Ravenswood-East Bashan Switch 69kV |  | OH | Meigs | Withdrawn | AEP | 0 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 3/12/2019 |  | 6/1/2020 |  |  | N | No
AC2-037 | Lick 69kV |  | OH | Jackson | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-038 | Lee 69kV |  | OH | Athens | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2038_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 9/27/2019 |  | 6/1/2019 |  |  | N | No
AC2-039 | Poston-Dexter 69kV |  | OH | Athens | Withdrawn | AEP | 43 | 43 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-040 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2040_imp.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-041 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2041_fea,pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-042 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2042_imp.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2017 | N/A | N/A |  | 10/18/2017 |  | 6/1/2019 |  |  | N | No
AC2-043 | W. Millersport-S. Baltimore 138kV |  | OH | Fairfield | Withdrawn | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2043_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2017 | N/A | N/A |  | 9/14/2018 |  | 12/15/2018 |  |  | N | No
AC2-044 | Maddox Creek 345kV |  | OH | Van Wert | Active | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2044_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2017 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AC2-045 | Clark 12kV | Solar Power and Light, LLC | OH | Athens | Suspended | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2045_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2045_wmpa.pdf | Not Required | N/A | N/A |  | 2/7/2017 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 |  | N | No
AC2-046 | EAst Beaver 138kV |  | OH | Jackson | Withdrawn | AEP | 63 | 63 | 39.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2046_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2017 | N/A | N/A |  | 9/26/2017 |  | 12/31/2018 |  |  | N | No
AC2-047 | Ashley-Millbrook Park 69 kV |  | OH | Scioto | Withdrawn | AEP | 18.3 | 18.3 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2047_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2017 | N/A | N/A |  | 10/23/2017 |  | 10/31/2018 |  |  | N | No
AC2-048 | Sporn 138kV |  | OH | Meigs | Active | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2048_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2017 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AC2-049 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2049_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2017 | N/A | N/A |  | 10/13/2017 |  | 6/1/2019 |  |  | N | No
AC2-050 | Tabernacle 12kV |  | NJ | Burlington | Active | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/10/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-051 | Pickaway Solar |  | OH | Pickaway | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2017 | N/A | N/A |  | 3/24/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-052 4862612 | PJM-LINDENVFT |  | N/A | N/A | Confirmed | Linden VFT, LLC | 300 | 330 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4862612_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 2/14/2017 | 6/1/2019 | 6/1/2024 | [6 empty] | FF | No
AC2-053 | Germantown 115kV | Brookview Solar I | PA | Adams | Suspended | ME | 55 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2053_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_053_csa.pdf | Document Posted | N/A | N/A |  | 2/14/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-054 | South Rultonham 69kV |  | OH | Muskingum | Withdrawn | AEP | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-055 | Buckskin 69kV |  | OH | Highland | Active | AEP | 47.5 | 47.5 | 18.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2055_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2017 | N/A | N/A |  |  |  | 7/1/2019 |  |  | N | No
AC2-056 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2017 | N/A | N/A |  | 5/5/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-057 | Ridgeway-Dan River 69kV |  | VA | Pittsylvania | Withdrawn | AEP | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2057_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  | 10/4/2017 |  | 12/31/2018 |  |  | N | No
AC2-058 | Newcomerstown-N. Philly 69kV |  | OH | Tuscarawas | Withdrawn | AEP | 16.4 | 16.37 | 16.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  | 7/12/2017 | Customer Initiated Withdrawal | 12/31/2018 |  |  | N | No
AC2-059 | Biers Run-Circleville 138kV |  | OH | Ross | Active | AEP | 127 | 127 | 62.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2059_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-060 | Buckskin 69kV |  | OH | Ross | Active | AEP | 100 | 100 | 64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2060_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-061 | Hillsboro-Clinton 138kV |  | OH | Ross | Active | AEP | 117 | 117 | 58.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2061_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-062 | Emerald-Kenton 138kV |  | OH | Brown | Withdrawn | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2062_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 10/4/2017 |  | 12/31/2019 |  |  | N | No
AC2-063 | Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 100 | 100 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 3/17/2017 | Customer Milestone Not Met | 10/31/2019 |  |  | N | No
AC2-064 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 12/9/2019 |  | 6/1/2019 |  |  | N | No
AC2-065 | N/A-N/A |  | N/A | N/A | Withdrawn | Dayton | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AC2-066 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | Under Construction | DEOK | 200 | 75 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2066_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_066_csa.pdf | Document Posted | N/A | N/A | 8/19/2020 | 2/24/2017 | N/A | N/A | 9/8/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-067 | Camden-Crystal I 69kV | Eaton OH Solar | OH | Preble | Engineering and Procurement | Dayton | 49.9 | 49.9 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2067_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2067_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_067_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_067_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2017 | N/A | N/A | 1/1/2022 |  |  | 2/1/2022 | 2/1/2022 |  | N | No
AC2-068 | Camden-Crystal II 69kV | Eaton OH Solar | OH | Preble | Engineering and Procurement | Dayton | 69.9 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_068_csa.pdf | Document Posted | N/A | N/A |  | 2/27/2017 | N/A | N/A | 1/1/2022 |  |  | 2/1/2022 | 2/1/2022 |  | N | No
AC2-069 | Jacsonville-Renaker 138kV III |  | KY | Harrison | Withdrawn | EKPC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2017 | N/A | N/A |  | 9/11/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-070 | Old Church 34.5kV | Hollyfield II | VA | King William | Engineering and Procurement | Dominion | 13 | 13 | 9.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2070_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2070_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2070_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/30/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-071 | Buckingham 35kV | Buckingham IIK | VA | Buckingham | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2071_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2071_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-072 | Nokesville 35kV | Nokesville | VA | Prince William | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2072_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2072_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2072_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-073 | Harmony Village 35kV | Church View | VA | Middlesex | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2073_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2073_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2073_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 | 9/24/2019 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-074 | Mt. Jackson 35kV | Mt. Jackson I | VA | Shenandoah | Engineering and Procurement | Dominion | 15.7 | 15.65 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2074_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2074_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2017 | N/A | N/A | 12/31/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-075 | Great Blue Heron Solar |  | KY | Harrison | Active | EKPC | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2075_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-076 | Kiski Valley–Vandergrift 25 kV | Kiski Valley | PA | Westmoreland | Withdrawn | APS | 19.9 | 19.9 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2076_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2076_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2076_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 10/22/2018 |  | 4/30/2020 | 4/30/2020 |  | N | No
AC2-077 | Sabinsville 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2077_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 8/1/2019 |  | 5/31/2018 |  |  | N | No
AC2-078 | Disputanta-Waverly 115kV |  | VA | Prince George | Active | Dominion | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2078_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-079 | Ivor-Oakridge 115kV |  | VA | Isle of Wight | Active | Dominion | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2079_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-080 | Olive-Reynolds 345kV |  | IN | Jasper | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2080_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-081 | Battle Town 115kV |  | VA | Clarke | Withdrawn | APS | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/24/2017 | Customer Milestone Not Met | 12/31/2019 |  |  | N | No
AC2-082 | Remington-Gainesville 230kV |  | VA | Fauquier | Withdrawn | Dominion | 85 | 85 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2082_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 6/5/2018 |  | 12/31/2019 |  |  | N | No
AC2-083 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-084 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-085 | Eastwood 34kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2085_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 7/2/2018 |  | 5/31/2019 |  |  | N | No
AC2-086 | Eastwood 34.5kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 4/10/2017 | Customer Initiated Withdrawal | 5/30/2019 |  |  | N | No
AC2-087 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 85 | 47.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2087_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 1/15/2020 |  | 5/31/2019 |  |  | N | No
AC2-088 | S. Bethel-Brown 69kV | Nestlewood Solar | OH | Brown | Engineering and Procurement | DEOK | 70 | 70 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_088_csa.pdf | Document Posted | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 12/15/2021 | 12/15/2021 |  | N | No
AC2-089 | Klockner 34.5 kV | Silverside Solar | VA | Wythe | Withdrawn | AEP | 18.2 | 18.2 | 8.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2089_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2089_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2089_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/22/2019 |  | 12/31/2019 | 12/31/2019 |  | N | No
AC2-090 | Losantville 345kV |  | IN | Randolph | Active | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2090_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-091 | Modoc (Riverstart Solar IV) 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-092 | Susquehanna-Lackawanna 500kV |  | PA | Luzerne | Active | PPL | 1105 | 55 | 65 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2017 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AC2-093 | Brunswick-Wake 500 kV |  | NC | Northhampton | Withdrawn | Dominion | 675 | 675 | 429.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2093_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2017 | N/A | N/A |  | 7/6/2018 |  | 12/1/2021 |  |  | N | No
AC2-094 | Louisa-North Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 99.9 | 99.9 | 63.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2094_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2017 | N/A | N/A |  | 10/30/2017 |  | 10/1/2019 |  |  | N | No
AC2-095 | Eastwood 138kV |  | OH | Clermont | Withdrawn | DEOK | 10 | 10 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2017 | N/A | N/A |  | 4/11/2017 | Customer Initiated Withdrawal | 5/30/2019 |  |  | N | No
AC2-096 | Wurno I 34.5KV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 1/10/2018 |  | 6/1/2018 |  |  | N | No
AC2-097 | Wurno II 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 1/10/2018 |  | 6/1/2018 |  |  | N | No
AC2-098 | Buckhorn-Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2098_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 8/30/2017 | Customer Initiated Withdrawal | 6/1/2018 |  |  | N | No
AC2-099 | Nursery 36kV |  | OH | Lake | Withdrawn | ATSI | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2099_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2017 | N/A | N/A |  | 9/8/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | Yes
AC2-100 | Halifax-Person 230kV |  | VA | Halifax | Active | Dominion | 50 | 50 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2100_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  |  |  | 3/7/2019 |  |  | N | No
AC2-101 | Ripley-Nanjemoy 69kV | Shugart Solar | MD | Charles | Engineering and Procurement | SMECO | 32.5 | 32.5 | 12.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2101_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2101_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2101_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2101_wmpa.pdf | Not Required | N/A | N/A |  | 3/10/2017 | N/A | N/A | 12/31/2020 |  |  | 3/15/2021 | 3/15/2021 |  | N | No
AC2-102 | Mitchell DP 115kV |  | VA | Culpeper | Withdrawn | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2102_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  | 4/15/2020 |  | 6/30/2019 |  |  | N | No
AC2-103 | Beaver-Davis Besse 345 kV I |  | OH | Erie | Active | ATSI | 297.7 | 297.66 | 38.69 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2103_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AC2-104 | Marysville-Sorenson 765kv |  | OH | Van Wert | Withdrawn | AEP | 500.3 | 500.25 | 65.03 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2017 | N/A | N/A |  | 11/7/2019 |  | 12/31/2020 |  |  | N | No
AC2-105 | Saddler 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 100 | 73.51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/29/2017 | Customer Initiated Withdrawal | 10/1/2019 |  |  | N | No
AC2-106 | Biers Run 138kV |  | OH | Ross | Withdrawn | AEP | 100 | 100 | 68.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2106_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 12/13/2017 |  | 10/1/2019 |  |  | N | No
AC2-107 | Perth 115kV |  | VA | Halifax | Withdrawn | Dominion | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/27/2019 |  | 10/1/2019 |  |  | N | No
AC2-108 | Wharton 115kV |  | NC | Beaufort | Withdrawn | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 9/30/2019 |  |  | N | No
AC2-110 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Engineering and Procurement | Dominion | 70 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2110_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_110_isa.pdf | Document Posted | N/A |  | Document Posted | N/A | N/A |  | 3/13/2017 | N/A | N/A |  |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AC2-111 | College Corner 138kV |  | OH | Preble | Active | AEP | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2111_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2017 | N/A | N/A |  |  |  | 7/1/2019 |  |  | N | No
AC2-112 | Stuarts Draft-Waynesboro 115kV |  | VA | Augusta | Active | Dominion | 150 | 150 | 103.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2112_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2017 | N/A | N/A |  |  |  | 10/31/2018 |  |  | N | No
AC2-113 | Culpeper 35kV | Culpeper North | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2113_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2113_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2113_wmpa.pdf | Not Required | N/A | N/A |  | 3/17/2017 | N/A | N/A |  | 10/8/2018 |  | 12/31/2021 | 12/31/2021 |  | N | No
AC2-114 | Magnolia-Summersville 69kV |  | KY | Campbell | Withdrawn | EKPC | 49.9 | 49.9 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2114_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2017 | N/A | N/A |  | 9/13/2017 | Customer Initiated Withdrawal | 7/1/2019 |  |  | N | No
AC2-115 | Rockford |  | IL | Winnebago | Active | ComEd | 360 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2115_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-116 | Rockford II |  | IL | Winnebago | Active | ComEd | 180 | 7 | 7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2116_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AC2-117 | University Park North | University Park North Energy Center | IL | Will | Engineering and Procurement | ComEd | 606 | 46 | 46 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2117_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_117_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2017 | N/A | N/A |  |  |  | 10/1/2020 | 10/1/2020 |  | N | No
AC2-118 | Cabot-Keystone 500kV |  | PA | Armstrong | Withdrawn | APS | 1200 | 1200 | 1100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2118_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2017 | N/A | N/A |  | 8/22/2017 | Customer Initiated Withdrawal | 6/1/2021 |  |  | N | No
AC2-119 | Grandview 138kV |  | WV | Raliegh | Withdrawn | AEP | 25 | 25 | 17.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2119_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2017 | N/A | N/A |  | 9/6/2017 | Customer Milestone Not Met | 12/31/2018 |  |  | N | No
AC2-120 | Ripley 69kV | Ripley Solar | MD | Charles | Engineering and Procurement | SMECO | 27.5 | 27.5 | 10.45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2120_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2120_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2120_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2120_wmpa.pdf | Not Required | N/A | N/A |  | 3/23/2017 | N/A | N/A | 10/1/2020 |  |  | 10/1/2020 | 10/1/2020 |  | N | No
AC2-121 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2121_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2017 | N/A | N/A |  | 11/2/2017 |  | 9/15/2019 |  |  | N | No
AC2-122 | Lick Run 115kV |  | PA | Somerset | Withdrawn | PENELEC | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2122_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2017 | N/A | N/A |  | 12/10/2018 |  | 12/15/2019 |  |  | N | No
AC2-123 | Jacksons Ferry 138kV |  | VA | Wythe | Active | AEP | 75 | 75 | 44.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2123_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2017 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AC2-124 | Gunn Road 345kV |  | OH | Hardin | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2124_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 11/19/2018 |  | 12/15/2019 |  |  | N | No
AC2-125 | Ladysmith 230 kV I | Ladysmith Combustion Turbines Unit 1 | VA | Carolina | Engineering and Procurement | Dominion | 209 | 19 | 14.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2125_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_125_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AC2-126 | Ladysmith 230 kV II | Ladysmith Combustion Turbines Unit 2 | VA | Carolina | Engineering and Procurement | Dominion | 209 | 19 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2126_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_126_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A | 6/1/2021 |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AC2-127 | Ladysmith CT Unit 3 |  | VA | Carolina | Withdrawn | Dominion | 209 | 19 | 8.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2127_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-128 | Ladysmith CT Unit 4 |  | VA | Carolina | Withdrawn | Dominion | 209 | 19 | 7.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2128_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-129 | Ladysmith CT Unit 5 |  | VA | Carolina | Withdrawn | Dominion | 209 | 19 | 7.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2129_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 4/12/2019 |  | 6/1/2017 |  |  | N | No
AC2-130 | Chesterfield 230kV 5 | Chesterfield Unit 5 | VA | Chesterfield | In Service | Dominion | 370 | 14 | 13.2 | 14 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2130_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_130_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 12/31/2018 | N | No
AC2-131 | Chesterfield 230kV 7 |  | VA | Chesterfield | Withdrawn | Dominion | 246 | 14 | 14.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2131_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 12/17/2018 |  | 6/1/2017 |  |  | N | No
AC2-132 | Chesterfield 230kV 8 |  | VA | Chesterfield | Withdrawn | Dominion | 246 | 11 | 8.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2132_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2017 | N/A | N/A |  | 12/17/2018 |  | 6/1/2017 |  |  | N | No
AC2-133 | Warren County 500kV | Warren County Power Station | VA | Warren | In Service | Dominion | 1484 | 20 | 20 | 20 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2133_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_133_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/24/2017 | N/A | N/A |  |  |  | 9/30/2018 | 9/30/2018 | 9/4/2018 | N | No
AC2-134 | Hamburg 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 9 | 9 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2134_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 10/24/2017 |  | 12/31/2018 |  |  | N | Yes
AC2-135 | Double Toll Gate 34.5kV |  | VA | Clarke | Withdrawn | APS | 20 | 20 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2018 |  |  | N | No
AC2-136 | East Hagerstown 12kV | East Hagerstown Solar | MD | Washington | Engineering and Procurement | APS | 11.8 | 11.8 | 5.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2136_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2136_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2136_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 12/31/2021 |  |  | 1/7/2021 | 1/7/2021 |  | N | No
AC2-137 | Elko 34.5kV | Briel Farm Solar | VA | Henrico | Under Construction | Dominion | 18.8 | 18.8 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2137_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2137_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2137_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 9/15/2020 |  |  | 8/30/2020 | 8/30/2020 |  | N | No
AC2-138 | Northern Neck 34.5kV | Gardy's Mill Solar | PA | Westmoreland | Under Construction | Dominion | 10.8 | 10.8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2138_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2138_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2138_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A | 9/15/2020 |  |  | 8/30/2020 | 8/30/2020 |  | N | No
AC2-139 | Mantua 12kV | The Home Depot Store # 0974 | NJ | Gloucester | Withdrawn | AEC | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2139_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2139_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2139_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2017 | N/A | N/A |  | 11/12/2018 |  | 12/30/2018 | 12/30/2018 |  | Y | No
AC2-140 | DC Cook Unit 2 | DC Cook Generating Plant Unit No. 2 | MI | Berrien | Engineering and Procurement | AEP | 1220 | 28 | 38 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2140_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_140_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/27/2017 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AC2-141 | Septa 500kV |  | VA | Isle of Wight | Active | Dominion | 240 | 240 | 168.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2141_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AC2-142 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | Engineering and Procurement | APS | 664.7 | 129.7 | 129.7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_142_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A | 5/31/2021 |  |  | 5/9/2021 | 5/9/2021 |  | N | No
AC2-143 | Cranbury 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2143_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Withdrawn | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 11/13/2017 | Customer Initiated Withdrawal | 3/31/2019 |  |  | Y | Yes
AC2-144 | Newburgh 12.47kV | 59 Newburgh | NJ | Warren | Suspended | JCPL | 0.3 | 0.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2144_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2144_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 |  | Y | Yes
AC2-145 | Beach Glen 4.8kV | 94-98 Ford | NJ | Morris | Suspended | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2145_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2145_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2145_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A |  |  |  | 6/1/2018 | 6/1/2018 |  | Y | Yes
AC2-146 | Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-147 | Maryland |  | IL | Ogle | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2147_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/18/2020 |  | 5/1/2019 |  |  | N | No
AC2-148 | South Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/6/2018 |  | 5/1/2019 |  |  | N | No
AC2-149 | Glidden |  | IL | DeKalb | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 7/5/2018 |  | 5/1/2019 |  |  | N | No
AC2-150 | Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 2/6/2018 |  | 5/1/2019 |  |  | N | No
AC2-151 | Mazon |  | IL | Grundy | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 5/30/2018 |  | 5/1/2019 |  |  | N | No
AC2-152 | Pontiac Midpoint |  | IL | Livingston | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 4/10/2018 |  | 5/1/2019 |  |  | N | No
AC2-153 | Steward |  | IL | DeKalb | Withdrawn | ComEd | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2017 | N/A | N/A |  | 4/10/2018 |  | 5/1/2019 |  |  | N | No
AC2-154 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2154_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-155 | North Franklin 138kV |  | WV | Pendleton | Withdrawn | APS | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 8/16/2017 | Customer Initiated Withdrawal | 12/31/2019 |  |  | N | No
AC2-156 | Sandwich 34.5kV |  | IL | DeKalb | Active | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2156_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  |  |  | 3/31/2019 |  |  | N | No
AC2-157 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2157_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AC2-158 | Cashie-Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 65 | 65 | 32.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2158_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 11/2/2017 |  | 5/1/2019 |  |  | N | No
AC2-159 | Jackson-Woodland 115kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 80 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 11/2/2017 |  | 5/1/2019 |  |  | N | No
AC2-160 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL |  | 1.9 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2160_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/8/2017 | Customer Initiated Withdrawal | 12/1/2017 |  |  | Y | No
AC2-161 | Smithfield 34.5kV | Solidago | VA | Isle of Wight | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2161_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2161_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2161_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/5/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-162 | Old Church 34.5kV | Sweetspire | VA | Hanover | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2162_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2162_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2162_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 9/10/2018 |  | 12/31/2020 | 12/31/2020 |  | N | No
AC2-163 | Harmony Village-Dunnsville 34.5kV |  | VA | Middlesex | Withdrawn | Dominion | 17.5 | 17.5 | 12.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 3/30/2017 | Customer Initiated Withdrawal | 6/3/2019 |  |  | N | No
AC2-164 | Darby-Urbana 138kV |  | OH | Champaign | Withdrawn | Dayton | 200 | 0 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2164_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2017 | N/A | N/A |  | 2/22/2018 |  | 12/15/2019 |  |  | N | No
AC2-165 | Bremo-Powhatan 230kV |  | VA | Powhatan | Active | Dominion | 99.9 | 99.9 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2165_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AC2-166 | Waterman 34 kV |  | IL | DeKalb | Withdrawn | ComEd | 40 | 40 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2166_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 9/25/2018 |  | 12/1/2019 |  |  | N | No
AC2-167 | Boykins-Murphy 115kV |  | VA | Southampton | Withdrawn | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2019 |  |  | N | No
AC2-168 | Clinton 23kV | Gaucho Solar | PA | Washington | Engineering and Procurement | DL | 11.7 | 11.7 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2168_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2168_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2168_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A | 12/31/2020 |  |  | 3/31/2021 | 3/31/2021 |  | N | Yes
AC2-169 | Nortonville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 4.1 | 4.14 | 2.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2017 |  |  | N | No
AC2-170 | Quarryville | Keystone Solar | PA | Lancaster | Engineering and Procurement | PPL | 5 | 0 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2170_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_170_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A | 11/1/2021 |  |  | 11/1/2021 | 11/1/2021 |  | N | No
AC2-171 | Jeffersonville 69kV |  | OH | Ross | Withdrawn | Dayton | 29 | 29 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2171_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 8/23/2017 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AC2-172 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 310 | 17 | 12 | 17 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2172_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_172_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A |  |  |  | 10/1/2018 | 10/1/2018 | 5/30/2016 | N | No
AC2-173 | Wempleton-Belvidere |  | IL | Winnebago | Withdrawn | ComEd | 90 | 90 | 60.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2173_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2017 | N/A | N/A |  | 10/13/2017 |  | 11/1/2018 | 11/1/2018 |  | N | No
AC2-174 | Double Tollgate 34.5kV | Double Tollgate Solar Project | VA | Clarke | Suspended | APS | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2174_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2174_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2174_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 |  | N | No
AC2-175 | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | Suspended | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2175_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 1/31/2019 | 1/31/2019 |  | N | Yes
AC2-176 | Jay 138 kV | Bitter Ridge Wind Farm | IN | Jay | Under Construction | AEP | 130 | 130 | 16.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2176_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_176_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_176_csa.pdf | Document Posted | N/A | N/A | 6/1/2020 | 3/31/2017 | N/A | N/A | 7/1/2020 |  |  | 10/31/2020 | 10/31/2020 |  | N | No
AC2-177 | Desoto-Tanners Creek 345kV |  | IN | Henry | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2177_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AC2-178 | Ortanna 138kV |  | MD | Frederick | Withdrawn | APS | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 5/31/2019 |  |  | N | No
AC2-179 | Natrium 138kV |  | WV | Marshall | Withdrawn | AEP | 57 | 57 | 48.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2179_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 7/12/2017 | Customer Initiated Withdrawal | 6/1/2019 |  |  | N | No
AC2-180 | Babcock & Wilcox 69kV |  | VA | Campbell | Withdrawn | AEP | 12 | 12 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2180_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 11/20/2019 |  | 10/1/2018 |  |  | N | No
AC2-181 | Payne 69kV |  | IN | Randolph | Withdrawn | AEP | 49.9 | 49.9 | 18.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 11/30/2019 |  |  | N | No
AC2-182 | McConnelsburg-Texas Eastern |  | PA | Franklin | Withdrawn | PENELEC | 80 | 80 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 6/30/2018 |  |  | N | No
AC2-183 | Pepper 69kV |  | DE | Sussex | Withdrawn | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 5/1/2017 | Customer Initiated Withdrawal | 12/15/2018 |  |  | N | No
AC2-184 | Cedar Creek 138kV I |  | DE | Kent | Active | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2184_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AC2-185 | Cedar Creek 138kV II |  | DE | Kent | Active | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2185_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AC2-186 | Harrington 25kV |  | DE | Kent | Active | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2186_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AC2-187 | Harrington 69kV |  | DE | Kent | Active | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AC2-188 | South Harrington 138kV |  | DE | Kent | Active | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2188_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AC2-189 | Crisfield-Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 11.6 | 11.6 | 10.3 |  | Capacity | Generation Interconnection | Methane; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2189_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 4/17/2018 |  | 12/31/2018 |  |  | N | No
AC2-190 | Sussex-Harbeson 69kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2190_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 9/15/2017 |  | 12/31/2018 |  |  | N | No
AC2-191 | Sussex-Harbeson 69kV II |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2191_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 9/15/2017 |  | 9/28/2018 |  |  | N | No
AC2-192 | Greene-Clark 138kV |  | OH | Fayette | Withdrawn | ATSI | 56 | 56 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2192_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 8/29/2017 | Customer Initiated Withdrawal | 5/31/2019 |  |  | N | No
AC2-193 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 3/31/2017 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AC2-194 | WinFall 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 16.2 | 16.2 | 6.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2194_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  | 11/8/2017 |  | 12/22/2017 |  |  | N | No
AC2-195 | Galion-Roberts South 138kV |  | OH | Marion | Active | ATSI | 100 | 99.96 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2195_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2195_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AC2-196 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Engineering and Procurement | Dominion | 16.7 | 16.7 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2196_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2196_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2196_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2196_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 12/15/2020 |  |  | 12/15/2020 | 12/15/2020 |  | N | No
AD1-001 | Kilmer 480 v | Kilmer 480V | NJ | Union | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1001_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-002 | North Bergen I 480 v | North Bergen I 480V | NJ | Hudson | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1002_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-003 | North Bergen II 480 v | North Bergen II 480V | NJ | Bergen | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1003_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/1/2020 | 1/1/2020 |  | Y | No
AD1-004 | Paramus 480 v | Paramus 480V | NJ | Bergen | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1004_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-005 | Jackson Rd 480 v | Jackson Road 480V | NJ | Passaic | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1005_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-006 | Secaucus 480 v |  | NJ | Hudson | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 10/26/2017 |  | 12/31/2017 |  |  | Y | No
AD1-007 | Bergenfield 480 v | Bergenfield 480V | NJ | Bergen | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1007_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-008 | Sand Hills 480 v | Sand Hills 480V | NJ | Middlesex | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1008_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/21/2020 | 1/21/2020 |  | Y | No
AD1-009 | Saddle Brook 480 v | Saddle Brook 480V | NJ | Passaic | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1009_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-010 | McLean 480 v | McLean 480V | NJ | Passaic | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1010_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-011 | Athenia 480 v | Atheina 480V | NJ | Passaic | Withdrawn | PSEG | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1011_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1011_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/6/2018 |  | 1/31/2020 | 1/31/2020 |  | Y | No
AD1-012 | Cheesequake 12.5 kV |  | NJ | Middlesex | Withdrawn | JCPL | 0.2 | 0.21 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2017 | N/A | N/A |  | 6/1/2017 | Customer Milestone Not Met | 3/31/2018 |  |  | Y | No
AD1-013 | Twombly Road 138kV |  | IL | Ogle | Active | RMU | 40 | 40 | 15.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1013_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/6/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AD1-014 | N/A-N/A |  | N/A | N/A | Withdrawn | Dayton | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 4/17/2017 | N/A | N/A |  | 5/24/2017 |  | 6/1/2018 |  |  | EE | No
AD1-015 | Frazeysburg 138 kV |  | OH | Muskingum | Active | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1015_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AD1-016 | Marengo |  | IL | McHenry | Active | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1016_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/28/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AD1-017 | Smith Mountain-Bearskin 138 kV |  | VA | Pittsylvania | Active | AEP | 120 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1017_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_017_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 5/11/2017 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AD1-018 | Carlos Jct - Plaza 34 kV | Pigtoe Bobcat Solar | MD | Allegany | Suspended | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1018_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1018_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1018_wmpa.pdf | Not Required | N/A | N/A |  | 5/12/2017 | N/A | N/A | 1/1/2021 |  |  | 1/1/2021 | 1/1/2021 |  | N | No
AD1-019 | Ontario 23 kV |  | NJ | Atlantic | Active | AEC | 13.1 | 7.6 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1019_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2017 | N/A | N/A |  |  |  | 6/3/2019 |  |  | N | No
AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | Engineering and Procurement | ME | 100 | 100 | 53.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1020_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_020_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 6/7/2017 | N/A | N/A | 5/15/2021 |  |  | 5/15/2021 | 5/15/2021 |  | N | No
AD1-021 4885734 | PJM-LindenVFT |  | N/A | N/A | Confirmed | Linden VFT, LLC | 330 | 330 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4885734_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4885734_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 6/13/2017 | 1/15/2018 | 6/1/2019 | [6 empty] | FF | No
AD1-022 | Cashie-Trowbridge 230 kV |  | NC | Bertie | Active | Dominion | 80 | 80 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1022_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AD1-023 | Cashie-Trowbridge 230 kV |  | NC | Bertie | Active | Dominion | 40 | 40 | 25.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1023_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2017 | N/A | N/A |  |  |  | 6/1/2019 |  |  | N | No
AD1-024 | Davis Creek-Wilmington |  | IL | Kankakee | Withdrawn | ComEd | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/19/2017 | N/A | N/A |  | 3/1/2018 |  | 5/1/2019 |  |  | N | No
AD1-025 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 150 | 94.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1025_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_025_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 6/28/2017 | N/A | N/A |  |  |  | 9/30/2019 |  |  | N | No
AD1-026 | Shenango-Hoytdale 345 kV | Hickory Run Energy Station | PA | Lawrence | Partially in Service - Under Construction | ATSI | 1000 | 0 | 130 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_026_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 4/22/2019 | 6/28/2017 | N/A | N/A |  |  |  | 3/30/2020 | 3/30/2020 | 4/28/2020 | N | No
AD1-027 | Camden 26 kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2017 | N/A | N/A |  | 8/9/2017 | Customer Milestone Not Met | 12/31/2017 |  |  | N | No
AD1-028 | Home DepotNJ #957 - Old Bridge | Old Bridge Fuel Cell | NJ | Middlesex | Withdrawn | JCPL | 0.2 | 0.2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1028_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1028_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1028_wmpa.pdf | Not Required | N/A | N/A |  | 7/11/2017 | N/A | N/A |  | 12/18/2018 |  | 3/31/2020 | 3/31/2020 |  | N | Yes
AD1-029 | Scotland Neck-South Justice 115 kV |  | NC | Halifax | Withdrawn | Dominion | 110 | 110 | 66.3 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2017 | N/A | N/A |  | 3/6/2018 |  | 12/1/2019 |  |  | N | No
AD1-030 | Camden 26 kV II |  | NJ | Burlington | Withdrawn | PSEG | 7 | 7 | 2.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2017 | N/A | N/A |  | 8/9/2017 | Customer Milestone Not Met | 5/31/2018 |  |  | N | No
AD1-031 | Kewanee 138 kV |  | IL | Henry | Active | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1031_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2017 | N/A | N/A |  |  |  | 10/31/2021 | 10/31/2021 |  | N | No
AD1-032 4893040 | PJM-OVEC |  | N/A | N/A | Retracted |  | 25 | 25 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 7/25/2017 | 11/1/2017 | 11/1/2018 | [6 empty] | FF | No
AD1-033 | Fentress-Landstown 230 kV |  | VA | City of Chesapeake | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1033_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_033_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 7/26/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-034 | Sapony 230 kV |  | VA | Sussex | Withdrawn | Dominion | 74.9 | 74.9 | 44.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1034_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2017 | N/A | N/A |  | 3/16/2018 |  | 12/31/2020 |  |  | N | No
AD1-035 | Darby-East Liberty 69 kV |  | OH | Union | Withdrawn | Dayton | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1035_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2017 | N/A | N/A |  | 2/20/2018 |  | 10/1/2019 |  |  | N | No
AD1-036 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 35 | 35 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2017 | N/A | N/A |  | 9/15/2017 |  | 12/31/2020 |  |  | N | No
AD1-037 | Martins Creek 230 kV | Lower Mount Bethel | PA | Northampton | Partially in Service - Under Construction | PPL | 651.6 | 51.6 | 86.6 | 51.6 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1037_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_037_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/28/2017 | N/A | N/A | 9/1/2020 |  |  | 9/29/2019 | 9/29/2019 | 7/10/2019 | N | No
AD1-038 | Oliver Solar |  | NJ | Burlington | Withdrawn | PSEG | 0.3 | 0.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2017 | N/A | N/A |  | 8/25/2017 | Customer Milestone Not Met | 10/31/2019 |  |  | Y | No
AD1-039 | Kendall-Tazewell & Dresden-Mole Creek |  | IL | Grundy | Active | ComEd | 1262.7 | 102.7 | 112.7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1039_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2017 | N/A | N/A |  |  |  | 3/1/2022 | 3/1/2022 |  | N | No
AD1-040 | Mount Eagle 34.5 kV |  | VA | Albemarle | Withdrawn | Dominion | 11 | 11 | 4.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 8/10/2017 | Customer Initiated Withdrawal | 4/30/2018 |  |  | N | No
AD1-041 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1041_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  |  |  | 12/23/2019 |  |  | N | No
AD1-042 | Stuarts Draft-Waynesboro 115 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 0 | 12.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1042_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 4/10/2018 |  | 10/31/2018 |  |  | N | No
AD1-043 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 120 | 45.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1043_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AD1-044 | Oak Grove 34.5 kV I | Oak Grove I | VA | Westmoreland | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1044_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1044_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-045 | Oak Grove 34.5 kV II | Oak Grove II | VA | Westmoreland | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1045_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1045_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1045_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-046 | Oak Grove 34.5 kV III | Oak Grove III | VA | Westmoreland | Engineering and Procurement | Dominion | 11.2 | 11.2 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1046_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1046_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1046_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2017 | N/A | N/A | 6/30/2021 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-047 | Brink 115 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1047_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2017 | N/A | N/A |  | 1/30/2020 |  | 12/1/2018 |  |  | N | No
AD1-048 | Turner 34.5 kV | Turner I Solar | VA | Henrico | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1048_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1048_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1048_wmpa.pdf | Not Required | N/A | N/A |  | 8/3/2017 | N/A | N/A | 12/31/2022 | 9/5/2019 |  | 12/31/2022 | 12/31/2022 |  | N | No
AD1-049 | Culpeper 34.5 kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 20 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1049_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/3/2017 | N/A | N/A |  | 9/11/2018 |  | 12/1/2019 |  |  | N | No
AD1-050 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 45 | 45 | 29.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1050_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2017 | N/A | N/A |  | 10/15/2019 |  | 12/1/2019 |  |  | N | No
AD1-051 | Sporn South 138 kV |  | WV | Mason | Withdrawn | AEP | 30 | 30 | 18.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1051_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2017 | N/A | N/A |  | 6/4/2018 |  | 12/31/2018 |  |  | N | No
AD1-052 | Freemont Energy Center | Freemont Energy Center | OH | Sandusky | Under Construction | ATSI | 745 | 38 | 26.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1052_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_052_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/10/2017 | N/A | N/A | 10/1/2020 |  |  | 10/1/2020 | 10/1/2020 |  | N | No
AD1-053 | Plainsboro 13 kV | Plainsboro 13kV | NJ | Middlesex | Withdrawn | PSEG | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1053_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1053_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1053_wmpa.pdf | Not Required | N/A | N/A |  | 8/11/2017 | N/A | N/A |  | 3/6/2019 |  | 12/31/2018 | 12/31/2018 |  | Y | Yes
AD1-054 | Bergen 13 kV | Bergen 13kV | NJ | Bergen | In Service | PSEG | 1.5 | 1.5 | 0 | 1.5 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1054_wmpa.pdf | Not Required | N/A | N/A |  | 8/11/2017 | N/A | N/A | 12/20/2019 |  |  | 10/15/2019 | 10/15/2019 | 12/31/2019 | Y | Yes
AD1-055 | Crystal Hill-Halifax 115 kV | Halifax County Solar | VA | Halifax | Engineering and Procurement | Dominion | 64.7 | 20 | 15.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1055_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1055_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_055_csa.pdf | Document Posted | N/A | N/A |  | 8/14/2017 | N/A | N/A |  |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-056 | Hornertown-Hathaway 230 kV |  | NC | Halifax | Active | Dominion | 60 | 60 | 38.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1056_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/14/2017 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AD1-057 | Hornertown-Hathaway 230 kV |  | NC | Halifax | Active | Dominion | 34 | 34 | 22.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1057_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/14/2017 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | Engineering and Procurement | Dominion | 75.1 | 45.9 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1058_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1058_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_058_csa.pdf | Document Posted | N/A | N/A |  | 8/15/2017 | N/A | N/A |  |  |  | 11/30/2021 | 11/30/2021 |  | N | No
AD1-059 | Lakewood 230 kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 280 | 0 | 14.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1059_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_059_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/17/2017 | N/A | N/A |  |  |  | 9/30/2019 | 9/30/2019 | 5/7/2018 | N | No
AD1-060 | Mercersburg-Milnor 34 kV | Upton Solar | PA | Franklin | Engineering and Procurement | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1060_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_060_csa.pdf | Document Posted | N/A | N/A |  | 8/18/2017 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 |  | N | No
AD1-061 | McConnelsburg-Mercersburg 34 kV |  | PA | Franklin | Active | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1061_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_061_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 8/18/2017 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AD1-062 | Itasca 12.5 kV | 0 | IL | Du Page | In Service | ComEd | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1062_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1062_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1062_wmpa.pdf | Not Required | N/A | N/A |  | 8/18/2017 | N/A | N/A |  |  |  | 12/1/2018 | 12/1/2018 | 9/5/2018 | Y | No
AD1-063 | Harmony Village 34.5 kV | Puller Solar | VA | Middlesex | In Service | Dominion | 15 | 15 | 9 | 15 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1063_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1063_wmpa.pdf | Not Required | N/A | N/A |  | 8/22/2017 | N/A | N/A | 10/8/2018 |  |  | 12/1/2018 | 12/1/2018 | 10/8/2018 | N | No
AD1-064 | White Rock-Wayne 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1064_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2017 | N/A | N/A |  | 9/19/2019 |  | 12/15/2019 |  |  | N | No
AD1-065 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 175.8 | 175.8 | 25.84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1065_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 10/15/2018 |  | 12/31/2020 |  |  | N | No
AD1-066 | Crescent Ridge |  | IL | Bureau | Withdrawn | ComEd | 79.4 | 0 | 9.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1066_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 7/1/2018 |  | 10/31/2019 |  |  | N | No
AD1-067 | Mendota Hills |  | IL | Lee | Active | ComEd | 76.1 | 5.725 | 1.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1067_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 11/30/2018 |  |  | N | No
AD1-068 | Albright-Garrett 138 kV |  | WV | Preston | Active | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1068_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 12/15/2020 |  |  | N | No
AD1-069 | Iron Bridge-Donegal 138 kV |  | PA | Fayette | Withdrawn | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1069_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 4/14/2020 |  | 12/15/2020 |  |  | N | No
AD1-070 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 205 | 205 | 36 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1070_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AD1-071 | Levittown 13kV | Levittown 13kV | NJ | Burlington | Withdrawn | PSEG | 2.6 | 2.6 | 0.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1071_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1071_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1071_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2017 | N/A | N/A |  | 11/8/2018 |  | 3/31/2019 | 3/31/2019 |  | N | Yes
AD1-072 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 147 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1072_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD1-073 | Buckskin 69 kV |  | OH | Ross | Active | AEP | 120 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1073_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD1-074 | Trowbridge 230 kV |  | NC | Washington | Active | Dominion | 300 | 300 | 198.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1074_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AD1-075 | Trowbridge 230 kV |  | NC | Washington | Active | Dominion | 75 | 75 | 49.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1075_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AD1-076 | Trowbridge 230 kV |  | NC | Washington | Active | Dominion | 109 | 109 | 72.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1076_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AD1-077 | Standardsville-Pratts 34.5 kV |  | VA | Greene | Withdrawn | APS | 17 | 17 | 10.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1077_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 4/25/2018 |  | 1/31/2019 |  |  | N | No
AD1-078 | Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1078_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 6/14/2019 |  | 1/31/2019 |  |  | N | No
AD1-079 4899239 | PJM-CPLE |  | N/A | N/A | Withdrawn | Invenergy LLC |  | 130 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/1/2017 | 1/1/2021 | 1/1/2026 |  | 9/28/2017 |  |  |  |  | FF | No
AD1-080 | Endless Caverns 34.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1080_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2017 | N/A | N/A |  | 4/24/2018 |  | 1/31/2019 |  |  | N | No
AD1-081 | Beatty-London 138 kV |  | OH | Madison | Active | ATSI | 196 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1081_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/5/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD1-082 | Bakers Pond-Ivor 115kV |  | VA | Sussex | Active | Dominion | 68 | 68 | 43.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1082_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/5/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD1-083 | Page-Bethel 138 kV |  | VA | Page | Active | APS | 100 | 100 | 60.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1083_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD1-084 | Cushaw 115 kV | Cushaw Hydropower Station | VA | Bedford | In Service | Dominion | 7.5 | 5.5 | 5.5 | 5.5 | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1084_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1084_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_084_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/12/2017 | N/A | N/A |  |  |  | 1/15/2019 | 1/15/2019 | 11/12/2018 | N | No
AD1-085 | North Shenandoah-Stanley 34.5 kV | North Shenandoah-Stanley 34.5kV | VA | Page | Engineering and Procurement | APS | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1085_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1085_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1085_wmpa.pdf | Not Required | N/A | N/A |  | 9/14/2017 | N/A | N/A | 5/1/2021 |  |  | 5/1/2021 | 5/1/2021 |  | N | No
AD1-086 | N/A-N/A |  | IL | Will | Active | ComEd | 23.9 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad1086_arr-imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2017 | N/A | N/A |  |  |  | 6/20/2021 | 6/20/2021 |  | EE | No
AD1-087 | Clover-Sedge Hill 230 kV |  | VA | Halifax | Active | Dominion | 64.2 | 64.2 | 43.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1087_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_087_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/15/2017 | N/A | N/A |  |  |  | 9/2/2019 |  |  | N | No
AD1-088 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 105 | 105 | 71.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1088_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_088_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/15/2017 | N/A | N/A |  |  |  | 9/2/2019 |  |  | N | No
AD1-089 | Birdneck 34.5 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 16 | 4 | 1.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2017 | N/A | N/A |  | 11/1/2017 |  | 12/1/2020 |  |  | N | No
AD1-090 | Muskingum River 345 kV Phase I |  | OH | Washington | Withdrawn | AEP | 1260 | 1260 | 1180 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1090_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2017 | N/A | N/A |  | 8/30/2019 |  | 1/1/2022 |  |  | N | No
AD1-091 | Muskingum River 345 kV Phase II |  | OH | Washington | Withdrawn | AEP | 630 | 630 | 590 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2017 | N/A | N/A |  | 11/7/2017 |  | 1/1/2022 |  |  | N | No
AD1-092 4902076 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 105 | 105 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4902076_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4902076_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-093 4902084 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 180 | 180 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4902084_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4902084_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-094 4902085 | AMIL-PJM |  | N/A | N/A | Withdrawn | Dynegy Power Marketing LLC | 34 | 34 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4902085_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4902085_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/18/2017 | 6/1/2019 | 6/1/2024 |  | 10/30/2018 |  |  |  |  | FF | No
AD1-095 | North Salisbury 25 kV |  | MD | Wicomico | Withdrawn | DPL | 8 | 2 | 2 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1095_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2017 | N/A | N/A |  | 2/6/2018 |  | 6/1/2019 |  |  | N | No
AD1-096 | Stillman Valley 34 kV |  | IL | Ogle | Active | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1096_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2017 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AD1-097 | Linwood 230 kV II |  | PA | Delaware | Active | PECO | 919 | 67 | 34.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1097_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2017 | N/A | N/A |  |  |  | 5/31/2019 |  |  | N | No
AD1-098 | Dixon-McGirr |  | IL | Lee | Active | ComEd | 100 | 100 | 57.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1098_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2017 | N/A | N/A |  |  |  | 12/1/2020 |  |  | N | No
AD1-099 | South Bend 500 kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 720 | 0 | 70 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1099_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_099_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 9/1/2019 | 9/1/2019 | 9/20/2018 | N | No
AD1-100 | Wilton Center-Loretto |  | IL | Ford | Active | ComEd | 850 | 850 | 150 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1100_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AD1-101 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 49.9 | 18.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1101_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 10/31/2020 |  |  | N | No
AD1-102 | Wurno-Claytor Lake 138 KV |  | VA | Pulaski | Active | AEP | 180 | 180.01 | 23.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/21/2017 | N/A | N/A |  |  |  | 12/18/2020 |  |  | N | No
AD1-103 | Beaver-Davis Besse 345 kV II |  | OH | Huron | Active | ATSI | 500.4 | 500.4 | 65.052 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1103_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  |  |  | 12/18/2020 |  |  | N | No
AD1-104 | Marysville-Sorenson 765 kV II |  | OH | Van Wert | Withdrawn | AEP | 403.2 | 403.2 | 52.42 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  | 3/27/2020 |  | 12/17/2021 |  |  | N | No
AD1-105 | Kings Dominion DP 115 kV |  | VA | King William | Active | Dominion | 77 | 77 | 45.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1105_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD1-106 | North Waldo-Wild Creek 138 kV |  | OH | Marion | Active | AEP | 60 | 60 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1106_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  |  |  | 6/12/2019 |  |  | N | No
AD1-107 | McGuire Battery Storage |  | NJ | Burlington | Withdrawn | JCPL | 1.3 | 1.25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2017 | N/A | N/A |  | 10/2/2017 |  | 8/1/2018 | 8/1/2018 |  | Y | No
AD1-108 | Grover 34 kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 9/17/2018 | 9/17/2018 | 7/16/2018 | N | No
AD1-109 | Canton 34.5 kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1109_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 5/10/2018 | N | No
AD1-110 | North Meshoppen 34.5 kV | Roundtop Energy Projects | PA | Susquehanna | In Service | PENELEC | 21.4 | 1.5 | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_110_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 8/9/2018 | 8/9/2018 | 6/22/2018 | N | No
AD1-111 | Woolrich 12.47 kV |  | PA | Clinton | Withdrawn | PPL | 4.1 | 4.125 | 4.125 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2017 | N/A | N/A |  | 1/3/2018 |  | 12/31/2018 |  |  | N | Yes
AD1-112 | Davis Creek 138 kV |  | IL | Kankakee | Withdrawn | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2017 | N/A | N/A |  | 10/2/2017 |  | 9/30/2020 |  |  | N | No
AD1-113 | Raritan River 230 kV | Woodbridge Energy Center | NJ | Middlesex | Suspended | JCPL | 820 | 35 | 75 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_113_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2017 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 |  | N | No
AD1-114 | Kelson Ridge 230kV | CPV Maryland | MD | Charles | In Service | PEPCO | 820 | 75 | 75 | 50 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_114_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/26/2017 | N/A | N/A |  |  |  | 5/31/2021 | 5/31/2021 | 3/28/2019 | N | No
AD1-115 | Mountain Run-Mitchell 115 kV |  | VA | Culpeper | Active | Dominion | 150 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1115_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2017 | N/A | N/A |  |  |  | 10/2/2019 |  |  | N | No
AD1-116 | Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1116_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-117 | Maryland 138 kV |  | IL | Ogle | Withdrawn | ComEd | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1117_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2017 | N/A | N/A |  | 12/11/2018 |  | 7/1/2020 |  |  | N | No
AD1-118 | Lemoyne |  | OH | Wood | Active | ATSI | 710 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1118_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2017 | N/A | N/A |  |  |  | 9/1/2018 |  |  | N | No
AD1-119 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 49.9 | 18.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1119_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 10/31/2020 |  |  | N | No
AD1-120 4904819 | DUK-PJM |  | N/A | N/A | Withdrawn | Cube Hydro Partners, LLC | 109 | 109 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4904819_ltf1.pdf |  |  |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/28/2017 | 6/1/2019 | 6/1/2024 |  | 10/3/2018 |  |  |  |  | FF | No
AD1-121 4904949 | CPLE-PJM |  | N/A | N/A | Withdrawn | Cube Hydro Partners, LLC | 109 | 109 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4904949_ltf1.pdf |  | Withdrawn |  | Withdrawn |  |  |  | N/A | N/A | [5 empty] | 9/28/2017 | 6/1/2019 | 6/1/2024 |  | 10/3/2018 |  |  |  |  | FF | No
AD1-122 4904950 | PJM-DUK |  | N/A | N/A | Withdrawn | Invenergy LLC | 130 | 130 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4904950_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4904950_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 9/28/2017 | 1/1/2021 | 1/1/2026 |  | 10/26/2018 |  |  |  |  | FF | No
AD1-123 | Welco 34.5 kV |  | VA | Halifax | Withdrawn | Dominion | 10 | 10 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1123_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 6/6/2018 |  | 12/31/2018 |  |  | N | Yes
AD1-124 | Lynbrook 12 kV |  | VA | Campbell | Withdrawn | AEP | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 9/10/2019 |  | 12/31/2019 |  |  | N | No
AD1-125 | Baker 138 kV |  | WV | Hardy | Active | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1125_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-126 | W. DeKalb-Waterman |  | IL | DeKalb | Withdrawn | ComEd | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1126_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 7/5/2018 |  | 12/31/2020 |  |  | N | No
AD1-127 | Cambria Slope 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 325 | 235 | 235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1127_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  | 5/8/2018 |  | 9/1/2020 |  |  | N | No
AD1-128 | Modoc 138 kV |  | IN | Randolph | Active | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1128_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AD1-129 | Belvidere 34 kV |  | IL | Boone | Active | ComEd | 12.5 | 12.5 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1129_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 6/30/2019 |  |  | N | Yes
AD1-130 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 170 | 170 | 115 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1130_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad1_130_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/28/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD1-131 | Sedge Hill-Person 230 kV |  | VA | Halifax | Active | Dominion | 70 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1131_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 3/7/2020 |  |  | N | No
AD1-132 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/15/2019 |  |  | N | No
AD1-133 | Pontiac MidPoint-Dresden |  | IL | Grundy | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD1-134 | JK Smith 138 kV |  | KY | Unknown | Withdrawn | EKPC | 73 | 73 | 72.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1134_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 4/22/2019 |  | 7/1/2020 |  |  | N | No
AD1-135 | Clinton 23 kV II | Gaucho Solar | PA | Washington | Engineering and Procurement | DL | 20 | 8.3 | 3.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1135_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1135_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1135_wmpa.pdf | Not Required | N/A | N/A |  | 9/29/2017 | N/A | N/A | 12/31/2020 |  |  | 3/31/2021 | 3/31/2021 |  | N | No
AD1-136 | South Bethel-Brown 69 kV | Nestlewood Solar | OH | Clermont | Engineering and Procurement | DEOK | 80 | 10 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1136_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1136_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_136_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 5/31/2019 |  |  | N | No
AD1-137 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1137_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 1/16/2020 |  | 12/18/2020 |  |  | N | No
AD1-138 | Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 100 | 100 | 65.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/1/2020 |  |  | N | No
AD1-139 | Mullin-Grant Tap 138 kV |  | IN | Madison | Withdrawn | AEP | 100 | 99.9968 | 68.9978 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 10/2/2017 |  | 12/1/2020 |  |  | N | No
AD1-140 | Greene-Clark 138 kV |  | OH | Greene | Active | ATSI | 175 | 175 | 95.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1140_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/Delay email sent 12/8/19 | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 5/29/2020 |  |  | N | No
AD1-141 | S. Lucasville-Wakefield 138 kV |  | OH | Scioto | Withdrawn | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1141_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  | 3/27/2020 |  | 12/1/2019 |  |  | N | No
AD1-142 | Milan 34.5 kV | Milan Energy | PA | Bradford | In Service | PENELEC | 21 | 1.1 | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_142_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 7/9/2018 | 7/9/2018 | 4/24/2018 | N | No
AD1-143 | Hauto-Siegfried 69 kV | Broad Mountain | PA | Carbon | Suspended | PPL | 90 | 90 | 11.84 |  | Capacity | Generation Interconnection | Wind; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1143_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1143_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_143_csa.pdf | Document Posted | N/A | N/A |  | 9/29/2017 | N/A | N/A |  |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-144 | Kings Fork 34.5 kV | TWE Myrtle Solar Project | VA | City of Suffolk | Engineering and Procurement | Dominion | 15 | 15 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1144_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1144_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1144_wmpa.pdf | Not Required | N/A | N/A | 4/15/2020 | 9/30/2017 | N/A | N/A | 5/5/2020 |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AD1-145 | Laurel-Dupont Seaford 69 kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | 9.6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1145_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 11/14/2018 |  | 7/31/2019 |  |  | N | No
AD1-146 | Millsboro 25 kV |  | DE | Sussex | Withdrawn | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1146_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/16/2018 |  | 6/30/2019 |  |  | N | No
AD1-147 | Martinsville-Wilmington 69 kV |  | OH | Clinton | Withdrawn | Dayton | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/3/2017 |  | 9/1/2020 |  |  | N | No
AD1-148 | Brokaw-Lanesville |  | IL | Logan | Active | ComEd | 185 | 0 | 36.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 11/30/2018 |  |  | N | No
AD1-149 | Carbondale 69 kV |  | WV | Kanawha | Withdrawn | AEP | 19.9 | 19.9 | 8.33 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 6/18/2018 |  | 6/30/2019 |  |  | N | No
AD1-150 | Kankakee 34.5 kV |  | IL | Kankakee | Withdrawn | ComEd | 19.9 | 19.9 | 3.98 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/5/2017 |  | 7/31/2019 |  |  | N | No
AD1-151 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1151_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1151_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-152 | Clover-Sedge Hill 230 kV |  | VA | Halifax | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1152_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-153 | Walker Mill 12 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.8 | 2.76 | 1.0488 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1153_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 12/24/2018 |  | 9/1/2018 |  |  | N | Yes
AD1-154 | Timblin 34.5 kV |  | PA | Jefferson | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1154_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD1-155 | Meadow Brook-Strasburg 138 kV |  | VA | Frederick | Active | APS | 75 | 75 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1155_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD1-156 | Poe 34.5 kV | Rives Road Solar | VA | Prince George | Withdrawn | Dominion | 19.7 | 19.7 | 11.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1156_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1156_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1156_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 6/1/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AD1-157 | South Creek 34.5 kV | Spout Springs Solar | VA | Appomattox | Engineering and Procurement | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1157_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1157_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1157_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 6/30/2021 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AD1-158 | Old Chapel-Millville 138kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/6/2017 |  | 6/30/2019 |  |  | N | No
AD1-159 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  | 10/6/2017 |  | 6/30/2019 |  |  | N | No
AD1-160 | Pamplin 34.5 kV | Pamplin Solar | VA | Appomattox | Withdrawn | Dominion | 15.7 | 15.7 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1160_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1160_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1160_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2017 | N/A | N/A | 6/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AD1-161 | Stonewall-Long Mountain 69 kV |  | VA | Appomattox | Active | AEP | 55 | 55 | 30.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1161_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-001 | Grangston 138 kV |  | WV | Wayne | Active | AEP | 319 | 19 | 19 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2001_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2017 | N/A | N/A |  |  |  | 2/1/2018 |  |  | N | No
AD2-002 | Franklin-Emerald 25 kV | Evergreene Energy | PA | Greene | Engineering and Procurement | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2002_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2002_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2002_wmpa.pdf | Not Required | N/A | N/A |  | 10/17/2017 | N/A | N/A | 12/31/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AD2-003 4907750 | PJM-OVEC |  | N/A | N/A | Withdrawn | Macquarie Energy, LLC | 41 | 41 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4907750_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 10/24/2017 | 2/1/2018 | 2/1/2019 |  | 12/27/2017 |  |  |  |  | FF | No
AD2-004 | Steel-Vienna 230 kV |  | MD | Caroline | Withdrawn | DPL | 600 | 600 | 600 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2004_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/26/2017 | N/A | N/A |  | 9/19/2018 |  | 12/1/2022 |  |  | N | No
AD2-005 | Nottingham-Freebyrd 138 kV |  | OH | Harrison | Active | AEP | 1085 | 35 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2005_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2017 | N/A | N/A |  |  |  | 10/21/2020 |  |  | N | No
AD2-006 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 7.5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2017 | N/A | N/A |  | 11/29/2017 |  | 11/30/2018 |  |  | N | No
AD2-007 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 7.6 | 7.6 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2007_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/4/2017 | N/A | N/A |  |  |  | 11/1/2019 |  |  | N | No
AD2-008 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 52.1 | 52.1 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2008_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2008_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/4/2017 | N/A | N/A |  |  |  | 9/30/2019 |  |  | N | No
AD2-009 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 70 | 48.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2009_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2017 | N/A | N/A |  |  |  | 6/30/2019 |  |  | N | No
AD2-010 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2010_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-011 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-012 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2012_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  | 11/9/2018 |  | 6/1/2019 |  |  | N | No
AD2-013 | Earleys 115 kV |  | NC | Hertford | Withdrawn | Dominion | 74.9 | 74.9 | 52.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2017 | N/A | N/A |  | 11/30/2017 |  | 12/31/2020 |  |  | N | No
AD2-014 | Steubenville-Tidd 138 kV |  | OH | Jefferson | Active | AEP | 53.3 | 53.325 | 22.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2014_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2017 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AD2-015 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2017 | N/A | N/A |  | 1/16/2018 |  | 12/18/2020 |  |  | N | No
AD2-016 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 274 | 127 | 62.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2016_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2017 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-017 | Buckskin 69 kV |  | OH | Ross | Withdrawn | AEP | 120 | 100 | 65.59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2017 | N/A | N/A |  | 1/18/2018 |  | 12/31/2020 |  |  | N | No
AD2-018 | N/A-N/A |  | NJ | Unknown | Engineering and Procurement | PSEG | 248 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad2018_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ad2018_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ad2_018_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 |  | EE | No
AD2-019 | N/A-N/A |  | NJ | Unknown | Engineering and Procurement | PSEG | 1399 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ad2019_arr-imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/arr-facilities-studies/ad2019_arr-fac.pdf | Document Posted | N/A |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-csa-studies/ad2_019_arr-csa.pdf | Document Posted | N/A | N/A |  | 11/14/2017 | N/A | N/A | 2/1/2021 |  |  | 2/28/2021 | 2/28/2021 |  | EE | No
AD2-020 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 100 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2020_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2017 | N/A | N/A |  |  |  | 12/1/2020 |  |  | N | No
AD2-021 | Elko 34.5 kV | Briel Farm Solar | VA | Henrico | Under Construction | Dominion | 20 | 1.2 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2021_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2021_wmpa.pdf | Not Required | N/A | N/A |  | 11/29/2017 | N/A | N/A | 9/15/2020 |  |  | 8/30/2020 | 8/30/2020 |  | N | No
AD2-022 | East Danville-Roxborough 230 kV |  | VA | Pittsylvania | Active | AEP | 96 | 96 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2022_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD2-023 | E. Danville-Roxborough 230 kV |  | VA | Pittsylvania | Active | AEP | 54 | 54 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2023_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2017 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD2-024 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2024_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2017 | N/A | N/A |  | 9/17/2018 |  | 6/1/2019 |  |  | N | No
AD2-025 | Hillsborough 13 kV | Hillsborough Storage | NJ | Somerset | Engineering and Procurement | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2025_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2025_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2025_wmpa.pdf | Not Required | N/A | N/A |  | 12/4/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | Y | No
AD2-026 | East Flemington-Frenchtown 34.5 kV II | Quakertown Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2026_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_026_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_026_csa.pdf | Document Posted | N/A | N/A |  | 12/6/2017 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 | 5/3/2019 | N | No
AD2-027 | Camden Switch 26 kV | Taylors Lane Solar | NJ | Burlington | In Service | PSEG | 10 | 10 | 3.8 | 10 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2027_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2027_wmpa.pdf | Not Required | N/A | N/A |  | 12/7/2017 | N/A | N/A |  |  |  | 2/15/2019 | 2/15/2019 | 3/22/2019 | N | No
AD2-028 | McConnellsburg-Texas Eastern |  | PA | Franklin | Withdrawn | APS | 150 | 150 | 76.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2028_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/12/2017 | N/A | N/A |  | 8/20/2018 |  | 6/30/2019 |  |  | N | No
AD2-029 | Dorchester County 12kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/13/2017 | N/A | N/A |  | 9/20/2018 |  | 12/31/2019 |  |  | N | No
AD2-030 | Wan 34.5 kV | Gloucester Solar | VA | Gloucester | In Service | Dominion | 19.8 | 19.8 | 13.1 | 19.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2030_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2030_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2030_wmpa.pdf | Not Required | N/A | N/A |  | 12/13/2017 | N/A | N/A |  |  |  | 5/21/2019 | 5/21/2019 | 3/22/2019 | N | No
AD2-031 | Martinsville-Wilmington 69 kV |  | OH | Clinton | Active | Dayton | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2031_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2017 | N/A | N/A |  |  |  | 9/1/2019 |  |  | N | No
AD2-032 | Morrisville 230 kV |  | VA | Accomack | Withdrawn | Dominion | 150 | 150 | 83.8495 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2017 | N/A | N/A |  | 1/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-033 | Chase City-Lunenburg 115 kV |  | VA | Lunenburg | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2033_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2017 | N/A | N/A |  |  |  | 10/31/2020 |  |  | N | No
AD2-035 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 630 | 38.9 | 14 | 38.9 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_035_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/12/2018 | N/A | N/A |  |  |  | 12/1/2019 |  | 12/1/2019 | N | No
AD2-036 | Jacksonville-Renaker 138kV IV |  | KY | Harrison | Withdrawn | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2036_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2018 | N/A | N/A |  | 8/19/2019 |  | 6/1/2020 |  |  | N | No
AD2-037 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 7.5 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2018 | N/A | N/A |  |  |  | 6/30/2019 |  |  | N | No
AD2-038 | Powerton |  | IL | Lasalle | Active | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2038_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AD2-039 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Engineering and Procurement | Dominion | 90 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2039_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2039_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_039_csa.pdf | Document Posted | N/A | N/A |  | 1/19/2018 | N/A | N/A |  |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AD2-040 | Showalter 34.5 kV |  | MD | Washington | Withdrawn | APS | 18.4 | 0 | 4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2040_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2018 | N/A | N/A |  | 8/20/2018 |  | 12/31/2018 |  |  | N | No
AD2-041 | Normandy |  | IL | Whiteside | Withdrawn | ComEd | 17 | 17 | 11.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2018 | N/A | N/A |  | 2/20/2018 |  | 12/31/2019 |  |  | N | No
AD2-042 | Camden Switch 26 kV II | Pennsauken Solar II | NJ | Camden | In Service | PSEG | 13.2 | 13.2 | 5 | 13.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2042_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2042_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2042_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 10/4/2019 |  |  | 9/10/2019 | 9/10/2019 | 10/4/2019 | N | No
AD2-043 | Crystal Hill 115 kV |  | VA | Halifax | Withdrawn | Dominion | 65.5 | 65.5 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2043_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2018 | N/A | N/A |  | 12/20/2019 |  | 1/31/2019 |  |  | N | No
AD2-044 | Northern Neck 34.5 kV | Gardy's Mill Solar | VA | Westmoreland | Under Construction | Dominion | 14 | 3.2 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2044_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2044_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2044_wmpa.pdf | Not Required | N/A | N/A |  | 1/29/2018 | N/A | N/A | 9/15/2020 |  |  | 8/30/2020 |  |  | N | No
AD2-045 | Price Solar |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 20 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2045_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2018 | N/A | N/A |  | 3/29/2019 |  | 10/1/2019 |  |  | N | No
AD2-046 | Boydton DP-Kerr Dam 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2046_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2018 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AD2-047 | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AD2-048 | Cynthia-Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 70 | 70 | 46.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2048_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD2-049 | Newport News 23kV | Newport News Battery Storage | VA | City of Newport News | Withdrawn | Dominion | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2049_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2049_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2049_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2018 | N/A | N/A | 4/30/2021 | 10/21/2019 |  | 4/30/2021 | 4/30/2021 |  | N | No
AD2-050 | Buxmont 69kV |  | PA | Bucks | Withdrawn | PPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 3/2/2018 |  | 12/31/2019 |  |  | N | No
AD2-051 | Earleys – Northampton 230kV |  | NC | Hertford | Active | Dominion | 74.9 | 74.9 | 52.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2051_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-052 | Laurel Lake Solar |  | NJ | Salem | Withdrawn | AEC | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2052_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2018 | N/A | N/A |  | 5/1/2019 |  | 6/30/2019 |  |  | N | No
AD2-053 | N/A-N/A |  | OH | Adams | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2018 | N/A | N/A |  | 9/19/2018 |  | 6/1/2019 |  |  | EE | No
AD2-054 | N/A-N/A |  | IN | St. Joseph | Withdrawn | AEP | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2018 | N/A | N/A |  | 5/2/2019 |  |  |  |  | EE | No
AD2-055 | Moshannon-East Towanda 230 kV |  | PA | Clinton | Active | PENELEC | 548 | 44 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2055_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/9/2018 | N/A | N/A |  |  |  | 10/1/2020 |  |  | N | No
AD2-056 | Charles City |  | VA | Henrico | Withdrawn | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2018 | N/A | N/A |  | 3/7/2018 |  | 12/31/2020 |  |  | N | No
AD2-057 | Highland-Hanna 345kV |  | OH | Trumbull | Withdrawn | ATSI | 940 | 940 | 850 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2057_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/20/2018 | N/A | N/A |  | 9/26/2018 |  | 10/16/2020 |  |  | N | No
AD2-058 | St. Barnabas 13 kV |  | MD | Prince George's | Active | PEPCO | 5.6 | 5.6 | 2.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2058_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/20/2018 | N/A | N/A |  |  |  | 9/30/2019 |  |  | N | No
AD2-059 | Chapel Street 138 kV |  | DE | New Castle | Active | DPL | 1 | 0.993 | 0.24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2059_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2018 | N/A | N/A |  |  |  | 10/1/2018 |  |  | N | No
AD2-060 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 70 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2060_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-061 | Spring Run 23 kV |  | PA | Adams | Withdrawn | PENELEC | 7.4 | 7.4 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2018 | N/A | N/A |  | 4/25/2018 |  | 6/1/2020 |  |  | N | No
AD2-062 | Roxbury-Greene 138 kV |  | PA | Franklin | Active | PENELEC | 80.3 | 80.3 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2062_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AD2-063 | Central-Chase City 115kV |  | VA | Charlotte | Active | Dominion | 149.5 | 149.5 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2063_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2018 | N/A | N/A |  |  |  | 3/31/2021 |  |  | N | No
AD2-064 | Tansboro 12kV |  | NJ | Camden | Active | AEC | 1.3 | 1.26 | 0.53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2064_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2064_fac.pdf | Document Posted | N/A |  | N/A |  | Not Required | N/A | N/A |  | 2/27/2018 | N/A | N/A |  |  |  | 12/1/2019 |  |  | N | No
AD2-065 | Berlin 12kV | Kettle Run | NJ | Burlington | Engineering and Procurement | AEC | 2.6 | 2.57 | 1.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2065_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2065_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2065_wmpa.pdf | Not Required | N/A | N/A |  | 2/27/2018 | N/A | N/A |  |  |  | 5/20/2022 | 5/20/2022 |  | N | No
AD2-066 | Mazon-Crescent Ridge |  | IL | Grundy | Active | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AD2-067 | Centerburg 138kV |  | OH | Licking | Active | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2067_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AD2-068 | Everetts-Greenville 230kV |  | NC | Pitt | Withdrawn | Dominion | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2068_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-069 | Cox's Corner 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 3 | 3 | 2.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2069_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2018 | N/A | N/A |  | 6/21/2019 |  | 9/30/2019 |  |  | N | No
AD2-070 | Gilbert-Morris Park 34.5kV | Milford Solar Farm | NJ | Hunterdon | In Service | JCPL | 7.5 | 7.5 | 3.2 | 7.5 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2070_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_070_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_070_csa.pdf | Document Posted | N/A | N/A |  | 3/12/2018 | N/A | N/A | 9/18/2019 |  |  | 6/1/2020 | 6/1/2020 | 9/18/2019 | N | No
AD2-071 | Strawton-Pipe Creek 138 kV |  | IN | Madison | Active | AEP | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2071_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AD2-072 | Van Arsdell-Mercer Industrial 69kV |  | KY | Unknown | Active | EKPC | 95 | 95 | 63.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2072_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AD2-073 | Sanders DP 230 kV |  | VA | Westmoreland | Active | Dominion | 19.9 | 19.92 | 13.32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2073_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  | Not Required | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/15/2019 |  |  | N | No
AD2-074 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 86 | 86 | 32.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2074_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AD2-075 | Segreto 345kV |  | MI | Van Buren | Active | AEP | 1340 | 285 | 145 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2075_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2018 | N/A | N/A |  |  |  | 5/4/2020 |  |  | N | No
AD2-076 | Centreville 69 kV |  | MD | Queen Anne's | Active | DPL | 49 | 49 | 18.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2076_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2018 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AD2-077 | Buxmont 69 kV |  | PA | Bucks | Active | PPL | 200 | 200 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2077_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2018 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AD2-078 | N. Haverhill 69kV |  | OH | Scioto | Active | AEP | 95 | 20 | 40 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2078_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AD2-079 | Capitol Ave 34.5kV |  | IN | St. Joseph | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2079_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad2_079_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 3/19/2018 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AD2-080 | N/A-N/A |  | IN | St. Joseph | Active | AEP | 309 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | EE | No
AD2-081 | Banister 34.5kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 9/13/2018 |  | 9/30/2019 |  |  | N | No
AD2-082 | Pamplin 34.5kV |  | VA | Prince Edward | Withdrawn | Dominion | 15 | 15 | 10.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2082_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/5/2019 |  | 9/30/2019 |  |  | N | No
AD2-083 | Larrabee 230kV |  | NJ | Monmouth | Active | JCPL | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ad2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ad2083_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AD2-084 | Cardiff 230kV |  | NJ | Atlantic | Active | AEC | 1100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ad2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/merch-impact-studies/ad2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AD2-085 | Myrtle-Windsor DP 115kV |  | VA | Isle of Wight | Active | Dominion | 51 | 51 | 19.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2085_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AD2-086 | Marysville-East Lima 345kV |  | OH | Hardin | Active | AEP | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2086_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-087 | Randolf 138kV |  | OH | Darke | Withdrawn | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2087_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 12/9/2019 |  | 12/31/2020 |  |  | N | No
AD2-088 | Laurel 69kV |  | DE | Sussex | Withdrawn | DPL | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2088_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 2/6/2020 |  | 12/31/2020 |  |  | N | No
AD2-089 | Anaconda-Tar River 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/Delay email sent 2/82/19; 3/31/19 | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 12/9/2019 |  | 12/31/2020 |  |  | N | No
AD2-090 | Handsom - Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2020 |  |  | N | No
AD2-091 | Hardin Tap 345kV |  | OH | Hardin | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-092 | Marysville 345kV |  | OH | Union | Active | AEP | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-093 | Marysville 345kV |  | OH | Union | Active | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2093_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-094 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2020 |  |  | N | No
AD2-095 | Todd 69 kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2021 |  |  | N | No
AD2-096 | Marysville 345kV |  | OH | Union | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2096_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2096_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-097 | Spruance NUG 230kV | Spruance Operating Services LLC | VA | Henrico | In Service | Dominion | 66 | 66 | 11 | 66 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2097_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_097_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/21/2018 | N/A | N/A | 8/1/2019 |  |  | 5/1/2019 | 5/1/2019 | 10/1/2019 | N | No
AD2-098 4934836 | PJM-WEC |  | N/A | N/A | Confirmed | WPPI Energy |  | 4 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4934836_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/4934836_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/21/2018 | 9/1/2018 | 6/1/2037 | [6 empty] | FF | No
AD2-099 4934920 |  |  | N/A | N/A | Withdrawn | Cypress Creek Renewables, LLC |  | 75 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4934920_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/21/2018 | 6/1/2021 | 6/1/2026 |  | 6/15/2018 |  |  |  |  | FF | No
AD2-100 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AD2-101 | Bloom-Davis Creek |  | IL | Will | Withdrawn | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2101_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 5/1/2019 |  | 12/31/2021 |  |  | N | No
AD2-102 | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2102_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AD2-103 | Crane CT 1 115kV |  | MD | Baltimore County | Active | BGE | 14 | 14 | 14 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2103_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No
AD2-104 | Crane CT 2-3-4 115kV |  | MD | Baltimore County | Active | BGE | 144.6 | 144.6 | 144.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2104_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No
AD2-105 | Leslie-Stinnett 161KV |  | KY | Leslie | Withdrawn | AEP | 100 | 100 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2105_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AD2-106 | Bulan 69kV |  | KY | Perry | Withdrawn | AEP | 80 | 80 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2106_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AD2-107 | Chavies-Bonnyman 69kV |  | KY | Perry | Withdrawn | AEP | 55 | 55 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2107_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2020 |  | 12/31/2021 |  |  | N | No
AD2-108 | Springdale CT II 138kV | Springdale | PA | Allegheny | In Service | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2108_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_108_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 | 7/10/2019 | N | No
AD2-109 | Gans 138kV |  | PA | Fayette | Withdrawn | APS | 100 | 4 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2109_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 7/12/2019 |  | 5/31/2022 |  |  | N | No
AD2-110 | Guilford 138kV |  | PA | Franklin | Active | APS | 100 | 12 | 12 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2110_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AD2-111 | Hunlock 69 kV |  | PA | Luzerne | Withdrawn | AEP | 50 | 6 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 3/28/2018 |  | 5/31/2022 |  |  | N | No
AD2-112 | Springdale CC II 138kV |  | PA | Allegheny | Active | APS | 610 | 20 | 50.4 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2112_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AD2-113 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | Engineering and Procurement | APS | 790 | 70 | 60.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2113_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_113_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A | 6/1/2023 |  |  | 6/1/2023 | 6/1/2023 |  | N | No
AD2-114 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | Engineering and Procurement | APS | 1200 | 410 | 400 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2114_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_114_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_114_csa.pdf | Document Posted | N/A | N/A |  | 3/22/2018 | N/A | N/A | 6/1/2023 |  |  | 6/1/2023 | 6/1/2023 |  | N | No
AD2-115 | Lyons-Moselem 69kV |  | PA | Berks | Active | ME | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2115_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 4/1/2020 |  |  | N | No
AD2-116 | Hokes-Grantley 69 kV |  | PA | York | Active | ME | 20 | 20 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2116_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 4/1/2020 |  |  | N | No
AD2-117 | Bernville 69kV |  | PA | Berks | Withdrawn | ME | 15 | 15 | 7.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2117_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 5/8/2019 |  | 4/1/2020 |  |  | N | No
AD2-118 | Laurel 12 kV |  | DE | Sussex | Withdrawn | DPL | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 3/28/2018 |  | 4/1/2020 |  |  | N | No
AD2-119 | Milesburg-Dale Summit 230kV |  | PA | Centre | Withdrawn | APS | 75 | 75 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2119_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 9/11/2018 |  | 12/15/2021 |  |  | N | No
AD2-120 | Shenango-McDowell 138kV |  | PA | Mercer | Withdrawn | ATSI | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2120_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 6/19/2019 |  | 12/15/2020 |  |  | N | No
AD2-121 | Oyster Creek 230 kV I |  | NJ | Ocean | Withdrawn | JCPL | 530 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AD2-122 | Oyster Creek 230 kV II |  | NJ | Ocean | Withdrawn | JCPL | 635 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/11/2018 |  | 6/1/2024 |  |  | S | No
AD2-123 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 94 | 94 | 68.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2018 |  | 6/1/2021 |  |  | N | No
AD2-124 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 20 | 20 | 14.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2018 | N/A | N/A |  | 4/16/2018 |  | 6/1/2021 |  |  | N | No
AD2-125 | Myersdale Storage |  | PA | Somerset | Withdrawn | PENELEC | 68 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-126 | Backbone Mountain 138 kV |  | WV | Tucker | Withdrawn | APS | 90 | 90 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/27/2018 |  | 12/31/2020 |  |  | N | No
AD2-127 | East Carbondale-Lackawanna 69 kV |  | PA | Wayne | Withdrawn | PPL | 89 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-128 | Mill Run 25 kV |  | PA | Fayette | Withdrawn | APS | 15 | 15 | 3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/27/2018 |  | 12/31/2020 |  |  | N | No
AD2-129 | Somerset Storage |  | PA | Somerset | Withdrawn | PENELEC | 18 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2020 |  |  | N | No
AD2-130 | ESS-J338 |  | IL | Will | Withdrawn | ComEd | 13.6 | 0 | 4.3 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2130_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 12/14/2018 |  | 9/14/2018 |  |  | N | No
AD2-131 | Latham Kincaid |  | IL | Christian | Active | ComEd | 50 | 50 | 8.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2131_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AD2-132 | Olive-Reynolds 345kV |  | IN | Pulaski | Withdrawn | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2132_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/10/2019 |  | 12/31/2020 |  |  | N | No
AD2-133 | Eagle Valley 115kV |  | PA | Centre | Active | PENELEC | 150.3 | 100.33 | 18 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-134 | Shady Oaks |  | IL | Lee | Active | ComEd | 227 | 117.5 | 22.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2134_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 10/31/2021 | 10/31/2021 |  | N | No
AD2-135 | Williamstown 12kV |  | NJ | Gloucester | Active | AEC | 1.6 | 1.62 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2135_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AD2-136 | Melmore Tap 138kV |  | OH | Seneca | Active | AEP | 360 | 360 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2136_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AD2-137 | Loretto-Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2137_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-138 | Olive-Reynolds 345kV |  | IN | Warren | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2138_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-139 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 200 | 200 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/31/2018 |  | 12/31/2020 |  |  | N | No
AD2-140 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2140_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-141 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 26.25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2141_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-142 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-143 | Richland Jct-East Leipsic 138kV |  | IN | Randolph | Withdrawn | AEP | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2143_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/7/2019 |  | 12/31/2020 |  |  | N | No
AD2-144 | Marysville 345kV |  | IN | Randolph | Withdrawn | AEP | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2144_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 1/7/2019 |  | 12/31/2020 |  |  | N | No
AD2-145 | Star 345kV |  | IN | Randolph | Withdrawn | ATSI | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2145_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 9/4/2018 |  | 12/31/2020 |  |  | N | No
AD2-146 | Wiley 138 kV |  | OH | Butler | Withdrawn | DEOK | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 3/31/2018 |  | 12/31/2020 |  |  | N | No
AD2-147 | South Charleston 345kV |  | OH | Butler | Withdrawn | Dayton | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2147_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 9/24/2019 |  | 12/31/2020 |  |  | N | No
AD2-148 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2148_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-149 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2149_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-150 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2150_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/28/2019 |  | 12/31/2020 |  |  | N | No
AD2-151 | Hillcrest 345kV |  | OH | Muskingum | Withdrawn | DEOK | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2151_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2151_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 7/26/2019 |  | 12/31/2020 |  |  | N | No
AD2-152 | Pocono 230 kV |  | PA | Wayne | Withdrawn | PPL | 150 | 150 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-153 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2153_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/19/2019 |  | 12/31/2020 |  |  | N | No
AD2-154 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2154_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/17/2019 |  | 12/31/2020 |  |  | N | No
AD2-155 | Brokaw-Pontiac Midpoint |  | IL | Kankakee | Withdrawn | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2155_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 6/17/2019 |  | 12/31/2020 |  |  | N | No
AD2-156 | Avery 138 kV |  | OH | Erie | Withdrawn | ATSI | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  | 4/2/2018 |  | 12/31/2020 |  |  | N | No
AD2-157 | Hampshire-Gore 138kV |  | WV | Hampshire | Active | APS | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2157_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 12/21/2021 |  |  | N | No
AD2-158 | Old Chapel-Millville 138kV |  | WV | Jefferson | Active | APS | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2158_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AD2-159 | Chestnut 345kV |  | IL | Macon | Active | ComEd | 187.5 | 187.5 | 33 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2159_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AD2-160 | Hickory-Moyock 230kV |  | NC | Currituck | Active | Dominion | 50 | 50 | 32.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2160_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-161 | Hunlock 69kV |  | PA | Luzerne | Withdrawn | PPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  | 3/28/2018 |  | 5/22/2022 |  |  | N | No
AD2-162 | Biers Run-Circleville 138kV |  | OH | Pickaway | Active | AEP | 110 | 110 | 73.81 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2162_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AD2-163 | Broadview-Tangy 138 kV |  | OH | Madison | Active | ATSI | 180 | 180 | 120.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2163_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AD2-164 | Peninsula 34.5kV | Langley AFB Generation | VA | City of Hampton | Engineering and Procurement | Dominion | 26.7 | 26.7 | 26.7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2164_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2164_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2164_wmpa.pdf | Not Required | N/A | N/A |  | 3/26/2018 | N/A | N/A | 6/1/2022 |  |  | 6/1/2022 | 6/1/2022 |  | N | No
AD2-165 | South River II 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 565 | 105 | 40 |  | Capacity | Generation Interconnection | Natural Gas; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2165_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2018 | N/A | N/A |  | 2/10/2020 |  | 5/1/2021 |  |  | N | No
AD2-166 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | Engineering and Procurement | ME | 825 | 75 | 89.8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2166_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_166_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 4/30/2022 | 4/30/2022 |  | N | No
AD2-167 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 1090 | 90 | 52 | 90 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2167_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_167_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/27/2018 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 7/27/2017 | N | No
AD2-168 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-169 | Pleasant Hill-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2169_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 1/28/2020 |  | 9/30/2020 |  |  | N | No
AD2-170 | Carll's Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 9/20/2018 |  | 1/1/2019 |  |  | N | No
AD2-171 | Branchburg-Alburtis 500kV |  | NJ | Hunterdon | Active | PSEG | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2171_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AD2-172 | Lena 138kV |  | IL | Stephenson | Active | ComEd | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2172_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  |  |  | 5/19/2020 |  |  | N | No
AD2-173 | Bremo-Kidds Store 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 75 | 75 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 4/2/2018 |  | 5/1/2020 |  |  | N | No
AD2-174 | Oakville-St. Andrews 69kV |  | MD | St. Mary's | Withdrawn | SMECO | 52.5 | 52.5 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 1/24/2019 |  | 9/30/2020 |  |  | N | No
AD2-175 | Davis Creek 345 kV |  | IL | Kankakee | Withdrawn | ComEd | 205 | 205 | 123 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2175_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 12/10/2019 |  | 12/31/2021 |  |  | N | No
AD2-176 | Marengo 138kV |  | IL | McHenry | Withdrawn | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2176_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 6/27/2019 |  | 12/31/2021 |  |  | N | No
AD2-177 | Pontiac MidPoint 345 kV |  | IL | Livingston | Withdrawn | ComEd | 205 | 205 | 123 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  | 3/23/2018 |  | 12/31/2021 |  |  | N | No
AD2-178 | Wurno 138kV |  | VA | Pulaski | Active | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2178_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AD2-179 | Morgans Cut-Glen Lyn 138kV |  | VA | Pulaski | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2179_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2018 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AD2-180 | Elk Garden-Parr Run 138kV |  | WV | Mineral | Active | APS | 110 | 110 | 15.08 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2180_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ad2_180_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AD2-181 | Shawboro-Sligo 230 kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 12/31/2018 |  |  | N | No
AD2-182 | George Washington 138 kV |  | WV | Marshall | Withdrawn | AEP | 481.5 | 481.5 | 380 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 4/1/2022 |  |  | N | No
AD2-183 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-184 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2020 |  |  | N | No
AD2-185 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 80 | 31.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/3/2018 |  | 9/15/2021 |  |  | N | No
AD2-186 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 9/30/2019 |  |  | N | No
AD2-187 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 8.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 9/30/2019 |  |  | N | No
AD2-188 | Nelson-Electric Junc |  | IL | Lee | Withdrawn | ComEd | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2018 | N/A | N/A |  | 4/6/2018 |  | 6/30/2021 |  |  | N | No
AD2-189 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | Under Construction | AEP | 1875 | 225 | 186 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2189_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_189_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_189_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AD2-190 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 11/1/2020 |  |  | N | No
AD2-191 | Melmore 138kV |  | OH | Seneca | Active | AEP | 370 | 170 | 22.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2191_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 11/2/2020 |  |  | N | No
AD2-192 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Suspended | APS | 625 | 45 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_192_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_192_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2018 | N/A | N/A | 7/30/2021 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AD2-193 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 556 | 208.5 | 208.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 11/1/2020 |  |  | N | No
AD2-194 | Elwood |  | IL | Will | Active | ComEd | 1260.9 | 60 | 120 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2194_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AD2-195 | Trowbridge-Pantero 115 kV |  | NC | Washington | Withdrawn | Dominion | 80 | 80 | 55.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2195_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 9/25/2018 |  | 6/1/2021 |  |  | N | No
AD2-196 | Acahela 230 kV |  | PA | Luzerne | Withdrawn | PPL | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/5/2018 |  | 12/31/2020 |  |  | N | No
AD2-197 | Carson-Rodgers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/9/2018 |  | 5/3/2021 |  |  | N | No
AD2-198 | Ellwood |  | IL | Will | Withdrawn | ComEd | 1745 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 3/1/2020 |  |  | N | No
AD2-199 | St. Barnabas 13kV II |  | MD | Prince George's | Active | PEPCO | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2199_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2199_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AD2-200 | Briery-Clover 230 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 144 | 14 | 9.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2200_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 10/16/2018 |  | 9/2/2019 |  |  | N | No
AD2-201 | South Creek 115 kV |  | VA | Appomattox | Withdrawn | Dominion | 62 | 62 | 40.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 3/31/2020 |  |  | N | No
AD2-201A | Hickman-Riverbend 69kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 50 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2201a_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 1/22/2019 |  | 5/3/2021 |  |  | N | No
AD2-202 | Clover-Sedge Hill 230kV |  | VA | Halifax | Active | Dominion | 83 | 18.8 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2202_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2202_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 9/2/2019 |  |  | N | No
AD2-203 | Clubhouse-Lakeville 230 kV |  | VA | Greensville | Withdrawn | Dominion | 72.3 | 72.3 | 49.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/6/2018 |  | 9/4/2020 |  |  | N | No
AD2-204 | Burlington 26 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/2/2018 |  | 5/31/2019 |  |  | N | No
AD2-205 | Byllesby 69 kV | Buck & Byllesby Hydro Project | VA | Carroll | In Service | AEP | 4 | 4 | 0 | 4 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2205_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_205_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/13/2018 | N/A | N/A |  |  |  | 12/31/2018 | 12/31/2018 | 1/31/2019 | N | No
AD2-206 | Clubhouse-Freeman DP 115 kV |  | VA | Greensville | Withdrawn | Dominion | 250 | 250 | 150.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 6/1/2020 |  |  | N | No
AD2-207 | Suffolk-Poe 115 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 6/1/2020 |  |  | N | No
AD2-208 | Boykins 115 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/5/2018 |  |  |  |  | N | No
AD2-209 | Cherryville 12.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2209_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 10/9/2018 |  | 11/30/2018 |  |  | N | No
AD2-210 | Cedar Knolls 12.5 kV | South Jefferson Road Storage | NJ | Morris | Suspended | JCPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2210_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2210_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2210_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2018 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AD2-211 | Great Adventure 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 3/31/2018 |  | 10/1/2018 |  |  | N | No
AD2-212 | Ocean Bay 128 kV |  | MD | Worcester | Withdrawn | DPL | 160 | 160 | 70 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/10/2018 |  | 6/1/2022 |  |  | N | No
AD2-213 | East Flemington-Lebanon 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2213_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2213_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 3/29/2019 |  |  | N | No
AD2-214 | Rock Falls-Garden Plains |  | IL | Whiteside | Active | ComEd | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2214_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  |  |  | 5/3/2021 |  |  | N | No
AD2-215 | Kings Fork 34.5 kV | Godwin Blvd Solar | VA | City of Suffolk | Engineering and Procurement | Dominion | 15 | 15 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2215_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2215_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2215_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2215_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2018 | N/A | N/A | 12/1/2021 |  |  | 12/1/2021 | 12/1/2021 |  | N | No
AD2-216 | Axton 138 kV |  | VA | Henry | Withdrawn | AEP | 68 | 68 | 43.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/3/2018 |  | 3/31/2020 |  |  | N | No
AD2-217 | Crossland 13 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 8.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2018 | N/A | N/A |  | 4/4/2018 |  | 3/1/2019 |  |  | N | No
AE1-001 | Calvert Cliffs |  | MD | Calvert | Active | BGE | 921.5 | 28.1 | 7.1 |  | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1001_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2018 | N/A | N/A |  |  |  | 3/17/2018 |  |  | N | No
AE1-002 | Wilton Center-Loretto |  | IN | Benton | Withdrawn | ComEd | 100 | 100 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/4/2018 | N/A | N/A |  | 7/29/2019 |  | 12/31/2020 |  |  | N | No
AE1-003 | Williams 138 kV |  | WV | Grant | Active | APS | 209 | 59 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1003_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/4/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No | This project slid two queues
AE1-004 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Engineering and Procurement | Dominion | 110 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_004_isa.pdf | Document Posted | N/A |  | Document Posted | N/A | N/A |  | 4/6/2018 | N/A | N/A |  |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AE1-005 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE1-006 | Germantown 115 kV | Brookview Solar I | PA | Adams | Suspended | ME | 75 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1006_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_006_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 4/23/2018 | N/A | N/A |  |  |  | 12/15/2022 | 12/15/2022 |  | N | No
AE1-007 | Camden-Crystal III 69 kV |  | OH | Preble | Active | Dayton | 89.9 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1007_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/23/2018 | N/A | N/A |  |  |  | 7/1/2019 |  |  | N | No
AE1-008 | College Corner 138 kV |  | OH | Preble | Withdrawn | AEP | 100 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1008_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/23/2018 | N/A | N/A |  | 8/1/2019 |  | 7/1/2019 |  |  | N | No
AE1-009 | Bremo-Cunningham DP 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1009_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/25/2018 | N/A | N/A |  | 3/11/2019 |  | 3/31/2020 |  |  | N | No
AE1-010 | Locust Grove-Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 95.5 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1131_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/27/2018 | N/A | N/A |  | 3/11/2019 |  | 9/30/2021 |  |  | N | No
AE1-011 | Livingston Road 13 kV |  | N/A | N/A | Withdrawn | PEPCO | 1.5 | 1.48 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2018 | N/A | N/A |  | 9/24/2018 |  | 3/31/2019 |  |  | Y | No
AE1-012 | 64th St. 13 kV | 1724 64th Street | MD | Prince George's | Engineering and Procurement | PEPCO | 0.5 | 0.54 | 0.22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1012_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1012_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1012_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1012_wmpa.pdf | Not Required | N/A | N/A |  | 10/2/2018 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE1-013 | Suitland Road 13 kV | 4179 Suitland Road | MD | Prince George's | Engineering and Procurement | PEPCO | 0.9 | 0.9 | 0.378 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1013_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1013_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1013_wmpa.pdf | Not Required | N/A | N/A |  | 5/2/2018 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE1-014 | Canada Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 0.5 | 0.54 | 0.23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/2/2018 | N/A | N/A |  | 9/24/2018 |  | 9/30/2019 |  |  | Y | No
AE1-015 | St. Barnabas Road 13 kV | 5203 Saint Barnabas Road | MD | Prince George's | Engineering and Procurement | PEPCO | 1.4 | 1.4 | 0.567 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1015_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1015_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1015_wmpa.pdf | Not Required | N/A | N/A |  | 5/2/2018 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE1-016 | Livingston Road 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 1.1 | 1.08 | 0.4536 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1016_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 5/3/2018 | N/A | N/A |  | 12/16/2019 |  | 9/30/2019 |  |  | N | No
AE1-017 | Peak Creek-Draper 34.5 kV |  | VA | Pulaski | Active | AEP | 20 | 20 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AE1-018 | Peak Creek-Memoria Drive 12 kV | Pulaski Community Solar | VA | Pulaski | Withdrawn | AEP | 5 | 5 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1018_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 5/14/2018 | N/A | N/A |  | 2/21/2020 |  | 6/1/2020 |  |  | N | No
AE1-019 | Earleys-Scotland Neck 115 kV |  | NC | Hertford | Withdrawn | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/15/2018 | N/A | N/A |  | 10/31/2018 |  | 6/30/2021 |  |  | N | No
AE1-020 | Oyster Creek 230 kV |  | NJ | Ocean | Active | JCPL | 816 | 816 | 229.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1020_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2018 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No | This project slid to the next queue
AE1-021 | Gavin #2 765 kV |  | OH | Gallia | Active | AEP | 1367 | 11 | 11 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2018 | N/A | N/A |  |  |  | 5/12/2019 |  |  | N | No
AE1-022 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 6/21/2018 |  | 11/2/2020 |  |  | N | No
AE1-023 | Wempletown |  | IL | Winnebago | Withdrawn | ComEd | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  | 6/25/2018 |  | 12/15/2021 |  |  | N | No
AE1-024 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1024_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AE1-025 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1025_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AE1-026 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 80 | 80 | 63.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1026_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2018 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AE1-027 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1027_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1027_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1027_wmpa.pdf | Not Required | N/A | N/A |  | 5/29/2018 | N/A | N/A | 8/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-028 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 12 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1028_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1028_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1028_wmpa.pdf | Not Required | N/A | N/A |  | 5/29/2018 | N/A | N/A | 8/15/2020 | 1/14/2020 |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-029 | Wheatland 12 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 8.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1029_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/30/2018 | N/A | N/A |  | 6/19/2019 |  | 3/1/2019 |  |  | N | No
AE1-030 | Stuart-Clinton 345 kV II |  | OH | Montgomery | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2018 | N/A | N/A |  | 6/29/2018 |  | 6/1/2021 |  |  | N | No
AE1-031 | Stuart-Clinton 345 kV III |  | OH | Montgomery | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/4/2018 | N/A | N/A |  | 6/29/2018 |  | 6/1/2020 |  |  | N | No
AE1-032 4948568 | AMIL-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. |  | 180 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/24/2018 | 6/1/2021 | 6/1/2026 |  | 10/4/2018 |  |  |  |  | PP | No
AE1-033 4950965 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. |  | 165 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/4/2018 | 6/1/2022 | 6/1/2027 |  | 12/21/2018 |  |  |  |  | PP | No
AE1-034 | Larrabee 230 kV |  | N/A | N/A | Withdrawn | JCPL | 1104 | 1104 | 310.224 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1034_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/7/2018 | N/A | N/A |  | 4/19/2019 |  | 6/1/2024 |  |  | N | No
AE1-035 | Earleys 230 kV | Aulander Holloman Solar Park | NC | Hertford | Engineering and Procurement | Dominion | 100 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1035_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_035_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 6/8/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AE1-036 | Red Oak 230 kV | Red Oak | NJ | Middlesex | In Service | JCPL | 776 | 0 | 9 | 0 | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1036_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_036_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 6/13/2018 | N/A | N/A |  |  |  | 7/1/2018 |  | 2/8/2019 | N | No
AE1-037 | Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | AC | 0 | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ae1037_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/18/2018 | N/A | N/A |  | 1/24/2020 |  | 12/31/2025 |  |  | S | No
AE1-038 | Cartanza 69 kV |  | DE | Kent | Withdrawn | DPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1038_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2018 | N/A | N/A |  | 9/30/2019 |  | 10/31/2020 |  |  | N | No
AE1-039 | West Street (Orchard Hills) 12.47 kV |  | MI | Berrien | Active | AEP | 4 | 0.8 | 0.8 |  | Capacity | Generation Interconnection | Methane |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1039_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2018 | N/A | N/A |  |  |  | 12/15/2018 |  |  | N | No
AE1-040 | Greenfield 69 kV |  | OH | Fayette | Active | Dayton | 48 | 48 | 31.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1040_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2018 | N/A | N/A |  |  |  | 7/1/2022 | 7/1/2022 |  | N | No
AE1-041 | Edison 4kV | Highland Park | NJ | Middlesex | In Service | PSEG | 1.1 | 1.1 | 0.2 | 1.1 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1041_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/25/2018 | N/A | N/A | 12/19/2019 |  |  | 1/31/2020 | 1/31/2020 | 12/30/2019 | N | No
AE1-042 4954950 | TVA-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services, L.P. |  | 180 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4954950_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 6/26/2018 | 6/1/2021 | 6/1/2026 |  | 2/1/2019 |  |  |  |  | PP | No
AE1-043 | Clayton-Woodstown 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/3/2018 | N/A | N/A |  | 7/25/2018 |  | 11/1/2018 |  |  | Y | No
AE1-044 | Morrisville 230 kV |  | VA | Fauquier | Active | Dominion | 200 | 200 | 111.7933 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1044_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/5/2018 | N/A | N/A |  |  |  | 11/2/2020 |  |  | N | No
AE1-045 | Minotola 12 kV I |  | NJ | Atlantic | Withdrawn | AEC | 3 | 3 | 2.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1045_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 3/4/2019 |  | 12/31/2019 |  |  | N | No
AE1-046 | Minotola 12 kV II |  | NJ | Atlantic | Withdrawn | AEC | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1046_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 9/20/2019 |  | 12/31/2019 |  |  | N | No
AE1-047 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 800 | 300 | 208.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2018 | N/A | N/A |  | 10/12/2018 |  | 11/1/2021 |  |  | N | No
AE1-048 | Wye Mills 25 kV |  | MD | Queen Anne's | Withdrawn | DPL | 1 | 1 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2018 | N/A | N/A |  | 8/9/2018 |  |  |  |  | Y | No
AE1-049 | N/A-N/A |  | OH | Adams | Withdrawn | DEOK |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2018 | N/A | N/A |  | 10/31/2018 |  |  |  |  | EE | No
AE1-050 | Gavin Unit 1 765 kV |  | OH | Gallia | Active | AEP | 1349 | 18 | 18 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  |  |  | 12/6/2020 |  |  | N | No
AE1-051 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Active | PPL | 74.5 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1051_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE1-052 | William 138 kV |  | WV | Tucker | Active | APS | 66 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1052_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE1-053 | Meyersdale North |  | PA | Somerset | Active | PENELEC | 30 | 0 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1053_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE1-054 | Mill Run 25kV |  | PA | Fayette | Active | APS | 15 | 0 | 7.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1054_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/23/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE1-055 | Mason 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 134 | 134 | 134 |  | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2018 | N/A | N/A |  | 8/14/2018 |  | 12/31/2021 |  |  | N | No
AE1-056 | Red House-South Creek 115 kV |  | VA | Appomattox | Active | Dominion | 60 | 60 | 38.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1056_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/25/2018 | N/A | N/A |  |  |  | 12/15/2020 |  |  | N | No
AE1-057 | Brandy DP 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2018 | N/A | N/A |  | 11/7/2018 |  | 12/1/2019 |  |  | N | No
AE1-058 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Active | PPL | 500 | 500 | 250 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1058_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2018 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AE1-059 | Stanton-Summit 230 kV |  | PA | Luzerne | Active | PPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1059_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2018 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AE1-060 | Kittatinny-Newton 34.5 kV |  | NJ | Sussex | Active | JCPL | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1060_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2018 | N/A | N/A |  |  |  | 8/31/2019 |  |  | N | No
AE1-061 | Minotola 12 kV |  | NJ | Atlantic | Active | AEC | 5.5 | 5.5 | 2.75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1061_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE1-062 | Silver Lake 69 kV |  | NJ | Camden | Active | AEC | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1062_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2018 | N/A | N/A |  |  |  | 10/30/2020 |  |  | N | No
AE1-063 | Buckeye-Ringoes 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1063_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2018 | N/A | N/A |  | 3/27/2019 |  | 11/29/2019 |  |  | N | No
AE1-064 | Rockcastle 138 kV |  | VA | Bedford | Active | AEP | 102.1 | 102.1 | 67.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1064_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 5/3/2021 |  |  | N | No
AE1-065 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1065_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2025 |  |  | N | No
AE1-066 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1066_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2027 |  |  | N | No
AE1-067 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/5/2019 |  | 12/31/2029 |  |  | N | No
AE1-068 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Active | Dominion | 500 | 500 | 322.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1068_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-069 | Carson-Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 400 | 400 | 254.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1069_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-070 | Elwood 345 kV |  | IL | Will | Active | ComEd | 1485 | 135 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1070_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE1-071 | Shade Gap-Roxbury 115 kV |  | PA | Franklin | Active | PENELEC | 100.1 | 100.1 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-072 | Shawboro-Sligo 230 kV |  | NC | Currituck | Active | Dominion | 150 | 150 | 98.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1072_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AE1-073 | Bremo-Kidds Store 115 kV |  | N/A | N/A | Withdrawn | Dominion | 75 | 75 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1073_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  | 3/13/2019 |  | 12/1/2021 |  |  | N | No
AE1-074 | Winterpock 34.5 kV | Winterpock I | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1074_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1074_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2023 | 12/1/2023 |  | N | No
AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | Engineering and Procurement | Dominion | 18 | 18 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1075_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1075_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2023 | 12/1/2023 |  | N | No
AE1-076 | Twombley Road 138 kV |  | IL | Ogle | Withdrawn | ComEd | 35.4 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 9/10/2018 |  | 12/31/2019 |  |  | N | No
AE1-077 | N/A-N/A |  | MD | Allegany | Active | BGE | 100 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ae1077_imp-arr.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | EE | No
AE1-078 | N/A-N/A |  | OH | Adams | Withdrawn | DEOK | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ae1078_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/7/2018 | N/A | N/A |  | 9/23/2019 |  | 6/1/2020 |  |  | EE | No
AE1-079 | Maysville-Sharon 69 kV |  | PA | Mercer | Active | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1079_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/10/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AE1-080 | Wylie Ridge 500 kV |  | PA | Washington | Active | APS | 1075 | 50 | 80 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1080_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/21/2018 | N/A | N/A |  |  |  | 2/1/2022 |  |  | N | No
AE1-080A 4964319 | PJM-MECS |  | N/A | N/A | Withdrawn | Exelon Generation Co., LLC (PT) |  | 300 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 8/16/2018 | 6/1/2020 | 6/1/2025 |  | 12/20/2018 |  |  |  |  | PP | No
AE1-081 | Landing 12.47 kV | Durban Ave Solar | NJ | Sussex | Engineering and Procurement | JCPL | 2.3 | 2.3 | 0.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1081_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1081_wmpa.pdf | Not Required | N/A | N/A |  | 8/27/2018 | N/A | N/A | 6/30/2020 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AE1-082 | Charles County 13 kV |  | MD | Charles | Withdrawn | SMECO | 1.3 | 1.25 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2018 | N/A | N/A |  | 9/13/2018 |  | 11/30/2018 |  |  | Y | No
AE1-083 | Busselton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1083_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2018 | N/A | N/A |  | 6/19/2019 |  | 5/31/2019 |  |  | N | No
AE1-084 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Active | Dominion | 83 | 83 | 49.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2018 | N/A | N/A |  |  |  | 11/13/2020 |  |  | N | No
AE1-085 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Active | Dominion | 75 | 75 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1085_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-086 | Grassy Falls 138 kV | Beech Ridge Wind Farm | WV | Greenbrier | Partially in Service - Under Construction | APS | 55.6 | 5 | 0.6 | 0 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1086_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_086_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 5/31/2020 |  |  | 5/31/2020 | 5/31/2020 | 3/14/2020 | N | No
AE1-087 | Todd 69 kV |  | MD | Dorchester | Active | DPL | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1087_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-088 | Five Points-Pantego 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1088_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 4/17/2020 |  | 12/31/2020 |  |  | N | No
AE1-089 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 310 | 310 | 130.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1089_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2021 |  |  | N | No
AE1-090 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 50 | 50 | 21.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1090_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-091 | West Newton-Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 110 | 46.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-092 | Blue Jacket-Kirby 138 kV |  | OH | Union | Active | Dayton | 229.5 | 229.5 | 96.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-093 | Elk 138 kV |  | OH | Vinton | Active | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1093_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-094 4966856 | PJM-HUDSON |  | N/A | N/A | Withdrawn | Hudson Transmission Partners, LLC |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966856_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2019 | 6/1/2020 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-095 4966859 | PJM-HUDSON |  | N/A | N/A | Withdrawn | Hudson Transmission Partners, LLC |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966859_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2020 | 6/1/2021 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-096 4966862 | PJM-HUDSON |  | N/A | N/A | Withdrawn | Hudson Transmission Partners, LLC |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966862_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2021 | 6/1/2022 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-097 4966877 | PJM-HUDSON |  | N/A | N/A | Withdrawn | Hudson Transmission Partners, LLC |  | 62 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966877_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/30/2018 | 6/1/2022 | 6/1/2027 |  | 2/27/2019 |  |  |  |  | PP | No
AE1-098 | Endless Caverns 34.5 kV | Endless Caverns Solar | VA | Rockingham | Engineering and Procurement | Dominion | 15.7 | 15.7 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1098_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1098_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1098_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 10/1/2020 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE1-099 | Endless Caverns 34.kV | Endless Caverns Solar | VA | Rockingham | Engineering and Procurement | Dominion | 15.7 | 15.7 | 10.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1099_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1099_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1099_wmpa.pdf | Not Required | N/A | N/A |  | 8/31/2018 | N/A | N/A | 10/1/2020 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE1-100 | Axton 138 kV |  | VA | Henry | Active | AEP | 66 | 66 | 41.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1100_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AE1-101 | McConnellsburg-Texas Eastern 138 kV |  | PA | Franklin | Active | APS | 150 | 150 | 100.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1101_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1101_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AE1-102 | Maddox Creek 345 kV |  | OH | Van Wert | Active | AEP | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-103 | Holland-Union Camp 115 kV |  | VA | Isle of Wight | Active | Dominion | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1103_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE1-104 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 432 | 432 | 121.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1104_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2018 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AE1-105 | North Longview 500 kV |  | WV | Preston | Active | APS | 1270 | 1270 | 1235 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1105_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-106 | Lake Lynn-Hazelton 138 kV |  | WV | Preston | Active | APS | 99.6 | 99.6 | 59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1106_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-107 | Mt. Pleasant-Lums Pond 138 kV |  | DE | New Castle | Active | DPL | 53.1 | 53.1 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1107_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-108 | Bremo-Scottsville 138 kV |  | VA | Buckingham | Active | AEP | 153 | 153 | 91.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1108_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2018 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AE1-109 | Frenchs Mill 34 kV |  | WV | Hampshire | Active | APS | 20 | 20 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1109_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2018 | N/A | N/A |  |  |  | 12/1/2019 |  |  | N | No
AE1-109A | Baker Pont-Ivor 115 kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1109a_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2018 | N/A | N/A |  | 3/6/2019 |  | 12/1/2022 |  |  | N | No
AE1-110 4966477 | PJM-DUK |  | N/A | N/A | Withdrawn | Morgan Stanley Capital Group Inc. |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966477_ltf1.pdf | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966477_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2030 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-111 4966479 | PJM-DUK |  | N/A | N/A | Withdrawn | Morgan Stanley Capital Group Inc. |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966479_ltf1.pdf | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966479_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2031 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-112 4966484 | PJM-DUK |  | N/A | N/A | Withdrawn | Morgan Stanley Capital Group Inc. |  | 100 |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966484_ltf1.pdf | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/4966484_ltf1.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/28/2018 | 1/1/2025 | 1/1/2032 |  | 2/28/2019 |  |  |  |  | PP | No
AE1-113 | Mole Creek 345 kV |  | IL | Woodford | Active | ComEd | 300 | 300 | 66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1113_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-114 | Maryland-Lancaster 138 kV |  | IL | Ogle | Active | ComEd | 150 | 150 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1114_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-115 | Churchtown 69 kV |  | NJ | Salem | Active | AEC | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1115_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AE1-116 | Somerset Windpower 23 kV |  | PA | Somerset | Active | PENELEC | 9 | 0 | 4.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1116_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  |  |  | 10/1/2020 |  |  | N | No
AE1-117 | Bethany 138 kV |  | DE | Sussex | Active | DPL | 152 | 152 | 41.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1117_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-118 | Bethany-138th Street 138 kV |  | DE | Sussex | Active | DPL | 152 | 152 | 41.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1118_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-119 | Lemoyne 345 kV |  | OH | Wood | Active | ATSI | 1260 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1119_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-120 | Hillcrest 138 kV | Hillcrest Solar I | OH | Brown | Engineering and Procurement | DEOK | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1120_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_120_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/17/2018 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-121 | Axton 138 kV |  | VA | Pittsylvania | Active | AEP | 529.5 | 529.5 | 483 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1121_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-122 | Axton 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 529.5 | 529.5 | 483 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1122_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  | 7/18/2019 |  | 6/1/2023 |  |  | N | No
AE1-123 | Emlenton 34.5 kV | Clarion Boards | PA | Clarion | Engineering and Procurement | PENELEC | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1123_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1123_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1123_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2018 | N/A | N/A | 6/30/2021 |  |  | 6/30/2021 | 6/30/2021 |  | N | No
AE1-124 | Oak Grove 34.5 kV | VSF Solar I | VA | Westmoreland | Engineering and Procurement | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1124_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1124_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1124_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2018 | N/A | N/A |  |  |  | 3/27/2024 | 3/27/2024 |  | N | No
AE1-125 | Mt. Jackson 34.5 kV |  | VA | Shenandoah | Withdrawn | Dominion | 18.9 | 18.9 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1125_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 3/11/2019 |  | 11/20/2020 |  |  | N | No
AE1-126 | Kingsland 26 kV |  | NJ | Bergen | Withdrawn | PSEG | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 10/1/2018 |  | 11/29/2019 |  |  | N | No
AE1-127 | Eldred-Sunbury 69 kV |  | PA | Northumberland | Withdrawn | PPL | 50 | 50 | 32.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1127_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  | 10/18/2019 |  | 6/7/2021 |  |  | N | No
AE1-128 | Bedford North-Wills Mounain 115 kV |  | PA | Bedford | Active | PENELEC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1128_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-129 | Zion View - Middletown 115 kV |  | PA | York | Active | ME | 79.6 | 79.6 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1129_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-130 | Meads Store 138 kV |  | VA | Bedford | Active | AEP | 83 | 83 | 55.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1130_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2018 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AE1-131 | Gardners-Hunterstown 115 kV |  | PA | Adams | Active | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1131_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-132 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1132_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-133 | Elizabeth City-Tanglewood 230 kV |  | N/A | N/A | Withdrawn | Dominion | 300 | 300 | 201 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1133_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/11/2019 |  | 9/1/2022 |  |  | N | No
AE1-134 | Nelson 345 kV |  | IL | Lee | Active | ComEd | 640 | 9 | 24.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1134_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/31/2018 |  |  | N | No
AE1-135 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/19/2019 |  | 6/30/2019 |  |  | N | No
AE1-136 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Withdrawn | APS | 53.3 | 53.32 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1136_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/26/2019 |  | 12/31/2021 |  |  | N | No
AE1-137 | Bluff Point-Randolph |  | IN | Randolph | Withdrawn | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/3/2018 |  | 10/31/2021 |  |  | N | No
AE1-138 | Hamilton 115 kV |  | PA | Adams | Active | ME | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1138_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-139 | Hunterstown 115 kV |  | PA | Adams | Active | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1139_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-140 | Fayetteville-West Waynesboro 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1140_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 4/30/2019 |  | 12/31/2021 |  |  | N | No
AE1-141 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2021 |  |  | N | No
AE1-142 | Manitou-Pleasant Plains 34.5 kV | Toms River Solar | NJ | Ocean | Engineering and Procurement | JCPL | 20 | 20 | 8.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1142_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_142_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_142_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-143 | Marion County 161 kV |  | KY | Unknown | Active | EKPC | 96 | 96 | 64.163 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1143_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-144 | Goddard-Plumville 138 kV |  | KY | Fleming | Active | EKPC | 120 | 120 | 80.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1144_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-145 | Wallops Island 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1145_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2020 |  |  | N | No
AE1-146 | Ebersole #2-Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 120 | 120 | 81.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1146_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 5/1/2020 |  |  | N | No
AE1-147 | Bellefonte 46 kV | Nittany Solar | PA | Centre | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1147_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1147_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1147_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A | 12/15/2022 |  |  | 12/15/2022 | 12/15/2022 |  | N | No
AE1-148 | Kerr Dam-Ridge Rd 115 kV |  | VA | Mecklenburg | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-149 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1149_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-150 | Curdsville-Willis Mountain 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1150_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 3/15/2019 |  | 12/1/2021 |  |  | N | No
AE1-151 | PACA Street 13.8kV |  | MD | Baltimore City | Withdrawn | BGE | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1151_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1151_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/8/2019 |  | 3/2/2020 |  |  | N | No
AE1-152 | Gosport 34.5 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 21.5 | 21.5 | 20.2 |  | Capacity | Generation Interconnection | Natural Gas; Diesel; Other; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 10/16/2018 |  | 10/16/2020 |  |  | N | No
AE1-153 | Remington-Gordonsville 230 kV |  | VA | Culpeper | Active | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1153_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 10/23/2020 |  |  | N | No
AE1-154 | Louisa-South Anna 230 kV | Belcher Solar | VA | Louisa | Engineering and Procurement | Dominion | 105.2 | 17 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1154_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ae1_154_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2020 | 12/1/2020 |  | N | No
AE1-155 | Garner-Northern Neck 115 kV |  | VA | City of Richmond | Active | Dominion | 127 | 127 | 76.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1155_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 10/23/2020 |  |  | N | No
AE1-156 | Quakertown Solar II 34.5 kV | Quakertown Solar Farm | NJ | Hunterdon | Suspended | JCPL | 17.6 | 7.6 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_156_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_156_csa.pdf | Document Posted | N/A | N/A |  | 9/24/2018 | N/A | N/A | 12/31/2020 |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AE1-157 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Active | Dominion | 120 | 120 | 77.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1157_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-158 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Active | Dominion | 120 | 120 | 79.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1158_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-159 | Fredericksburg-Pinewood 115 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 120 | 75.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1159_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 12/20/2019 |  | 12/1/2021 |  |  | N | No
AE1-160 | Venango 34.5 kV | Titusville Solar | PA | Venango | Engineering and Procurement | PENELEC | 20 | 20 | 12.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/Delay email sent 11/27/19 | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1160_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1160_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A | 12/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-161 | Landis 138 kV |  | NJ | Cumberland | Active | AEC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1161_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE1-162 | Smithfield 34.5 kV | Solidago Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1162_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1162_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1162_wmpa.pdf | Not Required | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AE1-163 | Powerton-Goodings Grove 345 kV |  | IL | Woodford | Active | ComEd | 350 | 350 | 49 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1163_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE1-164 | Old Chapel 138 kV |  | N/A | N/A | Withdrawn | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1164_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 2/19/2019 |  | 12/30/2021 |  |  | N | No
AE1-165 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1165_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 4/8/2019 |  | 12/30/2021 |  |  | N | No
AE1-166 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1166_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE1-167 | Wattsville 12 kV |  | VA | Accomack | Withdrawn | DPL | 11.1 | 11.09 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1167_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 4/22/2020 |  | 6/25/2021 |  |  | N | No
AE1-168 | Victoria-Martin 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1168_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/8/2020 |  | 9/1/2021 |  |  | N | No
AE1-169 | Titusville 115 kV |  | PA | Venango | Withdrawn | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1169_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/23/2020 |  | 7/1/2021 |  |  | N | No
AE1-170 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1170_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-171 | Reynolds-Olive 345 kV |  | IN | White | Withdrawn | AEP | 280 | 280 | 118 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-172 | Loretto-Wilton Center |  | IL | Livingston | Active | ComEd | 255 | 255 | 44.88 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1172_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE1-173 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-174 | Light Foot 34.5 kV |  | VA | James City | Active | Dominion | 5 | 5 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1174_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/23/2020 |  |  | N | No
AE1-175 | Light Foot 34.5 kV | Lightfoot 34.5 kV II | VA | James City | Engineering and Procurement | Dominion | 19.9 | 19.9 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1175_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1175_wmpa.pdf | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 11/15/2021 | 11/15/2021 |  | N | No
AE1-176 | Roanoke-Vinton 12 kV (Niagara Hydro) | Niagara Power Plant Dam | VA | Roanoke | Engineering and Procurement | AEP |  |  |  |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1176_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_176_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 6/1/2020 | 6/1/2020 |  | N | No
AE1-177 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 80 | 19 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 10/1/2018 |  | 10/31/2020 |  |  | N | No
AE1-178 | Wolf Hills 138 kV |  | VA | Washington | Active | AEP | 294 | 19 | 19 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1178_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 1/1/2019 |  |  | N | No
AE1-179 | South Millville-Newport 69 kV |  | NJ | Cumberland | Active | AEC | 59.7 | 59.7 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1179_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-180 | Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1180_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 8/7/2019 |  | 9/30/2020 |  |  | N | No
AE1-181 | St. Johns-Freeland 69 kV |  | PA | Luzerne | Active | PPL | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1181_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/27/2020 |  |  | N | No
AE1-182 | Newville-West Carlise 69 kV |  | PA | Cumberland | Active | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1182_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/20/2020 |  |  | N | No
AE1-183 | Maysville-McDowell 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1183_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/8/2020 |  |  | N | No
AE1-184 | N/A-N/A |  | IL | Livingston | Active | ComEd | 82.7 | 82.7 |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | EE | No
AE1-185 | Hokes-Jackson 69 kV |  | PA | York | Active | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE1-186 | Moselem-Lyons 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1186_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 3/25/2019 |  | 4/1/2021 |  |  | N | No
AE1-187 | North Lebanon- Cleona 69 kV |  | N/A | N/A | Withdrawn | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1187_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/26/2019 |  | 4/1/2021 |  |  | N | No
AE1-188 | Fayetteville 34.5 kV |  | PA | Franklin | Active | APS | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1188_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE1-189 | Penville-Adams 138 kV |  | IN | Jay | Withdrawn | AEP | 245 | 245 | 103 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-190 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1190_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/21/2020 |  |  | N | No
AE1-191 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1191_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/21/2020 |  |  | N | No
AE1-192 | Belle Haven-Tasley 69 kV |  | VA | Accomack | Active | ODEC | 70 | 70 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1192_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE1-193 | Crete 345 kV |  | IL | Henry | Active | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1193_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE1-194 | Crete 345 kV |  | IL | Will | Active | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1194_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE1-195 | Crete 345 kV |  | IL | Will | Active | ComEd | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1195_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE1-196 | Hokes-Jackson 69 kV |  | PA | York | Active | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1196_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1196_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE1-197 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 65 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 9/1/2021 |  |  | N | No
AE1-198 | Crete 345 kV |  | IL | McHenry | Active | ComEd | 357 | 357 | 193 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1198_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE1-199 | Twombly Road 138 kV |  | IL | Ogle | Withdrawn | Unknown | 40 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1199_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 8/14/2019 |  | 12/31/2019 |  |  | N | No
AE1-200 | College Corner-Randolph 138 kV |  | IN | Randolph | Withdrawn | AEP | 235 | 235 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-201 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 40 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1201_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 8/14/2019 |  | 9/15/2019 |  |  | N | No
AE1-202 | Effort Mountain 12.47 kV |  | PA | Monroe | Withdrawn | PPL | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1202_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1202_imp.pdf | Document Posted |  |  |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/4/2019 |  | 9/30/2020 |  |  | N | No
AE1-203 | Iliff 12.47 kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1203_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1203_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 9/30/2019 |  | 9/30/2019 |  |  | N | No
AE1-204 | Waukegan 13 kV |  | IL | Lake | Withdrawn | ComEd | 4.4 | 4.4 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1204_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 11/18/2019 |  | 9/30/2020 | 9/30/2020 |  | N | No
AE1-205 | McLean 345 kV |  | IL | Livingston | Active | ComEd | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1205_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-206 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Active | Dominion | 285 | 285 | 171 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1206_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-207 | Mississinewa-Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 160 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1207_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-208 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 130 | 130 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1208_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1208_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-209 | Desoto 345 kV |  | IN | Randolph | Active | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1209_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE1-210 | Desoto 345 kV |  | IN | Randolph | Active | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1210_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE1-211 | Reynolds 345 kV |  | IN | Jasper | Withdrawn | AEP | 302.4 | 302.4 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/1/2018 |  | 10/31/2020 |  |  | N | No
AE1-212 | Grandview-Clifftop 138 kV |  | WV | Raliegh | Active | AEP | 90 | 90 | 53.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1212_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-213 | Highland-Lordstown 1 & 2 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1170 | 1025 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  | 10/1/2018 |  | 11/1/2023 |  |  | N | No
AE1-214 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 800 | 625 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  | 12/1/2023 |  |  | N | No
AE1-215 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 395 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/1/2018 |  | 12/1/2023 |  |  | N | No
AE1-216 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 500 | 395 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  | 12/1/2023 |  |  | N | No
AE1-217 | Gaston 138kV |  | IN | Delaware | Withdrawn | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1217_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1217_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE1-218 | Glassboro 12 kV | Glassboro LF Solar | NJ | Gloucester | Engineering and Procurement | AEC | 2 | 2 | 0.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1218_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1218_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1218_wmpa.pdf | Not Required | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 7/17/2022 | 7/17/2022 |  | N | No
AE1-219 | Glassboro 12 kV II | Glassboro RE Solar | NJ | Gloucester | Engineering and Procurement | AEC | 4.4 | 4.4 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1219_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1219_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1219_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1219_wmpa.pdf | Not Required | N/A | N/A |  | 9/27/2018 | N/A | N/A |  |  |  | 7/17/2022 | 7/17/2022 |  | N | No
AE1-220 | Coleen-Clifford 138 kV |  | VA | Nelson | Withdrawn | AEP | 100 | 100 | 66.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 6/17/2019 |  | 6/1/2022 |  |  | N | No
AE1-221 | North Wales 34.5 kV | West Point Cogeneration Facility | PA | Montgomery | Engineering and Procurement | PECO | 38 | 0 | 14 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1221_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_221_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 |  | N | No
AE1-222 | Dresden Tazewell Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 2562.7 | 2562.7 | 1270 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1222_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 8/7/2019 |  | 6/1/2022 |  |  | N | No
AE1-223 | Allentown Booster 138 kV |  | NJ | Burlington | Withdrawn | PSEG | 1.9 | 1.86 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 6/3/2019 |  | 11/16/2018 |  |  | N | No
AE1-224 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 9/30/2018 |  | 9/30/2020 |  |  | N | No
AE1-225 | Milton-Sunbury 69kV |  | PA | Snyder | Active | PPL | 19.8 | 19.8 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1225_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1225_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE1-226 | Face Rock-Kinzer #13 69 kV |  | PA | Lancaster | Active | PPL | 19.8 | 19.8 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1226_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE1-227 | Cumberland 69 kV |  | OH | Guernsey | Active | AEP | 49.5 | 49.5 | 30.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1227_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-228 | Steward 138 kV |  | IL | Lee | Withdrawn | ComEd | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1228_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 8/12/2019 |  | 6/1/2021 |  |  | N | No
AE1-229 | Deepwater-Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 149.3 | 149.3 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1229_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-230 | Shockoe 69 kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 7.2 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1230_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1230_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 7/31/2020 |  |  | N | No
AE1-231 | Hughesville 69 kV |  | MD | Charles | Active | SMECO | 20 | 20 | 9.4 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1231_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 7/31/2020 |  |  | N | No
AE1-232 | Harrowgate-Locks 115 kV |  | VA | Chesterfield | Withdrawn | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2021 |  |  | N | No
AE1-233 | West Dekalb 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 97.5 | 97.5 | 24.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 1/3/2019 |  | 12/31/2021 |  |  | N | No
AE1-234 | N/A-N/A |  | PA | Chester | Withdrawn | PECO | 578 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Issued |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2018 | N/A | N/A |  | 10/2/2018 |  |  |  |  | EE | No
AE1-235 | Carson-Clover 500 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 180 | 180 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-236 | Corson-Septa 500 kV |  | NC | Edgecombe | Withdrawn | Dominion | 290 | 290 | 122 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 12/31/2022 |  |  | N | No
AE1-237 | Andover (Maysville) 69kV I |  | PA | Crawford | Active | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1237_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AE1-238 | Oceanview Wind 230 kV |  | NJ | Monmouth | Active | JCPL | 816 | 816 | 225 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1238_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1238_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AE1-239 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 38.2 | 38.2 | 22.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1239_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 3/28/2019 |  | 12/31/2021 |  |  | N | No
AE1-240 | Carlls Corner-Sherman Avenue 69 kV |  | NJ | Cumberland | Active | AEC | 49.7 | 49.7 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1240_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1240_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-241 | Wilmington-Davis Creek |  | IL | Will | Withdrawn | ComEd | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/1/2018 |  | 5/31/2021 |  |  | N | No
AE1-242 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 10/5/2018 |  | 12/31/2022 |  |  | N | No
AE1-243 | Warren Glen Storage 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1243_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1243_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  |  |  | 12/1/2019 |  |  | N | No
AE1-244 | Gilbert Storage 34.5 kV |  | N/A | N/A | Withdrawn | JCPL | 19.8 | 19.8 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1244_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1244_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 12/19/2019 |  | 9/30/2020 |  |  | N | No
AE1-245 | Haviland 138 kV |  | OH | Paulding | Active | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1245_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 120 | 120 | 80.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1246_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1246_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE1-247 | Barren County-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 205 | 205 | 137.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1247_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1247_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  | 2/11/2020 |  | 6/1/2022 |  |  | N | No
AE1-248 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1248_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No | This project slid to the next queue
AE1-249 | Reams 115 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 70 | 70 | 40.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1249_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  | 1/10/2020 |  | 12/31/2021 |  |  | N | No
AE1-250 | Smith Mountain-E. Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1250_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE1-251 | Penn-Lees Lick 69 kV |  | KY | Scott | Withdrawn | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2018 | N/A | N/A |  | 3/27/2019 |  | 9/30/2021 |  |  | N | No
AE1-252 | Loretto-Wilton Center |  | IL | Livingston | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1252_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2018 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE1-253 | N/A-N/A |  | PA | Adams | Withdrawn | APS | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2018 | N/A | N/A |  | 11/1/2018 |  | 5/31/2020 |  |  | EE | No
AE2-001 | Nittany-Zion 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2001_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2018 | N/A | N/A |  |  |  | 5/31/2020 |  |  | N | No
AE2-002 | 64th Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 3.8 | 3.6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2018 | N/A | N/A |  | 9/6/2019 |  | 12/31/2019 |  |  | N | No
AE2-003 | Walker Mill Road 13 kV |  | MD | Prince George's | Withdrawn | DPL | 3 | 3 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2018 | N/A | N/A |  | 9/6/2019 |  | 10/1/2019 |  |  | N | No
AE2-004 | Poolesville 230 kV |  | VA | Surry | Withdrawn | Dominion | 60 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2018 | N/A | N/A |  | 11/28/2018 |  | 6/30/2021 |  |  | N | No
AE2-005 | Harmony Village-Shackleford 115 kV |  | VA | King and Queen | Active | Dominion | 130 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2005_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2018 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AE2-006 | Twittys Creek 34.5 kV | Twittys Creek Solar | VA | Charlotte | Engineering and Procurement | Dominion | 13.8 | 0 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2006_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2006_wmpa.pdf | Not Required | N/A | N/A |  | 10/8/2018 | N/A | N/A |  |  |  | 7/31/2020 | 7/31/2020 |  | N | No
AE2-007 | Chesapeake 230 kV |  | VA | City of Chesapeake | Active | Dominion | 1205.6 | 967.6 | 967.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2007_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-008 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 390 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2008_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2018 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-009 | N/A-N/A |  | PA | Adams | Withdrawn | PECO | 11 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required | https://www.pjm.com/pub/planning/project-queues/arr-impact-studies/ae2009_arr-imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/17/2018 | N/A | N/A |  | 3/20/2020 |  | 6/1/2020 |  |  | EE | No
AE2-010 | Paper Tap 69 kV | Jericho | PA | Delaware | Engineering and Procurement | PECO | 29 | 29 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_010_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/30/2018 | N/A | N/A |  |  |  | 3/30/2020 | 3/30/2020 |  | N | No
AE2-011 | Tansboro 12 kV |  | NJ | Camden | Withdrawn | AEC | 3.1 | 3.1 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/7/2018 | N/A | N/A |  | 8/12/2019 |  | 11/30/2020 |  |  | N | No
AE2-012 | Red Oak-South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 570 | 570 | 540 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2018 | N/A | N/A |  | 3/29/2019 |  | 6/1/2023 |  |  | N | No
AE2-013 | Highland-Lordstown 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1170 | 1025 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2013_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/12/2018 | N/A | N/A |  | 8/27/2019 |  | 11/1/2023 |  |  | N | No
AE2-014 | Sewaren 230 kV |  | NJ | Middlesex | Withdrawn | PSEG | 1200 | 1200 | 1200 |  | Capacity | Merchant Transmission | Wind | DC | 1200 F/NF TIR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/ae2014_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2018 | N/A | N/A |  | 1/24/2020 |  | 1/1/2024 |  |  | S | No
AE2-015 | Cookstown-New Lisbon 34.5 kV |  | NJ | Burlington | Withdrawn | JCPL | 5 | 5 | 3.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2015_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2018 | N/A | N/A |  | 8/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-016 | Bustleton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.5 | 3.5 | 2.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/26/2018 | N/A | N/A |  | 5/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-017 | Lexington Park 69 kV |  | MD | St. Mary's | Active | SMECO | 20 | 20 | 10.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2017_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/28/2018 | N/A | N/A |  |  |  | 3/31/2021 |  |  | N | No
AE2-018 | Laurence 13.2 kV |  | NJ | Mercer | Withdrawn | PSEG | 3.5 | 3.5 | 2.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2018_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2018 | N/A | N/A |  | 8/15/2019 |  | 6/30/2020 |  |  | N | No
AE2-019 | New Road 230 kV |  | VA | Loudoun | Active | Dominion | 120 | 120 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2019_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2018 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AE2-020 | Cardiff 230 kV I |  | NJ | Atlantic | Active | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2020_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AE2-021 | Cardiff 230 kV II |  | NJ | Atlantic | Active | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AE2-022 | Cardiff 230 kV III |  | NJ | Atlantic | Active | AEC | 300 | 300 | 62.09 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2022_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AE2-023 | BL England 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 445.2 | 445.2 | 78.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2023_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  | 4/15/2020 |  | 12/1/2024 |  |  | N | No
AE2-024 | Larrabee 230 kV I |  | NJ | Ocean | Active | JCPL | 882 | 882 | 155.23 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2024_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AE2-025 | Larrabee 230 kV II |  | NJ | Ocean | Active | JCPL | 445.2 | 445.2 | 78.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2025_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/14/2018 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AE2-026 | Louisa-South Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 150 | 44.8 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2026_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2018 | N/A | N/A |  | 8/14/2019 |  | 10/30/2020 |  |  | N | No
AE2-027 | Harrowgate-Locks 115kV |  | VA | Chesterfield | Active | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2027_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2018 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-028 | Broadway 12.47 kV |  | NJ | Warren | Active | JCPL | 0.8 | 0.75 | 0.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2028_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2018 | N/A | N/A |  |  |  | 10/31/2019 |  |  | N | No
AE2-029 | Grottoes-Merck 115kV |  | VA | Rockingham | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2029_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/27/2018 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AE2-030 | Frostburg 138kV |  | MD | Allegany | Active | APS | 18 | 18 | 7.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2030_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2018 | N/A | N/A |  |  |  | 8/24/2020 |  |  | N | No
AE2-031 | Carson-Rawlings 500 kV |  | VA | Sussex | Active | Dominion | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2031_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-032 | Pnode 1369011078-Pnode 51299 |  | PA | Lackawanna | Withdrawn | PPL | 811 | 811 |  |  | Energy | Upgrade Request |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/arr-feas_docs/ae2032_arr-fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  | 9/5/2019 |  |  |  |  | EE | No
AE2-033 | Clubhouse-Sappony 230 kV |  | VA | Sussex | Active | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2033_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/7/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-034 | Mackeys 230 kV |  | NC | Washington | Active | Dominion | 140 | 60 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2034_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2019 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AE2-035 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2035_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2019 | N/A | N/A |  |  |  | 5/21/2021 |  |  | N | No
AE2-036 | Masury-Maysville 138 kV |  | PA | Mercer | Withdrawn | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2036_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/17/2019 | N/A | N/A |  | 8/12/2019 |  | 6/1/2019 |  |  | N | No
AE2-037 | Earleys-Everetts 230 kV |  | NC | Bertie | Withdrawn | Dominion | 71.5 | 71.5 | 48.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2037_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2019 | N/A | N/A |  | 4/13/2020 |  | 9/17/2021 |  |  | N | No
AE2-038 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Active | EKPC | 200 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2038_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-039 | Clayton-Williamstown 69 kV |  | NJ | Gloucester | Withdrawn | AEC | 44 | 44 | 28.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  | 2/20/2019 |  | 6/30/2022 |  |  | N | No
AE2-040 | Sapony 34.5 kV |  | VA | Sussex | Active | Dominion | 17.6 | 17.64 | 15.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2040_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AE2-041 | Harmony Village 230 kV |  | VA | Middlesex | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2041_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AE2-042 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 70 | 70 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2042_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-043 | Franklinville 138 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 4 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/23/2019 | N/A | N/A |  | 4/1/2019 |  | 5/1/2020 |  |  | N | No
AE2-044 | Anaconda-Dunbar 115 kV |  | NC | Edgecombe | Active | Dominion | 120 | 40 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2044_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2019 | N/A | N/A |  |  |  | 12/31/2019 |  |  | N | No
AE2-045 | Olive-Reynolds 345 kV |  | IN | Lake | Active | AEP | 280 | 280 | 118 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2045_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-046 | Harwood-East Hazelton 69 kV |  | PA | Schuylkill | Active | PPL | 50 | 50 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2046_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-047 | Ridgeway-Solite 69 kV |  | VA | Henry | Active | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2047_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AE2-048 | Muskingum-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 220 | 220 | 147.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2048_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-049 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2049_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-050 | Braidwood-E. Frankfort |  | IL | Will | Withdrawn | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2050_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-051 | Carson-Septa 500 kV |  | VA | Sussex | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2051_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-052 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2052_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-053 | Kerr Dam-Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2053_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2054_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 3/31/2021 |  |  | 3/31/2021 | 3/31/2021 |  | N | No
AE2-055 | Shingletown-Boalsburg 46 kV | Windmill Road | PA | Centre | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2055_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2055_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2055_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE2-056 | Howell 12.47 kV Solar I | Willow Brook Road Solar I | NJ | Monmouth | Engineering and Procurement | JCPL | 3 | 3 | 1.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2056_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2056_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2056_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 |  |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-057 | Jerseyville 12.47 kV Solar | Willow Brook Road Solar II | NJ | Monmouth | Engineering and Procurement | JCPL | 1 | 1 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2057_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2057_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2057_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 |  |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-058 | Cherokee-Milton 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2058_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  | 9/4/2019 |  | 3/5/2021 |  |  | N | No
AE2-059 | Derry Tap-Derry Bus 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2059_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-060 | Mifflintown Bus-Mifflintown Tap 69 kV |  | PA | Juniata | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2060_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-061 | Rock Springs 500 kV | Rock Springs Unit #1 and Unit #2 | MD | Cecil | In Service | Essential Power | 394 | 0 | 7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2061_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_061_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 2/4/2019 | N/A | N/A |  |  |  | 8/23/2019 | 8/23/2019 | 8/12/2019 | N | No
AE2-062 | Normantown |  | IL | Will | Active | ComEd | 1 | 0.98 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2062_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2019 | N/A | N/A |  |  |  | 9/2/2019 |  |  | Y | No
AE2-063 | Normantown |  | IL | Will | Withdrawn | ComEd | 1 | 0.98 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2063_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2019 | N/A | N/A |  | 1/14/2020 |  | 9/2/2019 |  |  | Y | No
AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | Under Construction | PSEG | 5.8 | 2 | 0.85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_064_csa.pdf | Document Posted | N/A | N/A |  | 2/6/2019 | N/A | N/A | 8/31/2020 |  |  | 8/31/2020 | 8/31/2020 |  | N | No
AE2-065 | Deptford 13 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | Under Construction | PSEG | 6.8 | 1.8 | 0.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_065_csa.pdf | Document Posted | N/A | N/A |  | 2/6/2019 | N/A | N/A | 8/31/2020 |  |  | 8/31/2020 | 8/31/2020 |  | N | No
AE2-066 | Gloucester 13 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4.5 | 4.5 | 1.89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2019 | N/A | N/A |  | 5/15/2019 |  | 12/10/2019 |  |  | N | No
AE2-067 | N. Meshoppen 34 kV |  | PA | Wyoming | Withdrawn | PENELEC | 20 | 20 | 19.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2067_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 9/4/2019 |  | 1/1/2021 |  |  | N | No
AE2-068 | Second Street12 kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 4/30/2019 |  | 6/1/2020 |  |  | N | No
AE2-069 | Burlington 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2019 | N/A | N/A |  | 4/10/2019 |  | 6/1/2020 |  |  | N | No
AE2-070 | White Rock 34 kV |  | MD | Howard | Withdrawn | BGE | 4 | 4 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2070_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-071 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-072 | East Leipsic-Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2072_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-073 | Centerburg 138kV |  | OH | Licking | Active | AEP | 200 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2073_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2019 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AE2-074 | Potter 46 kV |  | PA | Potter | Active | APS | 35 | 35 | 15.11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2074_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-075 | Second Street 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.4 | 4.4 | 2.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2019 | N/A | N/A |  | 4/30/2019 |  | 6/1/2020 |  |  | N | No
AE2-076 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2019 | N/A | N/A |  | 4/10/2019 |  | 6/1/2020 |  |  | N | No
AE2-077 | Pierpoint-Freeport |  | IL | Winnebago | Withdrawn | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2077_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 9/3/2019 |  | 12/31/2021 |  |  | N | No
AE2-078 | Poolesville 34.5 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2078_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 2/21/2019 | N/A | N/A |  |  |  | 6/18/2021 |  |  | N | No
AE2-079 | Poolesville 34.5 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2079_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 2/21/2019 | N/A | N/A |  |  |  | 6/18/2021 |  |  | N | No
AE2-080 | Poolesville 34.5 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2080_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2019 | N/A | N/A |  | 4/28/2020 |  | 6/18/2021 |  |  | N | No
AE2-081 | Howell 12.47 kV Solar II | Casino Drive Solar | NJ | Monmouth | Engineering and Procurement | JCPL | 3.2 | 3.2 | 1.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2081_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2081_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2081_wmpa.pdf | Not Required | N/A | N/A |  | 1/31/2019 | N/A | N/A | 5/1/2022 |  |  | 5/1/2022 | 5/1/2022 |  | N | No
AE2-082 | Englishtown-Wyckoff 34.5 kV Solar |  | NJ | Monmouth | Active | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2082_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 9/30/2019 |  |  | N | No
AE2-083 | Forrester Solar 34.5 kV |  | NJ | Mercer | Withdrawn | JCPL | 1.6 | 1.625 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 3/5/2019 |  | 3/2/2020 |  |  | N | No
AE2-084 | Derry Tap-Derry Bus 69 kV |  | PA | Montour | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-085 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5.04 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2085_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-086 | Reeder Road Solar 12.47 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-087 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.5 | 4.54 | 1.47 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2087_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-088 | Clayton 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 2.5 | 2.53 | 0.735 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2088_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-089 | Pennville-Adams 138 kV |  | IN | Jay | Active | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2089_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-090 | Randolph-Hodgin 138 kV |  | IN | Randolph | Active | AEP | 144 | 144 | 86.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2090_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-091 | Newport 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 35 | 35 | 23 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2091_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-092 | Kidds Store-Sherwood 115 kV |  | VA | Albemarle | Active | Dominion | 138 | 138 | 82.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2092_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AE2-093 | Easton-Steele 138 kV |  | MD | Talbot | Active | DPL | 44 | 44 | 16.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2093_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-094 | Carson-Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 300 | 300 | 207.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2094_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-095 | Hopewell 26 kV |  | NJ | Mercer | Withdrawn | PSEG | 2.2 | 2.145 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-096 | East Flemington-Frenchtown Solar 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.8 | 2.75 | 1.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2096_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 9/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-097 | Levittown 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2097_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-098 | Belvidere Solar 12 kV |  | NJ | Warren | Withdrawn | JCPL | 1.9 | 1.875 | 0.79 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-099 | Burlington 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2.8 | 2.77 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-100 | Carlstadt 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 2.3 | 2.3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2100_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-101 | Nortonville 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2101_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/21/2019 |  | 3/2/2020 |  |  | N | No
AE2-102 | Columbus 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5.04 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/4/2019 |  | 3/2/2020 |  |  | N | No
AE2-103 | Cookstown-Van Hiseville Solar 34.5 kV |  | NJ | Ocean | Withdrawn | JCPL | 3 | 3 | 1.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 5/23/2019 |  | 3/2/2020 |  |  | N | No
AE2-104 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 49 | 49 | 18.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2104_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-105 | Kittatinny-Newton Solar 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 3.5 | 1.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2105_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 9/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-106 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.9 | 4.915 | 1.63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2106_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 8/22/2019 |  | 3/2/2020 |  |  | N | No
AE2-107 | Haumesser Road 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2107_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-108 | Kings Dominion DP 115kV |  | VA | Hanover | Withdrawn | Dominion | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2108_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/8/2020 |  | 3/31/2020 |  |  | N | No
AE2-109 | Kings Dominion DP 115 kV |  | VA | Hanover | Withdrawn | Dominion | 7 | 7 | 2.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2109_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/8/2020 |  | 3/31/2021 |  |  | N | No
AE2-110 | Columbia-West Bloomsburg 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2110_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-111 | Beavertown Tap-Beavertown Weaving Tap 69kV |  | PA | Snyder | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2111_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-112 | Carville 138 kV |  | MD | Queen Anne's | Active | DPL | 66 | 17 | 6.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2112_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-113 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Active | APS | 130 | 130 | 62.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2113_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-114 | Midland 23 kV I | BE-PINE 1 Cain Road | PA | Beaver | Engineering and Procurement | DL | 17.1 | 17.1 | 10.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2114_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2114_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2114_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AE2-115 | Midland 23 kV II | BE-PINE 2 Dam Road | PA | Beaver | Engineering and Procurement | DL | 17.1 | 17.1 | 10.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2115_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2115_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2115_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N | No
AE2-116 | Midland 23 kV III |  | N/A | N/A | Withdrawn | DL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2116_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 12/3/2019 |  | 9/1/2021 |  |  | N | No
AE2-117 | ABW Tap-Alexandria 46 kV |  | PA | Huntingdon | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2117_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 8/2/2021 |  |  | N | No
AE2-118 | ABW Tap-Williamsburg 46 kV |  | PA | Huntingdon | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2118_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-119 | Shawville-Phillipsburg 34.5 kV |  | N/A | N/A | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2119_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 12/16/2019 |  | 9/1/2021 |  |  | N | No
AE2-120 | Graymont-Zion 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2120_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-121 | Milesburg-Tanney Junction 46 kV |  | PA | Centre | Active | APS | 10.6 | 10.64 | 6.384 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2121_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-122 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2122_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AE2-123 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 800.1 | 163.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2123_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AE2-124 | Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 800.1 | 148.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2124_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | Suspended | APS | 13.8 | 13.8 | 8.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2125_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2125_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2125_wmpa.pdf | Not Required | N/A | N/A |  | 2/28/2019 | N/A | N/A | 12/31/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AE2-126 | Dubois-Curwensville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2126_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-127 | Milesburg-Moshannon 230 kV |  | PA | Centre | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/12/2019 |  | 11/1/2021 |  |  | N | No
AE2-128 | Milesburg-Moshannon 230 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  | 4/12/2019 |  | 10/1/2021 |  |  | N | No
AE2-129 | Philipsburg-Clarence 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2129_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/9/2021 |  |  | N | No
AE2-130 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2130_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-131 | Philipsburg-Karthaus 34.5 |  | PA | Westmoreland | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2131_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 9/9/2021 |  |  | N | No
AE2-132 | Remington CT 230 kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 190 | 0 | 17.7 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2132_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_132_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/1/2019 | N/A | N/A |  |  |  | 5/31/2020 |  | 10/17/2019 | N | No
AE2-133 | Penns Tap-Richfield Tie 69 kV |  | PA | Snyder | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | Suspended | Dominion | 62.5 | 0 | 16.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_134_csa.pdf | Document Posted | N/A | N/A |  | 3/4/2019 | N/A | N/A |  |  |  | 12/31/2021 | 12/31/2021 |  | N | No
AE2-135 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 500 | 500 | 250 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2019 | N/A | N/A |  | 4/5/2019 |  | 12/15/2022 |  |  | N | No
AE2-136 | Muskingum River-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 114 | 114 | 83.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2136_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-137 | Yukon-Robbins 138 kV II |  | PA | Westmoreland | Active | APS | 625 | 84 | 87 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2137_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AE2-138 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 260 | 260 | 189.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2138_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-139 | East Towanda-Grover 230 kV |  | PA | McKean | Active | PENELEC | 100.5 | 100.5 | 60.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2139_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AE2-140 | Axton-Danville 138 kV |  | VA | Henry | Active | AEP | 201.1 | 201.1 | 120.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2140_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AE2-141 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 3 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2141_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/4/2019 |  | 6/1/2021 |  |  | N | No
AE2-142 | Glen Gardner-Washington Solar 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-143 | Yardville 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.9 | 3.905 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2143_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-144 | Deptford 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4 | 4.03 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2144_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-145 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 2.5 | 2.52 | 0.84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 4/3/2019 |  | 3/2/2020 |  |  | N | No
AE2-146 | Gold 115 kV |  | PA | Potter | Withdrawn | PENELEC | 183 | 183 | 75.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2019 | N/A | N/A |  | 9/4/2019 |  | 3/5/2021 |  |  | N | No
AE2-147 | Swamp 230 kV |  | NC | Perquimans | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2147_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-148 | Beatty-Greene 345 kV |  | OH | Madison | Active | AEP | 577 | 577 | 397.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/20/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-149 | Biers Run-Bixby 345 kV |  | OH | Pickaway | Active | AEP | 400 | 400 | 291.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2149_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-150 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Active | Dominion | 75 | 0 | 0 |  | Energy | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2150_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  | 8/26/2019 |  | 6/1/2022 |  |  | N | No
AE2-151 | Earleys 34.5kV |  | NC | Hertford | Active | Dominion | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2151_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2151_imp.pdf | Document Posted |  |  | N/A |  | N/A |  | Not Required | N/A | N/A |  | 3/14/2019 | N/A | N/A |  |  |  | 3/1/2020 |  |  | N | No
AE2-152 | Wilton Center-Loretto |  | IL | Kankakee | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2152_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2019 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE2-153 | Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2153_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  |  |  | 3/31/2021 |  |  | N | No
AE2-154 | Meadow Lake 345 kV (MLV VIII) |  | IN | White | Active | AEP | 250 | 250 | 32.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2154_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/14/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE2-155 | Old Church 34.5 kV | Hanover Solar | VA | Hanover | Engineering and Procurement | Dominion | 25 | 5 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2155_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_155_isa.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/1/2020 | 12/1/2020 |  | N | No
AE2-156 | Yadkin 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2156_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-157 | Wakefield–Waverly 115 kV |  | VA | Sussex | Withdrawn | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2157_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2021 |  |  | N | No
AE2-158 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 |  |  |  | Energy | Merchant Transmission | Hydro | AC | 48 NFTIR | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 4/1/2019 |  | 10/1/2021 |  |  | S | No
AE2-159 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 | 48 | 0 |  | Energy | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2159_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 11/21/2019 |  | 10/1/2021 |  |  | N | No
AE2-160 | Kanawha River 138 kV |  | WV | Fayette | Active | AEP | 51 | 51 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2160_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-161 | Morris Park-Washington 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 4/2/2019 |  | 3/2/2020 |  |  | N | No
AE2-162 | Lumberton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.8 | 3.78 | 1.26 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 5/6/2019 |  | 3/2/2020 |  |  | N | No
AE2-163 | West Caldwell 13.2 kV |  | NJ | Essex | Withdrawn | PSEG | 1 | 1 | 0.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2163_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-164 | Saddle Brook 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 1.4 | 1.4 | 0.588 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2164_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-165 | Cedar Grove 13.2 kV |  | NJ | Passaic | Withdrawn | PSEG | 2.6 | 2.6 | 1.092 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2165_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-166 | Stockton 138 kV |  | VA | Henry | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2166_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-167 | Belmont-Harrison 500 kV |  | WV | Doddridge | Withdrawn | APS | 1335 | 1335 | 1315 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2167_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 9/6/2019 |  | 7/1/2023 |  |  | N | No
AE2-168 | Belmont-Harrison 500 kV II |  | WV | Doddridge | Withdrawn | APS | 665 | 665 | 660 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2168_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 9/6/2019 |  | 7/1/2023 |  |  | N | No
AE2-169 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2169_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-170 | Gaston-Desoto 138 kV |  | IN | Delaware | Withdrawn | AEP | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-171 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 150 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2171_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-172 | Mississinewa-Gaston 138 kV |  | IN | Grant | Active | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2172_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-173 | McLean 345 kV |  | IL | McLean | Active | ComEd | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-174 | Seneca 138 kV |  | OH | Seneca | Active | AEP | 198 | 198 | 34.85 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2174_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE2-175 | Jackson-Long Pond 69 kV |  | PA | Monroe | Active | PPL | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2175_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE2-176 | Groton 138 kV Solar |  | OH | Erie | Active | ATSI | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2176_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE2-177 | Squabb SVC 230 kV |  | PA | Elk | Withdrawn | APS | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/8/2019 |  | 10/31/2021 |  |  | N | No
AE2-178 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/8/2019 |  | 10/31/2021 |  |  | N | No
AE2-179 | Lick-Waverly 115kV |  | OH | Pike | Withdrawn | OVEC | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/1/2019 |  | 10/31/2021 |  |  | N | No
AE2-180 | Beatty-London 138 kV III |  | OH | Madison | Withdrawn | ATSI | 79 | 79 | 47.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2180_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 9/3/2019 |  | 10/31/2021 |  |  | N | No
AE2-181 | Snyder 69kV |  | OH | Williams | Active | ATSI | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2181_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AE2-182 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 122 | 17 | 11.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2182_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AE2-183 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 1756 | 75 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2183_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 5/31/2020 |  |  | N | No
AE2-184 | Warren County 500 kV |  | VA | Warren | Active | Dominion | 1499 | 15 | 0 |  | Energy | Generation Interconnection | Natural Gas; Other |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2184_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 5/31/2020 |  |  | N | No
AE2-185 | Gladys DP-Stonemill Switching Station 69 kV |  | VA | Campbell | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-186 | Brandy DP-Remington 115 kV |  | VA | Fauquier | Withdrawn | Dominion | 60 | 60 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 4/29/2019 |  | 9/1/2020 |  |  | N | No
AE2-187 | Shockoe DP-Chatham 69 kV |  | VA | Pittsylvania | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-188 | Mitchell DP-Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2188_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2020 |  |  | N | No
AE2-189 | Housenville 138 kV |  | PA | Butler | Withdrawn | APS | 42 | 42 | 17.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2189_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  | 8/12/2019 |  | 12/31/2022 |  |  | N | No
AE2-190 | Elk Run D.P.-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 70 | 70 | 27.02 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2190_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-191 | Saxonburg 138 kV |  | PA | Butler | Active | APS | 52 | 52 | 21.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2191_Imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-192 | Orrtanna 115 kV |  | PA | Adams | Active | ME | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2192_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-193 | Shenango 138 kV |  | PA | Mercer | Active | ATSI | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2193_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2193_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-194 | Congress-Toronto 138 kV |  | OH | Columbiana | Active | ATSI | 175 | 175 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2194_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AE2-195 | East Canton-Robertsville 69 kV |  | OH | Stark | Active | AEP | 19.7 | 19.7 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2195_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2195_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-196 | Mt. Airy-Wythe 138 kV |  | VA | Wythe | Withdrawn | AEP | 94.6 | 94.6 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2196_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2196_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2022 |  |  | N | No
AE2-197 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  | 10/1/2020 |  |  | Y | No
AE2-198 |  |  | NJ | Mercer | Withdrawn | PSEG |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-199 |  |  | NJ | Camden | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-200 |  |  | NJ | Salem | Withdrawn | AEC |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 4/1/2019 |  |  |  |  | Y | No
AE2-201 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-202 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 3.9 | 3.88 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-203 |  |  | NJ | Warren | Withdrawn | JCPL | 4.4 | 4.38 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2019 |  |  |  |  | Y | No
AE2-204 | Bolivar 34.5 kV |  | OH | Stark | Active | AEP | 19.3 | 19.3 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2204_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  |  |  | 5/1/2021 |  |  | N | No
AE2-205 | Cumberland 230 kV |  | NJ | Cumberland | Withdrawn | AEC | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2205_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-206 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 99 | 99 | 41.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-207 | Heartsease DP-Mayo Dunbar 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 18 | 18 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2207_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 8/21/2019 |  | 12/31/2020 |  |  | N | No
AE2-208 | Chavies-Bonnyman 69 kV |  | KY | Perry | Withdrawn | AEP | 80 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2208_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2208_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2021 |  |  | N | No
AE2-209 | Airey 69 kV |  | MD | Dorchester | Withdrawn | DPL | 56 | 56 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2209_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 3/31/2020 |  | 12/31/2021 |  |  | N | No
AE2-210 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2210_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-211 | Jackson-Three Mile Island 230 kV |  | PA | York | Active | ME | 55 | 55 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2211_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2211_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-212 | Harrowgate 34 kV |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2212_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-213 | Thorofare 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 3.2 | 3.145 | 1.1025 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2213_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2213_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  | 8/14/2019 |  | 3/2/2020 |  |  | N | No
AE2-214 | Cole 345 kV |  | OH | Franklin | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2214_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2214_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-215 | Blaine 115 kV |  | PA | Perry | Withdrawn | PENELEC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2215_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2215_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  | 3/27/2020 |  | 12/31/2021 |  |  | N | No
AE2-216 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2216_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2216_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-217 | East Springfield-London 138 kV |  | OH | Clark | Active | ATSI | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2217_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2217_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-218 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 178 | 178 | 106 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2218_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-219 | Bluff Point-Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2219_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-220 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2220_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2220_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-221 | Clinton-Stuart 345 kV |  | OH | Clinton | Active | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2221_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-222 | Higbee 69 kV |  | NJ | Atlantic | Active | AEC | 300 | 300 | 85.424 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2222_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2222_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AE2-223 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2223_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-224 | Bearrock-Johnstown 230 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2224_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2224_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-225 | Suffolk 34 kV | Hosier Road Solar | VA | City of Suffolk | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2225_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2225_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2225_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2225_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AE2-226 | Millville-Old Chapel 138 kV |  | WV | Jefferson | Active | APS | 99 | 99 | 59.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2226_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-227 | Iron Bridge 34 kV |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2227_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-228 | Tyler 34 kv |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2228_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-229 | Suffolk 34 kV | Hosier Road Solar II | VA | City of Suffolk | Engineering and Procurement | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2229_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2229_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2229_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AE2-230 | Bartonsville-Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2230_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2230_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-231 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2231_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-232 | Oyster Creek 230 kV II |  | N/A | N/A | Withdrawn | JCPL | 400 | 400 | 112.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2232_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2232_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 3/26/2020 |  | 6/1/2023 |  |  | N | No
AE2-233 | Carson-Rogers Rd 500 kV |  | N/A | N/A | Withdrawn | Dominion | 94 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2233_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 10/2/2019 |  | 6/1/2022 |  |  | N | No
AE2-234 | Liberty Center-Buckeye Tap 69 kV |  | IN | Huntington | Active | AEP | 35 | 35 | 24.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2234_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2234_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 7/31/2021 |  |  | N | No
AE2-235 | Murphysville-Plumville 69 kV |  | KY | Mason | Withdrawn | EKPC | 60 | 60 | 41.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2235_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 8/13/2019 |  | 7/31/2021 |  |  | N | No
AE2-236 | Columbia-Northeast 138 kV |  | IN | Whitley | Active | AEP | 55 | 55 | 38.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2236_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2236_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 7/31/2021 |  |  | N | No
AE2-237 | Vernon-Sugar Loaf #2 115 kV |  | NJ | Sussex | Active | JCPL | 107 | 107 | 21.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2237_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AE2-238 | Reybold 12 kV |  | DE | New Castle | Withdrawn | DPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2238_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  | 9/17/2019 |  | 5/14/2021 |  |  | N | No
AE2-239 | Tanners Creek-East Bend & Miami Fort-Terminal 345 kV |  | N/A | N/A | Withdrawn | AEP | 100 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 4/1/2019 |  | 3/1/2023 |  |  | S | No
AE2-240 | Olive-Reynolds 1 & 2 345 kV |  | IN | Starke | Active | AEP | 3170 |  |  |  | Energy | Merchant Transmission |  | AC | 0 | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 6/1/2019 |  |  | S | No
AE2-241 | Bloomsburg-Columbia 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2241_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2241_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AE2-242 | Bowmanns Mill-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 85 | 85 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2242_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/24/2019 |  | 3/5/2021 |  |  | N | No
AE2-243 | East Carbondale 12.47 kV I |  | PA | Wayne | Withdrawn | PPL | 16.5 | 16.5 | 2.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2243_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/6/2019 |  | 3/31/2021 |  |  | N | No
AE2-244 | East Carbondale 12.47 kV II |  | PA | Wayne | Withdrawn | PPL | 16.5 | 16.5 | 2.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2244_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  | 9/6/2019 |  | 3/31/2021 |  |  | N | No
AE2-245 | Stockton-Axton 34.5 kV |  | VA | Henry | Active | AEP | 20 | 0 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2245_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  |  |  | 12/30/2020 |  |  | N | No
AE2-246 | Gretna DP 69 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 0 | 13.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2246_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  | 9/10/2019 |  | 12/15/2020 |  |  | N | No
AE2-247 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 71 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2247_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2247_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AE2-248 | Fillmore-Thompson Farm 46 kV |  | PA | Centre | Active | APS | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2248_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2248_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-249 | Bedford North-Pennsylvania Hollow 23 kV |  | PA | Bedford | Active | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2249_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AE2-250 | Purdy Sw.-Reams 115 kV |  | VA | Greensville | Active | Dominion | 82.5 | 82.5 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2250_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2250_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-251 | Cardiff 230 kV |  | NJ | Monmouth | Active | AEC | 1200 | 1200 | 337.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2251_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2251_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AE2-252 | Gardners-Mountain 115 kV |  | PA | Cumberland | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2252_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2252_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  | 3/25/2020 |  | 11/9/2021 |  |  | N | No
AE2-253 | Hickory-Moyock 230 kV |  | NC | Currituck | Active | Dominion | 100 | 50 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2253_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2253_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AE2-254 | Garrard County-Tommy-Gooch 69 kV |  | KY | Garrard | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2254_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-255 | Molecreek 345 kV |  | IL | Woodford | Active | ComEd | 400 | 100 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2255_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2255_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-256 | Copperstone-North Lebanon 230 kV |  | PA | Lebanon | Active | ME | 70 | 70 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2256_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-257 | Cedar Neck 69 kV |  | DE | Sussex | Active | DPL | 120 | 120 | 33 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2257_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-258 | Chase City 115 kV |  | VA | Mecklenburg | Active | Dominion | 49.9 | 0 | 14.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2258_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2258_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2019 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AE2-259 | Curdsville-Willis Mtn 115 kV |  | VA | Buckingham | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2259_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-260 | Clubhouse 230 kV |  | VA | Greensville | Active | Dominion | 200 | 200 | 82.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2260_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/30/2020 |  |  | N | No
AE2-261 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 299 | 299 | 179.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2261_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-262 | Moshannon-Milesburg 230 kV |  | PA | Centre | Active | PENELEC | 83.6 | 83.6 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2262_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2262_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-263 | Moshannon-Milesburg 230 kV |  | PA | Centre | Active | PENELEC | 78.4 | 78.38 | 47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2263_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2263_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 7/31/2022 |  |  | N | No
AE2-264 | Altoona-Raystown 230 kV |  | PA | Blair | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2264_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2264_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-265 | Corey 138 kV |  | MI | St. Joseph | Withdrawn | AEP | 150 | 150 | 47.78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 4/1/2019 |  | 9/1/2021 |  |  | N | No
AE2-266 | Corey 138kV |  | MI | St. Joseph | Withdrawn | AEP | 198.9 | 198.9 | 64.19 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 4/1/2019 |  | 9/1/2021 |  |  | N | No
AE2-267 | Woodsdale 345 kV |  | OH | Butler | Active | DEOK | 50 | 50 | 30.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2267_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2267_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 10/20/2021 |  |  | N | No
AE2-268 | Harmony Village 34 kV |  | VA | Middlesex | Withdrawn | Dominion | 15 | 15 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2268_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2268_imp.pdf | Document Posted |  | Not Required |  | Withdrawn | N/A |  | Not Required | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 9/12/2019 |  | 12/31/2021 |  |  | N | No
AE2-269 | Fayetteville 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 22 | 9.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2269_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  | 8/12/2019 |  | 12/31/2021 |  |  | N | No
AE2-270 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2270_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2270_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 9/29/2021 |  |  | N | No
AE2-271 | Montour 230 kV |  | PA | Montour | Active | PPL | 101.6 | 101.6 | 61 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2271_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2271_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-272 | Woodstown 12 kV | Pilesgrove Solar | NJ | Salem | In Service | AEC | 19.9 |  | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2272_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2272_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_272_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2019 | 12/31/2019 | 9/17/2019 | N | No
AE2-273 | Siegfried-Hauto 69KV | PA Solar Park | PA | Carbon | Partially in Service - Under Construction | PPL | 20 | 0 | 0.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2273_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2273_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_273_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_273_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-274 | Siegfried-Hauto 69 kV | PA Solar Park | PA | Carbon | Partially in Service - Under Construction | PPL | 20 | 0 | 0.4 | 0 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2274_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2274_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_274_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_274_csa.pdf | Document Posted | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 1/17/2020 | N | No
AE2-275 | JK Smith-Fawkes 138 kV |  | KY | Madison | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2275_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-276 | Sullivan 345kV |  | IN | Sullivan | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2276_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2276_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-277 | McDowell 138 kV |  | PA | Mercer | Active | ATSI | 38.2 | 38.2 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2277_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2277_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-278 | Urbana 138 kV |  | OH | Champaign | Active | Dayton | 150.7 | 150.7 | 90.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2278_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2278_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-279 | Oxford 115 kV |  | PA | Adams | Withdrawn | ME | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2279_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  | 9/6/2019 |  | 10/1/2021 |  |  | N | No
AE2-280 | Claytor Lake-Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 126.7 | 126.65 | 75.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2280_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-281 | Powerton-Goodings Grove |  | IL | Woodford | Active | ComEd | 400 | 50 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2281_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2281_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-282 | East Fayette 138 kV |  | OH | Fulton | Active | ATSI | 67 | 67 | 43.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2282_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2282_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AE2-283 | Gladys-Stone Mill 69 kV |  | VA | Campbell | Active | Dominion | 60.4 | 60.4 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2283_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-284 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Withdrawn | AEP | 225 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2284_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 1/30/2020 |  | 12/31/2022 |  |  | N | No
AE2-285 | Maysville 69 kV |  | PA | Mercer | Active | ATSI | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2285_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2285_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-286 | Airey 12 kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 19.5 | 7.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2286_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/1/2019 |  | 12/31/2019 |  |  | N | No
AE2-287 | Brunswick 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2287_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/22/2019 |  | 6/30/2022 |  |  | N | No
AE2-288 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 1233 | 90 | 206 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2288_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2288_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/7/2020 |  | 5/1/2023 |  |  | N | No
AE2-289 | Frostburg 138 kV |  | PA | Somerset | Active | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2289_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2289_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-290 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2290_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2290_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AE2-291 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Active | Dominion | 102 | 102 | 61.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2291_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE2-292 | Grit DP-Perth 115 kV |  | VA | Campbell | Active | Dominion | 127 | 127 | 76.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2292_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2292_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE2-293 | Dauphin-Pine Grove 69kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 6/1/2020 |  |  | N | No
AE2-294 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 3/31/2020 |  |  | N | No
AE2-295 | Eldred 230 kV |  | PA | Schuylkill | Active | PPL | 174.8 | 174.8 | 25.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2295_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2295_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AE2-296 | Hutchings West 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 104 | 104 | 104 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2296_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 8/20/2019 |  | 5/1/2020 |  |  | N | No
AE2-297 | Madison-Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 152.5 | 152.5 | 91.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2297_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-298 | Haviland-N. Van Wert 69 kV |  | OH | Van Wert | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2298_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2298_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-299 | Erie East 230 kV |  | PA | Erie | Active | PENELEC | 160 | 160 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2299_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AE2-300 |  |  | OH | Licking | Withdrawn | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/1/2019 |  | 9/22/2022 |  |  | N | No
AE2-301 | Crisfield 25 kV |  | PA | Somerset | Withdrawn | DPL | 5.5 | 5.5 | 2.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2301_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2301_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 3/26/2020 |  | 9/22/2021 |  |  | N | No
AE2-302 | East Beaver-Lick 138 kV |  | OH | Jackson | Active | AEP | 63 | 63 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2302_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2302_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AE2-303 | Honda Marysville Tap-Honda Marysville 69 kV |  | OH | Union | Active | Dayton | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2303_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2303_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AE2-304 | South Hertford 34 kV | South Hertford Solar | NC | Perquimans | Engineering and Procurement | Dominion | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2304_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2304_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2304_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2304_wmpa.pdf | Not Required | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 6/1/2022 | 6/1/2022 |  | N | No
AE2-305 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2305_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2305_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 8/1/2021 |  |  | N | No
AE2-306 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2306_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2306_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 8/1/2021 |  |  | N | No
AE2-307 | Braidwood-East Frankfort |  | IL | Will | Withdrawn | ComEd | 375 | 225 | 165 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2307_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-308 | Three Forks-Dale 138 kV |  | KY | Madison | Active | EKPC | 150 | 150 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2308_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AE2-309 | Carlos Junction-Lonaconing 34.5 kV |  | MD | Allegany | Active | APS | 19.8 | 19.84 | 16.66 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2309_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2309_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 10/30/2020 |  |  | N | No
AE2-310 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 200 | 85 | 67 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2310_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 2/7/2020 |  | 5/31/2021 |  |  | N | No
AE2-311 | Carson-Septa 500 kV |  | VA | Sussex | Withdrawn | Dominion | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 6/19/2019 |  | 12/31/2021 |  |  | N | No
AE2-312 | Rocky Road |  | IL | Kane | Withdrawn | ComEd | 411.7 | 7 | 7 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 4/4/2019 |  | 6/1/2019 |  |  | N | No
AE2-313 | Carson-Rawlings 500 kV |  | VA | Dinwiddie | Active | Dominion | 314 | 314 | 188.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2313_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2313_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AE2-314 | Cardiff 230 kV |  | NJ | Atlantic | Withdrawn | AEC | 72 | 72 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2314_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  | 12/16/2019 |  | 6/30/2022 |  |  | N | No
AE2-315 | Yankee Tap 69 kV |  | PA | Montgomery | Active | Dayton | 124 | 23.5 | 23.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2315_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2315_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AE2-316 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Active | PENELEC | 100 | 100 | 41.22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2316_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2316_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-317 | Pequest River 115 kV |  | N/A | N/A | Withdrawn | JCPL | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2317_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2317_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/7/2020 |  | 6/30/2022 |  |  | N | No
AE2-318 | Ford-Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 100 | 100 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2318_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2318_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-319 | Atlanta 69kV I |  | OH | Pickaway | Active | Dayton | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2319_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2319_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/1/2019 |  | 12/1/2022 |  |  | N | No
AE2-320 | Atlanta 69 kV II |  | OH | Pickaway | Active | Dayton | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2320_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2320_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-321 | Belvidere-Marengo 138 kV |  | IL | McHenry | Active | ComEd | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2321_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2321_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-322 | Mark Center 69 kV |  | OH | Defiance | Active | AEP | 60 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2322_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2322_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-323 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Active | AEP | 100 | 100 | 67.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2323_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-324 | Galion-Roberts South II 138 kV |  | OH | Marion | Active | ATSI | 120.3 | 20.3 | 20.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2324_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2324_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-325 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2325_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-326 | Jacksons Ferry 138 kV |  | VA | Wythe | Active | AEP | 127.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2326_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-327 | Biers Run-Circleville 138 kV |  | OH | Pickaway | Withdrawn | AEP | 162.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2327_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 3/6/2020 |  | 12/1/2021 |  |  | N | No
AE2-328 | Briery DP-Clover 230 kV |  | N/A | N/A | Withdrawn | Dominion | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2328_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 9/23/2019 |  | 4/1/2022 |  |  | N | No
AE2-329 | Cedarville-Ford 138 kV |  | OH | Clermont | Withdrawn | DEOK | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2022 |  |  | N | No
AE2-330 | Belvidere-Marengo |  | IL | McHenry | Withdrawn | ComEd | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-331 | Mark Center 69 kV |  | OH | Defiance | Withdrawn | AEP | 34.8 | 34.8 | 139.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-332 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2021 |  |  | N | No
AE2-333 | Bedington 138 kV |  | MD | Frederick | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2333_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-334 | Clayton-Williamstown 69 kV |  | NJ | Gloucester | Active | AEC | 44 | 44 | 28.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2334_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2334_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AE2-335 | Gloucester Solar II |  | NJ | Gloucester | Withdrawn | AEC | 60 | 60 | 41.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2335_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2335_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 3/31/2020 |  | 6/30/2022 |  |  | N | No
AE2-336 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 4.6 | 4.6 | 1.932 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2336_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 9/6/2019 |  | 12/31/2020 |  |  | N | No
AE2-337 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.4 | 2.4 | 1.008 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2337_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 9/6/2019 |  | 12/31/2020 |  |  | N | No
AE2-338 | Avon 138 kV |  | KY | Fayette | Withdrawn | EKPC | 20.3 | 20.3 | 81.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/22/2019 |  | 12/1/2022 |  |  | N | No
AE2-339 | Avon 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2339_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-340 | Sandwich-Plano |  | IL | Kendall | Withdrawn | ComEd | 52.2 | 52.2 | 208.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  | 4/29/2019 |  | 12/1/2022 |  |  | N | No
AE2-341 | Sandwich-Plano |  | IL | Kendall | Active | ComEd | 150 | 150 | 100.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2341_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-342 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2342_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2342_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-343 | Andover (Maysville) 69 kV II |  | PA | Crawford | Active | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE2-344 | Edinboro South-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 116.5 | 116.5 | 69.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2344_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2344_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-345 | Hunterstown-Texas Eastern Tap 115 kV |  | PA | Adams | Active | ME | 97.5 | 97.5 | 58.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2345_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2345_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-346 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 17 | 12 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2346_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2346_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 12/30/2019 |  |  | N | No
AF1-001 | Thayerville 34.5 kV |  | MD | Garrett | Active | APS | 13.8 | 13.75 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1001_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 3/2/2020 |  |  | N | No
AF1-002 | Berwick 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 5 | 5 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1002_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  | 3/4/2020 |  | 3/31/2020 |  |  | N | No
AF1-003 | Hawkins Gate-Billingsley Rd 69 kV |  | MD | Charles | Active | SMECO | 20 | 20 | 9.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1003_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 7/30/2021 |  |  | N | No
AF1-004 | Hwy 228-Bennsville 69 kV |  | MD | Charles | Active | SMECO | 16.8 | 16.8 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1004_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AF1-005 | Charles County Solar I |  | MD | Charles | Active | SMECO | 20 | 20 | 9.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1005_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 7/30/2021 |  |  | N | No
AF1-006 | Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1006_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AF1-007 | Indian River 230 kV I |  | DE | Sussex | Active | DPL | 255.1 | 7.3 | 1.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1007_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF1-008 | CPV NJ Solar |  | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 5/6/2019 |  | 12/31/2019 |  |  | N | No
AF1-009 | Dixon-McGirr |  | IL | Lee | Active | ComEd | 125 | 25 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1009_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-010 | Schauff Road |  | IL | Lee | Withdrawn | ComEd | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1010_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2021 |  |  | N | No
AF1-011 | Schauff Road |  | IL | Bureau | Active | ComEd | 30 | 30 | 11.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1011_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF1-012 | Electric Junc-Nelson |  | IL | Lee | Active | ComEd | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1012_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AF1-013 | Dixon-McGirr |  | IL | Lee | Withdrawn | ComEd | 25 | 25 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1013_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2019 | N/A | N/A |  | 3/9/2020 |  | 12/1/2020 |  |  | N | No
AF1-014 | Harmony Village-Shackleford 115 kV |  | VA | King and Queen | Active | Dominion | 149.9 | 19.9 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1014_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-015 | Easton-Steele 138 kV |  | MD | Talbot | Active | DPL | 66 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1015_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-016 | Suffolk 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 71 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1016_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1016_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  | 2/20/2020 |  | 11/30/2021 |  |  | N | No
AF1-017 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 91 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1017_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-018 | Harmony Village 230 kV |  | VA | Middlesex | Active | Dominion | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1018_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2019 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N | No
AF1-019 | Branchville-Holiday Lakes 34.5 kV |  | NJ | Sussex | Active | JCPL | 20 | 19.999 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1019_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/5/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-020 5006187 | PJM-TVA |  | N/A | N/A | Withdrawn | Morgan Stanley Capital Group Inc. |  | 300 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | Withdrawn | [5 empty] | N/A | N/A | [5 empty] | 4/1/2019 | 1/1/2025 | 1/1/2030 |  | 12/11/2019 |  |  |  |  | PP | No
AF1-021 | Bethelboro-Connellsville #1 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/15/2019 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF1-022 | Lake Lynn-Uniontown 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1022_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/15/2019 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF1-023 | Atlantic-Red Bank 34 kV II |  | NJ | Monmouth | Active | JCPL | 20 | 0 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1023_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/18/2019 | N/A | N/A |  |  |  | 12/5/2019 |  |  | N | No
AF1-024 | Freeland Municipal Authority |  | N/A | N/A | Withdrawn | PPL | 19.9 | 19.9 | 9.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2019 | N/A | N/A |  | 5/21/2019 |  | 12/31/2021 |  |  | N | No
AF1-025 | N/A-N/A |  | DE | New Castle | Active | DPL | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Not Required |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/3/2019 | N/A | N/A |  |  |  | 5/31/2020 |  |  | EE | No
AF1-026 | Edge Road Battery Storage (CIRs) |  | NJ | Warren | Active | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1026_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1026_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 5/31/2019 |  |  | N | No
AF1-027 | Plumsted 537 Energy Storage (CIRs) |  | NJ | Ocean | Active | JCPL | 20 | 0 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1027_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2019 | N/A | N/A |  |  |  | 5/31/2019 |  |  | N | No
AF1-028 | Endless Caverns 115 kV |  | VA | Rockingham | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1028_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2019 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF1-029 | Haviland-N Van Wert 69 kV |  | OH | Van Wert | Active | AEP | 75 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1029_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/14/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-030 | Plano-R 138 kV |  | IL | Kendall | Active | ComEd | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1030_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-031 | Kings Dominion DP 115 kV |  | VA | Caroline | Active | Dominion | 93.5 | 93.5 | 60.69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1031_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-032 | Suffolk 34.5 kV |  | VA | City of Suffolk | Active | Dominion | 15 | 15 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1032_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-033 | Poolesville 34 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1033_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1033_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF1-034 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2019 | N/A | N/A |  | 6/12/2019 |  | 11/1/2021 |  |  | N | No
AF1-035 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn | [5 empty] | Withdrawn | N/A |  |  | N/A | N/A |  | 5/22/2019 | N/A | N/A |  | 6/12/2019 |  | 11/1/2021 |  |  | N | No
AF1-036 | Carville 138 kV |  | MD | Queen Anne's | Active | DPL | 89 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1036_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-037 | C.P. Crane 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1037_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/31/2019 | N/A | N/A |  | 3/9/2020 |  | 6/1/2021 |  |  | N | No
AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV |  | VA | Russell | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-039 | Listonburg-Highpoint 24.9 kV |  | PA | Somerset | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1039_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/6/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF1-040 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Active | PPL | 20 | 20 | 1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1040_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2019 | N/A | N/A |  |  |  | 12/1/2020 |  |  | N | No
AF1-041 | Absecon 12.47 kV | Pear Street Solar | NJ | Atlantic | In Service | AEC | 2.4 | 2.4 | 0 | 2.4 | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1041_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1041_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1041_wmpa.pdf | Not Required | N/A | N/A |  | 6/18/2019 | N/A | N/A |  |  |  | 3/3/2022 | 3/3/2022 | 5/8/2020 | N | No
AF1-042 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 131 | 45 | 17.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1042_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/24/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-043 | Moshannon-East Towanda 230 kV |  | PA | Clinton | Active | PENELEC | 640 | 92 | 105 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1043_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AF1-044 | Wye Mills-Longwood 69 kV |  | N/A | N/A | Withdrawn | DPL | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1044_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  | 2/7/2020 |  | 11/30/2021 |  |  | N | No
AF1-045 | Cedarville-Ford 138 kV |  | OH | Clermont | Active | DEOK | 152.2 | 52.2 | 31.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1045_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-046 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Active | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1046_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-047 | Mark Center 69 kV |  | OH | Defiance | Active | AEP | 94.8 | 34.8 | 20.88 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1047_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-048 | Belvidere-Marengo |  | IL | McHenry | Active | ComEd | 52.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1048_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-049 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1049_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2019 | N/A | N/A |  |  |  | 11/25/2022 |  |  | N | No
AF1-050 | Summer Shade - Green County 161 kV |  | KY | Green | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1050_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-051 | Gavin 765 kV |  | OH | Gallia | Active | AEP | 1360 | 11 | 11 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1051_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2019 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AF1-052 | Mason 230 kV |  | NJ | Hudson | Active | PSEG | 131.5 | 131.5 | 114.2 |  | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1052_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2019 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AF1-053 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 118 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1053_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-054 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 156.5 | 38.5 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1054_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-055 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 69.5 | 69.5 | 41.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1055_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 2/19/2020 |  | 10/31/2021 |  |  | N | No
AF1-056 | Maysville/Masury 138 kV |  | PA | Mercer | Withdrawn | ATSI | 100 | 100 | 68.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 8/27/2019 |  | 10/1/2023 |  |  | N | No
AF1-057 | Jackson-Three Mile Island 230 kV II |  | PA | York | Active | ME | 75 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1057_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF1-058 | Welco 34.5 kV |  | VA | Halifax | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1058_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-059 | Brodnax-South Hill 115 kV |  | VA | Mecklenburg | Active | Dominion | 99.2 | 99.2 | 99.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1059_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AF1-060 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 110.3 | 10.34 | 10.34 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1060_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF1-061 | Fayetteville 12.47 kV |  | PA | Franklin | Active | APS | 4 | 4 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1061_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/10/2021 |  |  | N | No
AF1-062 | Jug Street 138 kV |  | OH | Licking | Active | AEP | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1062_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 8/22/2022 |  |  | N | No
AF1-063 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1063_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF1-064 | Weston 69 kV |  | OH | Wood | Active | ATSI | 50 | 50 | 33.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1064_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF1-065 | Tidd-Wylie Ridge 345 kV III |  | WV | Brooke | Active | APS | 930 | 100 | 0 |  | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1065_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/24/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-066 | New Road 230 kV |  | VA | Loudoun | Active | Dominion | 300 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1066_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/2/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-067 | Kings Dominion DP 115 kV |  | VA | Caroline | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1067_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2019 | N/A | N/A |  |  |  | 12/16/2022 |  |  | N | No
AF1-068 | Boalsburg-Centre Hall 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1068_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/8/2019 | N/A | N/A |  |  |  | 1/10/2022 |  |  | N | No
AF1-069 | Carson-Rogers Rd 500 kV |  | VA | Sussex | Active | Dominion | 394 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1069_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-070 | North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 350 | 350 | 255.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2019 | N/A | N/A |  | 10/1/2019 |  | 6/1/2022 |  |  | N | No
AF1-071 | College Corner 138 kV |  | OH | Preble | Active | AEP | 100 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1071_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2019 | N/A | N/A |  |  |  | 7/1/2019 |  |  | N | No
AF1-072 | Rocky Road |  | IL | Kane | Active | ComEd | 410.8 | 17.2 | 17.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1072_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/14/2019 | N/A | N/A |  |  |  | 8/1/2019 |  |  | N | No
AF1-073 | Trowbridge 230 kV |  | NC | Washington | Withdrawn | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1073_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  | 2/11/2020 |  | 10/31/2021 |  |  | N | No
AF1-074 | Waverly-Wakefield 115 kV |  | VA | Sussex | Withdrawn | Dominion | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1074_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2019 | N/A | N/A |  | 2/20/2020 |  | 6/30/2022 |  |  | N | No
AF1-075 | Harrisburg-Endless Caverns 230 kV |  | VA | Rockingham | Active | Dominion | 73 | 73 | 45.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1075_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-076 | Southwest Lima 138 kV |  | OH | Allen | Active | AEP | 100 | 100 | 61.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1076_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-077 | Southwest Lima 138 kV |  | OH | Allen | Active | AEP | 200 | 100 | 61.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1077_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/22/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-078 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 144 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1078_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-079 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 150 | 44.8 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1079_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AF1-080 | Deer Creek-Fisher Body-Mullin 138 kV |  | IN | Madison | Active | AEP | 220 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1080_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF1-081 | Cumberland 230 kV |  | N/A | N/A | Withdrawn | AEC | 238 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1081_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2019 | N/A | N/A |  | 2/27/2020 |  | 6/30/2022 |  |  | N | No
AF1-082 | Heartsease-Mayo Dunbar DP |  | NC | Edgecombe | Active | Dominion | 93 | 18 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1082_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF1-083 | Green County-Saloma 161 kV |  | WV | Taylor | Active | EKPC | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1083_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/29/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-084 | East Hartford-Murch 69 kV |  | MI | Van Buren | Active | AEP | 85 | 85 | 54.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1084_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF1-085 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Active | AEP | 77 | 77 | 32.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1085_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF1-086 | Madera-Westover South 115 kV |  | PA | Clearfield | Active | PENELEC | 109.9 | 109.9 | 20.54 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1086_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-087 | Bakers Pond-Bell Ave 115 kV II |  | N/A | N/A | Withdrawn | Dominion | 75 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1087_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 2/18/2020 |  | 6/1/2022 |  |  | N | No
AF1-088 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 1000 | 1000 | 1000 |  | Capacity | Merchant Transmission |  |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/af1088_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF1-089 | New Castle 69 kV |  | IN | Henry | Withdrawn | EKPC | 70 | 70 | 53.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1089_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 2/12/2020 |  | 6/1/2022 |  |  | N | No
AF1-090 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1090_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF1-091 | Butler-S Hicksville 138 kV |  | IN | DeKalb | Active | AEP | 180 | 180 | 138.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1091_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-092 | Huntington Jct. 138 kV |  | IN | Huntington | Active | AEP | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1092_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-093 | Henderson-Stoneboro 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1093_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 12/8/2020 |  |  | N | No
AF1-094 | Union City-Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1094_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AF1-095 | Hertlein Road-Winburne 34 kV |  | PA | Clearfield | Withdrawn | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 10/2/2019 |  | 1/1/2023 |  |  | N | No
AF1-096 | Titusville-Oil Creek 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1096_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AF1-097 | Zion-E College Ave 34 kV |  | PA | Centre | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  | 9/19/2019 |  | 1/1/2023 |  |  | N | No
AF1-098 | Four Mile Jct-Corry East 115 kV |  | PA | Erie | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1098_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 2/15/2023 |  |  | N | No
AF1-099 | Moshannon-Milesburg 230 kV |  | PA | Huntingdon | Active | PENELEC | 126.5 | 126.5 | 75.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1099_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-100 | Shawville-Moshannon 230 kV |  | PA | Clearfield | Active | PENELEC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1100_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-101 | Oyster Creek 230 kV III |  | NJ | Atlantic | Active | JCPL | 800 | 800 | 224.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1101_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2019 | N/A | N/A |  |  |  | 11/23/2022 |  |  | N | No
AF1-102 | Gans 138 kV II |  | PA | Fayette | Active | APS | 96 | 0 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1102_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2019 | N/A | N/A |  |  |  | 5/22/2022 |  |  | N | No
AF1-103 | Warren 34.5 kV |  | PA | Warren | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1103_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-104 | Erie West 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1104_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-105 | Glen Gardner 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1105_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-106 | East Sayre 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1106_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-107 | Pohatcong 230 kV |  | NJ | Warren | Withdrawn | JCPL | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1107_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 4/13/2020 |  | 6/1/2023 |  |  | N | No
AF1-108 | East Flemington 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1108_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-109 | Pleasant Valley 230 kV |  | NJ | Mercer | Active | PSEG | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1109_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-110 | Kingsland 26 kV |  | N/A | N/A | Withdrawn | PSEG | 2 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/23/2019 |  |  |  |  | Y | No
AF1-111 | Kingsland 26 kV |  | N/A | N/A | Withdrawn | PSEG | 2 |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  | 9/23/2019 |  |  |  |  | Y | No
AF1-112 | Centre Hall-Boalsburg 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1112_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 4/3/2022 |  |  | N | No
AF1-113 | Gristmill 345 kV |  | OH | Auglaize | Active | AEP | 180 | 180 | 137.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1113_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-114 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1114_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF1-115 | Poolesville 230 kV |  | VA | Surry | Active | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1115_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-116 | Marion County 161 kV |  | TN | Washington | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1116_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AF1-117 | Atlanta-Stuart 345 kV |  | OH | Ross | Active | AEP | 200 | 200 | 152.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1117_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-118 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 350 | 350 | 268.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1118_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-119 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1119_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-120 | East Fayette 2 138 kV |  | OH | Fulton | Active | ATSI | 107 | 40 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1120_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-121 | Crain Highway 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1121_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  | 3/5/2020 |  | 11/30/2021 |  |  | N | No
AF1-122 | Cardington 138 kV |  | OH | Morrow | Active | ATSI | 64 | 64 | 26.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1122_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF1-123 | Fentress 500 kV |  | VA | City of Chesapeake | Active | Dominion | 880 | 880 | 267.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1123_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AF1-124 | Fentress 500 kV |  | VA | City of Chesapeake | Active | Dominion | 880 | 880 | 267.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1124_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AF1-125 | Fentress 500 kV |  | VA | City of Chesapeake | Active | Dominion | 880 | 880 | 267.5 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1125_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AF1-126 | Cookstown 230 kV |  | NJ | Burlington | Active | JCPL | 250 | 250 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1126_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 10/22/2022 |  |  | N | No
AF1-127 | Avon 345 kV |  | KY | Fayette | Active | EKPC | 80 | 80 | 53.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1127_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-128 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1128_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-129 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1129_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AF1-130 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1130_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-131 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Active | APS | 16.2 | 16.15 | 9.69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1131_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF1-132 | Shingletown-Boalsburg 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1132_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AF1-133 | Pequest River-Richmond 34.5 kV |  | PA | Northampton | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-134 | Philipsburg-Madera 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1134_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-135 | Madera 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1135_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 4/1/2022 |  |  | N | No
AF1-136 | Warfordsburg-Purcell Junction 34.5 kV |  | PA | Fulton | Active | APS | 15.7 | 15.72 | 9.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1136_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-137 | Newlinville 34.5 kV |  | PA | Chester | Active | PECO | 9.8 | 9.75 | 5.85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1137_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-138 | Huntingdon-Warrier Ridge 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1138_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 4/1/2022 |  |  | N | No
AF1-139 | Thompson 34.5 kV |  | PA | Wayne | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1139_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 3/19/2020 |  | 6/1/2022 |  |  | N | No
AF1-140 | Claysburg 23 kV |  | PA | Blair | Active | PENELEC | 16.3 | 16.3 | 9.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1140_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-141 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 96 | 96 | 62.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1141_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-142 | Moshannon-Milesburg 230 kV |  | PA | Clearfield | Active | PENELEC | 202.4 | 202.4 | 121.44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1142_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-143 | Lick Run 115 kV |  | PA | Somerset | Active | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1143_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-144 | Hayden 345 kV |  | OH | Franklin | Active | AEP | 100 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1144_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-145 | Flanders-Netcong 34.5 kV |  | NJ | Morris | Withdrawn | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  | 10/7/2019 |  | 10/1/2021 |  |  | N | No
AF1-146 | Hoytdale -McClelland 345 kV |  | PA | Lawrence | Active | ATSI | 202 | 201.95 | 121.17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1146_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-147 | Poland Rd-Runway DP |  | VA | Loudoun | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1147_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-148 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 159 | 159 | 95.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1148_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 4/30/2023 |  |  | N | No
AF1-149 | Graymont-Zion 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1149_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-150 | Midfield 22.9 kV |  | PA | Allegheny | Active | DL | 14.4 | 14.4 | 4.28 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1150_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 10/31/2021 |  |  | N | No
AF1-151 | Fayetteville 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1151_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2022 |  |  | N | No
AF1-152 | Swamp 230 kV |  | NC | Pasquotank | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1152_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AF1-153 | Motion-Ridgeway 46 kV |  | PA | Elk | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1153_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-154 | Dauphin |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 10/8/2019 |  | 5/1/2022 |  |  | N | No
AF1-155 | Paper City-Wilcox 46 kV |  | PA | Elk | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1155_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-156 | Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1156_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF1-157 | Laurel-Sussex 69 kV |  | DE | Sussex | Active | DPL | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1157_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-158 | Edison-Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1158_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 4/30/2023 |  |  | N | No
AF1-159 | Martinsville-Wilmington 69 kV |  | OH | Clinton | Active | Dayton | 50 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1159_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 3/31/2021 |  |  | N | No
AF1-160 | Silver Lake 69 kV |  | NJ | Camden | Active | AEC | 40 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1160_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AF1-161 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1161_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF1-162 | Inez 138 kV |  | KY | Martin | Active | AEP | 300 | 100 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1162_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-163 | Barren-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 120 | 120 | 80.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  | 12/11/2019 |  | 6/1/2022 |  |  | N | No
AF1-164 | Southwest Lima 345 kV |  | OH | Allen | Active | AEP | 300 | 300 | 195 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1164_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF1-165 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1165_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-166 | Target-Chambers No.5 34.5 kV |  | PA | Franklin | Active | APS | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1166_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-167 | West Freedom-C&K Coal 25 kV |  | PA | Clarion | Active | APS | 13.5 | 13.51 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1167_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-168 | Kingsland 26.4 kV I |  | NJ | Bergen | Withdrawn | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 10/8/2019 |  | 9/30/2020 |  |  | N | No
AF1-169 | Kingsland 26.4 kV II |  | NJ | Bergen | Withdrawn | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  | 10/8/2019 |  | 9/30/2020 |  |  | N | No
AF1-170 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1170_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 2/15/2023 |  |  | N | No
AF1-171 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1171_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 2/15/2023 |  |  | N | No
AF1-172 | Moshannon-Chapman 230 kV |  | PA | Clinton | Withdrawn | PENELEC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1172_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  | 3/2/2020 |  | 10/31/2022 |  |  | N | No
AF1-173 | Gretna DP-Shockoe DP 69 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 0 | 13.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1173_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 12/15/2020 |  |  | N | No
AF1-174 | Newlinville 34.5 kv II |  | PA | Chester | Active | PECO | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1174_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-175 | Donald C Cook-Jackson Road 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 152 | 152 | 91.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1175_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  | 4/16/2020 |  | 4/30/2023 |  |  | N | No
AF1-176 | Corey 138 kV |  | MI | St. Joseph | Active | AEP | 300 | 300 | 155.684 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1176_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF1-177 | Warren 115 kV |  | PA | Warren | Active | PENELEC | 62 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1177_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-178 | Tolna 2 115 kV |  | PA | York | Active | ME | 21.5 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1178_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1178_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-179 | Tolna 1 115 kV |  | PA | York | Active | ME | 21 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1179_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-180 | Titus 4 & 5 69 kV |  | PA | Berks | Active | ME | 38.7 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1180_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1180_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-181 | Shawville 3 230 kV |  | PA | Adams | Active | PENELEC | 175 | 3 | 3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1181_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-182 | Shawville 4 230 kV |  | PA | Adams | Active | PENELEC | 175 | 4 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1182_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/3/2019 |  |  | N | No
AF1-183 | Shawville 1 230 kV |  | PA | Adams | Active | PENELEC | 123 | 1 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1183_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/4/2019 |  |  | N | No
AF1-184 | Shawnee 1 34.5 kv |  | PA | Monroe | Active | ME | 21 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1184_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/3/2019 |  |  | N | No
AF1-185 | Sayreville 1-2-3 230 kV | Sayreville Facility (Raritan River) | NJ | Middlesex | In Service | JCPL | 171.7 | 0 | 5.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_185_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-186 | Portland 5 230 kV |  | PA | Northampton | Active | ME | 147.5 | 6.5 | 6.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1186_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-187 | Portland 3 & 4 115 kV |  | PA | Northampton | Active | ME | 39.8 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/28/2019 |  |  | N | No
AF1-188 | Orrtanna 115 kV |  | PA | Adams | Active | ME | 27 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1188_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/27/2019 |  |  | N | No
AF1-189 | Niles CT A 23 kV |  | OH | Trumbull | Active | ATSI | 27.1 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1189_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 9/21/2019 |  |  | N | No
AF1-190 | New Castle 4 69 kV |  | PA | Lawrence | Active | ATSI | 93 | 1 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1190_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-191 | New Castle 5 138 kV |  | PA | Lawrence | Active | ATSI | 145 | 4 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1191_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-192 | Mountain 2 115 kV |  | PA | Cumberland | Active | ME | 28 | 1 | 1 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1192_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-193 | Hunterstown 115 kV |  | PA | Adams | Active | ME | 65 | 4 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1193_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1193_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-194 | Hamilton CT1 115 kV |  | PA | York | Active | ME | 27 | 1 | 1 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1194_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-195 | Gilbert CT9 230 kV | Gilbert Station Unit 9 | NJ | Hunterdon | In Service | JCPL | 168 | 0 | 1 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1195_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1195_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_195_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-196 | Gilbert CT 5-6-7 230 kV | Gilbert Station 4x1 Combined Cycle (Unit 4, Unit 5, Unit 6, Unit 7, and Unit 8) | NJ | Hunterdon | In Service | JCPL | 302.5 | 0 | 14.5 | 0 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1196_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1196_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_196_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 3/10/2020 | 3/10/2020 | 3/10/2020 | N | No
AF1-197 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 295 | 15 | 15 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1197_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  | 3/5/2020 |  | 10/1/2019 |  |  | N | No
AF1-198 | Blossburg #1 CT 34.5 kV |  | PA | Tioga | Active | PENELEC | 22.5 | 2.5 | 2.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1198_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1198_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-199 | Avon Lake 10 138 kV |  | OH | Lorain | Active | ATSI | 36 | 4 | 4 |  | Capacity | Generation Interconnection | Oil |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1199_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1199_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-200 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 2100 | 2100 | 2035 |  | Capacity | Merchant Transmission |  | DC | 2035 F/NFTIR/2100 NF/TWR | N/A | https://www.pjm.com/pub/planning/project-queues/merch-feas_docs/af1200_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 1/31/2025 |  |  | S | No
AF1-201 | Hayes-Whitemarsh 115 kV |  | VA | Gloucester | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1201_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-202 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1202_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-203 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 55 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-204 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 255 | 255 | 63.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1204_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-205 | Napolean Muni 138 kV |  | OH | Henry | Active | ATSI | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1205_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AF1-206 | Fayette-Lyons 138 kV |  | OH | Fulton | Active | ATSI | 199 | 199 | 119.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1206_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AF1-207 | Reynolds–Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 180 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1207_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-208 | Quinton-Roadstown 69 kV |  | NJ | Salem | Active | AEC | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1208_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-209 | Guilford 34.5 kV |  | PA | Franklin | Active | APS | 15.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1209_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-210 | Burma 23 kV |  | PA | Clarion | Active | APS | 15.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1210_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-211 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 30 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1211_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1211_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-212 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 45 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1212_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-213 | Bionol-Madera 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 151.8 | 151.8 | 91.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1213_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  | 4/13/2020 |  | 6/1/2023 |  |  | N | No
AF1-214 | Nittany-Zion 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1214_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-215 | Reynolds-Olive 345 kV |  | IN | Starke | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1215_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF1-216 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 143.1 | 143.11 | 85.87 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1216_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF1-217 | Edinboro -Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1217_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-218 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 10/17/2019 |  | 12/31/2020 |  |  | N | No
AF1-219 | Hunt Farm 69 kV |  | KY | Boyle | Active | EKPC | 30 | 30 | 20.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1219_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-220 | Ridgway-Whetstone 115 kV |  | PA | Elk | Active | PENELEC | 151.7 | 151.7 | 91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1220_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF1-221 | College Corner-Drewersburg 138 kV |  | IN | Franklin | Active | AEP | 180 | 180 | 138.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1221_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-222 | Oceanview Wind 2 230 kV |  | NJ | Monmouth | Active | JCPL | 1326 | 510 | 140.25 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1222_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AF1-223 | Jay-Desoto 138 kV |  | IN | Blackford | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1223_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-224 | Fayetteville 34.5 kV |  | PA | Franklin | Active | APS | 31.9 | 11.9 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1224_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1224_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AF1-225 | Milnor 34.5 kV |  | PA | Franklin | Active | APS | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1225_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/30/2021 |  |  | N | No
AF1-226 | Bowmans Mill-Scott 69 kV |  | PA | Columbia | Active | PPL | 35 | 35 | 14.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1226_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/5/2021 |  |  | N | No
AF1-227 | Marysville-East Lima 345 kV |  | OH | Union | Active | AEP | 425 | 425 | 295 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1227_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-228 | Beatty-Greene 345 kV |  | OH | Madison | Active | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1228_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF1-229 | Galion-South Berwick 345 kV |  | OH | Wyandot | Active | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1229_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF1-230 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1230_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 2/5/2020 |  | 10/31/2022 |  |  | N | No
AF1-231 | New Church 138 kV |  | VA | Accomack | Active | DPL | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1231_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-232 | Allegheny-Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 160 | 160 | 104 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1232_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-233 | Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 225 | 225 | 150.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1233_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-234 | Baldy-Wesnberg 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 11/11/2019 |  | 12/15/2022 |  |  | N | No
AF1-235 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 617 | 617 | 617 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1235_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/2/2020 |  | 5/1/2023 |  |  | N | No
AF1-236 | Mackeys 230 kV |  | NC | Tyrell | Active | Dominion | 1210 | 1210 | 459.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1236_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AF1-237 | Mercer 230 kV |  | NJ | Mercer | Active | PSEG | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1237_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-238 | Sherman Ave. 69 kV |  | NJ | Cumberland | Active | AEC | 127.5 | 127.5 | 51 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1238_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-239 | Sherman Ave-Vineland 69 kV |  | NJ | Cumberland | Active | AEC | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1239_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-240 | Timblin 34.5 kV |  | PA | Armstrong | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1240_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF1-241 | Watson 12.47 kV |  | N/A | N/A | Withdrawn | PPL | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1241_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/24/2020 |  | 7/1/2022 |  |  | N | No
AF1-242 | Wilcox-Paper City 46 kV |  | N/A | N/A | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1242_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/19/2020 |  | 8/1/2022 |  |  | N | No
AF1-243 | Tasley 25 kV |  | VA | Accomack | Active | ODEC | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1243_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2020 |  |  | N | No
AF1-244 | Kingston 25 kV |  | MD | Somerset | Active | DPL | 8 | 8 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1244_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2020 |  |  | N | No
AF1-245 | Hudson 230 kV |  | NJ | Hudson | Active | PSEG | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1245_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-246 | Clover-Rawlings 500 kV |  | VA | Charlotte | Active | Dominion | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1246_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF1-247 | Woodsdale 345 kV |  | OH | Butler | Withdrawn | DEOK | 50 | 50 | 30.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 1/27/2020 |  | 10/20/2021 |  |  | N | No
AF1-248 | Northern Neck 34.5 kV |  | VA | Westmoreland | Active | Dominion | 14 | 0 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1248_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1248_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF1-249 | Nickel 12.47 kV |  | OH | Warren | Active | DEOK | 19.9 | 19.92 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1249_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF1-250 | Maysville 69 kV II |  | PA | Mercer | Active | ATSI | 68 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1250_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF1-251 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 220 | 220 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1251_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/15/2023 |  |  | N | No
AF1-252 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 262.4 | 62.4 | 62.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1252_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF1-253 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 305.6 | 43.2 | 43.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1253_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF1-254 | Milnor-Huyetts 34.5 kV |  | PA | Franklin | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1254_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-255 | Osterburg-Claysburg 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 13.5 | 13.5 | 5.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1255_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/18/2020 |  | 12/31/2019 |  |  | N | No
AF1-256 | Flemingsburg-Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1256_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-257 | Hawks 2 12 kV |  | NJ | Hunterdon | Active | JCPL | 3 | 0 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1257_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-258 | Rockawalkin 69 kV |  | MD | Wicomico | Active | DPL | 15 | 0 | 3.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1258_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N | No
AF1-259 | Price 25 kV |  | MD | Queen Anne's | Active | DPL | 6 | 0 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1259_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2020 |  |  | N | No
AF1-260 | Allenwood-Larrabee 2 34.5 kV |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1260_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2020 |  |  | N | No
AF1-261 | Burlington 26 kV |  | NJ | Burlington | Active | PSEG | 7 | 0 | 0.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1261_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1261_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2020 |  |  | N | No
AF1-262 | Upper Pittsgrove 12 kV |  | NJ | Salem | Active | AEC | 2 | 0 | 0.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1262_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1262_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2020 |  |  | N | No
AF1-263 | Bennett-Farmingdale 2 34.5 kV |  | NJ | Salem | Withdrawn | JCPL | 2 | 0 | 0.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1263_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1263_imp.pdf | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/2/2020 |  | 10/1/2019 |  |  | N | No
AF1-264 | Runnemede 13 kV |  | NJ | Gloucester | Active | PSEG | 3 | 0 | 1.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1264_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1264_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2020 |  |  | N | No
AF1-265 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Active | Dominion | 450 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1265_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-266 | Clubhouse-Sapony 230 kV |  | VA | Dinwiddie | Active | Dominion | 223.5 | 74.5 | 74.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1266_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-267 | Union City Tap 138 kV |  | KY | Madison | Active | EKPC | 54 | 54 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1267_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 1/31/2022 |  |  | N | No
AF1-268 | Desoto-Jay 138 kV |  | IN | Delaware | Active | AEP | 83 | 83 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1268_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 1/31/2022 |  |  | N | No
AF1-269 | Airey-Golden Hill 69 kV |  | MD | Dorchester | Withdrawn | DPL | 67 | 11 | 11 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1269_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 5/12/2020 |  | 12/31/2022 |  |  | N | No
AF1-270 | Blue Jacket-Kirby 138 kV |  | OH | Logan | Active | Dayton | 279.5 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1270_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-271 | Keisters-Krendale 138 kV |  | PA | Butler | Active | APS | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1271_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-271A | Gratz 69 kV |  | PA | Dauphin | Active | PPL | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1271a_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF1-272 | Lucerne 115 kV |  | PA | Indiana | Active | PENELEC | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1272_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-273 | Allegheny 115 kV |  | PA | Somerset | Active | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1273_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-274 | Harvey Run 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1274_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 4/8/2020 |  | 12/31/2023 |  |  | N | No
AF1-275 | Cole 345 kV |  | OH | Franklin | Active | AEP | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1275_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-276 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1276_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/29/2024 |  |  | N | No
AF1-277 | Lewis Run-Pierce Brook 2 230 kV |  | PA | McKean | Active | PENELEC | 200 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1277_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/29/2024 |  |  | N | No
AF1-278 | Lewis Run-Pierce Brook 3 230 kV |  | PA | Mc Kean | Active | PENELEC | 280 | 80 | 53.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1278_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/29/2024 |  |  | N | No
AF1-279 | Carlisle 138 kV |  | OH | Lorain | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1279_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF1-280 | Nelson-Lee County |  | IL | Lee | Active | ComEd | 200 | 200 | 137 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1280_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-281 | Nelson-Lee County |  | IL | Lee | Active | ComEd | 220 | 20 | 3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1281_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-282 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1282_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/20/2022 |  |  | N | No
AF1-283 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1283_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AF1-284 | Penn Mar-Garrett 138 kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1284_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/20/2020 |  | 12/31/2021 |  |  | N | No
AF1-285 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 130 | 100 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1285_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/1/2021 |  |  | N | No
AF1-286 | East Sayre 34.5 kV II |  | PA | Bradford | Active | PENELEC | 13.6 | 13.6 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1286_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-287 | Edinboro South 34.5 kV II |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1287_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-288 | Curryville-Claysburg 115 kV I |  | PA | Bedford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1288_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/18/2020 |  | 3/1/2021 |  |  | N | No
AF1-289 | Curryville-Claysburg 115 kV II |  | PA | Bedford | Withdrawn | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1289_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  | 3/18/2020 |  | 3/1/2021 |  |  | N | No
AF1-290 | Feagans Mill-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 80 | 40.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1290_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/14/2021 |  |  | N | No
AF1-291 | Tyler 34.5 kV |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291_imp.pdf | Document Posted |  |  | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF1-291A | Bartonsville-Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 80 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291a_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-292 | Fields Crossroads 34.5 kV |  | VA | Greensville | Active | Dominion | 14.9 | 14.9 | 8.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1292_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF1-293 | Kidds Store-Fort Union 115 kV |  | VA | Fluvanna | Active | Dominion | 127.9 | 127.86 | 109.92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1293_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF1-294 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1294_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-295 | Blain 115 kV II |  | PA | Perry | Withdrawn | PENELEC | 72 | 12 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1295_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/25/2020 |  | 12/31/2022 |  |  | N | No
AF1-296 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 212.1 | 37.3296 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1296_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-297 | North Longview 500 kV |  | WV | Monongalia | Active | APS | 52.8 | 52.8 | 36.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1297_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-298 | Desoto 345 kV |  | IN | Delaware | Withdrawn | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1298_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/6/2020 |  | 10/31/2023 |  |  | N | No
AF1-299 | Otter Point 34.5 kV I |  | MD | Harford | Active | BGE | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1299_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF1-300 | Otter Point 34.5 kV II |  | MD | Harford | Active | BGE | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1300_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1300_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF1-301 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 127 | 127 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1301_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-302 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Active | APS | 142 | 42 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1302_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-303 | Vernon 115 kV |  | N/A | N/A | Withdrawn | JCPL | 107 | 107 | 21.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1303_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 2/18/2020 |  | 5/31/2022 |  |  | N | No
AF1-304 | Titusville-Grandview 115 kV |  | PA | Venango | Active | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1304_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-305 | Maysville-Masury 138 kV |  | PA | Mercer | Active | ATSI | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1305_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-306 | Squab Hollow 230 kV |  | PA | Elk | Active | APS | 246.5 | 246.5 | 49.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1306_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-307 | Seward-Jackson Rd 115 kV |  | PA | Indiana | Active | PENELEC | 66.5 | 66.5 | 39.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1307_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-308 | Waverly 138 kV |  | OH | Pike | Withdrawn | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1308_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2023 |  |  | N | No
AF1-309 | North Hanover 115 kV |  | PA | Adams | Active | ME | 32 | 32 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1309_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-310 | Clover 230 kV |  | VA | Halifax | Withdrawn | Dominion | 300 | 300 | 114 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 11/5/2019 |  | 9/30/2022 |  |  | N | No
AF1-311 | Montour 230 kV |  | PA | Montour | Active | PPL | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1311_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AF1-312 | Dan River-Ridgeway 138 kV |  | NC | Rockingham | Withdrawn | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 10/28/2019 |  | 12/31/2023 |  |  | N | No
AF1-313 | Wes Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1313_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-314 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 212 | 212 | 37.31 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1314_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-315 | Cedarville-Ford 138 kV |  | OH | Clermont | Active | DEOK | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1315_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-316 | Katydid Road 345 kV |  | IL | Grundy | Withdrawn | ComEd | 132 | 132 | 52.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1316_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/13/2020 |  | 6/1/2022 |  |  | N | No
AF1-317 | Electric Jct-Nelson |  | IL | Lee | Active | ComEd | 175 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1317_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF1-318 | Crescent Ridge-Corbin |  | IL | Putnam | Active | ComEd | 300 | 299.97 | 52.7947 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1318_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-319 | Honda Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 58 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1319_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF1-320 | Merrill Creek 115 kV |  | NJ | Warren | Active | JCPL | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1320_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-321 | Hooversville 115 kV I |  | PA | Somerset | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1321_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF1-322 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1322_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 8/15/2022 |  |  | N | No
AF1-323 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1323_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF1-324 | Greystone-West Denville 34.5 kV |  | NJ | Morris | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1324_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1324_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AF1-325 | Sparta-Woodruff's Gap 34.5 kV |  | NJ | Sussex | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1325_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AF1-326 | Pohatcong-Newburgh 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1326_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1326_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AF1-327 | Pohatcong-Newburgh 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1327_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1327_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AF1-328 | Hackettstown-Pohatcong 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1328_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AF1-329 | Chickahominy 230 kV |  | VA | Charles City | Withdrawn | Dominion | 570 | 250 | 172.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  | 10/10/2019 |  | 9/1/2021 |  |  | N | No
AF1-330 | Marengo |  | IL | McHenry | Active | ComEd | 40 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1330_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF1-331 | Twombley Road |  | IL | Ogle | Active | RMU | 60 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1331_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF1-332 | Electric Jct-Nelson |  | IL | Lee | Withdrawn | ComEd | 225 | 50 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1332_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  | 3/9/2020 |  | 12/31/2023 |  |  | N | No
AF1-333 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1333_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-334 | Northkill 69 kV |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1334_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-335 | Northkill 230 kV |  | PA | Berks | Active | ME | 101.2 | 101.2 | 60.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1335_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-336 | Northkill 69 kV |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1336_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-337 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1337_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-338 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1338_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-339 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1339_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF2-001 | Hooversville 15 kV |  | PA | Somerset | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-002 | Hooversville 115 kV II |  | PA | Somerset | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-003 | Powerton-Mole Creek |  | IL | Woodford | Active | ComEd | 303 | 303 | 39.39 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-004 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 378.2 | 33 | 33 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AF2-005 | Beaver 138 kV |  | OH | Lorain | Active | ATSI | 95.2 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AF2-006 | Jermyn Tap-Brownell 69 kV |  | PA | Lackawanna | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 9/16/2021 |  |  | N | No
AF2-007 | Tinker Tap–East Carbondale 69 kV |  | PA | Lackawanna | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF2-008 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 2000 | 1000 | 500 |  | Capacity | Merchant Transmission |  | DC | 500 FTIR/1000 NFTIR | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/3/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | S | No
AF2-009 | Queen Street 34.5 kV |  | PA | York | Withdrawn | ME | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/10/2019 | N/A | N/A |  | 1/10/2020 |  | 10/1/2021 |  |  | N | No
AF2-010 | Union City-Titusville 115 kV |  | PA | Erie | Active | PENELEC | 77 | 77 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-011 | Tait 69 kV |  | OH | Montgomery | Active | Dayton | 690 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  |  |  | 5/31/2020 |  |  | N | No
AF2-012 | Tait 69 kV |  | OH | Montgomery | Active | Dayton | 794 | 104 | 104 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  |  |  | 5/28/2021 |  |  | N | No
AF2-013 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-014 | Maddox Creek 345 kV |  | OH | Van Wert | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-015 | N/A-N/A |  | NJ | Essex | Active | PSEG | 50 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2019 | N/A | N/A |  |  |  | 7/1/2021 |  |  | EE | No
AF2-016 | Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF2-017 | John's Creek 34 kV |  | KY | Pike | Withdrawn | AEP | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/31/2019 | N/A | N/A |  | 3/6/2020 |  | 12/31/2021 |  |  | N | No
AF2-018 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-019 | Rio Grande 69 kV |  | NJ | Cape May | Active | AEC | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-020 | Carll's Corner 69 kV |  | NJ | Cumberland | Active | AEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-021 | Cedar 69 kV |  | NJ | Ocean | Active | AEC | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-022 | Cumberland 138 kV |  | NJ | Cumberland | Active | AEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-023 | Churchtown 69 kV |  | NJ | Salem | Active | AEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-024 | Mickleton 69 kV |  | NJ | Gloucester | Active | AEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-025 | Missouri Ave 69 kV |  | NJ | Atlantic | Active | AEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-026 | Sherman Ave 138 kV |  | NJ | Cumberland | Active | AEC | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-027 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 635 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-028 | N/A-N/A |  | MD | Baltimore County | Active | BGE |  |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  | Issued |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A | [6 empty] | EE | No
AF2-029 | Ronco 500 kV |  | PA | Fayette | Active | APS | 726 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-030 | Ontelaunee 230 kV |  | PA | Berks | Active | ME | 611.1 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-031 | River E.C. |  | IL | Cook | Active | ComEd | 347 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-032 | Kincaid |  | IL | Christian | Active | ComEd | 1132 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-033 | Miami Fort 138 kV |  | OH | Hamilton | Active | DEOK | 1076 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-034 | Kendall |  | IL | Kendall | Active | ComEd | 1238.8 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-035 | St. Johns 115 kV |  | VA | Hanover | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2019 | N/A | N/A |  |  |  | 10/27/2023 |  |  | N | No
AF2-036 | Garner-Northern Neck 115 kV |  | VA | Richmond | Withdrawn | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2019 | N/A | N/A |  | 1/23/2020 |  | 10/27/2023 |  |  | N | No
AF2-037 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 94 | 94 | 56.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2019 | N/A | N/A |  |  |  | 7/1/2021 |  |  | N | No
AF2-038 | Printz 230 kV |  | PA | Delaware | Active | PECO | 661.5 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-039 | Shawville-Clearfield 34.5 kV |  | PA | Clearfield | Active | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-040 | Elk Run-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-041 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-042 | Clover 500 kV |  | VA | Halifax | Active | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-043 | Suffolk 34.5 kV |  | VA | City of Suffolk | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2019 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-044 | Highland-Sammis and Highland-Mansfield 345 kV |  | OH | Trumbull | Active | ATSI | 940 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2019 | N/A | N/A |  |  |  | 1/1/2020 |  |  | N | No
AF2-045 | Cambria Nug 115 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/13/2019 | N/A | N/A |  |  |  | 12/28/2020 |  |  | N | No
AF2-046 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 150 | 150 | 117.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-047 | Creswell-Riders Creek 115 kV |  | NC | Washington | Active | Dominion | 150 | 150 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-048 | Rio-Lick 138 kV |  | OH | Jackson | Active | AEP | 140 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-049 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Active | Dominion | 180 | 60 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF2-050 | Bearrock-Johnstown 230 kV |  | PA | Cambria | Active | PENELEC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-051 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-052 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 55 | 55 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-053 | Chickahominy 500kV |  | VA | Charles City | Withdrawn | Dominion | 1800 | 200 | 200 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/26/2019 | N/A | N/A |  | 1/21/2020 |  | 6/1/2024 |  |  | N | No
AF2-054 | Wan 34.5 kV |  | VA | Gloucester | Active | Dominion | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/10/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AF2-055 | Plantation 69 kV |  | VA | Northampton | Active | ODEC | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AF2-056 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | PA | Schuylkill | Active | PPL | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-057 | Grassfield 34.5 kV |  | VA | Mecklenburg | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-058 | Fairton 12 kV |  | NJ | Cumberland | Active | AEC | 2.5 | 2.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 3/31/2021 |  |  | Y | No
AF2-059 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Active | AEP | 97 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF2-060 | Wattsville 12 kV |  | VA | Accomack | Active | DPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF2-061 | Wattsville 69kV |  | VA | Accomack | Active | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-062 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF2-063 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2020 | N/A | N/A |  |  |  | 2/1/2023 |  |  | N | No
AF2-064 | Flanders 115 kV |  | NJ | Warren | Withdrawn | JCPL | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2020 | N/A | N/A |  | 2/20/2020 |  | 12/18/2020 |  |  | N | No
AF2-065 | Surry-Hopewell 230 kV |  | VA | Surry | Active | Dominion | 300 | 150 | 76.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/21/2021 |  |  | N | No
AF2-066 | West Manchester 69 kV |  | OH | Preble | Active | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-067 | West Manchester-Crown 69 kV |  | OH | Preble | Active | Dayton | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-068 | Jay 138 kV |  | IN | Blackford | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-069 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 88.7 | 9.3 | 0 |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/4/2021 |  |  | N | No
AF2-070 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/4/2021 |  |  | N | No
AF2-071 | Windsor 230 kV |  | NJ | Mercer | Active | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AF2-072 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AF2-073 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Active | Dominion | 90 | 90 | 54.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AF2-074 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Active | Dominion | 130 | 40 | 24.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AF2-075 | Bartonsville-Meadow Brook 138 kV III |  | VA | Frederick | Active | APS | 130 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-076 | Suffolk-Nucor Steel 230 kV |  | VA | City of Suffolk | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-077 | White Marsh 34.5 kV |  | VA | Gloucester | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AF2-078 | Reynolds-Olive #1 345 kV |  | IN | White | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-079 | Greenville 138 kV |  | OH | Darke | Active | Dayton | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-080 | Chinquapin-Everetts 230 kV |  | NC | Pitt | Active | Dominion | 150 | 70 | 48.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-081 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-082 | Dauphin PG Tie–Dauphin Juniata Tie 69 k |  | PA | Dauphin | Active | PPL | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-083 | Ed Lowe-Kenzie Creek 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-084 | Honda-Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 100 | 42 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AF2-085 | Midlothian 34.5 kV |  | VA | Chesterfield | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-086 | Scott Tap-Bowmans Mill Tap 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AF2-087 | East Altoona-Pinecroft 12.47 kV |  | PA | Blair | Active | PENELEC | 7.3 | 7.25 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-088 | Shawville-Clearfield 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 6.5 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/5/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-089 | Titusville 34.5 kV |  | PA | Venango | Active | PENELEC | 25 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-090 | Central Hardin 138 kV |  | TN | Hardin | Active | EKPC | 110 | 110 | 73.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF2-091 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 34 | 14.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-092 | Snake Spring-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/11/2020 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF2-093 | Derry 12.47 kV |  | PA | Montour | Active | PPL | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-094 | Huntington Jct. 138 kV |  | IN | Huntington | Active | AEP | 190 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  |  |  | 2/1/2022 |  |  | N | No
AF2-095 | Wilmington-Davis Creek |  | IL | Kankakee | Active | ComEd | 200 | 200 | 136 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-096 | Braidwood-East Frankfort 345 kV |  | IL | Will | Active | ComEd | 375 | 375 | 255 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF2-097 | Fairview East 34.5 kV II |  | PA | Erie | Active | PENELEC | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-098 | Crittenden 12 kV |  | KY | Grant | Withdrawn | DEOK | 3.5 | 3.45 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/14/2020 | N/A | N/A |  | 4/30/2020 |  |  |  |  | Y | No
AF2-099 | Taxville 2 13.2 kV |  | PA | York | Active | ME | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-100 | Taxville 1 13.2 kV |  | PA | York | Active | ME | 3 | 3 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-101 | Allen 13.2 kV |  | PA | Cumberland | Active | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-102 | Germantown 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-103 | Haviland 138 kV |  | OH | Paulding | Active | AEP | 103.2 | 3.15 | 1.32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2020 | N/A | N/A |  |  |  | 8/1/2020 |  |  | N | No
AF2-104 | Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/21/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-105 | Morgans Cut 138 kV |  | VA | Pulaski | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/28/2022 |  |  | N | No
AF2-106 | Hazel Hollow 138 kV |  | VA | Pulaski | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/28/2022 |  |  | N | No
AF2-107 | Clifford 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-108 | Locks 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 17.5 | 17.5 | 17.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-109 | Church 69 kV |  | MD | Queen Anne's | Active | DPL | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-110 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 71 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-111 | North Clark-Spurlock 345 kV |  | KY | Mason | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-112 | Oakland-Gorman 69 kV |  | MD | Garrett | Active | APS | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-113 | Clinton-Stuart 345 kV |  | OH | Clinton | Withdrawn | Dayton | 375 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  | 3/26/2020 |  | 12/31/2022 |  |  | N | No
AF2-114 | Old Chapel-Millville 138 kV II |  | WV | Jefferson | Active | APS | 92.5 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AF2-115 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 66 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-116 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 90 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-117 | Warfordsburg-McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 70 | 46.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-118 | Gilbert-Morris Park (A-27) 34.5 kV II |  | NJ | Warren | Active | JCPL | 40 | 19.99 | 3.99 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 3/31/2021 |  |  | N | No
AF2-119 | Bristers-Sowego 115 kV |  | VA | Fauquier | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-120 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-121 | Philipsburg-Shawville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-122 | Kirk 138 kV |  | OH | Licking | Active | AEP | 107.7 | 107.7 | 64.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-123 | Lafayette 69 kV |  | OH | Madison | Active | ATSI | 49 | 49 | 20.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-124 | Kyger Creek-Pierce 345 kV |  | OH | Highland | Active | Unknown | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-125 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 150 | 54 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AF2-126 | Weston 69 kV II |  | OH | Wood | Active | ATSI | 110 | 60 | 40.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-127 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 68 | 38 | 24.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF2-128 | Crescent Ridge-Corbin 138 kV |  | IL | Lasalle | Active | ComEd | 79.5 | 79.5 | 13.992 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 8/26/2024 |  |  | N | No
AF2-129 | Sharon-Mercer 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-130 | Wolfs Corners 34.5 kV |  | PA | Clarion | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-131 | Cooper 34.5 kV |  | PA | York | Active | PECO | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-132 | Reynolds-Olive #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-133 | Reynolds-Olive #2 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-134 | Reynolds-Olive #2 345 kV |  | IN | Starke | Active | AEP | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-135 | Rockwood-Confluence 23 kV |  | PA | Somerset | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-136 | Swamp 230 kV |  | NC | Perquimans | Active | Dominion | 208 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2020 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AF2-137 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 500 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-138 | Flanders 34.5 kV |  | NJ | Morris | Active | JCPL | 24.2 | 24.2 | 10.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF2-139 | Gilbert-Warren Glen 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 8.8 | 8.8 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF2-140 | Saegers 230 kV |  | PA | Lycoming | Active | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2020 | N/A | N/A |  |  |  | 5/1/2021 |  |  | N | No
AF2-141 | Lick Run 115 kV |  | PA | Somerset | Active | PENELEC | 100 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2020 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AF2-142 | Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-143 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-144 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-145 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 194.1 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-146 | Hill Valley-Valley REC 46 kV |  | PA | Huntingdon | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-147 | McVeytown-Strodes Mill 46 kV |  | PA | Mifflin | Active | PENELEC | 13.1 | 13.1 | 7.86 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-148 | Shade Gap-Three Springs KTS 23 kV |  | PA | Huntingdon | Active | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-149 | Blackjack Road-Martinsburg 69 kV |  | OH | Knox | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-150 | Galion 138 kV |  | OH | Morrow | Active | ATSI | 88 | 88 | 36.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-151 | Dillsburg 13.2 kV |  | PA | York | Active | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-152 | Morgantown CT5 230 kV |  | MD | Charles | Active | PEPCO | 56 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-153 | Morgantown CT4 230 kV |  | MD | Charles | Active | PEPCO | 56 | 2 | 2 |  | Capacity | Generation Interconnection | Oil |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-154 | Dickerson H2 CT 230 kV |  | MD | Montgomery | Active | PEPCO | 173 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-155 | Chalk Point CT3-CT6 230 kV |  | MD | Prince George's | Active | PEPCO | 461.9 | 13 | 13 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-156 | Chalk Point CT2 230 kV |  | MD | Prince George's | Active | PEPCO | 30 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-157 | Chalk Point CT1 69 kV |  | MD | Prince George's | Active | PEPCO | 22 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-158 | Chalk Point ST1 230 kV |  | MD | Prince George's | Active | PEPCO | 589.3 | 4 | 4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-159 | Chalk Point ST3 230 kV |  | MD | Prince George's | Active | PEPCO | 598.2 | 2 | 2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 2/28/2021 |  |  | N | No
AF2-160 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 283.5 | 3.5 | 3.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 4/1/2020 |  |  | N | No
AF2-161 | Mount Rock 12.47 kV |  | PA | Cumberland | Active | PPL | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-162 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 245 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-163 | Lick Run 115 kV |  | PA | Somerset | Active | PENELEC | 34.5 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-164 | Handsome Lake 345 kV |  | PA | Venango | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2020 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AF2-165 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2020 | N/A | N/A |  |  |  | 3/15/2022 |  |  | N | No
AF2-166 | Clark Summit-Emlenton 34 kV |  | PA | Venango | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2020 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF2-167 | Eaton Crest-Red Bank 34.5 kV |  | NJ | Monmouth | Active | JCPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF2-168 | West Windsor 69 kV |  | NJ | Mercer | Active | PSEG | 5 | 5 | 0 |  | Energy | Generation Interconnection | Natural Gas; Other; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-169 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 552 | 552 | 155 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-170 | Erie West-Springboro 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF2-171 | Madisonville 115 kV |  | VA | Prince Edward | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF2-172 | Whibco 12 kV |  | NJ | Cumberland | Active | AEC | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-173 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-174 | Tabernacle 12 kV |  | NJ | Burlington | Active | AEC | 11 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF2-175 | Straban 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 1.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-176 | Masury-Maysville 138 kV |  | PA | Mercer | Active | ATSI | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF2-177 | Sorenson-DeSoto #2 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-178 | Roxbury 23 kV II |  | PA | Franklin | Active | PENELEC | 13.5 | 0 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 3/31/2020 |  |  | N | No
AF2-179 | St. Thomas-Mercersburg 34.5 kV II |  | PA | Franklin | Active | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 7/23/2020 |  |  | N | No
AF2-180 | St. Thomas-Guilford 34.5 kV II |  | PA | Franklin | Active | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 5/26/2020 |  |  | N | No
AF2-181 | Lexington Park 69 kV |  | MD | St. Mary's | Active | SMECO | 20 | 0 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-182 | Nelson-Lee County 345 kV II |  | IL | Lee | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-183 | Nelson-Lee County 345 kV |  | IL | Lee | Active | ComEd | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-184 | McConnelsburg-Mercersburg 34 kV II |  | PA | Franklin | Active | APS | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/7/2020 |  |  | N | No
AF2-185 | Mercersburg-Minor 34 kV II |  | PA | Franklin | Active | APS | 15 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/29/2020 |  |  | N | No
AF2-186 | South Cecil 69 kV |  | OH | Paulding | Active | AEP | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-187 | Brookside-Cloverdale 138 kV |  | OH | Wayne | Active | ATSI | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-188 | Reynolds-Meadow Lake #1 345 kV |  | IN | White | Active | AEP | 112 | 112 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-189 | Greentown 138 kV |  | IN | Howard | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-190 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 260 | 156 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-191 | New Carlisle 138 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-192 | East Flemington 13.2 kV |  | NJ | Hunterdon | Active | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-193 | Indian River 230 kV I |  | DE | Sussex | Active | DPL | 440 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AF2-194 | Indian River 230 kV II |  | DE | Sussex | Active | DPL | 880 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AF2-195 | Queen Street 115 kV |  | PA | York | Active | ME | 171.7 | 171.7 | 68.68 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-196 | Cedar Neck 69 kV II |  | DE | Sussex | Active | DPL | 150 | 30 | 9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-197 | East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 100.8 | 100.8 | 40.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF2-198 | Heath 69 kV |  | OH | Licking | Active | AEP | 22.4 | 22.4 | 8.96 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2020 | N/A | N/A |  |  |  | 10/15/2022 |  |  | N | No
AF2-199 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-200 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-201 | Lena-Ecogrove 138 kV |  | IL | Stephenson | Active | ComEd | 199 | 199 | 51.4 |  | Capacity | Generation Interconnection | Wind; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF2-202 | Landis 12 V |  | NJ | Salem | Active | AEC | 2.7 | 2.7 | 1.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-203 | Rohrsburg 12.5 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF2-204 | Van Buren 138 kV |  | IN | Grant | Active | AEP | 110 | 110 | 83.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-205 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-206 | Larrabee-Point Pleasant 34.5 kV |  | NJ | Monmouth | Active | JCPL | 15.4 | 15.4 | 6.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-207 | Nelson 69 kV |  | DE | Sussex | Active | DPL | 50.4 | 50.4 | 20.16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 10/15/2022 |  |  | N | No
AF2-208 | Colora 230 kV |  | MD | Cecil | Active | DPL | 100.8 | 100.8 | 40.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 10/15/2022 |  |  | N | No
AF2-209 | South Hicksville 138 kV |  | OH | Defiance | Active | AEP | 140 | 140 | 95.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 6/2/2023 |  |  | N | No
AF2-210 | Foster-Garver Road 345 kV |  | OH | Pickaway | Active | DEOK | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-211 | College Corner 138 kV |  | IN | Henry | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-212 | Shelby 138 kV |  | IN | Jay | Active | Dayton | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-213 | Zions View-Smith Street 115 kV |  | PA | York | Active | ME | 81.2 | 81.2 | 32.48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 10/15/2022 |  |  | N | No
AF2-214 | Heartsease DP-Anaconda 115 kV |  | NC | Edgecombe | Active | Dominion | 151.2 | 151.2 | 60.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 12/2/2022 |  |  | N | No
AF2-215 | Saint Thomas-LeMasters Junction 34.5 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-216 | Blue Jacket-Kirby 138 kV |  | OH | Union | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 8/30/2024 |  |  | N | No
AF2-217 | Hyatt-Marysville 345 kV |  | OH | Union | Active | AEP | 220 | 220 | 132 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 8/30/2024 |  |  | N | No
AF2-218 | Gettysburg 69 kV |  | OH | Darke | Active | Dayton | 50 | 49.99 | 29.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 8/30/2024 |  |  | N | No
AF2-219 |  |  | NC | Halifax | Withdrawn | Dominion | 58 | 58 | 38.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  | 4/22/2020 |  | 12/31/2023 |  |  | N | No
AF2-220 | Hickman-River Bend 69 kV |  | VA | Pulaski | Active | AEP | 37 | 37 | 22.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-221 | Scalp Level 22.9 kV |  | PA | Somerset | Active | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 3/15/2023 |  |  | N | No
AF2-222 | Pamplin-Chase City 115 kV |  | VA | Charlotte | Active | Dominion | 167 | 167 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF2-223 | Marysville 345 kV |  | OH | Union | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-224 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-225 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-226 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-227 | Martins Creek-Factorville Tap #2 69 kV |  | PA | Northampton | Active | PPL | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-228 | Zions View-Middletown 115 kV |  | PA | York | Active | ME | 61 | 61 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-229 | Roxbury 23 kV |  | PA | Cumberland | Active | PENELEC | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-230 | Lock 34 kV |  | PA | Chester | Active | PECO | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-231 | Belleville 12.47 kV |  | PA | Mifflin | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-232 | Bowmanns Mill Tap-Scott 69 kV |  | PA | Columbia | Active | PPL | 75 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-233 | Penns-Richfield Tie #1 69 kV |  | PA | Snyder | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-234 | Sunbury Yard #1-Richfield Tie #2 69 kV |  | PA | Snyder | Active | PPL | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-235 | Titusville-Oil Creek 34.5 kV |  | PA | Crawford | Active | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AF2-236 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Active | ATSI | 28 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 2/15/2023 |  |  | N | No
AF2-237 | Union City-Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AF2-238 | Mansfield-South Troy 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-239 | Wyalusing-Hollenback WRC 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 11.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-240 | North Orwell 12.47 kV |  | PA | Bradford | Active | PENELEC | 7 | 7 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-241 | Athens-Milan 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 11.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-242 | Wharton 115 kV |  | NC | Edgecombe | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AF2-243 | Clark Summit 34.5 kV |  | PA | Venango | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF2-244 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 15 | 15 | 9.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AF2-245 | Spurlock-Flemingsburg 345 kV |  | KY | Mason | Active | EKPC | 132 | 132 | 79.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-246 | Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 58 | 58 | 38.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/16/2020 |  | 12/29/2023 |  |  | N | No
AF2-247 | Bustleton 13.2 kV |  | NJ | Burlington | Active | PSEG | 5 | 5 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF2-248 | Edgewood 12 kV I |  | MD | Wicomico | Active | DPL | 7.2 | 7.2 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-249 | Edgewood 12 kV II |  | MD | Wicomico | Active | DPL | 3 | 3 | 0.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-250 | Edgewood 12 kV III |  | MD | Wicomico | Active | DPL | 2 | 1.95 | 1.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/1/2020 |  |  | N | No
AF2-251 | Susquehanna unit 1 230 kV |  | PA | Luzerne | Active | PPL | 1260 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2020 |  |  | N | No
AF2-252 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-253 | McClelland-Shenango 345 kV |  | PA | Lawrence | Active | ATSI | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-254 | Cookstown-New Lisbon 34.5 kV |  | NJ | Burlington | Active | JCPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 2/3/2020 |  |  | N | No
AF2-255 | Iron Bridge 34.5 kV |  | VA | Chesterfield | Active | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-256 | Tyler 34.5 kV |  | VA | Chesterfield | Active | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-257 | Tyler 34.5 kV |  | VA | Chesterfield | Active | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-258 | Harrowgate 34.5 kV |  | VA | Chesterfield | Active | Dominion | 25 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-259 | Locks 34.5 kV |  | VA | Chesterfield | Active | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-260 | Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 90 | 90 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-261 | Harwood-Susquehanna #1 230 kV |  | PA | Luzerne | Active | PPL | 75 | 75 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AF2-262 | Freeland #1 Tap-Jeddo-Highland 69 kV |  | PA | Luzerne | Active | PPL | 45 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-263 | Shelby 138 kV |  | OH | Shelby | Active | Dayton | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-264 | Tunis 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 13.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AF2-265 | South Troy-Athens 34.5 kV |  | PA | Bradford | Active | PENELEC | 15 | 15 | 8.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-266 | Clover 230 kV |  | VA | Charlotte | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-267 | Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 210.9 | 210.9 | 37.1184 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF2-268 | Orrtanna 13.2 kV |  | OH | Adams | Active | ME | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-269 | Adams Y Solar II |  | N/A | N/A | Withdrawn | ME |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  | 4/27/2020 |  |  |  |  | Y | No
AF2-270 | Bedford South RCB-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 3.7 | 3.72 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-271 | Pemberton-Sinking Valley 12.47 kV |  | PA | Blair | Active | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-272 | Bernville 13.2 kV |  | PA | Blair | Active | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-273 | Sligo 25 kV |  | PA | Clarion | Active | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2020 |  |  | Y | No
AF2-274 | Lardin 138 kV |  | TN | Fayette | Active | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-275 | Guilford 34.5 kV |  | IN | Franklin | Active | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-276 | Guilford 34.5 kV |  | IN | Franklin | Active | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-277 | Richland 12.47 kV |  | PA | Bucks | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-278 | Halifax 12.47 kV |  | PA | Dauphin | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-279 | Letort 12.47 kV |  | VA | Lancaster | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-280 | Buck 12.47 kV |  | PA | Lancaster | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 7/1/2021 |  |  | Y | No
AF2-281 | Lynnville 13.2 kV |  | PA | Lehigh | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-282 | Edelle 12.47 kV |  | PA | Lackawanna | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-283 | Greenfield 12.47 kV |  | PA | Lackawanna | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-284 | Watson 12.47 kV |  | VA | Northumberland | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-285 | W. Damascus 12.47 kV |  | PA | Wayne | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-286 | Shermansdale 12.47 kV |  | IL | Perry | Active | PPL | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-287 | Green Park 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A | [6 empty] | Y | No
AF2-288 | Benvenue 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A | [6 empty] | Y | No
AF2-289 | Watson 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A | [6 empty] | Y | No
AF2-290 | Derry 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A | [6 empty] | Y | No
AF2-291 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF2-292 | South Union 138 kV |  | TN | Fayette | Active | APS | 1.2 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-293 | Beech Creek 46 kV |  | MI | Clinton | Active | APS | 1.2 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-294 | Thompson 34.5 kV |  | PA | Wayne | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-295 | Wilcox-Paper City 46 kV |  | PA | Elk | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | N | No
AF2-296 | Madera 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF2-297 | Sedge Hill 115 kV |  | VA | Halifax | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 3/12/2022 |  |  | N | No
AF2-298 | Crown-Brookville 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF2-299 | Fields 34.5 kV |  | VA | Greensville | Active | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-300 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-301 | Poolesville-Winchester 230 kV |  | VA | Isle of Wight | Active | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AF2-302 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 75 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-303 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 190 | 190 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-304 | Surry-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 150 | 150 | 89 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-305 | Brokaw-Lanesville 345 kV |  | N/A | N/A | Active | ComEd |  |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-306 | Hope-Blevins Valley Tap 69 kV |  | KY | Barren | Active | EKPC | 26 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-307 | Hope-Blevins Valley Tap 69 kV |  | VA | Bath | Active | EKPC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-308 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-310 | Jennings-Hoyes Road 34.5 kV |  | N/A | N/A | Active | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF2-311 | Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 100 | 100 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-312 | Carrolltown-Patton 46 kV |  | PA | Cambria | Active | PENELEC | 18 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF2-313 | Price 69 kV |  | MD | Queen Anne's | Active | DPL | 19.9 | 19.9 | 13.4922 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/15/2021 |  |  | N | No
AF2-314 | Vandergrift 25 kV |  | PA | Armstrong | Active | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF2-315 | Susquehanna unit 2 230 kV |  | PA | Luzerne | Active | PPL | 1260 | 50 | 0 |  | Energy | Generation Interconnection | Nuclear |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/1/2020 |  |  | N | No
AF2-316 | Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 150 | 150 | 82.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-317 | Hill Topper 345 kV |  | IL | Logan | Active | ComEd |  |  |  |  | Energy | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 5/31/2020 |  |  | N | No
AF2-318 | East Towanda-New Albany 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-319 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-320 | N/A-N/A |  | N/A | N/A | Active | AEP | 48 |  |  |  | Energy | Upgrade Request |  |  |  | N/A | [6 empty] | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | EE | No
AF2-321 | Stryker-Ridgeville 138 kV |  | OH | Williams | Active | ATSI | 148 | 148 | 88.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-322 | Hoytdale-McClelland 345 kV |  | PA | Lawrence | Active | ATSI | 401.6 | 199.67 | 119.802 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-323 | Geneva-Franklin Tap 115 kV |  | PA | Crawford | Active | PENELEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-324 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 75 | 75 | 48.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF2-325 | Jacktown 12 kV |  | MD | Dorchester | Active | DPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 2/28/2022 |  |  | N | No
AF2-326 | Edgecombe 13 kV |  | NC | Edgecombe | Active | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-327 | Wakefield 13 kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No
AF2-328 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-329 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 152.2 | 52.2 | 52.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-330 | Claysburg-Summit 115 kV |  | PA | Cambria | Active | PENELEC | 70 | 70 | 48.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-331 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-332 | Montour 230 kV |  | PA | Montour | Active | PPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-333 | Montour 230 kV |  | PA | Montour | Active | PPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-334 | Montour 230 kV |  | PA | Montour | Active | PPL |  |  |  |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-335 | West Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 140 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-336 | Snake Spring 115 kV |  | PA | Bedford | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-337 | Snake Spring 115 kV |  | PA | Bedford | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-338 | Snake Spring-Saxton 115 kV |  | PA | Bedford | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-339 | Snake Spring-Saxton 115 kV |  | PA | Bedford | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-340 |  |  | N/A | N/A | Withdrawn | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/10/2020 |  | 12/31/2023 |  |  | N | No
AF2-341 | Maysville138 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-342 | Maysville138 kV II |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-343 | Maysville 138 kV III |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-344 | Maysville 138 kV IV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-345 | Maysville 138 kV V |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-346 | Electric Junction-Nelson 345 kV |  | IL | Lee | Active | ComEd | 250 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-347 | N/A-N/A |  | OH | Montgomery | Active | ATSI | 68 |  |  |  | Energy | Upgrade Request |  |  |  | N/A |  |  |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | EE | No
AF2-348 | North Clark-Spurlock 345 kV |  | KY | Madison | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-349 | Garden Prairie-Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-350 | Kensington 138 kV |  | IL | Kankakee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-351 | Kensington 138 kV |  | IL | Kankakee | Active | ComEd | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-352 | Blue Mound 34.5 kV |  | IL | McLean | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-353 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 800 | 800 | 560 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-354 | Washington 34.5 kV II |  | NJ | Warren | Active | JCPL | 19.8 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AF2-355 | West Gerrard-J.K. Smith 345 nkV |  | KY | Madison | Active | EKPC | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-356 | Albright-Mt. Zion 138 kV |  | MD | Garrett | Active | APS | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-357 | Nipetown-Reid 138 kV |  | MD | Washington | Active | APS | 24 | 24 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-358 | Airey-Vienna 69 kV |  | N/A | N/A | Active | DPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-359 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-360 | Keeney-Steele 230 kV |  | N/A | N/A | Withdrawn | DPL | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 5/1/2020 |  | 12/15/2023 |  |  | N | No
AF2-361 | Mifflintown-Walker 69 kV |  | PA | Juniata | Active | PPL | 85 | 85 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-362 |  |  | VA | Lancaster | Withdrawn | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/22/2020 |  | 12/12/2023 |  |  | N | No
AF2-363 | Glidden 138 kV |  | N/A | N/A | Active | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF2-364 | Wayne Red 138 kV |  | N/A | N/A | Active | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-365 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-366 | Glidden-Waterman 345 kV |  | N/A | N/A | Active | ComEd | 94.9 | 94.9 | 56.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-367 | Neville 23 kV |  | PA | Allegheny | Active | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AF2-368 | Pine Creek 23 kV |  | PA | Allegheny | Active | DL | 9.5 | 9.5 | 9.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AF2-369 | Kirby 138 kV |  | MD | Garrett | Active | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-370 | West Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 140 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-371 | Harrison-Poston 138 kV |  | OH | Fairfield | Active | AEP | 84 | 84 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-372 | Black Branch 34.5 kV |  | VA | Lunenburg | Active | Dominion | 20 | 19.95 | 7.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 11/26/2021 |  |  | N | No
AF2-373 | Mount Laurel 115 kV |  | VA | Halifax | Active | Dominion | 14.3 | 14.25 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/30/2022 |  |  | N | No
AF2-374 | Woodland 34.5 kV |  | VA | Southampton | Active | Dominion | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/29/2021 |  |  | N | No
AF2-375 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 129.6 | 129.6 | 77.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-376 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-377 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-378 | Cambridge 12 kV |  | MD | Dorchester | Active | DPL | 2.7 | 2.65 | 1.11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 2/28/2022 |  |  | N | No
AF2-379 | Princess Anne 25 kV |  | MD | Somerset | Active | DPL | 3.9 | 3.9 | 1.638 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 2/28/2022 |  |  | N | No
AF2-380 | Karns City-Bear Creek 25 kV |  | PA | Clarion | Active | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF2-381 | Bedford North-Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 125 | 125 | 81.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-382 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-383 | Tolna 115 kV |  | PA | York | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-384 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-385 | Nelson 69 kV |  | DE | Sussex | Active | DPL | 75 | 75 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-386 | Bryan 69 kV |  | OH | Williams | Active | ATSI | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-387 | Hillsboro 138 kV |  | MD | Queen Anne's | Active | DPL | 100 | 100 | 66.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-388 | Desoto-Sorenson 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-389 | Pokagon-Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-390 | Kenzie Creek138 kV |  | MI | Cass | Withdrawn | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/30/2020 |  | 10/31/2023 |  |  | N | No
AF2-391 | Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AF2-392 | Nelson-Dixon 138 kV |  | N/A | N/A | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-393 | Nelson-Dixon 138 kV |  | N/A | N/A | Active | ComEd | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-394 | Nelson-Dixon 138 kV |  | N/A | N/A | Active | ComEd | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-395 | Flatlick 765 kV |  | OH | Vinton | Active | AEP | 1045 | 51.1 | 89.6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF2-396 | Stinger 138 kV |  | MI | Cass | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-397 | Fork Union-Mt. Eagle 230 kV |  | VA | Fluvanna | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-398 | Necessity-Dinnerbell 12.47 kV |  | PA | Fayette | Active | APS | 3 | 3 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-399 | Crewe 12.5 kV |  | VA | Nottoway | Active | Dominion | 5.2 | 5.2 | 1.938 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/29/2021 |  |  | N | No
AF2-400 | Watkins Corner 13.2 kV |  | VA | Nottoway | Active | Dominion | 7.1 | 7.125 | 2.7075 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/29/2021 |  |  | N | No
AF2-401 | Culpeper 34.5 kV |  | VA | Culpeper | Active | Dominion | 9.3 | 9.3 | 3.523 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/29/2021 |  |  | N | No
AF2-402 | Ivor-Oak Ridge 115 kV |  | VA | Southampton | Active | Dominion | 16.6 | 16.6 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-403 | Shockoe DP-Chatham 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-404 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-405 | East Sayre 34.5 kV III |  | PA | Bradford | Active | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-406 | Sayre 115 kV |  | PA | Bradford | Active | PENELEC | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-407 | Fall Creek 345 kV |  | IN | Madison | Active | AEP | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-408 | Fall Creek 138 kV |  | IN | Madison | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-409 | Vienna 138 kV |  | MD | Dorchester | Active | DPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-410 | Vienna 18 kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  | 4/24/2020 |  | 6/1/2021 |  |  | N | No
AF2-411 | Mainesburg 345 kV |  | PA | Tioga | Active | PENELEC | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-412 | Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-413 | Raritan River 230 kV |  | N/A | N/A | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-414 | Bergen 345 kV |  | NJ | Hudson | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-415 | Bergen 138 kV |  | NJ | Hudson | Active | PSEG | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-416 | Bergen 26 kV |  | NJ | Hudson | Active | PSEG | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-417 | West Damascus Tap-West Damascus 69 kV |  | N/A | N/A | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-418 | Millville Tap 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF2-419 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AF2-420 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Active | EKPC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF2-421 | Luzerne 69 kV |  | N/A | N/A | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-422 | East Hazelton 12.47 kV |  | N/A | N/A | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-423 | East Hazelton 12.47 kV |  | N/A | N/A | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-424 | Reed-Reed Tap #1 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-425 | Sunbury-Reed 69 kV |  | N/A | N/A | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-426 | Bethelboro 12 kV |  | PA | Fayette | Active | APS | 1.2 | 1.17 |  |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-427 | Watson 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A | [6 empty] | Y | No
AF2-428 | West Boyertown 13.2 kV |  | PA | Berks | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-429 | South Hamburg 34.5 kV |  | PA | Berks | Active | ME | 3.7 | 3.72 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-430 | Moselem 13.2 kV |  | PA | Berks | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-431 | Baldy 13.2 kV |  | PA | Berks | Active | ME | 1.2 | 1.17 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 8/1/2021 |  |  | Y | No
AF2-432 | Bloomsburg 12.47 kV |  | N/A | N/A | Active | PPL |  |  |  |  | Energy | Generation Interconnection |  |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A | [6 empty] | Y | No
AF2-433 | Columbia-Geisinger Tap #1 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-434 | Columbis-Geisinger Tap #1 69 kV |  | MD | Anne Arundel | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-435 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Active | BGE | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-436 | Wyalusing 34.5 kV II |  | PA | Bradford | Active | PENELEC | 21.4 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/13/2020 |  |  | N | No
AF2-437 | Oxbow 34.5 kV III |  | PA | Wyoming | Active | PENELEC | 21.4 | 1.5 | 1.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/13/2020 |  |  | N | No
AF2-438 | Heidleberg-Lavino 69 kV |  | PA | Mercer | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-439 | Roxbury-Carlisle 115 kV |  | PA | Franklin | Active | PENELEC | 50 | 50 | 26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-440 | Martinsville-Highland 69 kV |  | N/A | N/A | Active | Dayton | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-441 | Burnham 138kV |  | IL | Cook | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AF2-442 | Vernon 115 kV |  | NJ | Sussex | Active | JCPL | 84 | 84 | 0 |  | Energy | Merchant Transmission |  | AC | 84 NFTIR/NFTWR | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | S | No
AF2-443 | Vernon 115 kV |  | NJ | Sussex | Active | JCPL | 84 | 84 | 0 |  | Energy | Merchant Transmission |  | AC | 84 NFTIR/NFTWR | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | S | No
AF2-444 | Reed-Fairview Tap #2 69 kV |  | PA | Northumberland | Active | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-445A | Fishbach-Port Carbon 69 kV |  | VA | Northumberland | Active | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AG1-001 | US Silica-Unimin 69 kV |  | NJ | Cumberland | Active | AEC | 31 | 31 | 11.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2020 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AG1-002 |  |  | PA | Allegheny | Withdrawn | DL | 5.3 | 5.25 | 5.25 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/16/2020 | N/A | N/A |  | 5/22/2020 |  | 12/31/2022 |  |  | N | No
AG1-003 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 900 | 400 | 226 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-004 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 1100 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
1003606 | FE-PJM |  | N/A | N/A | Withdrawn | First Energy Solutions | 208 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/11/2008 | 11/1/2008 | 6/1/2009 | [6 empty] | FF | No
1041672 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 106 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041677 | PJM-TVA |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
1041678 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 52 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/20/2008 | 2/1/2009 | 2/1/2011 | [6 empty] | FF | No
1070958 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070959 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 42 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1070962 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070966 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 7/1/2009 | 7/1/2014 | [6 empty] | FF | No
1070967 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/6/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1091513 | OVEC-PJM |  | N/A | N/A | Confirmed | Allegheny | 68 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091532 | OVEC-PJM |  | N/A | N/A | Confirmed | Allegheny | 11 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 2/1/2009 | 3/13/2026 | [6 empty] | FF | No
1091549 | OVEC-PJM |  | N/A | N/A | Confirmed | Buckeye | 203 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/29/2009 | 5/1/2009 | 3/13/2026 | [6 empty] | FF | No
1115220 | PJM-AMIL |  | N/A | N/A | Confirmed | AEP | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/3/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1119633 | OVEC-PJM |  | N/A | N/A | Confirmed | First Energy Solutions | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1119653 | OVEC-PJM |  | N/A | N/A | Confirmed | First Energy Solutions | 118 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/10/2009 | 5/1/2009 | 5/1/2014 | [6 empty] | FF | No
1121578 | PJM-WEC |  | N/A | N/A | Confirmed | WPPI Energy | 10 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/12/2009 | 6/1/2009 | 6/1/2017 | [6 empty] | FF | No
1129395 | PJM-MECS |  | N/A | N/A | Confirmed | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2011 | [6 empty] | FF | No
1132597 | PJM-MECS |  | N/A | N/A | Confirmed | AEP | 25 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2010 | [6 empty] | FF | No
1132611 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 38 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/25/2009 | 6/1/2009 | 6/1/2012 | [6 empty] | FF | No
1134215 | FE-PJM |  | N/A | N/A | Annulled | First Energy Solutions | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134216 | FE-PJM |  | N/A | N/A | Annulled | First Energy Solutions | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134217 | FE-PJM |  | N/A | N/A | Annulled | First Energy Solutions | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1134219 | FE-PJM |  | N/A | N/A | Annulled | First Energy Solutions | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2009 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
1180629 | DUK-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/16/2009 | 10/1/2009 | 10/1/2014 | [6 empty] | FF | No
1251680 | PJM-TVA |  | N/A | N/A | Confirmed | TVA | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252025 | PJM-CIN |  | N/A | N/A | Confirmed | Cargill Power Markets, LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252026 | PJM-CIN |  | N/A | N/A | Confirmed | Cargill Power Markets, LLC | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
1252090 | PJM-ALTW |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252092 | PJM-ALTW |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 65 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252093 | PJM-ALTW |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 149 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252097 | PJM-ALTE |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 40 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252098 | PJM-ALTE |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
1252099 | PJM-ALTE |  | N/A | N/A | Confirmed | Alliant Energy Corporate Services | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 11/2/2009 | 1/1/2010 | 1/1/2015 | [6 empty] | FF | No
4183678 | DUK-PJM |  | N/A | N/A | Confirmed | North Carolina Electric Membership | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/19/2012 | 10/1/2013 | 10/1/2018 | [6 empty] | FF | No
4244941 | PJM-TVA |  | N/A | N/A | Confirmed | TVA Bishop Hill | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/26/2012 | 6/1/2012 | 6/1/2017 | [6 empty] | FF | No
500310 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 10/1/2006 | 4/1/2007 | [6 empty] | FF | No
500311 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 10/1/2006 | 1/1/2007 | [6 empty] | FF | No
501061 | PJM-NYIS |  | N/A | N/A | Withdrawn | Cavallo Power, LP | 500 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/501061_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 7/31/2006 | 6/1/2009 | 6/1/2019 | [6 empty] | FF | No
502025 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
502029 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
506017 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 2/1/2007 | [6 empty] | FF | No
507525 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2007 | 1/1/2008 | [6 empty] | FF | No
510924 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510926 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
510942 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/510942_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 11/16/2006 | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510945 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510946 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510947 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
510948 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520595 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 2/1/2008 | [6 empty] | FF | No
520948 | PJM-NYIS |  | N/A | N/A | Confirmed | Cargill Power Markets, LLC | 26 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/520948_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
520949 | PJM-NYIS |  | N/A | N/A | Confirmed | Cargill Power Markets, LLC | 26 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
520950 | PJM-NYIS |  | N/A | N/A | Confirmed | Cargill Power Markets, LLC | 26 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/5/2007 | 1/1/2010 | 1/1/2012 | [6 empty] | FF | No
527594 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
527597 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
528018 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528021 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528023 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528024 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 9/1/2007 | [6 empty] | FF | No
528028 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 2/1/2007 | 6/1/2007 | [6 empty] | FF | No
529891 |  |  | N/A | N/A | Annulled | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/529891_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/8/2007 | 7/1/2009 | 7/1/2010 | [6 empty] | FF | No
530761 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
530778 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
530783 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 1/1/2008 | 1/1/2009 | [6 empty] | FF | No
531601 | OVEC-PJM |  | N/A | N/A | Confirmed | First Energy Solutions | 253 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/531601_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/531601_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 3/6/2007 | 10/1/2008 | 10/1/2013 | [6 empty] | FF | No
531604 | OVEC_PJM |  | N/A | N/A | Confirmed | First Energy Solutions | 210 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/531604_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/531604_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
531616 | FE-PJM |  | N/A | N/A | Withdrawn | First Energy Solutions | 2510 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
531617 | FE-PJM |  | N/A | N/A | Withdrawn | First Energy Solutions | 1940 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/15/2007 | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
532696 | PJM-CIN |  | N/A | N/A | Withdrawn | Cinergy Services, CGE | 300 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/532696_ltf1.pdf |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-2/532696_ltf2.pdf | Executed Agreement and/or Study |  |  |  | N/A | N/A | [5 empty] | 2/19/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
533213 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
533260 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
539601 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/539601_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 3/20/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
539610 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
547020 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
547022 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
549214 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
549854 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 12/1/2007 | [6 empty] | FF | No
554476 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
554497 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2010 | 1/1/2011 | [6 empty] | FF | No
554504 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554507 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
554509 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
554950 | LGEE-PJM |  | N/A | N/A | Confirmed | IMEA | 63 |  |  |  | Energy | Long-Term Firm Transmission |  |  |  | https://www.pjm.com/pub/planning/project-queues/ltf-phase-1/554950_ltf1.pdf | [7 empty] | N/A | N/A | [5 empty] | 5/8/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
555079 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555085 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555092 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
555096 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2007 | 6/1/2008 | [6 empty] | FF | No
560490 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
560494 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2007 | 7/1/2008 | [6 empty] | FF | No
564527 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564533 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564538 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564539 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2009 | 1/1/2011 | [6 empty] | FF | No
564543 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2011 | 1/1/2013 | [6 empty] | FF | No
564544 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2013 | 1/1/2014 | [6 empty] | FF | No
564878 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564884 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564895 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564938 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
564940 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/30/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
565380 |  |  | N/A | N/A | Confirmed | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 5/31/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
568552 | PJM.AP-PJM.DPL |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568554 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568555 | PJM.AP-PJM.PSEG |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568556 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
568557 | PJM.AP-PJM.PPL |  | N/A | N/A | Withdrawn | Gen Power Coal III, LLC | 125 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/1/2007 | 1/1/2014 | 1/1/2034 | [6 empty] | FF | No
708103 | PJM-CPLE |  | N/A | N/A | Confirmed | Southeastern Power Administration | 89 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 6/15/2007 | 11/1/2007 | 11/1/2008 | [6 empty] | FF | No
811046 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811048 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811061 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811067 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811071 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811073 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 27 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811074 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 27 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811075 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811080 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 2/1/2008 | 6/1/2009 | [6 empty] | FF | No
811082 | PJM_MECS |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811086 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811089 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811092 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811095 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811097 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811101 | PJM-FE |  | N/A | N/A | Confirmed | AEP | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
811105 | PJM-AMIL |  | N/A | N/A | Withdrawn | AEP | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/20/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
816850 | PJM-ALTE |  | N/A | N/A | Confirmed | Madison Gas &amp; Electric | 15 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/4/2007 | 1/1/2008 | 6/1/2009 | [6 empty] | FF | No
818965 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 180 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818967 | PJM-TVA |  | N/A | N/A | Confirmed | Constellation Energy Commodities Group | 138 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 2/1/2008 | 2/1/2009 | [6 empty] | FF | No
818976 | PJM-TVA |  | N/A | N/A | Confirmed | TVA | 600 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/10/2007 | 1/1/2008 | 1/1/2010 | [6 empty] | FF | No
825955 | PJM-AMIL |  | N/A | N/A | Confirmed | AEP | 250 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 10/30/2007 | 4/1/2008 | 6/1/2009 | [6 empty] | FF | No
847949 | PJM-MEC |  | N/A | N/A | Confirmed | MidAmerican | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 12/27/2007 | 6/1/2008 | 6/1/2010 | [6 empty] | FF | No
863796 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
863799 |  |  | N/A | N/A | Withdrawn | [5 empty] | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 1/31/2008 | 6/1/2011 | 6/1/2016 | [6 empty] | FF | No
866859 | ALTE-PJM |  | N/A | N/A | Withdrawn | Calpine Energy Services | 468 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/6/2008 | 6/1/2012 | 6/1/2013 | [6 empty] | FF | No
869320 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869642 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 42 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 1/1/2009 | 1/1/2010 | [6 empty] | FF | No
869659 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 142 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
869681 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 50 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [6 empty] | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
869803 | PJM-FE |  | N/A | N/A | Confirmed | American Municipal Power, Inc. | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/12/2008 | 7/1/2008 | 7/1/2009 | [6 empty] | FF | No
893173 | OVEC-PJM-FE |  | N/A | N/A | Confirmed | First Energy Solutions | 462 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 3/31/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893692 | FE-PJM |  | N/A | N/A | Confirmed | Pennelec | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893694 | FE-PJM |  | N/A | N/A | Confirmed | Pennelec | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893702 | FE-PJM |  | N/A | N/A | Confirmed | Met_Ed | 300 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
893704 | FE-PJM |  | N/A | N/A | Confirmed | Met_Ed | 200 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/1/2008 | 6/1/2008 | 6/1/2009 | [6 empty] | FF | No
894765 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894769 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 7/1/2008 | 7/1/2010 | [6 empty] | FF | No
894770 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
894774 | PJM-CIN |  | N/A | N/A | Confirmed | MidAmerican | 100 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/3/2008 | 12/1/2008 | 12/1/2010 | [6 empty] | FF | No
903384 | PJM-WEC |  | N/A | N/A | Confirmed | WEP | 320 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 4/25/2008 | 5/15/2010 | 5/31/2011 | [6 empty] | FF | No
988887 | PJM-CIN |  | N/A | N/A | Confirmed | Cinergy Services, CGE | 20 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/10/2008 | 6/1/2009 | 6/1/2014 | [6 empty] | FF | No
994856 | PJM-TVA |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 138 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994857 | PJM-TVA |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
994858 | PJM-TVA |  | N/A | N/A | Withdrawn | Constellation Energy Commodities Group | 90 |  |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 9/18/2008 | 2/1/2009 | 2/1/2014 | [6 empty] | FF | No
AB2-034 4788768 |  |  | N/A | N/A | Withdrawn |  | 100 | 100 |  |  | Energy | Long-Term Firm Transmission | [11 empty] | N/A | N/A | [5 empty] | 2/23/2016 | 6/1/2017 | 6/1/2022 |  | 2/23/2016 |  |  |  |  | FF | No

## Definitions-Mapping
Column Names from Data Tab
Queue | Queue/OASIS Number
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the queue position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection queue process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Queue Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Queue
Sliding Queue